## Overview
OPBOH™ 37 Stages / Work Packages
Full-Cycle Stage-Gate Architecture ¦ Controlled Master Register ¦ Version 1.1
From Strategic Inception to Sustainable Impact, Performance Monitoring and Future Expansion
37 Stages / work packages |  | 222 Controlled focus fields |  | 3,700 Stage-gate questions |  | 100 Questions per stage
Full-cycle control logic
Each work package is a controlled assurance unit. It has a defined purpose, six primary focus fields, 100 evidence-based questions, accountable roles, entry and exit conditions, decision risks, mandatory outputs and a documented progression recommendation. No stage progresses on elapsed time or a tick-box response alone.
Lifecycle Cluster | Stages | Questions | Focus Fields |  | Control Test | Required | Result
Opportunity, Mandate and Site Control | 5 | 500 | 30 |  | Stage count | 37 | 37
Feasibility, Rights, Approvals and Stakeholders | 7 | 700 | 42 |  | Question count | 3700 | 3700
Concept, Commercial Alignment and Occupier Strategy | 7 | 700 | 42 |  | Focus field count | 222 | 222
Design, Cost, Capital, Procurement and Permitting | 7 | 700 | 42 |  | Stages with 100 questions | 37 | 37
Construction, Quality, Commissioning and Handover | 7 | 700 | 42
Operations, Maintenance, Impact and Expansion | 4 | 400 | 24
Evidence rule: Yes/No/N/A and a 0–5 score are assessment inputs; progression requires accepted, current, complete, signed where applicable and traceable evidence, reviewed under delegated authority.

## 37 Stage Register
OPBOH™ 37-Stage / Work-Package Master Register
Complete lifecycle identity, focus, dependencies, accountabilities and coverage controls
Stage | WP Code | Stage / Work Package | Lifecycle Cluster | Primary Focus | Stage Purpose | Predecessor | Successor | Accountable Roles | Principal Decision Risk | Decision Options | Questions | Focus Fields
01 | WP01 | Strategic Inception and Project Mandate | Opportunity, Mandate and Site Control | Project vision, scope mandate, decision authority, developer appointment, client objectives, governance structure | Establish, assess and evidence project vision, scope mandate, decision authority, developer appointment, client objectives, governance structure before authorising progression beyond strategic inception and project mandate. | Opportunity intake / mandate initiation | WP02 | Project Sponsor; OPBOH Lead Assessor; Legal/Governance Lead; Project Manager | Unclear mandate, ownership, authority or site control may invalidate later commitments and expenditure. | Proceed / Proceed with conditions / Remediate and reassess / Hold / Rework / Stop or restructure | 100 | 6
02 | WP02 | Site Identification and Opportunity Discovery | Opportunity, Mandate and Site Control | R567 exposure, 3 ha site extent, market gap, community catchment, mobility flows, competitive landscape | Establish, assess and evidence r567 exposure, 3 ha site extent, market gap, community catchment, mobility flows, competitive landscape before authorising progression beyond site identification and opportunity discovery. | WP01 | WP03 | Project Sponsor; OPBOH Lead Assessor; Legal/Governance Lead; Project Manager | Unclear mandate, ownership, authority or site control may invalidate later commitments and expenditure. | Proceed / Proceed with conditions / Remediate and reassess / Hold / Rework / Stop or restructure | 100 | 6
03 | WP03 | Preliminary Site Screening | Opportunity, Mandate and Site Control | Ownership confirmation, servitudes, basic zoning position, environmental sensitivity, access constraints, bulk services proximity | Establish, assess and evidence ownership confirmation, servitudes, basic zoning position, environmental sensitivity, access constraints, bulk services proximity before authorising progression beyond preliminary site screening. | WP02 | WP04 | Project Sponsor; OPBOH Lead Assessor; Legal/Governance Lead; Project Manager | Unclear mandate, ownership, authority or site control may invalidate later commitments and expenditure. | Proceed / Proceed with conditions / Remediate and reassess / Hold / Rework / Stop or restructure | 100 | 6
04 | WP04 | Sponsor and Entity Readiness | Opportunity, Mandate and Site Control | Client capacity, corporate documentation, tax status, decision-making mandate, funding preparedness, legal authority | Establish, assess and evidence client capacity, corporate documentation, tax status, decision-making mandate, funding preparedness, legal authority before authorising progression beyond sponsor and entity readiness. | WP03 | WP05 | Project Sponsor; OPBOH Lead Assessor; Legal/Governance Lead; Project Manager | Unclear mandate, ownership, authority or site control may invalidate later commitments and expenditure. | Proceed / Proceed with conditions / Remediate and reassess / Hold / Rework / Stop or restructure | 100 | 6
05 | WP05 | Land Security and Site Control | Opportunity, Mandate and Site Control | Title deed, landowner consent, lease or purchase rights, site boundaries, SG diagram, wayleaves | Establish, assess and evidence title deed, landowner consent, lease or purchase rights, site boundaries, sg diagram, wayleaves before authorising progression beyond land security and site control. | WP04 | WP06 | Project Sponsor; OPBOH Lead Assessor; Legal/Governance Lead; Project Manager | Unclear mandate, ownership, authority or site control may invalidate later commitments and expenditure. | Proceed / Proceed with conditions / Remediate and reassess / Hold / Rework / Stop or restructure | 100 | 6
06 | WP06 | Feasibility Studies and Market Demand | Feasibility, Rights, Approvals and Stakeholders | Retail demand, fuel demand, Boxer anchor viability, line-shop demand, fast-food demand, traffic volumes | Establish, assess and evidence retail demand, fuel demand, boxer anchor viability, line-shop demand, fast-food demand, traffic volumes before authorising progression beyond feasibility studies and market demand. | WP05 | WP07 | Project Manager; Planning/Environmental/Engineering Specialists; Relevant Authorities; OPBOH Assessor | Unresolved feasibility, access, services, environmental, zoning or stakeholder constraints may make the project non-viable or delay approvals. | Proceed / Proceed with conditions / Remediate and reassess / Hold / Rework / Stop or restructure | 100 | 6
07 | WP07 | Traffic, Access and Mobility Feasibility | Feasibility, Rights, Approvals and Stakeholders | R567 entrance, turning lanes, sight distances, heavy vehicle movement, pedestrian safety, public transport interface | Establish, assess and evidence r567 entrance, turning lanes, sight distances, heavy vehicle movement, pedestrian safety, public transport interface before authorising progression beyond traffic, access and mobility feasibility. | WP06 | WP08 | Project Manager; Planning/Environmental/Engineering Specialists; Relevant Authorities; OPBOH Assessor | Unresolved feasibility, access, services, environmental, zoning or stakeholder constraints may make the project non-viable or delay approvals. | Proceed / Proceed with conditions / Remediate and reassess / Hold / Rework / Stop or restructure | 100 | 6
08 | WP08 | Bulk Services and Infrastructure Feasibility | Feasibility, Rights, Approvals and Stakeholders | Water supply, sewer capacity, stormwater discharge, electrical capacity, fire water, ICT services | Establish, assess and evidence water supply, sewer capacity, stormwater discharge, electrical capacity, fire water, ict services before authorising progression beyond bulk services and infrastructure feasibility. | WP07 | WP09 | Project Manager; Planning/Environmental/Engineering Specialists; Relevant Authorities; OPBOH Assessor | Unresolved feasibility, access, services, environmental, zoning or stakeholder constraints may make the project non-viable or delay approvals. | Proceed / Proceed with conditions / Remediate and reassess / Hold / Rework / Stop or restructure | 100 | 6
09 | WP09 | Environmental Screening and Scoping | Feasibility, Rights, Approvals and Stakeholders | NEMA triggers, wetland sensitivity, biodiversity risk, heritage risk, groundwater risk, noise sources | Establish, assess and evidence nema triggers, wetland sensitivity, biodiversity risk, heritage risk, groundwater risk, noise sources before authorising progression beyond environmental screening and scoping. | WP08 | WP10 | Project Manager; Planning/Environmental/Engineering Specialists; Relevant Authorities; OPBOH Assessor | Unresolved feasibility, access, services, environmental, zoning or stakeholder constraints may make the project non-viable or delay approvals. | Proceed / Proceed with conditions / Remediate and reassess / Hold / Rework / Stop or restructure | 100 | 6
10 | WP10 | Land Use Rights and Zoning | Feasibility, Rights, Approvals and Stakeholders | Current agricultural zoning, rezoning pathway, consent use, site development plan, parking compliance, FAR and coverage | Establish, assess and evidence current agricultural zoning, rezoning pathway, consent use, site development plan, parking compliance, far and coverage before authorising progression beyond land use rights and zoning. | WP09 | WP11 | Project Manager; Planning/Environmental/Engineering Specialists; Relevant Authorities; OPBOH Assessor | Unresolved feasibility, access, services, environmental, zoning or stakeholder constraints may make the project non-viable or delay approvals. | Proceed / Proceed with conditions / Remediate and reassess / Hold / Rework / Stop or restructure | 100 | 6
11 | WP11 | Environmental Authorisation - Estimated 10 Months | Feasibility, Rights, Approvals and Stakeholders | Screening report, specialist studies, draft BAR or EIA, public participation, authority comments, empr | Establish, assess and evidence screening report, specialist studies, draft bar or eia, public participation, authority comments, empr before authorising progression beyond environmental authorisation - estimated 10 months. | WP10 | WP12 | Project Manager; Planning/Environmental/Engineering Specialists; Relevant Authorities; OPBOH Assessor | Unresolved feasibility, access, services, environmental, zoning or stakeholder constraints may make the project non-viable or delay approvals. | Proceed / Proceed with conditions / Remediate and reassess / Hold / Rework / Stop or restructure | 100 | 6
12 | WP12 | Stakeholder Mapping and Public Participation | Feasibility, Rights, Approvals and Stakeholders | Municipality, road authority, DMRE, environmental authority, community leaders, neighbouring landowners | Establish, assess and evidence municipality, road authority, dmre, environmental authority, community leaders, neighbouring landowners before authorising progression beyond stakeholder mapping and public participation. | WP11 | WP13 | Project Manager; Planning/Environmental/Engineering Specialists; Relevant Authorities; OPBOH Assessor | Unresolved feasibility, access, services, environmental, zoning or stakeholder constraints may make the project non-viable or delay approvals. | Proceed / Proceed with conditions / Remediate and reassess / Hold / Rework / Stop or restructure | 100 | 6
13 | WP13 | Concept Development | Concept, Commercial Alignment and Occupier Strategy | Site layout, Boxer store placement, fuel forecourt interface, line-shop frontage, QSR positioning, parking concept | Establish, assess and evidence site layout, boxer store placement, fuel forecourt interface, line-shop frontage, qsr positioning, parking concept before authorising progression beyond concept development. | WP12 | WP14 | Developer; Architect/Masterplanner; Leasing Lead; Anchor/Tenant/Fuel Partner Representatives | Misaligned concept, tenant demand, anchor requirements or commercial positioning may undermine income and design viability. | Proceed / Proceed with conditions / Remediate and reassess / Hold / Rework / Stop or restructure | 100 | 6
14 | WP14 | Retail Masterplanning and GLA Strategy | Concept, Commercial Alignment and Occupier Strategy | Anchor GLA, line-shop GLA, QSR GLA, forecourt convenience offer, back-of-house allocation, loading areas | Establish, assess and evidence anchor gla, line-shop gla, qsr gla, forecourt convenience offer, back-of-house allocation, loading areas before authorising progression beyond retail masterplanning and gla strategy. | WP13 | WP15 | Developer; Architect/Masterplanner; Leasing Lead; Anchor/Tenant/Fuel Partner Representatives | Misaligned concept, tenant demand, anchor requirements or commercial positioning may undermine income and design viability. | Proceed / Proceed with conditions / Remediate and reassess / Hold / Rework / Stop or restructure | 100 | 6
15 | WP15 | Boxer Superstores Anchor Alignment | Concept, Commercial Alignment and Occupier Strategy | Boxer specifications, anchor lease principles, loading requirements, store footprint, service yard, delivery windows | Establish, assess and evidence boxer specifications, anchor lease principles, loading requirements, store footprint, service yard, delivery windows before authorising progression beyond boxer superstores anchor alignment. | WP14 | WP16 | Developer; Architect/Masterplanner; Leasing Lead; Anchor/Tenant/Fuel Partner Representatives | Misaligned concept, tenant demand, anchor requirements or commercial positioning may undermine income and design viability. | Proceed / Proceed with conditions / Remediate and reassess / Hold / Rework / Stop or restructure | 100 | 6
16 | WP16 | Tenant Acquisition Strategy | Concept, Commercial Alignment and Occupier Strategy | Target tenant list, leasing brochure, anchor-led positioning, rental assumptions, tenant due diligence, letters of intent | Establish, assess and evidence target tenant list, leasing brochure, anchor-led positioning, rental assumptions, tenant due diligence, letters of intent before authorising progression beyond tenant acquisition strategy. | WP15 | WP17 | Developer; Architect/Masterplanner; Leasing Lead; Anchor/Tenant/Fuel Partner Representatives | Misaligned concept, tenant demand, anchor requirements or commercial positioning may undermine income and design viability. | Proceed / Proceed with conditions / Remediate and reassess / Hold / Rework / Stop or restructure | 100 | 6
17 | WP17 | Line-Shop Tenant Mix and Leasing | Concept, Commercial Alignment and Occupier Strategy | Pharmacy option, cellular tenant, banking/ATM, bakery or deli, local enterprise, beauty or personal care | Establish, assess and evidence pharmacy option, cellular tenant, banking/atm, bakery or deli, local enterprise, beauty or personal care before authorising progression beyond line-shop tenant mix and leasing. | WP16 | WP18 | Developer; Architect/Masterplanner; Leasing Lead; Anchor/Tenant/Fuel Partner Representatives | Misaligned concept, tenant demand, anchor requirements or commercial positioning may undermine income and design viability. | Proceed / Proceed with conditions / Remediate and reassess / Hold / Rework / Stop or restructure | 100 | 6
18 | WP18 | Fast-Food Chain Restaurant Acquisition | Concept, Commercial Alignment and Occupier Strategy | Brand targeting, drive-through feasibility, kitchen extraction, grease traps, delivery access, seating areas | Establish, assess and evidence brand targeting, drive-through feasibility, kitchen extraction, grease traps, delivery access, seating areas before authorising progression beyond fast-food chain restaurant acquisition. | WP17 | WP19 | Developer; Architect/Masterplanner; Leasing Lead; Anchor/Tenant/Fuel Partner Representatives | Misaligned concept, tenant demand, anchor requirements or commercial positioning may undermine income and design viability. | Proceed / Proceed with conditions / Remediate and reassess / Hold / Rework / Stop or restructure | 100 | 6
19 | WP19 | Fuel Partner and Forecourt Coordination | Concept, Commercial Alignment and Occupier Strategy | Totalenergies standards, forecourt layout, tank farm, fuel logistics, C-store integration, brand signage | Establish, assess and evidence totalenergies standards, forecourt layout, tank farm, fuel logistics, c-store integration, brand signage before authorising progression beyond fuel partner and forecourt coordination. | WP18 | WP20 | Developer; Architect/Masterplanner; Leasing Lead; Anchor/Tenant/Fuel Partner Representatives | Misaligned concept, tenant demand, anchor requirements or commercial positioning may undermine income and design viability. | Proceed / Proceed with conditions / Remediate and reassess / Hold / Rework / Stop or restructure | 100 | 6
20 | WP20 | Development Design | Design, Cost, Capital, Procurement and Permitting | Architectural design, civil design, structural design, MEP design, fire strategy, landscaping | Establish, assess and evidence architectural design, civil design, structural design, mep design, fire strategy, landscaping before authorising progression beyond development design. | WP19 | WP21 | Professional Design Team; Quantity Surveyor; Financial Adviser; Sponsor/Funder Representatives | Incomplete design, cost, funding, procurement or permit readiness may expose capital, programme, compliance and contracting decisions. | Proceed / Proceed with conditions / Remediate and reassess / Hold / Rework / Stop or restructure | 100 | 6
21 | WP21 | Engineering Design and Technical Documentation | Design, Cost, Capital, Procurement and Permitting | Bulk earthworks, stormwater design, road pavements, water reticulation, sewer reticulation, electrical reticulation | Establish, assess and evidence bulk earthworks, stormwater design, road pavements, water reticulation, sewer reticulation, electrical reticulation before authorising progression beyond engineering design and technical documentation. | WP20 | WP22 | Professional Design Team; Quantity Surveyor; Financial Adviser; Sponsor/Funder Representatives | Incomplete design, cost, funding, procurement or permit readiness may expose capital, programme, compliance and contracting decisions. | Proceed / Proceed with conditions / Remediate and reassess / Hold / Rework / Stop or restructure | 100 | 6
22 | WP22 | Cost Planning and Financial Modelling | Design, Cost, Capital, Procurement and Permitting | CAPEX estimate, professional fees, approval costs, tenant fit-out allowances, contingency, rental income | Establish, assess and evidence capex estimate, professional fees, approval costs, tenant fit-out allowances, contingency, rental income before authorising progression beyond cost planning and financial modelling. | WP21 | WP23 | Professional Design Team; Quantity Surveyor; Financial Adviser; Sponsor/Funder Representatives | Incomplete design, cost, funding, procurement or permit readiness may expose capital, programme, compliance and contracting decisions. | Proceed / Proceed with conditions / Remediate and reassess / Hold / Rework / Stop or restructure | 100 | 6
23 | WP23 | Capital Structuring and Funding Readiness | Design, Cost, Capital, Procurement and Permitting | Equity contribution, debt funding, drawdown plan, security package, funder due diligence, term sheet | Establish, assess and evidence equity contribution, debt funding, drawdown plan, security package, funder due diligence, term sheet before authorising progression beyond capital structuring and funding readiness. | WP22 | WP24 | Professional Design Team; Quantity Surveyor; Financial Adviser; Sponsor/Funder Representatives | Incomplete design, cost, funding, procurement or permit readiness may expose capital, programme, compliance and contracting decisions. | Proceed / Proceed with conditions / Remediate and reassess / Hold / Rework / Stop or restructure | 100 | 6
24 | WP24 | Procurement Strategy and Tender Documentation | Design, Cost, Capital, Procurement and Permitting | Procurement route, tender pack, BOQ, contract conditions, bid evaluation, supplier strategy | Establish, assess and evidence procurement route, tender pack, boq, contract conditions, bid evaluation, supplier strategy before authorising progression beyond procurement strategy and tender documentation. | WP23 | WP25 | Project Manager; Procurement/Legal Lead; Professional Team; Authorities; Gate Authority | Incomplete design, cost, funding, procurement or permit readiness may expose capital, programme, compliance and contracting decisions. | Proceed / Proceed with conditions / Remediate and reassess / Hold / Rework / Stop or restructure | 100 | 6
25 | WP25 | Contractor Due Diligence and Appointment | Design, Cost, Capital, Procurement and Permitting | Contractor capacity, financial strength, similar project experience, HSE record, quality systems, programme credibility | Establish, assess and evidence contractor capacity, financial strength, similar project experience, hse record, quality systems, programme credibility before authorising progression beyond contractor due diligence and appointment. | WP24 | WP26 | Project Manager; Procurement/Legal Lead; Professional Team; Authorities; Gate Authority | Incomplete design, cost, funding, procurement or permit readiness may expose capital, programme, compliance and contracting decisions. | Proceed / Proceed with conditions / Remediate and reassess / Hold / Rework / Stop or restructure | 100 | 6
26 | WP26 | Regulatory Permitting and Building Plan Approval | Design, Cost, Capital, Procurement and Permitting | Building plans, fire approval, health approval, road access approval, water connection, sewer connection | Establish, assess and evidence building plans, fire approval, health approval, road access approval, water connection, sewer connection before authorising progression beyond regulatory permitting and building plan approval. | WP25 | WP27 | Project Manager; Procurement/Legal Lead; Professional Team; Authorities; Gate Authority | Incomplete design, cost, funding, procurement or permit readiness may expose capital, programme, compliance and contracting decisions. | Proceed / Proceed with conditions / Remediate and reassess / Hold / Rework / Stop or restructure | 100 | 6
27 | WP27 | Construction Mobilisation | Construction, Quality, Commissioning and Handover | Site handover, site camp, survey setting out, HSE file, environmental controls, baseline programme | Establish, assess and evidence site handover, site camp, survey setting out, hse file, environmental controls, baseline programme before authorising progression beyond construction mobilisation. | WP26 | WP28 | Principal Agent; Contractor; HSE/Quality Leads; Professional Team; Project Manager | Weak mobilisation, construction, quality, HSE, testing or handover controls may cause defects, incidents, delay and non-functional assets. | Proceed / Proceed with conditions / Remediate and reassess / Hold / Rework / Stop or restructure | 100 | 6
28 | WP28 | Civil Works, Earthworks and Access Construction | Construction, Quality, Commissioning and Handover | Clearing and grubbing, bulk earthworks, platforms, R567 entrance works, stormwater structures, internal roads | Establish, assess and evidence clearing and grubbing, bulk earthworks, platforms, r567 entrance works, stormwater structures, internal roads before authorising progression beyond civil works, earthworks and access construction. | WP27 | WP29 | Principal Agent; Contractor; HSE/Quality Leads; Professional Team; Project Manager | Weak mobilisation, construction, quality, HSE, testing or handover controls may cause defects, incidents, delay and non-functional assets. | Proceed / Proceed with conditions / Remediate and reassess / Hold / Rework / Stop or restructure | 100 | 6
29 | WP29 | Building Shells and Services Installation | Construction, Quality, Commissioning and Handover | Boxer shell, line-shop shells, QSR shells, roofing, shopfronts, water services | Establish, assess and evidence boxer shell, line-shop shells, qsr shells, roofing, shopfronts, water services before authorising progression beyond building shells and services installation. | WP28 | WP30 | Principal Agent; Contractor; HSE/Quality Leads; Professional Team; Project Manager | Weak mobilisation, construction, quality, HSE, testing or handover controls may cause defects, incidents, delay and non-functional assets. | Proceed / Proceed with conditions / Remediate and reassess / Hold / Rework / Stop or restructure | 100 | 6
30 | WP30 | Tenant Fit-Out Coordination | Construction, Quality, Commissioning and Handover | Boxer fit-out, line-shop fit-out, fast-food fit-out, handover dates, fit-out rules, tenant utilities | Establish, assess and evidence boxer fit-out, line-shop fit-out, fast-food fit-out, handover dates, fit-out rules, tenant utilities before authorising progression beyond tenant fit-out coordination. | WP29 | WP31 | Principal Agent; Contractor; HSE/Quality Leads; Professional Team; Project Manager | Weak mobilisation, construction, quality, HSE, testing or handover controls may cause defects, incidents, delay and non-functional assets. | Proceed / Proceed with conditions / Remediate and reassess / Hold / Rework / Stop or restructure | 100 | 6
31 | WP31 | Quality Assurance, HSE and Compliance Control | Construction, Quality, Commissioning and Handover | Quality inspections, HSE audits, environmental monitoring, material approvals, variation control, payment certification | Establish, assess and evidence quality inspections, hse audits, environmental monitoring, material approvals, variation control, payment certification before authorising progression beyond quality assurance, hse and compliance control. | WP30 | WP32 | Principal Agent; Contractor; HSE/Quality Leads; Professional Team; Project Manager | Weak mobilisation, construction, quality, HSE, testing or handover controls may cause defects, incidents, delay and non-functional assets. | Proceed / Proceed with conditions / Remediate and reassess / Hold / Rework / Stop or restructure | 100 | 6
32 | WP32 | Commissioning and Testing | Construction, Quality, Commissioning and Handover | Electrical testing, water pressure testing, fire system testing, stormwater checks, HVAC testing, ICT testing | Establish, assess and evidence electrical testing, water pressure testing, fire system testing, stormwater checks, hvac testing, ict testing before authorising progression beyond commissioning and testing. | WP31 | WP33 | Commissioning Lead; Professional Team; Operators/Tenants; Asset Owner; Project Manager | Weak mobilisation, construction, quality, HSE, testing or handover controls may cause defects, incidents, delay and non-functional assets. | Proceed / Proceed with conditions / Remediate and reassess / Hold / Rework / Stop or restructure | 100 | 6
33 | WP33 | Handover to Operators and Tenants | Construction, Quality, Commissioning and Handover | Handover manuals, as-built drawings, warranty register, tenant certificates, maintenance plans, operator training | Establish, assess and evidence handover manuals, as-built drawings, warranty register, tenant certificates, maintenance plans, operator training before authorising progression beyond handover to operators and tenants. | WP32 | WP34 | Commissioning Lead; Professional Team; Operators/Tenants; Asset Owner; Project Manager | Weak mobilisation, construction, quality, HSE, testing or handover controls may cause defects, incidents, delay and non-functional assets. | Proceed / Proceed with conditions / Remediate and reassess / Hold / Rework / Stop or restructure | 100 | 6
34 | WP34 | Operational Ramp-Up | Operations, Maintenance, Impact and Expansion | Soft opening, Boxer opening, tenant trading readiness, traffic management, customer service, operations dashboard | Establish, assess and evidence soft opening, boxer opening, tenant trading readiness, traffic management, customer service, operations dashboard before authorising progression beyond operational ramp-up. | WP33 | WP35 | Asset/Property Manager; Operators/Tenants; Maintenance Lead; ESG/MERL Lead; Owner Governance | Weak operating, maintenance or impact controls may erode functionality, financial sustainability, compliance and long-term benefits. | Proceed / Proceed with conditions / Remediate and reassess / Hold / Rework / Stop or restructure | 100 | 6
35 | WP35 | Operations Management | Operations, Maintenance, Impact and Expansion | Property management, lease administration, tenant relations, security operations, cleaning operations, parking control | Establish, assess and evidence property management, lease administration, tenant relations, security operations, cleaning operations, parking control before authorising progression beyond operations management. | WP34 | WP36 | Asset/Property Manager; Operators/Tenants; Maintenance Lead; ESG/MERL Lead; Owner Governance | Weak operating, maintenance or impact controls may erode functionality, financial sustainability, compliance and long-term benefits. | Proceed / Proceed with conditions / Remediate and reassess / Hold / Rework / Stop or restructure | 100 | 6
36 | WP36 | Maintenance Management | Operations, Maintenance, Impact and Expansion | Preventive maintenance, reactive maintenance, roof and gutters, electrical systems, plumbing systems, fire equipment | Establish, assess and evidence preventive maintenance, reactive maintenance, roof and gutters, electrical systems, plumbing systems, fire equipment before authorising progression beyond maintenance management. | WP35 | WP37 | Asset/Property Manager; Operators/Tenants; Maintenance Lead; ESG/MERL Lead; Owner Governance | Weak operating, maintenance or impact controls may erode functionality, financial sustainability, compliance and long-term benefits. | Proceed / Proceed with conditions / Remediate and reassess / Hold / Rework / Stop or restructure | 100 | 6
37 | WP37 | Sustainable Impact, Performance Monitoring and Future Expansion | Operations, Maintenance, Impact and Expansion | ESG reporting, job creation, local procurement, community benefit, energy efficiency, water performance | Establish, assess and evidence esg reporting, job creation, local procurement, community benefit, energy efficiency, water performance before authorising progression beyond sustainable impact, performance monitoring and future expansion. | WP36 | Operations and impact-continuity assurance | Asset/Property Manager; Operators/Tenants; Maintenance Lead; ESG/MERL Lead; Owner Governance | Weak operating, maintenance or impact controls may erode functionality, financial sustainability, compliance and long-term benefits. | Proceed / Proceed with conditions / Remediate and reassess / Hold / Rework / Stop or restructure | 100 | 6

## 222 Focus Fields
OPBOH™ 222 Controlled Stage Focus Fields
Six explicit focus fields mapped to every one of the 37 work packages
Field Code | Stage | WP Code | Stage / Work Package | Focus Field | Data Type / Allowed Values | Req. | Validation and Assurance Use | Lifecycle Cluster | Source Status
WP01-01 | 01 | WP01 | Strategic Inception and Project Mandate | Project Vision | Structured value + evidence + status | M/C | Captures the controlled project vision data for Stage 01 (Strategic Inception and Project Mandate); link source, owner, status, evidence, risk and decision impact. | Opportunity, Mandate and Site Control | Controlled v1.1
WP01-02 | 01 | WP01 | Strategic Inception and Project Mandate | Scope Mandate | Structured value + evidence + status | M/C | Captures the controlled scope mandate data for Stage 01 (Strategic Inception and Project Mandate); link source, owner, status, evidence, risk and decision impact. | Opportunity, Mandate and Site Control | Controlled v1.1
WP01-03 | 01 | WP01 | Strategic Inception and Project Mandate | Decision Authority | Linked party / engagement / due-diligence status | M/C | Captures the controlled decision authority data for Stage 01 (Strategic Inception and Project Mandate); link source, owner, status, evidence, risk and decision impact. | Opportunity, Mandate and Site Control | Controlled v1.1
WP01-04 | 01 | WP01 | Strategic Inception and Project Mandate | Developer Appointment | Structured value + evidence + status | M/C | Captures the controlled developer appointment data for Stage 01 (Strategic Inception and Project Mandate); link source, owner, status, evidence, risk and decision impact. | Opportunity, Mandate and Site Control | Controlled v1.1
WP01-05 | 01 | WP01 | Strategic Inception and Project Mandate | Client Objectives | Structured value + evidence + status | M/C | Captures the controlled client objectives data for Stage 01 (Strategic Inception and Project Mandate); link source, owner, status, evidence, risk and decision impact. | Opportunity, Mandate and Site Control | Controlled v1.1
WP01-06 | 01 | WP01 | Strategic Inception and Project Mandate | Governance Structure | Structured value + evidence + status | M/C | Captures the controlled governance structure data for Stage 01 (Strategic Inception and Project Mandate); link source, owner, status, evidence, risk and decision impact. | Opportunity, Mandate and Site Control | Controlled v1.1
WP02-01 | 02 | WP02 | Site Identification and Opportunity Discovery | R567 Exposure | Structured value + evidence + status | M/C | Captures the controlled r567 exposure data for Stage 02 (Site Identification and Opportunity Discovery); link source, owner, status, evidence, risk and decision impact. | Opportunity, Mandate and Site Control | Controlled v1.1
WP02-02 | 02 | WP02 | Site Identification and Opportunity Discovery | 3 Ha Site Extent | Numeric / percentage / currency with unit and period | M/C | Captures the controlled 3 ha site extent data for Stage 02 (Site Identification and Opportunity Discovery); link source, owner, status, evidence, risk and decision impact. | Opportunity, Mandate and Site Control | Controlled v1.1
WP02-03 | 02 | WP02 | Site Identification and Opportunity Discovery | Market Gap | Structured value + evidence + status | M/C | Captures the controlled market gap data for Stage 02 (Site Identification and Opportunity Discovery); link source, owner, status, evidence, risk and decision impact. | Opportunity, Mandate and Site Control | Controlled v1.1
WP02-04 | 02 | WP02 | Site Identification and Opportunity Discovery | Community Catchment | Structured value + evidence + status | M/C | Captures the controlled community catchment data for Stage 02 (Site Identification and Opportunity Discovery); link source, owner, status, evidence, risk and decision impact. | Opportunity, Mandate and Site Control | Controlled v1.1
WP02-05 | 02 | WP02 | Site Identification and Opportunity Discovery | Mobility Flows | Structured value + evidence + status | M/C | Captures the controlled mobility flows data for Stage 02 (Site Identification and Opportunity Discovery); link source, owner, status, evidence, risk and decision impact. | Opportunity, Mandate and Site Control | Controlled v1.1
WP02-06 | 02 | WP02 | Site Identification and Opportunity Discovery | Competitive Landscape | Structured value + evidence + status | M/C | Captures the controlled competitive landscape data for Stage 02 (Site Identification and Opportunity Discovery); link source, owner, status, evidence, risk and decision impact. | Opportunity, Mandate and Site Control | Controlled v1.1
WP03-01 | 03 | WP03 | Preliminary Site Screening | Ownership Confirmation | Structured value + evidence + status | M/C | Captures the controlled ownership confirmation data for Stage 03 (Preliminary Site Screening); link source, owner, status, evidence, risk and decision impact. | Opportunity, Mandate and Site Control | Controlled v1.1
WP03-02 | 03 | WP03 | Preliminary Site Screening | Servitudes | Structured value + evidence + status | M/C | Captures the controlled servitudes data for Stage 03 (Preliminary Site Screening); link source, owner, status, evidence, risk and decision impact. | Opportunity, Mandate and Site Control | Controlled v1.1
WP03-03 | 03 | WP03 | Preliminary Site Screening | Basic Zoning Position | Status + authority/reference + dates/conditions | M/C | Captures the controlled basic zoning position data for Stage 03 (Preliminary Site Screening); link source, owner, status, evidence, risk and decision impact. | Opportunity, Mandate and Site Control | Controlled v1.1
WP03-04 | 03 | WP03 | Preliminary Site Screening | Environmental Sensitivity | Structured value + evidence + status | M/C | Captures the controlled environmental sensitivity data for Stage 03 (Preliminary Site Screening); link source, owner, status, evidence, risk and decision impact. | Opportunity, Mandate and Site Control | Controlled v1.1
WP03-05 | 03 | WP03 | Preliminary Site Screening | Access Constraints | Structured value + evidence + status | M/C | Captures the controlled access constraints data for Stage 03 (Preliminary Site Screening); link source, owner, status, evidence, risk and decision impact. | Opportunity, Mandate and Site Control | Controlled v1.1
WP03-06 | 03 | WP03 | Preliminary Site Screening | Bulk Services Proximity | Structured value + evidence + status | M/C | Captures the controlled bulk services proximity data for Stage 03 (Preliminary Site Screening); link source, owner, status, evidence, risk and decision impact. | Opportunity, Mandate and Site Control | Controlled v1.1
WP04-01 | 04 | WP04 | Sponsor and Entity Readiness | Client Capacity | Numeric / percentage / currency with unit and period | M/C | Captures the controlled client capacity data for Stage 04 (Sponsor and Entity Readiness); link source, owner, status, evidence, risk and decision impact. | Opportunity, Mandate and Site Control | Controlled v1.1
WP04-02 | 04 | WP04 | Sponsor and Entity Readiness | Corporate Documentation | Document / version / review and approval status | M/C | Captures the controlled corporate documentation data for Stage 04 (Sponsor and Entity Readiness); link source, owner, status, evidence, risk and decision impact. | Opportunity, Mandate and Site Control | Controlled v1.1
WP04-03 | 04 | WP04 | Sponsor and Entity Readiness | Tax Status | Structured value + evidence + status | M/C | Captures the controlled tax status data for Stage 04 (Sponsor and Entity Readiness); link source, owner, status, evidence, risk and decision impact. | Opportunity, Mandate and Site Control | Controlled v1.1
WP04-04 | 04 | WP04 | Sponsor and Entity Readiness | Decision-Making Mandate | Structured value + evidence + status | M/C | Captures the controlled decision-making mandate data for Stage 04 (Sponsor and Entity Readiness); link source, owner, status, evidence, risk and decision impact. | Opportunity, Mandate and Site Control | Controlled v1.1
WP04-05 | 04 | WP04 | Sponsor and Entity Readiness | Funding Preparedness | Numeric / percentage / currency with unit and period | M/C | Captures the controlled funding preparedness data for Stage 04 (Sponsor and Entity Readiness); link source, owner, status, evidence, risk and decision impact. | Opportunity, Mandate and Site Control | Controlled v1.1
WP04-06 | 04 | WP04 | Sponsor and Entity Readiness | Legal Authority | Linked party / engagement / due-diligence status | M/C | Captures the controlled legal authority data for Stage 04 (Sponsor and Entity Readiness); link source, owner, status, evidence, risk and decision impact. | Opportunity, Mandate and Site Control | Controlled v1.1
WP05-01 | 05 | WP05 | Land Security and Site Control | Title Deed | Structured value + evidence + status | M/C | Captures the controlled title deed data for Stage 05 (Land Security and Site Control); link source, owner, status, evidence, risk and decision impact. | Opportunity, Mandate and Site Control | Controlled v1.1
WP05-02 | 05 | WP05 | Land Security and Site Control | Landowner Consent | Status + authority/reference + dates/conditions | M/C | Captures the controlled landowner consent data for Stage 05 (Land Security and Site Control); link source, owner, status, evidence, risk and decision impact. | Opportunity, Mandate and Site Control | Controlled v1.1
WP05-03 | 05 | WP05 | Land Security and Site Control | Lease Or Purchase Rights | Status + authority/reference + dates/conditions | M/C | Captures the controlled lease or purchase rights data for Stage 05 (Land Security and Site Control); link source, owner, status, evidence, risk and decision impact. | Opportunity, Mandate and Site Control | Controlled v1.1
WP05-04 | 05 | WP05 | Land Security and Site Control | Site Boundaries | Structured value + evidence + status | M/C | Captures the controlled site boundaries data for Stage 05 (Land Security and Site Control); link source, owner, status, evidence, risk and decision impact. | Opportunity, Mandate and Site Control | Controlled v1.1
WP05-05 | 05 | WP05 | Land Security and Site Control | Sg Diagram | Structured value + evidence + status | M/C | Captures the controlled sg diagram data for Stage 05 (Land Security and Site Control); link source, owner, status, evidence, risk and decision impact. | Opportunity, Mandate and Site Control | Controlled v1.1
WP05-06 | 05 | WP05 | Land Security and Site Control | Wayleaves | Status + authority/reference + dates/conditions | M/C | Captures the controlled wayleaves data for Stage 05 (Land Security and Site Control); link source, owner, status, evidence, risk and decision impact. | Opportunity, Mandate and Site Control | Controlled v1.1
WP06-01 | 06 | WP06 | Feasibility Studies and Market Demand | Retail Demand | Structured value + evidence + status | M/C | Captures the controlled retail demand data for Stage 06 (Feasibility Studies and Market Demand); link source, owner, status, evidence, risk and decision impact. | Feasibility, Rights, Approvals and Stakeholders | Controlled v1.1
WP06-02 | 06 | WP06 | Feasibility Studies and Market Demand | Fuel Demand | Structured value + evidence + status | M/C | Captures the controlled fuel demand data for Stage 06 (Feasibility Studies and Market Demand); link source, owner, status, evidence, risk and decision impact. | Feasibility, Rights, Approvals and Stakeholders | Controlled v1.1
WP06-03 | 06 | WP06 | Feasibility Studies and Market Demand | Boxer Anchor Viability | Linked party / engagement / due-diligence status | M/C | Captures the controlled boxer anchor viability data for Stage 06 (Feasibility Studies and Market Demand); link source, owner, status, evidence, risk and decision impact. | Feasibility, Rights, Approvals and Stakeholders | Controlled v1.1
WP06-04 | 06 | WP06 | Feasibility Studies and Market Demand | Line-Shop Demand | Structured value + evidence + status | M/C | Captures the controlled line-shop demand data for Stage 06 (Feasibility Studies and Market Demand); link source, owner, status, evidence, risk and decision impact. | Feasibility, Rights, Approvals and Stakeholders | Controlled v1.1
WP06-05 | 06 | WP06 | Feasibility Studies and Market Demand | Fast-Food Demand | Structured value + evidence + status | M/C | Captures the controlled fast-food demand data for Stage 06 (Feasibility Studies and Market Demand); link source, owner, status, evidence, risk and decision impact. | Feasibility, Rights, Approvals and Stakeholders | Controlled v1.1
WP06-06 | 06 | WP06 | Feasibility Studies and Market Demand | Traffic Volumes | Numeric / percentage / currency with unit and period | M/C | Captures the controlled traffic volumes data for Stage 06 (Feasibility Studies and Market Demand); link source, owner, status, evidence, risk and decision impact. | Feasibility, Rights, Approvals and Stakeholders | Controlled v1.1
WP07-01 | 07 | WP07 | Traffic, Access and Mobility Feasibility | R567 Entrance | Structured value + evidence + status | M/C | Captures the controlled r567 entrance data for Stage 07 (Traffic, Access and Mobility Feasibility); link source, owner, status, evidence, risk and decision impact. | Feasibility, Rights, Approvals and Stakeholders | Controlled v1.1
WP07-02 | 07 | WP07 | Traffic, Access and Mobility Feasibility | Turning Lanes | Structured value + evidence + status | M/C | Captures the controlled turning lanes data for Stage 07 (Traffic, Access and Mobility Feasibility); link source, owner, status, evidence, risk and decision impact. | Feasibility, Rights, Approvals and Stakeholders | Controlled v1.1
WP07-03 | 07 | WP07 | Traffic, Access and Mobility Feasibility | Sight Distances | Structured value + evidence + status | M/C | Captures the controlled sight distances data for Stage 07 (Traffic, Access and Mobility Feasibility); link source, owner, status, evidence, risk and decision impact. | Feasibility, Rights, Approvals and Stakeholders | Controlled v1.1
WP07-04 | 07 | WP07 | Traffic, Access and Mobility Feasibility | Heavy Vehicle Movement | Structured value + evidence + status | M/C | Captures the controlled heavy vehicle movement data for Stage 07 (Traffic, Access and Mobility Feasibility); link source, owner, status, evidence, risk and decision impact. | Feasibility, Rights, Approvals and Stakeholders | Controlled v1.1
WP07-05 | 07 | WP07 | Traffic, Access and Mobility Feasibility | Pedestrian Safety | Structured value + evidence + status | M/C | Captures the controlled pedestrian safety data for Stage 07 (Traffic, Access and Mobility Feasibility); link source, owner, status, evidence, risk and decision impact. | Feasibility, Rights, Approvals and Stakeholders | Controlled v1.1
WP07-06 | 07 | WP07 | Traffic, Access and Mobility Feasibility | Public Transport Interface | Structured value + evidence + status | M/C | Captures the controlled public transport interface data for Stage 07 (Traffic, Access and Mobility Feasibility); link source, owner, status, evidence, risk and decision impact. | Feasibility, Rights, Approvals and Stakeholders | Controlled v1.1
WP08-01 | 08 | WP08 | Bulk Services and Infrastructure Feasibility | Water Supply | Structured value + evidence + status | M/C | Captures the controlled water supply data for Stage 08 (Bulk Services and Infrastructure Feasibility); link source, owner, status, evidence, risk and decision impact. | Feasibility, Rights, Approvals and Stakeholders | Controlled v1.1
WP08-02 | 08 | WP08 | Bulk Services and Infrastructure Feasibility | Sewer Capacity | Numeric / percentage / currency with unit and period | M/C | Captures the controlled sewer capacity data for Stage 08 (Bulk Services and Infrastructure Feasibility); link source, owner, status, evidence, risk and decision impact. | Feasibility, Rights, Approvals and Stakeholders | Controlled v1.1
WP08-03 | 08 | WP08 | Bulk Services and Infrastructure Feasibility | Stormwater Discharge | Structured value + evidence + status | M/C | Captures the controlled stormwater discharge data for Stage 08 (Bulk Services and Infrastructure Feasibility); link source, owner, status, evidence, risk and decision impact. | Feasibility, Rights, Approvals and Stakeholders | Controlled v1.1
WP08-04 | 08 | WP08 | Bulk Services and Infrastructure Feasibility | Electrical Capacity | Numeric / percentage / currency with unit and period | M/C | Captures the controlled electrical capacity data for Stage 08 (Bulk Services and Infrastructure Feasibility); link source, owner, status, evidence, risk and decision impact. | Feasibility, Rights, Approvals and Stakeholders | Controlled v1.1
WP08-05 | 08 | WP08 | Bulk Services and Infrastructure Feasibility | Fire Water | Structured value + evidence + status | M/C | Captures the controlled fire water data for Stage 08 (Bulk Services and Infrastructure Feasibility); link source, owner, status, evidence, risk and decision impact. | Feasibility, Rights, Approvals and Stakeholders | Controlled v1.1
WP08-06 | 08 | WP08 | Bulk Services and Infrastructure Feasibility | Ict Services | Structured value + evidence + status | M/C | Captures the controlled ict services data for Stage 08 (Bulk Services and Infrastructure Feasibility); link source, owner, status, evidence, risk and decision impact. | Feasibility, Rights, Approvals and Stakeholders | Controlled v1.1
WP09-01 | 09 | WP09 | Environmental Screening and Scoping | Nema Triggers | Structured value + evidence + status | M/C | Captures the controlled nema triggers data for Stage 09 (Environmental Screening and Scoping); link source, owner, status, evidence, risk and decision impact. | Feasibility, Rights, Approvals and Stakeholders | Controlled v1.1
WP09-02 | 09 | WP09 | Environmental Screening and Scoping | Wetland Sensitivity | Structured value + evidence + status | M/C | Captures the controlled wetland sensitivity data for Stage 09 (Environmental Screening and Scoping); link source, owner, status, evidence, risk and decision impact. | Feasibility, Rights, Approvals and Stakeholders | Controlled v1.1
WP09-03 | 09 | WP09 | Environmental Screening and Scoping | Biodiversity Risk | Structured value + evidence + status | M/C | Captures the controlled biodiversity risk data for Stage 09 (Environmental Screening and Scoping); link source, owner, status, evidence, risk and decision impact. | Feasibility, Rights, Approvals and Stakeholders | Controlled v1.1
WP09-04 | 09 | WP09 | Environmental Screening and Scoping | Heritage Risk | Structured value + evidence + status | M/C | Captures the controlled heritage risk data for Stage 09 (Environmental Screening and Scoping); link source, owner, status, evidence, risk and decision impact. | Feasibility, Rights, Approvals and Stakeholders | Controlled v1.1
WP09-05 | 09 | WP09 | Environmental Screening and Scoping | Groundwater Risk | Structured value + evidence + status | M/C | Captures the controlled groundwater risk data for Stage 09 (Environmental Screening and Scoping); link source, owner, status, evidence, risk and decision impact. | Feasibility, Rights, Approvals and Stakeholders | Controlled v1.1
WP09-06 | 09 | WP09 | Environmental Screening and Scoping | Noise Sources | Structured value + evidence + status | M/C | Captures the controlled noise sources data for Stage 09 (Environmental Screening and Scoping); link source, owner, status, evidence, risk and decision impact. | Feasibility, Rights, Approvals and Stakeholders | Controlled v1.1
WP10-01 | 10 | WP10 | Land Use Rights and Zoning | Current Agricultural Zoning | Status + authority/reference + dates/conditions | M/C | Captures the controlled current agricultural zoning data for Stage 10 (Land Use Rights and Zoning); link source, owner, status, evidence, risk and decision impact. | Feasibility, Rights, Approvals and Stakeholders | Controlled v1.1
WP10-02 | 10 | WP10 | Land Use Rights and Zoning | Rezoning Pathway | Status + authority/reference + dates/conditions | M/C | Captures the controlled rezoning pathway data for Stage 10 (Land Use Rights and Zoning); link source, owner, status, evidence, risk and decision impact. | Feasibility, Rights, Approvals and Stakeholders | Controlled v1.1
WP10-03 | 10 | WP10 | Land Use Rights and Zoning | Consent Use | Status + authority/reference + dates/conditions | M/C | Captures the controlled consent use data for Stage 10 (Land Use Rights and Zoning); link source, owner, status, evidence, risk and decision impact. | Feasibility, Rights, Approvals and Stakeholders | Controlled v1.1
WP10-04 | 10 | WP10 | Land Use Rights and Zoning | Site Development Plan | Document / version / review and approval status | M/C | Captures the controlled site development plan data for Stage 10 (Land Use Rights and Zoning); link source, owner, status, evidence, risk and decision impact. | Feasibility, Rights, Approvals and Stakeholders | Controlled v1.1
WP10-05 | 10 | WP10 | Land Use Rights and Zoning | Parking Compliance | Structured value + evidence + status | M/C | Captures the controlled parking compliance data for Stage 10 (Land Use Rights and Zoning); link source, owner, status, evidence, risk and decision impact. | Feasibility, Rights, Approvals and Stakeholders | Controlled v1.1
WP10-06 | 10 | WP10 | Land Use Rights and Zoning | Far And Coverage | Numeric / percentage / currency with unit and period | M/C | Captures the controlled far and coverage data for Stage 10 (Land Use Rights and Zoning); link source, owner, status, evidence, risk and decision impact. | Feasibility, Rights, Approvals and Stakeholders | Controlled v1.1
WP11-01 | 11 | WP11 | Environmental Authorisation - Estimated 10 Months | Screening Report | Document / version / review and approval status | M/C | Captures the controlled screening report data for Stage 11 (Environmental Authorisation - Estimated 10 Months); link source, owner, status, evidence, risk and decision impact. | Feasibility, Rights, Approvals and Stakeholders | Controlled v1.1
WP11-02 | 11 | WP11 | Environmental Authorisation - Estimated 10 Months | Specialist Studies | Document / version / review and approval status | M/C | Captures the controlled specialist studies data for Stage 11 (Environmental Authorisation - Estimated 10 Months); link source, owner, status, evidence, risk and decision impact. | Feasibility, Rights, Approvals and Stakeholders | Controlled v1.1
WP11-03 | 11 | WP11 | Environmental Authorisation - Estimated 10 Months | Draft Bar Or Eia | Structured value + evidence + status | M/C | Captures the controlled draft bar or eia data for Stage 11 (Environmental Authorisation - Estimated 10 Months); link source, owner, status, evidence, risk and decision impact. | Feasibility, Rights, Approvals and Stakeholders | Controlled v1.1
WP11-04 | 11 | WP11 | Environmental Authorisation - Estimated 10 Months | Public Participation | Structured value + evidence + status | M/C | Captures the controlled public participation data for Stage 11 (Environmental Authorisation - Estimated 10 Months); link source, owner, status, evidence, risk and decision impact. | Feasibility, Rights, Approvals and Stakeholders | Controlled v1.1
WP11-05 | 11 | WP11 | Environmental Authorisation - Estimated 10 Months | Authority Comments | Linked party / engagement / due-diligence status | M/C | Captures the controlled authority comments data for Stage 11 (Environmental Authorisation - Estimated 10 Months); link source, owner, status, evidence, risk and decision impact. | Feasibility, Rights, Approvals and Stakeholders | Controlled v1.1
WP11-06 | 11 | WP11 | Environmental Authorisation - Estimated 10 Months | Empr | Document / version / review and approval status | M/C | Captures the controlled empr data for Stage 11 (Environmental Authorisation - Estimated 10 Months); link source, owner, status, evidence, risk and decision impact. | Feasibility, Rights, Approvals and Stakeholders | Controlled v1.1
WP12-01 | 12 | WP12 | Stakeholder Mapping and Public Participation | Municipality | Structured value + evidence + status | M/C | Captures the controlled municipality data for Stage 12 (Stakeholder Mapping and Public Participation); link source, owner, status, evidence, risk and decision impact. | Feasibility, Rights, Approvals and Stakeholders | Controlled v1.1
WP12-02 | 12 | WP12 | Stakeholder Mapping and Public Participation | Road Authority | Linked party / engagement / due-diligence status | M/C | Captures the controlled road authority data for Stage 12 (Stakeholder Mapping and Public Participation); link source, owner, status, evidence, risk and decision impact. | Feasibility, Rights, Approvals and Stakeholders | Controlled v1.1
WP12-03 | 12 | WP12 | Stakeholder Mapping and Public Participation | Dmre | Structured value + evidence + status | M/C | Captures the controlled dmre data for Stage 12 (Stakeholder Mapping and Public Participation); link source, owner, status, evidence, risk and decision impact. | Feasibility, Rights, Approvals and Stakeholders | Controlled v1.1
WP12-04 | 12 | WP12 | Stakeholder Mapping and Public Participation | Environmental Authority | Linked party / engagement / due-diligence status | M/C | Captures the controlled environmental authority data for Stage 12 (Stakeholder Mapping and Public Participation); link source, owner, status, evidence, risk and decision impact. | Feasibility, Rights, Approvals and Stakeholders | Controlled v1.1
WP12-05 | 12 | WP12 | Stakeholder Mapping and Public Participation | Community Leaders | Linked party / engagement / due-diligence status | M/C | Captures the controlled community leaders data for Stage 12 (Stakeholder Mapping and Public Participation); link source, owner, status, evidence, risk and decision impact. | Feasibility, Rights, Approvals and Stakeholders | Controlled v1.1
WP12-06 | 12 | WP12 | Stakeholder Mapping and Public Participation | Neighbouring Landowners | Linked party / engagement / due-diligence status | M/C | Captures the controlled neighbouring landowners data for Stage 12 (Stakeholder Mapping and Public Participation); link source, owner, status, evidence, risk and decision impact. | Feasibility, Rights, Approvals and Stakeholders | Controlled v1.1
WP13-01 | 13 | WP13 | Concept Development | Site Layout | Document / version / review and approval status | M/C | Captures the controlled site layout data for Stage 13 (Concept Development); link source, owner, status, evidence, risk and decision impact. | Concept, Commercial Alignment and Occupier Strategy | Controlled v1.1
WP13-02 | 13 | WP13 | Concept Development | Boxer Store Placement | Linked party / engagement / due-diligence status | M/C | Captures the controlled boxer store placement data for Stage 13 (Concept Development); link source, owner, status, evidence, risk and decision impact. | Concept, Commercial Alignment and Occupier Strategy | Controlled v1.1
WP13-03 | 13 | WP13 | Concept Development | Fuel Forecourt Interface | Structured value + evidence + status | M/C | Captures the controlled fuel forecourt interface data for Stage 13 (Concept Development); link source, owner, status, evidence, risk and decision impact. | Concept, Commercial Alignment and Occupier Strategy | Controlled v1.1
WP13-04 | 13 | WP13 | Concept Development | Line-Shop Frontage | Structured value + evidence + status | M/C | Captures the controlled line-shop frontage data for Stage 13 (Concept Development); link source, owner, status, evidence, risk and decision impact. | Concept, Commercial Alignment and Occupier Strategy | Controlled v1.1
WP13-05 | 13 | WP13 | Concept Development | Qsr Positioning | Structured value + evidence + status | M/C | Captures the controlled qsr positioning data for Stage 13 (Concept Development); link source, owner, status, evidence, risk and decision impact. | Concept, Commercial Alignment and Occupier Strategy | Controlled v1.1
WP13-06 | 13 | WP13 | Concept Development | Parking Concept | Structured value + evidence + status | M/C | Captures the controlled parking concept data for Stage 13 (Concept Development); link source, owner, status, evidence, risk and decision impact. | Concept, Commercial Alignment and Occupier Strategy | Controlled v1.1
WP14-01 | 14 | WP14 | Retail Masterplanning and GLA Strategy | Anchor Gla | Numeric / percentage / currency with unit and period | M/C | Captures the controlled anchor gla data for Stage 14 (Retail Masterplanning and GLA Strategy); link source, owner, status, evidence, risk and decision impact. | Concept, Commercial Alignment and Occupier Strategy | Controlled v1.1
WP14-02 | 14 | WP14 | Retail Masterplanning and GLA Strategy | Line-Shop Gla | Numeric / percentage / currency with unit and period | M/C | Captures the controlled line-shop gla data for Stage 14 (Retail Masterplanning and GLA Strategy); link source, owner, status, evidence, risk and decision impact. | Concept, Commercial Alignment and Occupier Strategy | Controlled v1.1
WP14-03 | 14 | WP14 | Retail Masterplanning and GLA Strategy | Qsr Gla | Numeric / percentage / currency with unit and period | M/C | Captures the controlled qsr gla data for Stage 14 (Retail Masterplanning and GLA Strategy); link source, owner, status, evidence, risk and decision impact. | Concept, Commercial Alignment and Occupier Strategy | Controlled v1.1
WP14-04 | 14 | WP14 | Retail Masterplanning and GLA Strategy | Forecourt Convenience Offer | Structured value + evidence + status | M/C | Captures the controlled forecourt convenience offer data for Stage 14 (Retail Masterplanning and GLA Strategy); link source, owner, status, evidence, risk and decision impact. | Concept, Commercial Alignment and Occupier Strategy | Controlled v1.1
WP14-05 | 14 | WP14 | Retail Masterplanning and GLA Strategy | Back-Of-House Allocation | Structured value + evidence + status | M/C | Captures the controlled back-of-house allocation data for Stage 14 (Retail Masterplanning and GLA Strategy); link source, owner, status, evidence, risk and decision impact. | Concept, Commercial Alignment and Occupier Strategy | Controlled v1.1
WP14-06 | 14 | WP14 | Retail Masterplanning and GLA Strategy | Loading Areas | Structured value + evidence + status | M/C | Captures the controlled loading areas data for Stage 14 (Retail Masterplanning and GLA Strategy); link source, owner, status, evidence, risk and decision impact. | Concept, Commercial Alignment and Occupier Strategy | Controlled v1.1
WP15-01 | 15 | WP15 | Boxer Superstores Anchor Alignment | Boxer Specifications | Linked party / engagement / due-diligence status | M/C | Captures the controlled boxer specifications data for Stage 15 (Boxer Superstores Anchor Alignment); link source, owner, status, evidence, risk and decision impact. | Concept, Commercial Alignment and Occupier Strategy | Controlled v1.1
WP15-02 | 15 | WP15 | Boxer Superstores Anchor Alignment | Anchor Lease Principles | Structured value + evidence + status | M/C | Captures the controlled anchor lease principles data for Stage 15 (Boxer Superstores Anchor Alignment); link source, owner, status, evidence, risk and decision impact. | Concept, Commercial Alignment and Occupier Strategy | Controlled v1.1
WP15-03 | 15 | WP15 | Boxer Superstores Anchor Alignment | Loading Requirements | Structured value + evidence + status | M/C | Captures the controlled loading requirements data for Stage 15 (Boxer Superstores Anchor Alignment); link source, owner, status, evidence, risk and decision impact. | Concept, Commercial Alignment and Occupier Strategy | Controlled v1.1
WP15-04 | 15 | WP15 | Boxer Superstores Anchor Alignment | Store Footprint | Structured value + evidence + status | M/C | Captures the controlled store footprint data for Stage 15 (Boxer Superstores Anchor Alignment); link source, owner, status, evidence, risk and decision impact. | Concept, Commercial Alignment and Occupier Strategy | Controlled v1.1
WP15-05 | 15 | WP15 | Boxer Superstores Anchor Alignment | Service Yard | Structured value + evidence + status | M/C | Captures the controlled service yard data for Stage 15 (Boxer Superstores Anchor Alignment); link source, owner, status, evidence, risk and decision impact. | Concept, Commercial Alignment and Occupier Strategy | Controlled v1.1
WP15-06 | 15 | WP15 | Boxer Superstores Anchor Alignment | Delivery Windows | Date / duration / schedule status | M/C | Captures the controlled delivery windows data for Stage 15 (Boxer Superstores Anchor Alignment); link source, owner, status, evidence, risk and decision impact. | Concept, Commercial Alignment and Occupier Strategy | Controlled v1.1
WP16-01 | 16 | WP16 | Tenant Acquisition Strategy | Target Tenant List | Linked party / engagement / due-diligence status | M/C | Captures the controlled target tenant list data for Stage 16 (Tenant Acquisition Strategy); link source, owner, status, evidence, risk and decision impact. | Concept, Commercial Alignment and Occupier Strategy | Controlled v1.1
WP16-02 | 16 | WP16 | Tenant Acquisition Strategy | Leasing Brochure | Structured value + evidence + status | M/C | Captures the controlled leasing brochure data for Stage 16 (Tenant Acquisition Strategy); link source, owner, status, evidence, risk and decision impact. | Concept, Commercial Alignment and Occupier Strategy | Controlled v1.1
WP16-03 | 16 | WP16 | Tenant Acquisition Strategy | Anchor-Led Positioning | Structured value + evidence + status | M/C | Captures the controlled anchor-led positioning data for Stage 16 (Tenant Acquisition Strategy); link source, owner, status, evidence, risk and decision impact. | Concept, Commercial Alignment and Occupier Strategy | Controlled v1.1
WP16-04 | 16 | WP16 | Tenant Acquisition Strategy | Rental Assumptions | Structured value + evidence + status | M/C | Captures the controlled rental assumptions data for Stage 16 (Tenant Acquisition Strategy); link source, owner, status, evidence, risk and decision impact. | Concept, Commercial Alignment and Occupier Strategy | Controlled v1.1
WP16-05 | 16 | WP16 | Tenant Acquisition Strategy | Tenant Due Diligence | Linked party / engagement / due-diligence status | M/C | Captures the controlled tenant due diligence data for Stage 16 (Tenant Acquisition Strategy); link source, owner, status, evidence, risk and decision impact. | Concept, Commercial Alignment and Occupier Strategy | Controlled v1.1
WP16-06 | 16 | WP16 | Tenant Acquisition Strategy | Letters Of Intent | Structured value + evidence + status | M/C | Captures the controlled letters of intent data for Stage 16 (Tenant Acquisition Strategy); link source, owner, status, evidence, risk and decision impact. | Concept, Commercial Alignment and Occupier Strategy | Controlled v1.1
WP17-01 | 17 | WP17 | Line-Shop Tenant Mix and Leasing | Pharmacy Option | Structured value + evidence + status | M/C | Captures the controlled pharmacy option data for Stage 17 (Line-Shop Tenant Mix and Leasing); link source, owner, status, evidence, risk and decision impact. | Concept, Commercial Alignment and Occupier Strategy | Controlled v1.1
WP17-02 | 17 | WP17 | Line-Shop Tenant Mix and Leasing | Cellular Tenant | Linked party / engagement / due-diligence status | M/C | Captures the controlled cellular tenant data for Stage 17 (Line-Shop Tenant Mix and Leasing); link source, owner, status, evidence, risk and decision impact. | Concept, Commercial Alignment and Occupier Strategy | Controlled v1.1
WP17-03 | 17 | WP17 | Line-Shop Tenant Mix and Leasing | Banking/Atm | Structured value + evidence + status | M/C | Captures the controlled banking/atm data for Stage 17 (Line-Shop Tenant Mix and Leasing); link source, owner, status, evidence, risk and decision impact. | Concept, Commercial Alignment and Occupier Strategy | Controlled v1.1
WP17-04 | 17 | WP17 | Line-Shop Tenant Mix and Leasing | Bakery Or Deli | Structured value + evidence + status | M/C | Captures the controlled bakery or deli data for Stage 17 (Line-Shop Tenant Mix and Leasing); link source, owner, status, evidence, risk and decision impact. | Concept, Commercial Alignment and Occupier Strategy | Controlled v1.1
WP17-05 | 17 | WP17 | Line-Shop Tenant Mix and Leasing | Local Enterprise | Structured value + evidence + status | M/C | Captures the controlled local enterprise data for Stage 17 (Line-Shop Tenant Mix and Leasing); link source, owner, status, evidence, risk and decision impact. | Concept, Commercial Alignment and Occupier Strategy | Controlled v1.1
WP17-06 | 17 | WP17 | Line-Shop Tenant Mix and Leasing | Beauty Or Personal Care | Structured value + evidence + status | M/C | Captures the controlled beauty or personal care data for Stage 17 (Line-Shop Tenant Mix and Leasing); link source, owner, status, evidence, risk and decision impact. | Concept, Commercial Alignment and Occupier Strategy | Controlled v1.1
WP18-01 | 18 | WP18 | Fast-Food Chain Restaurant Acquisition | Brand Targeting | Structured value + evidence + status | M/C | Captures the controlled brand targeting data for Stage 18 (Fast-Food Chain Restaurant Acquisition); link source, owner, status, evidence, risk and decision impact. | Concept, Commercial Alignment and Occupier Strategy | Controlled v1.1
WP18-02 | 18 | WP18 | Fast-Food Chain Restaurant Acquisition | Drive-Through Feasibility | Structured value + evidence + status | M/C | Captures the controlled drive-through feasibility data for Stage 18 (Fast-Food Chain Restaurant Acquisition); link source, owner, status, evidence, risk and decision impact. | Concept, Commercial Alignment and Occupier Strategy | Controlled v1.1
WP18-03 | 18 | WP18 | Fast-Food Chain Restaurant Acquisition | Kitchen Extraction | Structured value + evidence + status | M/C | Captures the controlled kitchen extraction data for Stage 18 (Fast-Food Chain Restaurant Acquisition); link source, owner, status, evidence, risk and decision impact. | Concept, Commercial Alignment and Occupier Strategy | Controlled v1.1
WP18-04 | 18 | WP18 | Fast-Food Chain Restaurant Acquisition | Grease Traps | Structured value + evidence + status | M/C | Captures the controlled grease traps data for Stage 18 (Fast-Food Chain Restaurant Acquisition); link source, owner, status, evidence, risk and decision impact. | Concept, Commercial Alignment and Occupier Strategy | Controlled v1.1
WP18-05 | 18 | WP18 | Fast-Food Chain Restaurant Acquisition | Delivery Access | Structured value + evidence + status | M/C | Captures the controlled delivery access data for Stage 18 (Fast-Food Chain Restaurant Acquisition); link source, owner, status, evidence, risk and decision impact. | Concept, Commercial Alignment and Occupier Strategy | Controlled v1.1
WP18-06 | 18 | WP18 | Fast-Food Chain Restaurant Acquisition | Seating Areas | Structured value + evidence + status | M/C | Captures the controlled seating areas data for Stage 18 (Fast-Food Chain Restaurant Acquisition); link source, owner, status, evidence, risk and decision impact. | Concept, Commercial Alignment and Occupier Strategy | Controlled v1.1
WP19-01 | 19 | WP19 | Fuel Partner and Forecourt Coordination | Totalenergies Standards | Structured value + evidence + status | M/C | Captures the controlled totalenergies standards data for Stage 19 (Fuel Partner and Forecourt Coordination); link source, owner, status, evidence, risk and decision impact. | Concept, Commercial Alignment and Occupier Strategy | Controlled v1.1
WP19-02 | 19 | WP19 | Fuel Partner and Forecourt Coordination | Forecourt Layout | Document / version / review and approval status | M/C | Captures the controlled forecourt layout data for Stage 19 (Fuel Partner and Forecourt Coordination); link source, owner, status, evidence, risk and decision impact. | Concept, Commercial Alignment and Occupier Strategy | Controlled v1.1
WP19-03 | 19 | WP19 | Fuel Partner and Forecourt Coordination | Tank Farm | Structured value + evidence + status | M/C | Captures the controlled tank farm data for Stage 19 (Fuel Partner and Forecourt Coordination); link source, owner, status, evidence, risk and decision impact. | Concept, Commercial Alignment and Occupier Strategy | Controlled v1.1
WP19-04 | 19 | WP19 | Fuel Partner and Forecourt Coordination | Fuel Logistics | Structured value + evidence + status | M/C | Captures the controlled fuel logistics data for Stage 19 (Fuel Partner and Forecourt Coordination); link source, owner, status, evidence, risk and decision impact. | Concept, Commercial Alignment and Occupier Strategy | Controlled v1.1
WP19-05 | 19 | WP19 | Fuel Partner and Forecourt Coordination | C-Store Integration | Structured value + evidence + status | M/C | Captures the controlled c-store integration data for Stage 19 (Fuel Partner and Forecourt Coordination); link source, owner, status, evidence, risk and decision impact. | Concept, Commercial Alignment and Occupier Strategy | Controlled v1.1
WP19-06 | 19 | WP19 | Fuel Partner and Forecourt Coordination | Brand Signage | Structured value + evidence + status | M/C | Captures the controlled brand signage data for Stage 19 (Fuel Partner and Forecourt Coordination); link source, owner, status, evidence, risk and decision impact. | Concept, Commercial Alignment and Occupier Strategy | Controlled v1.1
WP20-01 | 20 | WP20 | Development Design | Architectural Design | Document / version / review and approval status | M/C | Captures the controlled architectural design data for Stage 20 (Development Design); link source, owner, status, evidence, risk and decision impact. | Design, Cost, Capital, Procurement and Permitting | Controlled v1.1
WP20-02 | 20 | WP20 | Development Design | Civil Design | Document / version / review and approval status | M/C | Captures the controlled civil design data for Stage 20 (Development Design); link source, owner, status, evidence, risk and decision impact. | Design, Cost, Capital, Procurement and Permitting | Controlled v1.1
WP20-03 | 20 | WP20 | Development Design | Structural Design | Document / version / review and approval status | M/C | Captures the controlled structural design data for Stage 20 (Development Design); link source, owner, status, evidence, risk and decision impact. | Design, Cost, Capital, Procurement and Permitting | Controlled v1.1
WP20-04 | 20 | WP20 | Development Design | Mep Design | Document / version / review and approval status | M/C | Captures the controlled mep design data for Stage 20 (Development Design); link source, owner, status, evidence, risk and decision impact. | Design, Cost, Capital, Procurement and Permitting | Controlled v1.1
WP20-05 | 20 | WP20 | Development Design | Fire Strategy | Document / version / review and approval status | M/C | Captures the controlled fire strategy data for Stage 20 (Development Design); link source, owner, status, evidence, risk and decision impact. | Design, Cost, Capital, Procurement and Permitting | Controlled v1.1
WP20-06 | 20 | WP20 | Development Design | Landscaping | Structured value + evidence + status | M/C | Captures the controlled landscaping data for Stage 20 (Development Design); link source, owner, status, evidence, risk and decision impact. | Design, Cost, Capital, Procurement and Permitting | Controlled v1.1
WP21-01 | 21 | WP21 | Engineering Design and Technical Documentation | Bulk Earthworks | Structured value + evidence + status | M/C | Captures the controlled bulk earthworks data for Stage 21 (Engineering Design and Technical Documentation); link source, owner, status, evidence, risk and decision impact. | Design, Cost, Capital, Procurement and Permitting | Controlled v1.1
WP21-02 | 21 | WP21 | Engineering Design and Technical Documentation | Stormwater Design | Document / version / review and approval status | M/C | Captures the controlled stormwater design data for Stage 21 (Engineering Design and Technical Documentation); link source, owner, status, evidence, risk and decision impact. | Design, Cost, Capital, Procurement and Permitting | Controlled v1.1
WP21-03 | 21 | WP21 | Engineering Design and Technical Documentation | Road Pavements | Structured value + evidence + status | M/C | Captures the controlled road pavements data for Stage 21 (Engineering Design and Technical Documentation); link source, owner, status, evidence, risk and decision impact. | Design, Cost, Capital, Procurement and Permitting | Controlled v1.1
WP21-04 | 21 | WP21 | Engineering Design and Technical Documentation | Water Reticulation | Structured value + evidence + status | M/C | Captures the controlled water reticulation data for Stage 21 (Engineering Design and Technical Documentation); link source, owner, status, evidence, risk and decision impact. | Design, Cost, Capital, Procurement and Permitting | Controlled v1.1
WP21-05 | 21 | WP21 | Engineering Design and Technical Documentation | Sewer Reticulation | Structured value + evidence + status | M/C | Captures the controlled sewer reticulation data for Stage 21 (Engineering Design and Technical Documentation); link source, owner, status, evidence, risk and decision impact. | Design, Cost, Capital, Procurement and Permitting | Controlled v1.1
WP21-06 | 21 | WP21 | Engineering Design and Technical Documentation | Electrical Reticulation | Structured value + evidence + status | M/C | Captures the controlled electrical reticulation data for Stage 21 (Engineering Design and Technical Documentation); link source, owner, status, evidence, risk and decision impact. | Design, Cost, Capital, Procurement and Permitting | Controlled v1.1
WP22-01 | 22 | WP22 | Cost Planning and Financial Modelling | Capex Estimate | Structured value + evidence + status | M/C | Captures the controlled capex estimate data for Stage 22 (Cost Planning and Financial Modelling); link source, owner, status, evidence, risk and decision impact. | Design, Cost, Capital, Procurement and Permitting | Controlled v1.1
WP22-02 | 22 | WP22 | Cost Planning and Financial Modelling | Professional Fees | Numeric / percentage / currency with unit and period | M/C | Captures the controlled professional fees data for Stage 22 (Cost Planning and Financial Modelling); link source, owner, status, evidence, risk and decision impact. | Design, Cost, Capital, Procurement and Permitting | Controlled v1.1
WP22-03 | 22 | WP22 | Cost Planning and Financial Modelling | Approval Costs | Numeric / percentage / currency with unit and period | M/C | Captures the controlled approval costs data for Stage 22 (Cost Planning and Financial Modelling); link source, owner, status, evidence, risk and decision impact. | Design, Cost, Capital, Procurement and Permitting | Controlled v1.1
WP22-04 | 22 | WP22 | Cost Planning and Financial Modelling | Tenant Fit-Out Allowances | Numeric / percentage / currency with unit and period | M/C | Captures the controlled tenant fit-out allowances data for Stage 22 (Cost Planning and Financial Modelling); link source, owner, status, evidence, risk and decision impact. | Design, Cost, Capital, Procurement and Permitting | Controlled v1.1
WP22-05 | 22 | WP22 | Cost Planning and Financial Modelling | Contingency | Numeric / percentage / currency with unit and period | M/C | Captures the controlled contingency data for Stage 22 (Cost Planning and Financial Modelling); link source, owner, status, evidence, risk and decision impact. | Design, Cost, Capital, Procurement and Permitting | Controlled v1.1
WP22-06 | 22 | WP22 | Cost Planning and Financial Modelling | Rental Income | Numeric / percentage / currency with unit and period | M/C | Captures the controlled rental income data for Stage 22 (Cost Planning and Financial Modelling); link source, owner, status, evidence, risk and decision impact. | Design, Cost, Capital, Procurement and Permitting | Controlled v1.1
WP23-01 | 23 | WP23 | Capital Structuring and Funding Readiness | Equity Contribution | Numeric / percentage / currency with unit and period | M/C | Captures the controlled equity contribution data for Stage 23 (Capital Structuring and Funding Readiness); link source, owner, status, evidence, risk and decision impact. | Design, Cost, Capital, Procurement and Permitting | Controlled v1.1
WP23-02 | 23 | WP23 | Capital Structuring and Funding Readiness | Debt Funding | Numeric / percentage / currency with unit and period | M/C | Captures the controlled debt funding data for Stage 23 (Capital Structuring and Funding Readiness); link source, owner, status, evidence, risk and decision impact. | Design, Cost, Capital, Procurement and Permitting | Controlled v1.1
WP23-03 | 23 | WP23 | Capital Structuring and Funding Readiness | Drawdown Plan | Document / version / review and approval status | M/C | Captures the controlled drawdown plan data for Stage 23 (Capital Structuring and Funding Readiness); link source, owner, status, evidence, risk and decision impact. | Design, Cost, Capital, Procurement and Permitting | Controlled v1.1
WP23-04 | 23 | WP23 | Capital Structuring and Funding Readiness | Security Package | Structured value + evidence + status | M/C | Captures the controlled security package data for Stage 23 (Capital Structuring and Funding Readiness); link source, owner, status, evidence, risk and decision impact. | Design, Cost, Capital, Procurement and Permitting | Controlled v1.1
WP23-05 | 23 | WP23 | Capital Structuring and Funding Readiness | Funder Due Diligence | Structured value + evidence + status | M/C | Captures the controlled funder due diligence data for Stage 23 (Capital Structuring and Funding Readiness); link source, owner, status, evidence, risk and decision impact. | Design, Cost, Capital, Procurement and Permitting | Controlled v1.1
WP23-06 | 23 | WP23 | Capital Structuring and Funding Readiness | Term Sheet | Structured value + evidence + status | M/C | Captures the controlled term sheet data for Stage 23 (Capital Structuring and Funding Readiness); link source, owner, status, evidence, risk and decision impact. | Design, Cost, Capital, Procurement and Permitting | Controlled v1.1
WP24-01 | 24 | WP24 | Procurement Strategy and Tender Documentation | Procurement Route | Numeric / percentage / currency with unit and period | M/C | Captures the controlled procurement route data for Stage 24 (Procurement Strategy and Tender Documentation); link source, owner, status, evidence, risk and decision impact. | Design, Cost, Capital, Procurement and Permitting | Controlled v1.1
WP24-02 | 24 | WP24 | Procurement Strategy and Tender Documentation | Tender Pack | Structured value + evidence + status | M/C | Captures the controlled tender pack data for Stage 24 (Procurement Strategy and Tender Documentation); link source, owner, status, evidence, risk and decision impact. | Design, Cost, Capital, Procurement and Permitting | Controlled v1.1
WP24-03 | 24 | WP24 | Procurement Strategy and Tender Documentation | Boq | Document / version / review and approval status | M/C | Captures the controlled boq data for Stage 24 (Procurement Strategy and Tender Documentation); link source, owner, status, evidence, risk and decision impact. | Design, Cost, Capital, Procurement and Permitting | Controlled v1.1
WP24-04 | 24 | WP24 | Procurement Strategy and Tender Documentation | Contract Conditions | Structured value + evidence + status | M/C | Captures the controlled contract conditions data for Stage 24 (Procurement Strategy and Tender Documentation); link source, owner, status, evidence, risk and decision impact. | Design, Cost, Capital, Procurement and Permitting | Controlled v1.1
WP24-05 | 24 | WP24 | Procurement Strategy and Tender Documentation | Bid Evaluation | Structured value + evidence + status | M/C | Captures the controlled bid evaluation data for Stage 24 (Procurement Strategy and Tender Documentation); link source, owner, status, evidence, risk and decision impact. | Design, Cost, Capital, Procurement and Permitting | Controlled v1.1
WP24-06 | 24 | WP24 | Procurement Strategy and Tender Documentation | Supplier Strategy | Linked party / engagement / due-diligence status | M/C | Captures the controlled supplier strategy data for Stage 24 (Procurement Strategy and Tender Documentation); link source, owner, status, evidence, risk and decision impact. | Design, Cost, Capital, Procurement and Permitting | Controlled v1.1
WP25-01 | 25 | WP25 | Contractor Due Diligence and Appointment | Contractor Capacity | Numeric / percentage / currency with unit and period | M/C | Captures the controlled contractor capacity data for Stage 25 (Contractor Due Diligence and Appointment); link source, owner, status, evidence, risk and decision impact. | Design, Cost, Capital, Procurement and Permitting | Controlled v1.1
WP25-02 | 25 | WP25 | Contractor Due Diligence and Appointment | Financial Strength | Structured value + evidence + status | M/C | Captures the controlled financial strength data for Stage 25 (Contractor Due Diligence and Appointment); link source, owner, status, evidence, risk and decision impact. | Design, Cost, Capital, Procurement and Permitting | Controlled v1.1
WP25-03 | 25 | WP25 | Contractor Due Diligence and Appointment | Similar Project Experience | Structured value + evidence + status | M/C | Captures the controlled similar project experience data for Stage 25 (Contractor Due Diligence and Appointment); link source, owner, status, evidence, risk and decision impact. | Design, Cost, Capital, Procurement and Permitting | Controlled v1.1
WP25-04 | 25 | WP25 | Contractor Due Diligence and Appointment | Hse Record | Structured value + evidence + status | M/C | Captures the controlled hse record data for Stage 25 (Contractor Due Diligence and Appointment); link source, owner, status, evidence, risk and decision impact. | Design, Cost, Capital, Procurement and Permitting | Controlled v1.1
WP25-05 | 25 | WP25 | Contractor Due Diligence and Appointment | Quality Systems | Structured value + evidence + status | M/C | Captures the controlled quality systems data for Stage 25 (Contractor Due Diligence and Appointment); link source, owner, status, evidence, risk and decision impact. | Design, Cost, Capital, Procurement and Permitting | Controlled v1.1
WP25-06 | 25 | WP25 | Contractor Due Diligence and Appointment | Programme Credibility | Document / version / review and approval status | M/C | Captures the controlled programme credibility data for Stage 25 (Contractor Due Diligence and Appointment); link source, owner, status, evidence, risk and decision impact. | Design, Cost, Capital, Procurement and Permitting | Controlled v1.1
WP26-01 | 26 | WP26 | Regulatory Permitting and Building Plan Approval | Building Plans | Document / version / review and approval status | M/C | Captures the controlled building plans data for Stage 26 (Regulatory Permitting and Building Plan Approval); link source, owner, status, evidence, risk and decision impact. | Design, Cost, Capital, Procurement and Permitting | Controlled v1.1
WP26-02 | 26 | WP26 | Regulatory Permitting and Building Plan Approval | Fire Approval | Status + authority/reference + dates/conditions | M/C | Captures the controlled fire approval data for Stage 26 (Regulatory Permitting and Building Plan Approval); link source, owner, status, evidence, risk and decision impact. | Design, Cost, Capital, Procurement and Permitting | Controlled v1.1
WP26-03 | 26 | WP26 | Regulatory Permitting and Building Plan Approval | Health Approval | Status + authority/reference + dates/conditions | M/C | Captures the controlled health approval data for Stage 26 (Regulatory Permitting and Building Plan Approval); link source, owner, status, evidence, risk and decision impact. | Design, Cost, Capital, Procurement and Permitting | Controlled v1.1
WP26-04 | 26 | WP26 | Regulatory Permitting and Building Plan Approval | Road Access Approval | Status + authority/reference + dates/conditions | M/C | Captures the controlled road access approval data for Stage 26 (Regulatory Permitting and Building Plan Approval); link source, owner, status, evidence, risk and decision impact. | Design, Cost, Capital, Procurement and Permitting | Controlled v1.1
WP26-05 | 26 | WP26 | Regulatory Permitting and Building Plan Approval | Water Connection | Structured value + evidence + status | M/C | Captures the controlled water connection data for Stage 26 (Regulatory Permitting and Building Plan Approval); link source, owner, status, evidence, risk and decision impact. | Design, Cost, Capital, Procurement and Permitting | Controlled v1.1
WP26-06 | 26 | WP26 | Regulatory Permitting and Building Plan Approval | Sewer Connection | Structured value + evidence + status | M/C | Captures the controlled sewer connection data for Stage 26 (Regulatory Permitting and Building Plan Approval); link source, owner, status, evidence, risk and decision impact. | Design, Cost, Capital, Procurement and Permitting | Controlled v1.1
WP27-01 | 27 | WP27 | Construction Mobilisation | Site Handover | Structured value + evidence + status | M/C | Captures the controlled site handover data for Stage 27 (Construction Mobilisation); link source, owner, status, evidence, risk and decision impact. | Construction, Quality, Commissioning and Handover | Controlled v1.1
WP27-02 | 27 | WP27 | Construction Mobilisation | Site Camp | Structured value + evidence + status | M/C | Captures the controlled site camp data for Stage 27 (Construction Mobilisation); link source, owner, status, evidence, risk and decision impact. | Construction, Quality, Commissioning and Handover | Controlled v1.1
WP27-03 | 27 | WP27 | Construction Mobilisation | Survey Setting Out | Structured value + evidence + status | M/C | Captures the controlled survey setting out data for Stage 27 (Construction Mobilisation); link source, owner, status, evidence, risk and decision impact. | Construction, Quality, Commissioning and Handover | Controlled v1.1
WP27-04 | 27 | WP27 | Construction Mobilisation | Hse File | Document / version / review and approval status | M/C | Captures the controlled hse file data for Stage 27 (Construction Mobilisation); link source, owner, status, evidence, risk and decision impact. | Construction, Quality, Commissioning and Handover | Controlled v1.1
WP27-05 | 27 | WP27 | Construction Mobilisation | Environmental Controls | Structured value + evidence + status | M/C | Captures the controlled environmental controls data for Stage 27 (Construction Mobilisation); link source, owner, status, evidence, risk and decision impact. | Construction, Quality, Commissioning and Handover | Controlled v1.1
WP27-06 | 27 | WP27 | Construction Mobilisation | Baseline Programme | Document / version / review and approval status | M/C | Captures the controlled baseline programme data for Stage 27 (Construction Mobilisation); link source, owner, status, evidence, risk and decision impact. | Construction, Quality, Commissioning and Handover | Controlled v1.1
WP28-01 | 28 | WP28 | Civil Works, Earthworks and Access Construction | Clearing And Grubbing | Structured value + evidence + status | M/C | Captures the controlled clearing and grubbing data for Stage 28 (Civil Works, Earthworks and Access Construction); link source, owner, status, evidence, risk and decision impact. | Construction, Quality, Commissioning and Handover | Controlled v1.1
WP28-02 | 28 | WP28 | Civil Works, Earthworks and Access Construction | Bulk Earthworks | Structured value + evidence + status | M/C | Captures the controlled bulk earthworks data for Stage 28 (Civil Works, Earthworks and Access Construction); link source, owner, status, evidence, risk and decision impact. | Construction, Quality, Commissioning and Handover | Controlled v1.1
WP28-03 | 28 | WP28 | Civil Works, Earthworks and Access Construction | Platforms | Structured value + evidence + status | M/C | Captures the controlled platforms data for Stage 28 (Civil Works, Earthworks and Access Construction); link source, owner, status, evidence, risk and decision impact. | Construction, Quality, Commissioning and Handover | Controlled v1.1
WP28-04 | 28 | WP28 | Civil Works, Earthworks and Access Construction | R567 Entrance Works | Structured value + evidence + status | M/C | Captures the controlled r567 entrance works data for Stage 28 (Civil Works, Earthworks and Access Construction); link source, owner, status, evidence, risk and decision impact. | Construction, Quality, Commissioning and Handover | Controlled v1.1
WP28-05 | 28 | WP28 | Civil Works, Earthworks and Access Construction | Stormwater Structures | Structured value + evidence + status | M/C | Captures the controlled stormwater structures data for Stage 28 (Civil Works, Earthworks and Access Construction); link source, owner, status, evidence, risk and decision impact. | Construction, Quality, Commissioning and Handover | Controlled v1.1
WP28-06 | 28 | WP28 | Civil Works, Earthworks and Access Construction | Internal Roads | Structured value + evidence + status | M/C | Captures the controlled internal roads data for Stage 28 (Civil Works, Earthworks and Access Construction); link source, owner, status, evidence, risk and decision impact. | Construction, Quality, Commissioning and Handover | Controlled v1.1
WP29-01 | 29 | WP29 | Building Shells and Services Installation | Boxer Shell | Linked party / engagement / due-diligence status | M/C | Captures the controlled boxer shell data for Stage 29 (Building Shells and Services Installation); link source, owner, status, evidence, risk and decision impact. | Construction, Quality, Commissioning and Handover | Controlled v1.1
WP29-02 | 29 | WP29 | Building Shells and Services Installation | Line-Shop Shells | Structured value + evidence + status | M/C | Captures the controlled line-shop shells data for Stage 29 (Building Shells and Services Installation); link source, owner, status, evidence, risk and decision impact. | Construction, Quality, Commissioning and Handover | Controlled v1.1
WP29-03 | 29 | WP29 | Building Shells and Services Installation | Qsr Shells | Structured value + evidence + status | M/C | Captures the controlled qsr shells data for Stage 29 (Building Shells and Services Installation); link source, owner, status, evidence, risk and decision impact. | Construction, Quality, Commissioning and Handover | Controlled v1.1
WP29-04 | 29 | WP29 | Building Shells and Services Installation | Roofing | Structured value + evidence + status | M/C | Captures the controlled roofing data for Stage 29 (Building Shells and Services Installation); link source, owner, status, evidence, risk and decision impact. | Construction, Quality, Commissioning and Handover | Controlled v1.1
WP29-05 | 29 | WP29 | Building Shells and Services Installation | Shopfronts | Structured value + evidence + status | M/C | Captures the controlled shopfronts data for Stage 29 (Building Shells and Services Installation); link source, owner, status, evidence, risk and decision impact. | Construction, Quality, Commissioning and Handover | Controlled v1.1
WP29-06 | 29 | WP29 | Building Shells and Services Installation | Water Services | Structured value + evidence + status | M/C | Captures the controlled water services data for Stage 29 (Building Shells and Services Installation); link source, owner, status, evidence, risk and decision impact. | Construction, Quality, Commissioning and Handover | Controlled v1.1
WP30-01 | 30 | WP30 | Tenant Fit-Out Coordination | Boxer Fit-Out | Linked party / engagement / due-diligence status | M/C | Captures the controlled boxer fit-out data for Stage 30 (Tenant Fit-Out Coordination); link source, owner, status, evidence, risk and decision impact. | Construction, Quality, Commissioning and Handover | Controlled v1.1
WP30-02 | 30 | WP30 | Tenant Fit-Out Coordination | Line-Shop Fit-Out | Structured value + evidence + status | M/C | Captures the controlled line-shop fit-out data for Stage 30 (Tenant Fit-Out Coordination); link source, owner, status, evidence, risk and decision impact. | Construction, Quality, Commissioning and Handover | Controlled v1.1
WP30-03 | 30 | WP30 | Tenant Fit-Out Coordination | Fast-Food Fit-Out | Structured value + evidence + status | M/C | Captures the controlled fast-food fit-out data for Stage 30 (Tenant Fit-Out Coordination); link source, owner, status, evidence, risk and decision impact. | Construction, Quality, Commissioning and Handover | Controlled v1.1
WP30-04 | 30 | WP30 | Tenant Fit-Out Coordination | Handover Dates | Date / duration / schedule status | M/C | Captures the controlled handover dates data for Stage 30 (Tenant Fit-Out Coordination); link source, owner, status, evidence, risk and decision impact. | Construction, Quality, Commissioning and Handover | Controlled v1.1
WP30-05 | 30 | WP30 | Tenant Fit-Out Coordination | Fit-Out Rules | Structured value + evidence + status | M/C | Captures the controlled fit-out rules data for Stage 30 (Tenant Fit-Out Coordination); link source, owner, status, evidence, risk and decision impact. | Construction, Quality, Commissioning and Handover | Controlled v1.1
WP30-06 | 30 | WP30 | Tenant Fit-Out Coordination | Tenant Utilities | Linked party / engagement / due-diligence status | M/C | Captures the controlled tenant utilities data for Stage 30 (Tenant Fit-Out Coordination); link source, owner, status, evidence, risk and decision impact. | Construction, Quality, Commissioning and Handover | Controlled v1.1
WP31-01 | 31 | WP31 | Quality Assurance, HSE and Compliance Control | Quality Inspections | Structured value + evidence + status | M/C | Captures the controlled quality inspections data for Stage 31 (Quality Assurance, HSE and Compliance Control); link source, owner, status, evidence, risk and decision impact. | Construction, Quality, Commissioning and Handover | Controlled v1.1
WP31-02 | 31 | WP31 | Quality Assurance, HSE and Compliance Control | Hse Audits | Structured value + evidence + status | M/C | Captures the controlled hse audits data for Stage 31 (Quality Assurance, HSE and Compliance Control); link source, owner, status, evidence, risk and decision impact. | Construction, Quality, Commissioning and Handover | Controlled v1.1
WP31-03 | 31 | WP31 | Quality Assurance, HSE and Compliance Control | Environmental Monitoring | Structured value + evidence + status | M/C | Captures the controlled environmental monitoring data for Stage 31 (Quality Assurance, HSE and Compliance Control); link source, owner, status, evidence, risk and decision impact. | Construction, Quality, Commissioning and Handover | Controlled v1.1
WP31-04 | 31 | WP31 | Quality Assurance, HSE and Compliance Control | Material Approvals | Status + authority/reference + dates/conditions | M/C | Captures the controlled material approvals data for Stage 31 (Quality Assurance, HSE and Compliance Control); link source, owner, status, evidence, risk and decision impact. | Construction, Quality, Commissioning and Handover | Controlled v1.1
WP31-05 | 31 | WP31 | Quality Assurance, HSE and Compliance Control | Variation Control | Structured value + evidence + status | M/C | Captures the controlled variation control data for Stage 31 (Quality Assurance, HSE and Compliance Control); link source, owner, status, evidence, risk and decision impact. | Construction, Quality, Commissioning and Handover | Controlled v1.1
WP31-06 | 31 | WP31 | Quality Assurance, HSE and Compliance Control | Payment Certification | Structured value + evidence + status | M/C | Captures the controlled payment certification data for Stage 31 (Quality Assurance, HSE and Compliance Control); link source, owner, status, evidence, risk and decision impact. | Construction, Quality, Commissioning and Handover | Controlled v1.1
WP32-01 | 32 | WP32 | Commissioning and Testing | Electrical Testing | Structured value + evidence + status | M/C | Captures the controlled electrical testing data for Stage 32 (Commissioning and Testing); link source, owner, status, evidence, risk and decision impact. | Construction, Quality, Commissioning and Handover | Controlled v1.1
WP32-02 | 32 | WP32 | Commissioning and Testing | Water Pressure Testing | Structured value + evidence + status | M/C | Captures the controlled water pressure testing data for Stage 32 (Commissioning and Testing); link source, owner, status, evidence, risk and decision impact. | Construction, Quality, Commissioning and Handover | Controlled v1.1
WP32-03 | 32 | WP32 | Commissioning and Testing | Fire System Testing | Structured value + evidence + status | M/C | Captures the controlled fire system testing data for Stage 32 (Commissioning and Testing); link source, owner, status, evidence, risk and decision impact. | Construction, Quality, Commissioning and Handover | Controlled v1.1
WP32-04 | 32 | WP32 | Commissioning and Testing | Stormwater Checks | Structured value + evidence + status | M/C | Captures the controlled stormwater checks data for Stage 32 (Commissioning and Testing); link source, owner, status, evidence, risk and decision impact. | Construction, Quality, Commissioning and Handover | Controlled v1.1
WP32-05 | 32 | WP32 | Commissioning and Testing | Hvac Testing | Structured value + evidence + status | M/C | Captures the controlled hvac testing data for Stage 32 (Commissioning and Testing); link source, owner, status, evidence, risk and decision impact. | Construction, Quality, Commissioning and Handover | Controlled v1.1
WP32-06 | 32 | WP32 | Commissioning and Testing | Ict Testing | Structured value + evidence + status | M/C | Captures the controlled ict testing data for Stage 32 (Commissioning and Testing); link source, owner, status, evidence, risk and decision impact. | Construction, Quality, Commissioning and Handover | Controlled v1.1
WP33-01 | 33 | WP33 | Handover to Operators and Tenants | Handover Manuals | Structured value + evidence + status | M/C | Captures the controlled handover manuals data for Stage 33 (Handover to Operators and Tenants); link source, owner, status, evidence, risk and decision impact. | Construction, Quality, Commissioning and Handover | Controlled v1.1
WP33-02 | 33 | WP33 | Handover to Operators and Tenants | As-Built Drawings | Document / version / review and approval status | M/C | Captures the controlled as-built drawings data for Stage 33 (Handover to Operators and Tenants); link source, owner, status, evidence, risk and decision impact. | Construction, Quality, Commissioning and Handover | Controlled v1.1
WP33-03 | 33 | WP33 | Handover to Operators and Tenants | Warranty Register | Document / version / review and approval status | M/C | Captures the controlled warranty register data for Stage 33 (Handover to Operators and Tenants); link source, owner, status, evidence, risk and decision impact. | Construction, Quality, Commissioning and Handover | Controlled v1.1
WP33-04 | 33 | WP33 | Handover to Operators and Tenants | Tenant Certificates | Status + authority/reference + dates/conditions | M/C | Captures the controlled tenant certificates data for Stage 33 (Handover to Operators and Tenants); link source, owner, status, evidence, risk and decision impact. | Construction, Quality, Commissioning and Handover | Controlled v1.1
WP33-05 | 33 | WP33 | Handover to Operators and Tenants | Maintenance Plans | Document / version / review and approval status | M/C | Captures the controlled maintenance plans data for Stage 33 (Handover to Operators and Tenants); link source, owner, status, evidence, risk and decision impact. | Construction, Quality, Commissioning and Handover | Controlled v1.1
WP33-06 | 33 | WP33 | Handover to Operators and Tenants | Operator Training | Structured value + evidence + status | M/C | Captures the controlled operator training data for Stage 33 (Handover to Operators and Tenants); link source, owner, status, evidence, risk and decision impact. | Construction, Quality, Commissioning and Handover | Controlled v1.1
WP34-01 | 34 | WP34 | Operational Ramp-Up | Soft Opening | Structured value + evidence + status | M/C | Captures the controlled soft opening data for Stage 34 (Operational Ramp-Up); link source, owner, status, evidence, risk and decision impact. | Operations, Maintenance, Impact and Expansion | Controlled v1.1
WP34-02 | 34 | WP34 | Operational Ramp-Up | Boxer Opening | Linked party / engagement / due-diligence status | M/C | Captures the controlled boxer opening data for Stage 34 (Operational Ramp-Up); link source, owner, status, evidence, risk and decision impact. | Operations, Maintenance, Impact and Expansion | Controlled v1.1
WP34-03 | 34 | WP34 | Operational Ramp-Up | Tenant Trading Readiness | Linked party / engagement / due-diligence status | M/C | Captures the controlled tenant trading readiness data for Stage 34 (Operational Ramp-Up); link source, owner, status, evidence, risk and decision impact. | Operations, Maintenance, Impact and Expansion | Controlled v1.1
WP34-04 | 34 | WP34 | Operational Ramp-Up | Traffic Management | Structured value + evidence + status | M/C | Captures the controlled traffic management data for Stage 34 (Operational Ramp-Up); link source, owner, status, evidence, risk and decision impact. | Operations, Maintenance, Impact and Expansion | Controlled v1.1
WP34-05 | 34 | WP34 | Operational Ramp-Up | Customer Service | Structured value + evidence + status | M/C | Captures the controlled customer service data for Stage 34 (Operational Ramp-Up); link source, owner, status, evidence, risk and decision impact. | Operations, Maintenance, Impact and Expansion | Controlled v1.1
WP34-06 | 34 | WP34 | Operational Ramp-Up | Operations Dashboard | Structured value + evidence + status | M/C | Captures the controlled operations dashboard data for Stage 34 (Operational Ramp-Up); link source, owner, status, evidence, risk and decision impact. | Operations, Maintenance, Impact and Expansion | Controlled v1.1
WP35-01 | 35 | WP35 | Operations Management | Property Management | Structured value + evidence + status | M/C | Captures the controlled property management data for Stage 35 (Operations Management); link source, owner, status, evidence, risk and decision impact. | Operations, Maintenance, Impact and Expansion | Controlled v1.1
WP35-02 | 35 | WP35 | Operations Management | Lease Administration | Structured value + evidence + status | M/C | Captures the controlled lease administration data for Stage 35 (Operations Management); link source, owner, status, evidence, risk and decision impact. | Operations, Maintenance, Impact and Expansion | Controlled v1.1
WP35-03 | 35 | WP35 | Operations Management | Tenant Relations | Linked party / engagement / due-diligence status | M/C | Captures the controlled tenant relations data for Stage 35 (Operations Management); link source, owner, status, evidence, risk and decision impact. | Operations, Maintenance, Impact and Expansion | Controlled v1.1
WP35-04 | 35 | WP35 | Operations Management | Security Operations | Structured value + evidence + status | M/C | Captures the controlled security operations data for Stage 35 (Operations Management); link source, owner, status, evidence, risk and decision impact. | Operations, Maintenance, Impact and Expansion | Controlled v1.1
WP35-05 | 35 | WP35 | Operations Management | Cleaning Operations | Structured value + evidence + status | M/C | Captures the controlled cleaning operations data for Stage 35 (Operations Management); link source, owner, status, evidence, risk and decision impact. | Operations, Maintenance, Impact and Expansion | Controlled v1.1
WP35-06 | 35 | WP35 | Operations Management | Parking Control | Structured value + evidence + status | M/C | Captures the controlled parking control data for Stage 35 (Operations Management); link source, owner, status, evidence, risk and decision impact. | Operations, Maintenance, Impact and Expansion | Controlled v1.1
WP36-01 | 36 | WP36 | Maintenance Management | Preventive Maintenance | Structured value + evidence + status | M/C | Captures the controlled preventive maintenance data for Stage 36 (Maintenance Management); link source, owner, status, evidence, risk and decision impact. | Operations, Maintenance, Impact and Expansion | Controlled v1.1
WP36-02 | 36 | WP36 | Maintenance Management | Reactive Maintenance | Structured value + evidence + status | M/C | Captures the controlled reactive maintenance data for Stage 36 (Maintenance Management); link source, owner, status, evidence, risk and decision impact. | Operations, Maintenance, Impact and Expansion | Controlled v1.1
WP36-03 | 36 | WP36 | Maintenance Management | Roof And Gutters | Structured value + evidence + status | M/C | Captures the controlled roof and gutters data for Stage 36 (Maintenance Management); link source, owner, status, evidence, risk and decision impact. | Operations, Maintenance, Impact and Expansion | Controlled v1.1
WP36-04 | 36 | WP36 | Maintenance Management | Electrical Systems | Structured value + evidence + status | M/C | Captures the controlled electrical systems data for Stage 36 (Maintenance Management); link source, owner, status, evidence, risk and decision impact. | Operations, Maintenance, Impact and Expansion | Controlled v1.1
WP36-05 | 36 | WP36 | Maintenance Management | Plumbing Systems | Structured value + evidence + status | M/C | Captures the controlled plumbing systems data for Stage 36 (Maintenance Management); link source, owner, status, evidence, risk and decision impact. | Operations, Maintenance, Impact and Expansion | Controlled v1.1
WP36-06 | 36 | WP36 | Maintenance Management | Fire Equipment | Structured value + evidence + status | M/C | Captures the controlled fire equipment data for Stage 36 (Maintenance Management); link source, owner, status, evidence, risk and decision impact. | Operations, Maintenance, Impact and Expansion | Controlled v1.1
WP37-01 | 37 | WP37 | Sustainable Impact, Performance Monitoring and Future Expansion | Esg Reporting | Document / version / review and approval status | M/C | Captures the controlled esg reporting data for Stage 37 (Sustainable Impact, Performance Monitoring and Future Expansion); link source, owner, status, evidence, risk and decision impact. | Operations, Maintenance, Impact and Expansion | Controlled v1.1
WP37-02 | 37 | WP37 | Sustainable Impact, Performance Monitoring and Future Expansion | Job Creation | Numeric / percentage / currency with unit and period | M/C | Captures the controlled job creation data for Stage 37 (Sustainable Impact, Performance Monitoring and Future Expansion); link source, owner, status, evidence, risk and decision impact. | Operations, Maintenance, Impact and Expansion | Controlled v1.1
WP37-03 | 37 | WP37 | Sustainable Impact, Performance Monitoring and Future Expansion | Local Procurement | Numeric / percentage / currency with unit and period | M/C | Captures the controlled local procurement data for Stage 37 (Sustainable Impact, Performance Monitoring and Future Expansion); link source, owner, status, evidence, risk and decision impact. | Operations, Maintenance, Impact and Expansion | Controlled v1.1
WP37-04 | 37 | WP37 | Sustainable Impact, Performance Monitoring and Future Expansion | Community Benefit | Structured value + evidence + status | M/C | Captures the controlled community benefit data for Stage 37 (Sustainable Impact, Performance Monitoring and Future Expansion); link source, owner, status, evidence, risk and decision impact. | Operations, Maintenance, Impact and Expansion | Controlled v1.1
WP37-05 | 37 | WP37 | Sustainable Impact, Performance Monitoring and Future Expansion | Energy Efficiency | Numeric / percentage / currency with unit and period | M/C | Captures the controlled energy efficiency data for Stage 37 (Sustainable Impact, Performance Monitoring and Future Expansion); link source, owner, status, evidence, risk and decision impact. | Operations, Maintenance, Impact and Expansion | Controlled v1.1
WP37-06 | 37 | WP37 | Sustainable Impact, Performance Monitoring and Future Expansion | Water Performance | Numeric / percentage / currency with unit and period | M/C | Captures the controlled water performance data for Stage 37 (Sustainable Impact, Performance Monitoring and Future Expansion); link source, owner, status, evidence, risk and decision impact. | Operations, Maintenance, Impact and Expansion | Controlled v1.1

## Stage Control Matrix
OPBOH™ Stage Assurance Control Matrix
Operational entry, exit, evidence, risk, output and progression controls for each work package
Stage | WP Code | Stage / Work Package | Entry Condition | Top Evidence Patterns | Top Reference Bases | Exit Condition | Mandatory Outputs | Responsible Roles | Decision Risk | Decision Options | Control Status
01 | WP01 | Strategic Inception and Project Mandate | Prior work-package outputs accepted or formally waived; mandate, owner and applicable evidence request confirmed. | Signed memo, checklist, source document and responsible-person confirmation. ¦ Register entry, supporting drawing/report, approval note and updated risk item. ¦ Professional/specialist note, meeting minute, correspondence and decision record. ¦ Updated schedule, cost note, assumption log and evidence index reference. ¦ Authority response, compliance checklist, file note and management approval. | King IV governance practice; Companies Act 71 of 2008; project mandate file ¦ PMBOK stage-gate governance; board resolution; delegated authority matrix ¦ ISO 31000 risk management; stakeholder decision register; project charter | Applicable questions completed; required evidence accepted; critical failures resolved or escalated; decision and conditions approved by the delegated authority. | Approved Strategic Inception and Project Mandate assessment record; evidence index; findings and risk update; corrective-action/condition register; signed progression recommendation. | Project Sponsor; OPBOH Lead Assessor; Legal/Governance Lead; Project Manager | Unclear mandate, ownership, authority or site control may invalidate later commitments and expenditure. | Proceed / Proceed with conditions / Remediate and reassess / Hold / Rework / Stop or restructure | Controlled
02 | WP02 | Site Identification and Opportunity Discovery | Prior work-package outputs accepted or formally waived; mandate, owner and applicable evidence request confirmed. | Signed memo, checklist, source document and responsible-person confirmation. ¦ Register entry, supporting drawing/report, approval note and updated risk item. ¦ Professional/specialist note, meeting minute, correspondence and decision record. ¦ Updated schedule, cost note, assumption log and evidence index reference. ¦ Authority response, compliance checklist, file note and management approval. | SPLUMA Act 16 of 2013; municipal land use scheme; title deed/SG diagram ¦ Deeds Registries Act 47 of 1937; Surveyor-General records; servitude register ¦ Municipal Planning By-law; wayleave requirements; landowner consent | Applicable questions completed; required evidence accepted; critical failures resolved or escalated; decision and conditions approved by the delegated authority. | Approved Site Identification and Opportunity Discovery assessment record; evidence index; findings and risk update; corrective-action/condition register; signed progression recommendation. | Project Sponsor; OPBOH Lead Assessor; Legal/Governance Lead; Project Manager | Unclear mandate, ownership, authority or site control may invalidate later commitments and expenditure. | Proceed / Proceed with conditions / Remediate and reassess / Hold / Rework / Stop or restructure | Controlled
03 | WP03 | Preliminary Site Screening | Prior work-package outputs accepted or formally waived; mandate, owner and applicable evidence request confirmed. | Signed memo, checklist, source document and responsible-person confirmation. ¦ Register entry, supporting drawing/report, approval note and updated risk item. ¦ Professional/specialist note, meeting minute, correspondence and decision record. ¦ Updated schedule, cost note, assumption log and evidence index reference. ¦ Authority response, compliance checklist, file note and management approval. | SPLUMA Act 16 of 2013; municipal land use scheme; title deed/SG diagram ¦ Deeds Registries Act 47 of 1937; Surveyor-General records; servitude register ¦ Municipal Planning By-law; wayleave requirements; landowner consent | Applicable questions completed; required evidence accepted; critical failures resolved or escalated; decision and conditions approved by the delegated authority. | Approved Preliminary Site Screening assessment record; evidence index; findings and risk update; corrective-action/condition register; signed progression recommendation. | Project Sponsor; OPBOH Lead Assessor; Legal/Governance Lead; Project Manager | Unclear mandate, ownership, authority or site control may invalidate later commitments and expenditure. | Proceed / Proceed with conditions / Remediate and reassess / Hold / Rework / Stop or restructure | Controlled
04 | WP04 | Sponsor and Entity Readiness | Prior work-package outputs accepted or formally waived; mandate, owner and applicable evidence request confirmed. | Signed memo, checklist, source document and responsible-person confirmation. ¦ Register entry, supporting drawing/report, approval note and updated risk item. ¦ Professional/specialist note, meeting minute, correspondence and decision record. ¦ Updated schedule, cost note, assumption log and evidence index reference. ¦ Authority response, compliance checklist, file note and management approval. | King IV governance practice; Companies Act 71 of 2008; project mandate file ¦ PMBOK stage-gate governance; board resolution; delegated authority matrix ¦ ISO 31000 risk management; stakeholder decision register; project charter | Applicable questions completed; required evidence accepted; critical failures resolved or escalated; decision and conditions approved by the delegated authority. | Approved Sponsor and Entity Readiness assessment record; evidence index; findings and risk update; corrective-action/condition register; signed progression recommendation. | Project Sponsor; OPBOH Lead Assessor; Legal/Governance Lead; Project Manager | Unclear mandate, ownership, authority or site control may invalidate later commitments and expenditure. | Proceed / Proceed with conditions / Remediate and reassess / Hold / Rework / Stop or restructure | Controlled
05 | WP05 | Land Security and Site Control | Prior work-package outputs accepted or formally waived; mandate, owner and applicable evidence request confirmed. | Signed memo, checklist, source document and responsible-person confirmation. ¦ Register entry, supporting drawing/report, approval note and updated risk item. ¦ Professional/specialist note, meeting minute, correspondence and decision record. ¦ Updated schedule, cost note, assumption log and evidence index reference. ¦ Authority response, compliance checklist, file note and management approval. | SPLUMA Act 16 of 2013; municipal land use scheme; title deed/SG diagram ¦ Deeds Registries Act 47 of 1937; Surveyor-General records; servitude register ¦ Municipal Planning By-law; wayleave requirements; landowner consent | Applicable questions completed; required evidence accepted; critical failures resolved or escalated; decision and conditions approved by the delegated authority. | Approved Land Security and Site Control assessment record; evidence index; findings and risk update; corrective-action/condition register; signed progression recommendation. | Project Sponsor; OPBOH Lead Assessor; Legal/Governance Lead; Project Manager | Unclear mandate, ownership, authority or site control may invalidate later commitments and expenditure. | Proceed / Proceed with conditions / Remediate and reassess / Hold / Rework / Stop or restructure | Controlled
06 | WP06 | Feasibility Studies and Market Demand | Prior work-package outputs accepted or formally waived; mandate, owner and applicable evidence request confirmed. | Signed memo, checklist, source document and responsible-person confirmation. ¦ Register entry, supporting drawing/report, approval note and updated risk item. ¦ Professional/specialist note, meeting minute, correspondence and decision record. ¦ Updated schedule, cost note, assumption log and evidence index reference. ¦ Authority response, compliance checklist, file note and management approval. | IFRS/IFRS for SMEs principles; lender due diligence checklist; signed financial model ¦ CIDB/procurement best practice; cost plan; QS measurement and BOQ controls ¦ Treasury-style value-for-money principles; funding term sheet; drawdown controls | Applicable questions completed; required evidence accepted; critical failures resolved or escalated; decision and conditions approved by the delegated authority. | Approved Feasibility Studies and Market Demand assessment record; evidence index; findings and risk update; corrective-action/condition register; signed progression recommendation. | Project Manager; Planning/Environmental/Engineering Specialists; Relevant Authorities; OPBOH Assessor | Unresolved feasibility, access, services, environmental, zoning or stakeholder constraints may make the project non-viable or delay approvals. | Proceed / Proceed with conditions / Remediate and reassess / Hold / Rework / Stop or restructure | Controlled
07 | WP07 | Traffic, Access and Mobility Feasibility | Prior work-package outputs accepted or formally waived; mandate, owner and applicable evidence request confirmed. | Signed memo, checklist, source document and responsible-person confirmation. ¦ Register entry, supporting drawing/report, approval note and updated risk item. ¦ Professional/specialist note, meeting minute, correspondence and decision record. ¦ Updated schedule, cost note, assumption log and evidence index reference. ¦ Authority response, compliance checklist, file note and management approval. | SANRAL/road authority access requirements; TMH/TRH road design guidance ¦ Municipal roads and stormwater standards; traffic impact assessment ¦ SANS 10400-S access; pedestrian safety and universal access principles | Applicable questions completed; required evidence accepted; critical failures resolved or escalated; decision and conditions approved by the delegated authority. | Approved Traffic, Access and Mobility Feasibility assessment record; evidence index; findings and risk update; corrective-action/condition register; signed progression recommendation. | Project Manager; Planning/Environmental/Engineering Specialists; Relevant Authorities; OPBOH Assessor | Unresolved feasibility, access, services, environmental, zoning or stakeholder constraints may make the project non-viable or delay approvals. | Proceed / Proceed with conditions / Remediate and reassess / Hold / Rework / Stop or restructure | Controlled
08 | WP08 | Bulk Services and Infrastructure Feasibility | Prior work-package outputs accepted or formally waived; mandate, owner and applicable evidence request confirmed. | Signed memo, checklist, source document and responsible-person confirmation. ¦ Register entry, supporting drawing/report, approval note and updated risk item. ¦ Professional/specialist note, meeting minute, correspondence and decision record. ¦ Updated schedule, cost note, assumption log and evidence index reference. ¦ Authority response, compliance checklist, file note and management approval. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 ¦ SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates ¦ SANS/municipal engineering standards; approved SDP; rational fire design | Applicable questions completed; required evidence accepted; critical failures resolved or escalated; decision and conditions approved by the delegated authority. | Approved Bulk Services and Infrastructure Feasibility assessment record; evidence index; findings and risk update; corrective-action/condition register; signed progression recommendation. | Project Manager; Planning/Environmental/Engineering Specialists; Relevant Authorities; OPBOH Assessor | Unresolved feasibility, access, services, environmental, zoning or stakeholder constraints may make the project non-viable or delay approvals. | Proceed / Proceed with conditions / Remediate and reassess / Hold / Rework / Stop or restructure | Controlled
09 | WP09 | Environmental Screening and Scoping | Prior work-package outputs accepted or formally waived; mandate, owner and applicable evidence request confirmed. | Signed memo, checklist, source document and responsible-person confirmation. ¦ Register entry, supporting drawing/report, approval note and updated risk item. ¦ Professional/specialist note, meeting minute, correspondence and decision record. ¦ Updated schedule, cost note, assumption log and evidence index reference. ¦ Authority response, compliance checklist, file note and management approval. | NEMA Act 107 of 1998; EIA Regulations, 2014; DFFE screening requirements ¦ National Water Act 36 of 1998; biodiversity and wetland specialist guidance ¦ NHRA Act 25 of 1999; public participation record; EMPr controls | Applicable questions completed; required evidence accepted; critical failures resolved or escalated; decision and conditions approved by the delegated authority. | Approved Environmental Screening and Scoping assessment record; evidence index; findings and risk update; corrective-action/condition register; signed progression recommendation. | Project Manager; Planning/Environmental/Engineering Specialists; Relevant Authorities; OPBOH Assessor | Unresolved feasibility, access, services, environmental, zoning or stakeholder constraints may make the project non-viable or delay approvals. | Proceed / Proceed with conditions / Remediate and reassess / Hold / Rework / Stop or restructure | Controlled
10 | WP10 | Land Use Rights and Zoning | Prior work-package outputs accepted or formally waived; mandate, owner and applicable evidence request confirmed. | Signed memo, checklist, source document and responsible-person confirmation. ¦ Register entry, supporting drawing/report, approval note and updated risk item. ¦ Professional/specialist note, meeting minute, correspondence and decision record. ¦ Updated schedule, cost note, assumption log and evidence index reference. ¦ Authority response, compliance checklist, file note and management approval. | SPLUMA Act 16 of 2013; municipal land use scheme; title deed/SG diagram ¦ Deeds Registries Act 47 of 1937; Surveyor-General records; servitude register ¦ Municipal Planning By-law; wayleave requirements; landowner consent | Applicable questions completed; required evidence accepted; critical failures resolved or escalated; decision and conditions approved by the delegated authority. | Approved Land Use Rights and Zoning assessment record; evidence index; findings and risk update; corrective-action/condition register; signed progression recommendation. | Project Manager; Planning/Environmental/Engineering Specialists; Relevant Authorities; OPBOH Assessor | Unresolved feasibility, access, services, environmental, zoning or stakeholder constraints may make the project non-viable or delay approvals. | Proceed / Proceed with conditions / Remediate and reassess / Hold / Rework / Stop or restructure | Controlled
11 | WP11 | Environmental Authorisation - Estimated 10 Months | Prior work-package outputs accepted or formally waived; mandate, owner and applicable evidence request confirmed. | Signed memo, checklist, source document and responsible-person confirmation. ¦ Register entry, supporting drawing/report, approval note and updated risk item. ¦ Professional/specialist note, meeting minute, correspondence and decision record. ¦ Updated schedule, cost note, assumption log and evidence index reference. ¦ Authority response, compliance checklist, file note and management approval. | NEMA Act 107 of 1998; EIA Regulations, 2014; DFFE screening requirements ¦ National Water Act 36 of 1998; biodiversity and wetland specialist guidance ¦ NHRA Act 25 of 1999; public participation record; EMPr controls | Applicable questions completed; required evidence accepted; critical failures resolved or escalated; decision and conditions approved by the delegated authority. | Approved Environmental Authorisation - Estimated 10 Months assessment record; evidence index; findings and risk update; corrective-action/condition register; signed progression recommendation. | Project Manager; Planning/Environmental/Engineering Specialists; Relevant Authorities; OPBOH Assessor | Unresolved feasibility, access, services, environmental, zoning or stakeholder constraints may make the project non-viable or delay approvals. | Proceed / Proceed with conditions / Remediate and reassess / Hold / Rework / Stop or restructure | Controlled
12 | WP12 | Stakeholder Mapping and Public Participation | Prior work-package outputs accepted or formally waived; mandate, owner and applicable evidence request confirmed. | Signed memo, checklist, source document and responsible-person confirmation. ¦ Register entry, supporting drawing/report, approval note and updated risk item. ¦ Professional/specialist note, meeting minute, correspondence and decision record. ¦ Updated schedule, cost note, assumption log and evidence index reference. ¦ Authority response, compliance checklist, file note and management approval. | King IV governance practice; Companies Act 71 of 2008; project mandate file ¦ PMBOK stage-gate governance; board resolution; delegated authority matrix ¦ ISO 31000 risk management; stakeholder decision register; project charter | Applicable questions completed; required evidence accepted; critical failures resolved or escalated; decision and conditions approved by the delegated authority. | Approved Stakeholder Mapping and Public Participation assessment record; evidence index; findings and risk update; corrective-action/condition register; signed progression recommendation. | Project Manager; Planning/Environmental/Engineering Specialists; Relevant Authorities; OPBOH Assessor | Unresolved feasibility, access, services, environmental, zoning or stakeholder constraints may make the project non-viable or delay approvals. | Proceed / Proceed with conditions / Remediate and reassess / Hold / Rework / Stop or restructure | Controlled
13 | WP13 | Concept Development | Prior work-package outputs accepted or formally waived; mandate, owner and applicable evidence request confirmed. | Signed memo, checklist, source document and responsible-person confirmation. ¦ Register entry, supporting drawing/report, approval note and updated risk item. ¦ Professional/specialist note, meeting minute, correspondence and decision record. ¦ Updated schedule, cost note, assumption log and evidence index reference. ¦ Authority response, compliance checklist, file note and management approval. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 ¦ SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates ¦ SANS/municipal engineering standards; approved SDP; rational fire design | Applicable questions completed; required evidence accepted; critical failures resolved or escalated; decision and conditions approved by the delegated authority. | Approved Concept Development assessment record; evidence index; findings and risk update; corrective-action/condition register; signed progression recommendation. | Developer; Architect/Masterplanner; Leasing Lead; Anchor/Tenant/Fuel Partner Representatives | Misaligned concept, tenant demand, anchor requirements or commercial positioning may undermine income and design viability. | Proceed / Proceed with conditions / Remediate and reassess / Hold / Rework / Stop or restructure | Controlled
14 | WP14 | Retail Masterplanning and GLA Strategy | Prior work-package outputs accepted or formally waived; mandate, owner and applicable evidence request confirmed. | Signed memo, checklist, source document and responsible-person confirmation. ¦ Register entry, supporting drawing/report, approval note and updated risk item. ¦ Professional/specialist note, meeting minute, correspondence and decision record. ¦ Updated schedule, cost note, assumption log and evidence index reference. ¦ Authority response, compliance checklist, file note and management approval. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule ¦ Tenant design and fit-out manual; anchor specifications; trading-readiness checklist ¦ CPA/POPIA where applicable; tenant compliance file; rental assumptions | Applicable questions completed; required evidence accepted; critical failures resolved or escalated; decision and conditions approved by the delegated authority. | Approved Retail Masterplanning and GLA Strategy assessment record; evidence index; findings and risk update; corrective-action/condition register; signed progression recommendation. | Developer; Architect/Masterplanner; Leasing Lead; Anchor/Tenant/Fuel Partner Representatives | Misaligned concept, tenant demand, anchor requirements or commercial positioning may undermine income and design viability. | Proceed / Proceed with conditions / Remediate and reassess / Hold / Rework / Stop or restructure | Controlled
15 | WP15 | Boxer Superstores Anchor Alignment | Prior work-package outputs accepted or formally waived; mandate, owner and applicable evidence request confirmed. | Signed memo, checklist, source document and responsible-person confirmation. ¦ Register entry, supporting drawing/report, approval note and updated risk item. ¦ Professional/specialist note, meeting minute, correspondence and decision record. ¦ Updated schedule, cost note, assumption log and evidence index reference. ¦ Authority response, compliance checklist, file note and management approval. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule ¦ Tenant design and fit-out manual; anchor specifications; trading-readiness checklist ¦ CPA/POPIA where applicable; tenant compliance file; rental assumptions | Applicable questions completed; required evidence accepted; critical failures resolved or escalated; decision and conditions approved by the delegated authority. | Approved Boxer Superstores Anchor Alignment assessment record; evidence index; findings and risk update; corrective-action/condition register; signed progression recommendation. | Developer; Architect/Masterplanner; Leasing Lead; Anchor/Tenant/Fuel Partner Representatives | Misaligned concept, tenant demand, anchor requirements or commercial positioning may undermine income and design viability. | Proceed / Proceed with conditions / Remediate and reassess / Hold / Rework / Stop or restructure | Controlled
16 | WP16 | Tenant Acquisition Strategy | Prior work-package outputs accepted or formally waived; mandate, owner and applicable evidence request confirmed. | Signed memo, checklist, source document and responsible-person confirmation. ¦ Register entry, supporting drawing/report, approval note and updated risk item. ¦ Professional/specialist note, meeting minute, correspondence and decision record. ¦ Updated schedule, cost note, assumption log and evidence index reference. ¦ Authority response, compliance checklist, file note and management approval. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule ¦ Tenant design and fit-out manual; anchor specifications; trading-readiness checklist ¦ CPA/POPIA where applicable; tenant compliance file; rental assumptions | Applicable questions completed; required evidence accepted; critical failures resolved or escalated; decision and conditions approved by the delegated authority. | Approved Tenant Acquisition Strategy assessment record; evidence index; findings and risk update; corrective-action/condition register; signed progression recommendation. | Developer; Architect/Masterplanner; Leasing Lead; Anchor/Tenant/Fuel Partner Representatives | Misaligned concept, tenant demand, anchor requirements or commercial positioning may undermine income and design viability. | Proceed / Proceed with conditions / Remediate and reassess / Hold / Rework / Stop or restructure | Controlled
17 | WP17 | Line-Shop Tenant Mix and Leasing | Prior work-package outputs accepted or formally waived; mandate, owner and applicable evidence request confirmed. | Signed memo, checklist, source document and responsible-person confirmation. ¦ Register entry, supporting drawing/report, approval note and updated risk item. ¦ Professional/specialist note, meeting minute, correspondence and decision record. ¦ Updated schedule, cost note, assumption log and evidence index reference. ¦ Authority response, compliance checklist, file note and management approval. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule ¦ Tenant design and fit-out manual; anchor specifications; trading-readiness checklist ¦ CPA/POPIA where applicable; tenant compliance file; rental assumptions | Applicable questions completed; required evidence accepted; critical failures resolved or escalated; decision and conditions approved by the delegated authority. | Approved Line-Shop Tenant Mix and Leasing assessment record; evidence index; findings and risk update; corrective-action/condition register; signed progression recommendation. | Developer; Architect/Masterplanner; Leasing Lead; Anchor/Tenant/Fuel Partner Representatives | Misaligned concept, tenant demand, anchor requirements or commercial positioning may undermine income and design viability. | Proceed / Proceed with conditions / Remediate and reassess / Hold / Rework / Stop or restructure | Controlled
18 | WP18 | Fast-Food Chain Restaurant Acquisition | Prior work-package outputs accepted or formally waived; mandate, owner and applicable evidence request confirmed. | Signed memo, checklist, source document and responsible-person confirmation. ¦ Register entry, supporting drawing/report, approval note and updated risk item. ¦ Professional/specialist note, meeting minute, correspondence and decision record. ¦ Updated schedule, cost note, assumption log and evidence index reference. ¦ Authority response, compliance checklist, file note and management approval. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule ¦ Tenant design and fit-out manual; anchor specifications; trading-readiness checklist ¦ CPA/POPIA where applicable; tenant compliance file; rental assumptions | Applicable questions completed; required evidence accepted; critical failures resolved or escalated; decision and conditions approved by the delegated authority. | Approved Fast-Food Chain Restaurant Acquisition assessment record; evidence index; findings and risk update; corrective-action/condition register; signed progression recommendation. | Developer; Architect/Masterplanner; Leasing Lead; Anchor/Tenant/Fuel Partner Representatives | Misaligned concept, tenant demand, anchor requirements or commercial positioning may undermine income and design viability. | Proceed / Proceed with conditions / Remediate and reassess / Hold / Rework / Stop or restructure | Controlled
19 | WP19 | Fuel Partner and Forecourt Coordination | Prior work-package outputs accepted or formally waived; mandate, owner and applicable evidence request confirmed. | Signed memo, checklist, source document and responsible-person confirmation. ¦ Register entry, supporting drawing/report, approval note and updated risk item. ¦ Professional/specialist note, meeting minute, correspondence and decision record. ¦ Updated schedule, cost note, assumption log and evidence index reference. ¦ Authority response, compliance checklist, file note and management approval. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule ¦ Tenant design and fit-out manual; anchor specifications; trading-readiness checklist ¦ CPA/POPIA where applicable; tenant compliance file; rental assumptions | Applicable questions completed; required evidence accepted; critical failures resolved or escalated; decision and conditions approved by the delegated authority. | Approved Fuel Partner and Forecourt Coordination assessment record; evidence index; findings and risk update; corrective-action/condition register; signed progression recommendation. | Developer; Architect/Masterplanner; Leasing Lead; Anchor/Tenant/Fuel Partner Representatives | Misaligned concept, tenant demand, anchor requirements or commercial positioning may undermine income and design viability. | Proceed / Proceed with conditions / Remediate and reassess / Hold / Rework / Stop or restructure | Controlled
20 | WP20 | Development Design | Prior work-package outputs accepted or formally waived; mandate, owner and applicable evidence request confirmed. | Signed memo, checklist, source document and responsible-person confirmation. ¦ Register entry, supporting drawing/report, approval note and updated risk item. ¦ Professional/specialist note, meeting minute, correspondence and decision record. ¦ Updated schedule, cost note, assumption log and evidence index reference. ¦ Authority response, compliance checklist, file note and management approval. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 ¦ SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates ¦ SANS/municipal engineering standards; approved SDP; rational fire design | Applicable questions completed; required evidence accepted; critical failures resolved or escalated; decision and conditions approved by the delegated authority. | Approved Development Design assessment record; evidence index; findings and risk update; corrective-action/condition register; signed progression recommendation. | Professional Design Team; Quantity Surveyor; Financial Adviser; Sponsor/Funder Representatives | Incomplete design, cost, funding, procurement or permit readiness may expose capital, programme, compliance and contracting decisions. | Proceed / Proceed with conditions / Remediate and reassess / Hold / Rework / Stop or restructure | Controlled
21 | WP21 | Engineering Design and Technical Documentation | Prior work-package outputs accepted or formally waived; mandate, owner and applicable evidence request confirmed. | Signed memo, checklist, source document and responsible-person confirmation. ¦ Register entry, supporting drawing/report, approval note and updated risk item. ¦ Professional/specialist note, meeting minute, correspondence and decision record. ¦ Updated schedule, cost note, assumption log and evidence index reference. ¦ Authority response, compliance checklist, file note and management approval. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 ¦ SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates ¦ SANS/municipal engineering standards; approved SDP; rational fire design | Applicable questions completed; required evidence accepted; critical failures resolved or escalated; decision and conditions approved by the delegated authority. | Approved Engineering Design and Technical Documentation assessment record; evidence index; findings and risk update; corrective-action/condition register; signed progression recommendation. | Professional Design Team; Quantity Surveyor; Financial Adviser; Sponsor/Funder Representatives | Incomplete design, cost, funding, procurement or permit readiness may expose capital, programme, compliance and contracting decisions. | Proceed / Proceed with conditions / Remediate and reassess / Hold / Rework / Stop or restructure | Controlled
22 | WP22 | Cost Planning and Financial Modelling | Prior work-package outputs accepted or formally waived; mandate, owner and applicable evidence request confirmed. | Signed memo, checklist, source document and responsible-person confirmation. ¦ Register entry, supporting drawing/report, approval note and updated risk item. ¦ Professional/specialist note, meeting minute, correspondence and decision record. ¦ Updated schedule, cost note, assumption log and evidence index reference. ¦ Authority response, compliance checklist, file note and management approval. | IFRS/IFRS for SMEs principles; lender due diligence checklist; signed financial model ¦ CIDB/procurement best practice; cost plan; QS measurement and BOQ controls ¦ Treasury-style value-for-money principles; funding term sheet; drawdown controls | Applicable questions completed; required evidence accepted; critical failures resolved or escalated; decision and conditions approved by the delegated authority. | Approved Cost Planning and Financial Modelling assessment record; evidence index; findings and risk update; corrective-action/condition register; signed progression recommendation. | Professional Design Team; Quantity Surveyor; Financial Adviser; Sponsor/Funder Representatives | Incomplete design, cost, funding, procurement or permit readiness may expose capital, programme, compliance and contracting decisions. | Proceed / Proceed with conditions / Remediate and reassess / Hold / Rework / Stop or restructure | Controlled
23 | WP23 | Capital Structuring and Funding Readiness | Prior work-package outputs accepted or formally waived; mandate, owner and applicable evidence request confirmed. | Signed memo, checklist, source document and responsible-person confirmation. ¦ Register entry, supporting drawing/report, approval note and updated risk item. ¦ Professional/specialist note, meeting minute, correspondence and decision record. ¦ Updated schedule, cost note, assumption log and evidence index reference. ¦ Authority response, compliance checklist, file note and management approval. | King IV governance practice; Companies Act 71 of 2008; project mandate file ¦ PMBOK stage-gate governance; board resolution; delegated authority matrix ¦ ISO 31000 risk management; stakeholder decision register; project charter | Applicable questions completed; required evidence accepted; critical failures resolved or escalated; decision and conditions approved by the delegated authority. | Approved Capital Structuring and Funding Readiness assessment record; evidence index; findings and risk update; corrective-action/condition register; signed progression recommendation. | Professional Design Team; Quantity Surveyor; Financial Adviser; Sponsor/Funder Representatives | Incomplete design, cost, funding, procurement or permit readiness may expose capital, programme, compliance and contracting decisions. | Proceed / Proceed with conditions / Remediate and reassess / Hold / Rework / Stop or restructure | Controlled
24 | WP24 | Procurement Strategy and Tender Documentation | Prior work-package outputs accepted or formally waived; mandate, owner and applicable evidence request confirmed. | Signed memo, checklist, source document and responsible-person confirmation. ¦ Register entry, supporting drawing/report, approval note and updated risk item. ¦ Professional/specialist note, meeting minute, correspondence and decision record. ¦ Updated schedule, cost note, assumption log and evidence index reference. ¦ Authority response, compliance checklist, file note and management approval. | IFRS/IFRS for SMEs principles; lender due diligence checklist; signed financial model ¦ CIDB/procurement best practice; cost plan; QS measurement and BOQ controls ¦ Treasury-style value-for-money principles; funding term sheet; drawdown controls | Applicable questions completed; required evidence accepted; critical failures resolved or escalated; decision and conditions approved by the delegated authority. | Approved Procurement Strategy and Tender Documentation assessment record; evidence index; findings and risk update; corrective-action/condition register; signed progression recommendation. | Project Manager; Procurement/Legal Lead; Professional Team; Authorities; Gate Authority | Incomplete design, cost, funding, procurement or permit readiness may expose capital, programme, compliance and contracting decisions. | Proceed / Proceed with conditions / Remediate and reassess / Hold / Rework / Stop or restructure | Controlled
25 | WP25 | Contractor Due Diligence and Appointment | Prior work-package outputs accepted or formally waived; mandate, owner and applicable evidence request confirmed. | Signed memo, checklist, source document and responsible-person confirmation. ¦ Register entry, supporting drawing/report, approval note and updated risk item. ¦ Professional/specialist note, meeting minute, correspondence and decision record. ¦ Updated schedule, cost note, assumption log and evidence index reference. ¦ Authority response, compliance checklist, file note and management approval. | IFRS/IFRS for SMEs principles; lender due diligence checklist; signed financial model ¦ CIDB/procurement best practice; cost plan; QS measurement and BOQ controls ¦ Treasury-style value-for-money principles; funding term sheet; drawdown controls | Applicable questions completed; required evidence accepted; critical failures resolved or escalated; decision and conditions approved by the delegated authority. | Approved Contractor Due Diligence and Appointment assessment record; evidence index; findings and risk update; corrective-action/condition register; signed progression recommendation. | Project Manager; Procurement/Legal Lead; Professional Team; Authorities; Gate Authority | Incomplete design, cost, funding, procurement or permit readiness may expose capital, programme, compliance and contracting decisions. | Proceed / Proceed with conditions / Remediate and reassess / Hold / Rework / Stop or restructure | Controlled
26 | WP26 | Regulatory Permitting and Building Plan Approval | Prior work-package outputs accepted or formally waived; mandate, owner and applicable evidence request confirmed. | Signed memo, checklist, source document and responsible-person confirmation. ¦ Register entry, supporting drawing/report, approval note and updated risk item. ¦ Professional/specialist note, meeting minute, correspondence and decision record. ¦ Updated schedule, cost note, assumption log and evidence index reference. ¦ Authority response, compliance checklist, file note and management approval. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 ¦ SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates ¦ SANS/municipal engineering standards; approved SDP; rational fire design | Applicable questions completed; required evidence accepted; critical failures resolved or escalated; decision and conditions approved by the delegated authority. | Approved Regulatory Permitting and Building Plan Approval assessment record; evidence index; findings and risk update; corrective-action/condition register; signed progression recommendation. | Project Manager; Procurement/Legal Lead; Professional Team; Authorities; Gate Authority | Incomplete design, cost, funding, procurement or permit readiness may expose capital, programme, compliance and contracting decisions. | Proceed / Proceed with conditions / Remediate and reassess / Hold / Rework / Stop or restructure | Controlled
27 | WP27 | Construction Mobilisation | Prior work-package outputs accepted or formally waived; mandate, owner and applicable evidence request confirmed. | Signed memo, checklist, source document and responsible-person confirmation. ¦ Register entry, supporting drawing/report, approval note and updated risk item. ¦ Professional/specialist note, meeting minute, correspondence and decision record. ¦ Updated schedule, cost note, assumption log and evidence index reference. ¦ Authority response, compliance checklist, file note and management approval. | OHS Act 85 of 1993; Construction Regulations, 2014; HSE file ¦ JBCC/NEC/FIDIC contract conditions; QA/QC inspection and test plans ¦ NEMA EMPr; municipal inspections; material approvals and payment certification | Applicable questions completed; required evidence accepted; critical failures resolved or escalated; decision and conditions approved by the delegated authority. | Approved Construction Mobilisation assessment record; evidence index; findings and risk update; corrective-action/condition register; signed progression recommendation. | Principal Agent; Contractor; HSE/Quality Leads; Professional Team; Project Manager | Weak mobilisation, construction, quality, HSE, testing or handover controls may cause defects, incidents, delay and non-functional assets. | Proceed / Proceed with conditions / Remediate and reassess / Hold / Rework / Stop or restructure | Controlled
28 | WP28 | Civil Works, Earthworks and Access Construction | Prior work-package outputs accepted or formally waived; mandate, owner and applicable evidence request confirmed. | Signed memo, checklist, source document and responsible-person confirmation. ¦ Register entry, supporting drawing/report, approval note and updated risk item. ¦ Professional/specialist note, meeting minute, correspondence and decision record. ¦ Updated schedule, cost note, assumption log and evidence index reference. ¦ Authority response, compliance checklist, file note and management approval. | OHS Act 85 of 1993; Construction Regulations, 2014; HSE file ¦ JBCC/NEC/FIDIC contract conditions; QA/QC inspection and test plans ¦ NEMA EMPr; municipal inspections; material approvals and payment certification | Applicable questions completed; required evidence accepted; critical failures resolved or escalated; decision and conditions approved by the delegated authority. | Approved Civil Works, Earthworks and Access Construction assessment record; evidence index; findings and risk update; corrective-action/condition register; signed progression recommendation. | Principal Agent; Contractor; HSE/Quality Leads; Professional Team; Project Manager | Weak mobilisation, construction, quality, HSE, testing or handover controls may cause defects, incidents, delay and non-functional assets. | Proceed / Proceed with conditions / Remediate and reassess / Hold / Rework / Stop or restructure | Controlled
29 | WP29 | Building Shells and Services Installation | Prior work-package outputs accepted or formally waived; mandate, owner and applicable evidence request confirmed. | Signed memo, checklist, source document and responsible-person confirmation. ¦ Register entry, supporting drawing/report, approval note and updated risk item. ¦ Professional/specialist note, meeting minute, correspondence and decision record. ¦ Updated schedule, cost note, assumption log and evidence index reference. ¦ Authority response, compliance checklist, file note and management approval. | OHS Act 85 of 1993; Construction Regulations, 2014; HSE file ¦ JBCC/NEC/FIDIC contract conditions; QA/QC inspection and test plans ¦ NEMA EMPr; municipal inspections; material approvals and payment certification | Applicable questions completed; required evidence accepted; critical failures resolved or escalated; decision and conditions approved by the delegated authority. | Approved Building Shells and Services Installation assessment record; evidence index; findings and risk update; corrective-action/condition register; signed progression recommendation. | Principal Agent; Contractor; HSE/Quality Leads; Professional Team; Project Manager | Weak mobilisation, construction, quality, HSE, testing or handover controls may cause defects, incidents, delay and non-functional assets. | Proceed / Proceed with conditions / Remediate and reassess / Hold / Rework / Stop or restructure | Controlled
30 | WP30 | Tenant Fit-Out Coordination | Prior work-package outputs accepted or formally waived; mandate, owner and applicable evidence request confirmed. | Signed memo, checklist, source document and responsible-person confirmation. ¦ Register entry, supporting drawing/report, approval note and updated risk item. ¦ Professional/specialist note, meeting minute, correspondence and decision record. ¦ Updated schedule, cost note, assumption log and evidence index reference. ¦ Authority response, compliance checklist, file note and management approval. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule ¦ Tenant design and fit-out manual; anchor specifications; trading-readiness checklist ¦ CPA/POPIA where applicable; tenant compliance file; rental assumptions | Applicable questions completed; required evidence accepted; critical failures resolved or escalated; decision and conditions approved by the delegated authority. | Approved Tenant Fit-Out Coordination assessment record; evidence index; findings and risk update; corrective-action/condition register; signed progression recommendation. | Principal Agent; Contractor; HSE/Quality Leads; Professional Team; Project Manager | Weak mobilisation, construction, quality, HSE, testing or handover controls may cause defects, incidents, delay and non-functional assets. | Proceed / Proceed with conditions / Remediate and reassess / Hold / Rework / Stop or restructure | Controlled
31 | WP31 | Quality Assurance, HSE and Compliance Control | Prior work-package outputs accepted or formally waived; mandate, owner and applicable evidence request confirmed. | Signed memo, checklist, source document and responsible-person confirmation. ¦ Register entry, supporting drawing/report, approval note and updated risk item. ¦ Professional/specialist note, meeting minute, correspondence and decision record. ¦ Updated schedule, cost note, assumption log and evidence index reference. ¦ Authority response, compliance checklist, file note and management approval. | OHS Act 85 of 1993; Construction Regulations, 2014; HSE file ¦ JBCC/NEC/FIDIC contract conditions; QA/QC inspection and test plans ¦ NEMA EMPr; municipal inspections; material approvals and payment certification | Applicable questions completed; required evidence accepted; critical failures resolved or escalated; decision and conditions approved by the delegated authority. | Approved Quality Assurance, HSE and Compliance Control assessment record; evidence index; findings and risk update; corrective-action/condition register; signed progression recommendation. | Principal Agent; Contractor; HSE/Quality Leads; Professional Team; Project Manager | Weak mobilisation, construction, quality, HSE, testing or handover controls may cause defects, incidents, delay and non-functional assets. | Proceed / Proceed with conditions / Remediate and reassess / Hold / Rework / Stop or restructure | Controlled
32 | WP32 | Commissioning and Testing | Prior work-package outputs accepted or formally waived; mandate, owner and applicable evidence request confirmed. | Signed memo, checklist, source document and responsible-person confirmation. ¦ Register entry, supporting drawing/report, approval note and updated risk item. ¦ Professional/specialist note, meeting minute, correspondence and decision record. ¦ Updated schedule, cost note, assumption log and evidence index reference. ¦ Authority response, compliance checklist, file note and management approval. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 ¦ SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates ¦ SANS/municipal engineering standards; approved SDP; rational fire design | Applicable questions completed; required evidence accepted; critical failures resolved or escalated; decision and conditions approved by the delegated authority. | Approved Commissioning and Testing assessment record; evidence index; findings and risk update; corrective-action/condition register; signed progression recommendation. | Commissioning Lead; Professional Team; Operators/Tenants; Asset Owner; Project Manager | Weak mobilisation, construction, quality, HSE, testing or handover controls may cause defects, incidents, delay and non-functional assets. | Proceed / Proceed with conditions / Remediate and reassess / Hold / Rework / Stop or restructure | Controlled
33 | WP33 | Handover to Operators and Tenants | Prior work-package outputs accepted or formally waived; mandate, owner and applicable evidence request confirmed. | Signed memo, checklist, source document and responsible-person confirmation. ¦ Register entry, supporting drawing/report, approval note and updated risk item. ¦ Professional/specialist note, meeting minute, correspondence and decision record. ¦ Updated schedule, cost note, assumption log and evidence index reference. ¦ Authority response, compliance checklist, file note and management approval. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule ¦ Tenant design and fit-out manual; anchor specifications; trading-readiness checklist ¦ CPA/POPIA where applicable; tenant compliance file; rental assumptions | Applicable questions completed; required evidence accepted; critical failures resolved or escalated; decision and conditions approved by the delegated authority. | Approved Handover to Operators and Tenants assessment record; evidence index; findings and risk update; corrective-action/condition register; signed progression recommendation. | Commissioning Lead; Professional Team; Operators/Tenants; Asset Owner; Project Manager | Weak mobilisation, construction, quality, HSE, testing or handover controls may cause defects, incidents, delay and non-functional assets. | Proceed / Proceed with conditions / Remediate and reassess / Hold / Rework / Stop or restructure | Controlled
34 | WP34 | Operational Ramp-Up | Prior work-package outputs accepted or formally waived; mandate, owner and applicable evidence request confirmed. | Signed memo, checklist, source document and responsible-person confirmation. ¦ Register entry, supporting drawing/report, approval note and updated risk item. ¦ Professional/specialist note, meeting minute, correspondence and decision record. ¦ Updated schedule, cost note, assumption log and evidence index reference. ¦ Authority response, compliance checklist, file note and management approval. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule ¦ Tenant design and fit-out manual; anchor specifications; trading-readiness checklist ¦ CPA/POPIA where applicable; tenant compliance file; rental assumptions | Applicable questions completed; required evidence accepted; critical failures resolved or escalated; decision and conditions approved by the delegated authority. | Approved Operational Ramp-Up assessment record; evidence index; findings and risk update; corrective-action/condition register; signed progression recommendation. | Asset/Property Manager; Operators/Tenants; Maintenance Lead; ESG/MERL Lead; Owner Governance | Weak operating, maintenance or impact controls may erode functionality, financial sustainability, compliance and long-term benefits. | Proceed / Proceed with conditions / Remediate and reassess / Hold / Rework / Stop or restructure | Controlled
35 | WP35 | Operations Management | Prior work-package outputs accepted or formally waived; mandate, owner and applicable evidence request confirmed. | Signed memo, checklist, source document and responsible-person confirmation. ¦ Register entry, supporting drawing/report, approval note and updated risk item. ¦ Professional/specialist note, meeting minute, correspondence and decision record. ¦ Updated schedule, cost note, assumption log and evidence index reference. ¦ Authority response, compliance checklist, file note and management approval. | SANS 10400 occupancy and fire safety; municipal health and fire requirements ¦ ISO 55000 asset management principles; maintenance plan; OHS operational file ¦ Lease administration best practice; service-level agreements; security and cleaning SOPs | Applicable questions completed; required evidence accepted; critical failures resolved or escalated; decision and conditions approved by the delegated authority. | Approved Operations Management assessment record; evidence index; findings and risk update; corrective-action/condition register; signed progression recommendation. | Asset/Property Manager; Operators/Tenants; Maintenance Lead; ESG/MERL Lead; Owner Governance | Weak operating, maintenance or impact controls may erode functionality, financial sustainability, compliance and long-term benefits. | Proceed / Proceed with conditions / Remediate and reassess / Hold / Rework / Stop or restructure | Controlled
36 | WP36 | Maintenance Management | Prior work-package outputs accepted or formally waived; mandate, owner and applicable evidence request confirmed. | Signed memo, checklist, source document and responsible-person confirmation. ¦ Register entry, supporting drawing/report, approval note and updated risk item. ¦ Professional/specialist note, meeting minute, correspondence and decision record. ¦ Updated schedule, cost note, assumption log and evidence index reference. ¦ Authority response, compliance checklist, file note and management approval. | SANS 10400 occupancy and fire safety; municipal health and fire requirements ¦ ISO 55000 asset management principles; maintenance plan; OHS operational file ¦ Lease administration best practice; service-level agreements; security and cleaning SOPs | Applicable questions completed; required evidence accepted; critical failures resolved or escalated; decision and conditions approved by the delegated authority. | Approved Maintenance Management assessment record; evidence index; findings and risk update; corrective-action/condition register; signed progression recommendation. | Asset/Property Manager; Operators/Tenants; Maintenance Lead; ESG/MERL Lead; Owner Governance | Weak operating, maintenance or impact controls may erode functionality, financial sustainability, compliance and long-term benefits. | Proceed / Proceed with conditions / Remediate and reassess / Hold / Rework / Stop or restructure | Controlled
37 | WP37 | Sustainable Impact, Performance Monitoring and Future Expansion | Prior work-package outputs accepted or formally waived; mandate, owner and applicable evidence request confirmed. | Signed memo, checklist, source document and responsible-person confirmation. ¦ Register entry, supporting drawing/report, approval note and updated risk item. ¦ Professional/specialist note, meeting minute, correspondence and decision record. ¦ Updated schedule, cost note, assumption log and evidence index reference. ¦ Authority response, compliance checklist, file note and management approval. | ESG reporting practice; local economic development commitments; utility performance data ¦ ISO 14001 environmental management principles; water and energy monitoring ¦ Socio-economic impact reporting; community benefit register; future expansion plan | Applicable questions completed; required evidence accepted; critical failures resolved or escalated; decision and conditions approved by the delegated authority. | Approved Sustainable Impact, Performance Monitoring and Future Expansion assessment record; evidence index; findings and risk update; corrective-action/condition register; signed progression recommendation. | Asset/Property Manager; Operators/Tenants; Maintenance Lead; ESG/MERL Lead; Owner Governance | Weak operating, maintenance or impact controls may erode functionality, financial sustainability, compliance and long-term benefits. | Proceed / Proceed with conditions / Remediate and reassess / Hold / Rework / Stop or restructure | Controlled

## 3,700 Question Index
OPBOH™ 3,700 Stage-Gate Question Index
Source questions mapped to the 37 controlled stages; assessment-response columns are ready for implementation
Question No. | Stage | WP Code | Stage / Work Package | Strategic Stage-Gate Question | Evidence Required | Reference Basis | Assessment Control
01.001 | 01 | WP01 | Strategic Inception and Project Mandate | Has the project team confirmed project vision - governance approval in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | King IV governance practice; Companies Act 71 of 2008; project mandate file | Yes / No / N/A + Score 0–5 + Rating
01.002 | 01 | WP01 | Strategic Inception and Project Mandate | Is there a responsible owner, due date and approval route for scope mandate - governance approval? | Register entry, supporting drawing/report, approval note and updated risk item. | PMBOK stage-gate governance; board resolution; delegated authority matrix | Yes / No / N/A + Score 0–5 + Rating
01.003 | 01 | WP01 | Strategic Inception and Project Mandate | Has the gate file tested whether decision authority - governance approval creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | ISO 31000 risk management; stakeholder decision register; project charter | Yes / No / N/A + Score 0–5 + Rating
01.004 | 01 | WP01 | Strategic Inception and Project Mandate | Are assumptions for developer appointment - governance approval documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | King IV governance practice; Companies Act 71 of 2008; project mandate file | Yes / No / N/A + Score 0–5 + Rating
01.005 | 01 | WP01 | Strategic Inception and Project Mandate | Has the relevant authority, specialist or professional adviser reviewed client objectives - governance approval where required? | Authority response, compliance checklist, file note and management approval. | PMBOK stage-gate governance; board resolution; delegated authority matrix | Yes / No / N/A + Score 0–5 + Rating
01.006 | 01 | WP01 | Strategic Inception and Project Mandate | Is the decision record for governance structure - governance approval aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | ISO 31000 risk management; stakeholder decision register; project charter | Yes / No / N/A + Score 0–5 + Rating
01.007 | 01 | WP01 | Strategic Inception and Project Mandate | Have cost, programme and compliance implications of project vision - legal authority been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | King IV governance practice; Companies Act 71 of 2008; project mandate file | Yes / No / N/A + Score 0–5 + Rating
01.008 | 01 | WP01 | Strategic Inception and Project Mandate | Has the team obtained written confirmation or documented proof for scope mandate - legal authority? | Current certificate/letter/report, version control and document-control entry. | PMBOK stage-gate governance; board resolution; delegated authority matrix | Yes / No / N/A + Score 0–5 + Rating
01.009 | 01 | WP01 | Strategic Inception and Project Mandate | Does the evidence for decision authority - legal authority support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | ISO 31000 risk management; stakeholder decision register; project charter | Yes / No / N/A + Score 0–5 + Rating
01.010 | 01 | WP01 | Strategic Inception and Project Mandate | Have dependencies linked to developer appointment - legal authority been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | King IV governance practice; Companies Act 71 of 2008; project mandate file | Yes / No / N/A + Score 0–5 + Rating
01.011 | 01 | WP01 | Strategic Inception and Project Mandate | Has the project team confirmed client objectives - legal authority in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | PMBOK stage-gate governance; board resolution; delegated authority matrix | Yes / No / N/A + Score 0–5 + Rating
01.012 | 01 | WP01 | Strategic Inception and Project Mandate | Is there a responsible owner, due date and approval route for governance structure - legal authority? | Register entry, supporting drawing/report, approval note and updated risk item. | ISO 31000 risk management; stakeholder decision register; project charter | Yes / No / N/A + Score 0–5 + Rating
01.013 | 01 | WP01 | Strategic Inception and Project Mandate | Has the gate file tested whether project vision - technical feasibility creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | King IV governance practice; Companies Act 71 of 2008; project mandate file | Yes / No / N/A + Score 0–5 + Rating
01.014 | 01 | WP01 | Strategic Inception and Project Mandate | Are assumptions for scope mandate - technical feasibility documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | PMBOK stage-gate governance; board resolution; delegated authority matrix | Yes / No / N/A + Score 0–5 + Rating
01.015 | 01 | WP01 | Strategic Inception and Project Mandate | Has the relevant authority, specialist or professional adviser reviewed decision authority - technical feasibility where required? | Authority response, compliance checklist, file note and management approval. | ISO 31000 risk management; stakeholder decision register; project charter | Yes / No / N/A + Score 0–5 + Rating
01.016 | 01 | WP01 | Strategic Inception and Project Mandate | Is the decision record for developer appointment - technical feasibility aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | King IV governance practice; Companies Act 71 of 2008; project mandate file | Yes / No / N/A + Score 0–5 + Rating
01.017 | 01 | WP01 | Strategic Inception and Project Mandate | Have cost, programme and compliance implications of client objectives - technical feasibility been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | PMBOK stage-gate governance; board resolution; delegated authority matrix | Yes / No / N/A + Score 0–5 + Rating
01.018 | 01 | WP01 | Strategic Inception and Project Mandate | Has the team obtained written confirmation or documented proof for governance structure - technical feasibility? | Current certificate/letter/report, version control and document-control entry. | ISO 31000 risk management; stakeholder decision register; project charter | Yes / No / N/A + Score 0–5 + Rating
01.019 | 01 | WP01 | Strategic Inception and Project Mandate | Does the evidence for project vision - financial viability support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | King IV governance practice; Companies Act 71 of 2008; project mandate file | Yes / No / N/A + Score 0–5 + Rating
01.020 | 01 | WP01 | Strategic Inception and Project Mandate | Have dependencies linked to scope mandate - financial viability been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | PMBOK stage-gate governance; board resolution; delegated authority matrix | Yes / No / N/A + Score 0–5 + Rating
01.021 | 01 | WP01 | Strategic Inception and Project Mandate | Has the project team confirmed decision authority - financial viability in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | ISO 31000 risk management; stakeholder decision register; project charter | Yes / No / N/A + Score 0–5 + Rating
01.022 | 01 | WP01 | Strategic Inception and Project Mandate | Is there a responsible owner, due date and approval route for developer appointment - financial viability? | Register entry, supporting drawing/report, approval note and updated risk item. | King IV governance practice; Companies Act 71 of 2008; project mandate file | Yes / No / N/A + Score 0–5 + Rating
01.023 | 01 | WP01 | Strategic Inception and Project Mandate | Has the gate file tested whether client objectives - financial viability creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | PMBOK stage-gate governance; board resolution; delegated authority matrix | Yes / No / N/A + Score 0–5 + Rating
01.024 | 01 | WP01 | Strategic Inception and Project Mandate | Are assumptions for governance structure - financial viability documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | ISO 31000 risk management; stakeholder decision register; project charter | Yes / No / N/A + Score 0–5 + Rating
01.025 | 01 | WP01 | Strategic Inception and Project Mandate | Has the relevant authority, specialist or professional adviser reviewed project vision - programme impact where required? | Authority response, compliance checklist, file note and management approval. | King IV governance practice; Companies Act 71 of 2008; project mandate file | Yes / No / N/A + Score 0–5 + Rating
01.026 | 01 | WP01 | Strategic Inception and Project Mandate | Is the decision record for scope mandate - programme impact aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | PMBOK stage-gate governance; board resolution; delegated authority matrix | Yes / No / N/A + Score 0–5 + Rating
01.027 | 01 | WP01 | Strategic Inception and Project Mandate | Have cost, programme and compliance implications of decision authority - programme impact been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | ISO 31000 risk management; stakeholder decision register; project charter | Yes / No / N/A + Score 0–5 + Rating
01.028 | 01 | WP01 | Strategic Inception and Project Mandate | Has the team obtained written confirmation or documented proof for developer appointment - programme impact? | Current certificate/letter/report, version control and document-control entry. | King IV governance practice; Companies Act 71 of 2008; project mandate file | Yes / No / N/A + Score 0–5 + Rating
01.029 | 01 | WP01 | Strategic Inception and Project Mandate | Does the evidence for client objectives - programme impact support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | PMBOK stage-gate governance; board resolution; delegated authority matrix | Yes / No / N/A + Score 0–5 + Rating
01.030 | 01 | WP01 | Strategic Inception and Project Mandate | Have dependencies linked to governance structure - programme impact been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | ISO 31000 risk management; stakeholder decision register; project charter | Yes / No / N/A + Score 0–5 + Rating
01.031 | 01 | WP01 | Strategic Inception and Project Mandate | Has the project team confirmed project vision - risk mitigation in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | King IV governance practice; Companies Act 71 of 2008; project mandate file | Yes / No / N/A + Score 0–5 + Rating
01.032 | 01 | WP01 | Strategic Inception and Project Mandate | Is there a responsible owner, due date and approval route for scope mandate - risk mitigation? | Register entry, supporting drawing/report, approval note and updated risk item. | PMBOK stage-gate governance; board resolution; delegated authority matrix | Yes / No / N/A + Score 0–5 + Rating
01.033 | 01 | WP01 | Strategic Inception and Project Mandate | Has the gate file tested whether decision authority - risk mitigation creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | ISO 31000 risk management; stakeholder decision register; project charter | Yes / No / N/A + Score 0–5 + Rating
01.034 | 01 | WP01 | Strategic Inception and Project Mandate | Are assumptions for developer appointment - risk mitigation documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | King IV governance practice; Companies Act 71 of 2008; project mandate file | Yes / No / N/A + Score 0–5 + Rating
01.035 | 01 | WP01 | Strategic Inception and Project Mandate | Has the relevant authority, specialist or professional adviser reviewed client objectives - risk mitigation where required? | Authority response, compliance checklist, file note and management approval. | PMBOK stage-gate governance; board resolution; delegated authority matrix | Yes / No / N/A + Score 0–5 + Rating
01.036 | 01 | WP01 | Strategic Inception and Project Mandate | Is the decision record for governance structure - risk mitigation aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | ISO 31000 risk management; stakeholder decision register; project charter | Yes / No / N/A + Score 0–5 + Rating
01.037 | 01 | WP01 | Strategic Inception and Project Mandate | Have cost, programme and compliance implications of project vision - stakeholder acceptance been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | King IV governance practice; Companies Act 71 of 2008; project mandate file | Yes / No / N/A + Score 0–5 + Rating
01.038 | 01 | WP01 | Strategic Inception and Project Mandate | Has the team obtained written confirmation or documented proof for scope mandate - stakeholder acceptance? | Current certificate/letter/report, version control and document-control entry. | PMBOK stage-gate governance; board resolution; delegated authority matrix | Yes / No / N/A + Score 0–5 + Rating
01.039 | 01 | WP01 | Strategic Inception and Project Mandate | Does the evidence for decision authority - stakeholder acceptance support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | ISO 31000 risk management; stakeholder decision register; project charter | Yes / No / N/A + Score 0–5 + Rating
01.040 | 01 | WP01 | Strategic Inception and Project Mandate | Have dependencies linked to developer appointment - stakeholder acceptance been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | King IV governance practice; Companies Act 71 of 2008; project mandate file | Yes / No / N/A + Score 0–5 + Rating
01.041 | 01 | WP01 | Strategic Inception and Project Mandate | Has the project team confirmed client objectives - stakeholder acceptance in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | PMBOK stage-gate governance; board resolution; delegated authority matrix | Yes / No / N/A + Score 0–5 + Rating
01.042 | 01 | WP01 | Strategic Inception and Project Mandate | Is there a responsible owner, due date and approval route for governance structure - stakeholder acceptance? | Register entry, supporting drawing/report, approval note and updated risk item. | ISO 31000 risk management; stakeholder decision register; project charter | Yes / No / N/A + Score 0–5 + Rating
01.043 | 01 | WP01 | Strategic Inception and Project Mandate | Has the gate file tested whether project vision - document control creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | King IV governance practice; Companies Act 71 of 2008; project mandate file | Yes / No / N/A + Score 0–5 + Rating
01.044 | 01 | WP01 | Strategic Inception and Project Mandate | Are assumptions for scope mandate - document control documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | PMBOK stage-gate governance; board resolution; delegated authority matrix | Yes / No / N/A + Score 0–5 + Rating
01.045 | 01 | WP01 | Strategic Inception and Project Mandate | Has the relevant authority, specialist or professional adviser reviewed decision authority - document control where required? | Authority response, compliance checklist, file note and management approval. | ISO 31000 risk management; stakeholder decision register; project charter | Yes / No / N/A + Score 0–5 + Rating
01.046 | 01 | WP01 | Strategic Inception and Project Mandate | Is the decision record for developer appointment - document control aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | King IV governance practice; Companies Act 71 of 2008; project mandate file | Yes / No / N/A + Score 0–5 + Rating
01.047 | 01 | WP01 | Strategic Inception and Project Mandate | Have cost, programme and compliance implications of client objectives - document control been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | PMBOK stage-gate governance; board resolution; delegated authority matrix | Yes / No / N/A + Score 0–5 + Rating
01.048 | 01 | WP01 | Strategic Inception and Project Mandate | Has the team obtained written confirmation or documented proof for governance structure - document control? | Current certificate/letter/report, version control and document-control entry. | ISO 31000 risk management; stakeholder decision register; project charter | Yes / No / N/A + Score 0–5 + Rating
01.049 | 01 | WP01 | Strategic Inception and Project Mandate | Does the evidence for project vision - professional certification support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | King IV governance practice; Companies Act 71 of 2008; project mandate file | Yes / No / N/A + Score 0–5 + Rating
01.050 | 01 | WP01 | Strategic Inception and Project Mandate | Have dependencies linked to scope mandate - professional certification been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | PMBOK stage-gate governance; board resolution; delegated authority matrix | Yes / No / N/A + Score 0–5 + Rating
01.051 | 01 | WP01 | Strategic Inception and Project Mandate | Has the project team confirmed decision authority - professional certification in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | ISO 31000 risk management; stakeholder decision register; project charter | Yes / No / N/A + Score 0–5 + Rating
01.052 | 01 | WP01 | Strategic Inception and Project Mandate | Is there a responsible owner, due date and approval route for developer appointment - professional certification? | Register entry, supporting drawing/report, approval note and updated risk item. | King IV governance practice; Companies Act 71 of 2008; project mandate file | Yes / No / N/A + Score 0–5 + Rating
01.053 | 01 | WP01 | Strategic Inception and Project Mandate | Has the gate file tested whether client objectives - professional certification creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | PMBOK stage-gate governance; board resolution; delegated authority matrix | Yes / No / N/A + Score 0–5 + Rating
01.054 | 01 | WP01 | Strategic Inception and Project Mandate | Are assumptions for governance structure - professional certification documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | ISO 31000 risk management; stakeholder decision register; project charter | Yes / No / N/A + Score 0–5 + Rating
01.055 | 01 | WP01 | Strategic Inception and Project Mandate | Has the relevant authority, specialist or professional adviser reviewed project vision - implementation readiness where required? | Authority response, compliance checklist, file note and management approval. | King IV governance practice; Companies Act 71 of 2008; project mandate file | Yes / No / N/A + Score 0–5 + Rating
01.056 | 01 | WP01 | Strategic Inception and Project Mandate | Is the decision record for scope mandate - implementation readiness aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | PMBOK stage-gate governance; board resolution; delegated authority matrix | Yes / No / N/A + Score 0–5 + Rating
01.057 | 01 | WP01 | Strategic Inception and Project Mandate | Have cost, programme and compliance implications of decision authority - implementation readiness been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | ISO 31000 risk management; stakeholder decision register; project charter | Yes / No / N/A + Score 0–5 + Rating
01.058 | 01 | WP01 | Strategic Inception and Project Mandate | Has the team obtained written confirmation or documented proof for developer appointment - implementation readiness? | Current certificate/letter/report, version control and document-control entry. | King IV governance practice; Companies Act 71 of 2008; project mandate file | Yes / No / N/A + Score 0–5 + Rating
01.059 | 01 | WP01 | Strategic Inception and Project Mandate | Does the evidence for client objectives - implementation readiness support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | PMBOK stage-gate governance; board resolution; delegated authority matrix | Yes / No / N/A + Score 0–5 + Rating
01.060 | 01 | WP01 | Strategic Inception and Project Mandate | Have dependencies linked to governance structure - implementation readiness been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | ISO 31000 risk management; stakeholder decision register; project charter | Yes / No / N/A + Score 0–5 + Rating
01.061 | 01 | WP01 | Strategic Inception and Project Mandate | Has the project team confirmed project vision - governance approval in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | King IV governance practice; Companies Act 71 of 2008; project mandate file | Yes / No / N/A + Score 0–5 + Rating
01.062 | 01 | WP01 | Strategic Inception and Project Mandate | Is there a responsible owner, due date and approval route for scope mandate - governance approval? | Register entry, supporting drawing/report, approval note and updated risk item. | PMBOK stage-gate governance; board resolution; delegated authority matrix | Yes / No / N/A + Score 0–5 + Rating
01.063 | 01 | WP01 | Strategic Inception and Project Mandate | Has the gate file tested whether decision authority - governance approval creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | ISO 31000 risk management; stakeholder decision register; project charter | Yes / No / N/A + Score 0–5 + Rating
01.064 | 01 | WP01 | Strategic Inception and Project Mandate | Are assumptions for developer appointment - governance approval documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | King IV governance practice; Companies Act 71 of 2008; project mandate file | Yes / No / N/A + Score 0–5 + Rating
01.065 | 01 | WP01 | Strategic Inception and Project Mandate | Has the relevant authority, specialist or professional adviser reviewed client objectives - governance approval where required? | Authority response, compliance checklist, file note and management approval. | PMBOK stage-gate governance; board resolution; delegated authority matrix | Yes / No / N/A + Score 0–5 + Rating
01.066 | 01 | WP01 | Strategic Inception and Project Mandate | Is the decision record for governance structure - governance approval aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | ISO 31000 risk management; stakeholder decision register; project charter | Yes / No / N/A + Score 0–5 + Rating
01.067 | 01 | WP01 | Strategic Inception and Project Mandate | Have cost, programme and compliance implications of project vision - legal authority been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | King IV governance practice; Companies Act 71 of 2008; project mandate file | Yes / No / N/A + Score 0–5 + Rating
01.068 | 01 | WP01 | Strategic Inception and Project Mandate | Has the team obtained written confirmation or documented proof for scope mandate - legal authority? | Current certificate/letter/report, version control and document-control entry. | PMBOK stage-gate governance; board resolution; delegated authority matrix | Yes / No / N/A + Score 0–5 + Rating
01.069 | 01 | WP01 | Strategic Inception and Project Mandate | Does the evidence for decision authority - legal authority support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | ISO 31000 risk management; stakeholder decision register; project charter | Yes / No / N/A + Score 0–5 + Rating
01.070 | 01 | WP01 | Strategic Inception and Project Mandate | Have dependencies linked to developer appointment - legal authority been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | King IV governance practice; Companies Act 71 of 2008; project mandate file | Yes / No / N/A + Score 0–5 + Rating
01.071 | 01 | WP01 | Strategic Inception and Project Mandate | Has the project team confirmed client objectives - legal authority in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | PMBOK stage-gate governance; board resolution; delegated authority matrix | Yes / No / N/A + Score 0–5 + Rating
01.072 | 01 | WP01 | Strategic Inception and Project Mandate | Is there a responsible owner, due date and approval route for governance structure - legal authority? | Register entry, supporting drawing/report, approval note and updated risk item. | ISO 31000 risk management; stakeholder decision register; project charter | Yes / No / N/A + Score 0–5 + Rating
01.073 | 01 | WP01 | Strategic Inception and Project Mandate | Has the gate file tested whether project vision - technical feasibility creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | King IV governance practice; Companies Act 71 of 2008; project mandate file | Yes / No / N/A + Score 0–5 + Rating
01.074 | 01 | WP01 | Strategic Inception and Project Mandate | Are assumptions for scope mandate - technical feasibility documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | PMBOK stage-gate governance; board resolution; delegated authority matrix | Yes / No / N/A + Score 0–5 + Rating
01.075 | 01 | WP01 | Strategic Inception and Project Mandate | Has the relevant authority, specialist or professional adviser reviewed decision authority - technical feasibility where required? | Authority response, compliance checklist, file note and management approval. | ISO 31000 risk management; stakeholder decision register; project charter | Yes / No / N/A + Score 0–5 + Rating
01.076 | 01 | WP01 | Strategic Inception and Project Mandate | Is the decision record for developer appointment - technical feasibility aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | King IV governance practice; Companies Act 71 of 2008; project mandate file | Yes / No / N/A + Score 0–5 + Rating
01.077 | 01 | WP01 | Strategic Inception and Project Mandate | Have cost, programme and compliance implications of client objectives - technical feasibility been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | PMBOK stage-gate governance; board resolution; delegated authority matrix | Yes / No / N/A + Score 0–5 + Rating
01.078 | 01 | WP01 | Strategic Inception and Project Mandate | Has the team obtained written confirmation or documented proof for governance structure - technical feasibility? | Current certificate/letter/report, version control and document-control entry. | ISO 31000 risk management; stakeholder decision register; project charter | Yes / No / N/A + Score 0–5 + Rating
01.079 | 01 | WP01 | Strategic Inception and Project Mandate | Does the evidence for project vision - financial viability support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | King IV governance practice; Companies Act 71 of 2008; project mandate file | Yes / No / N/A + Score 0–5 + Rating
01.080 | 01 | WP01 | Strategic Inception and Project Mandate | Have dependencies linked to scope mandate - financial viability been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | PMBOK stage-gate governance; board resolution; delegated authority matrix | Yes / No / N/A + Score 0–5 + Rating
01.081 | 01 | WP01 | Strategic Inception and Project Mandate | Has the project team confirmed decision authority - financial viability in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | ISO 31000 risk management; stakeholder decision register; project charter | Yes / No / N/A + Score 0–5 + Rating
01.082 | 01 | WP01 | Strategic Inception and Project Mandate | Is there a responsible owner, due date and approval route for developer appointment - financial viability? | Register entry, supporting drawing/report, approval note and updated risk item. | King IV governance practice; Companies Act 71 of 2008; project mandate file | Yes / No / N/A + Score 0–5 + Rating
01.083 | 01 | WP01 | Strategic Inception and Project Mandate | Has the gate file tested whether client objectives - financial viability creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | PMBOK stage-gate governance; board resolution; delegated authority matrix | Yes / No / N/A + Score 0–5 + Rating
01.084 | 01 | WP01 | Strategic Inception and Project Mandate | Are assumptions for governance structure - financial viability documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | ISO 31000 risk management; stakeholder decision register; project charter | Yes / No / N/A + Score 0–5 + Rating
01.085 | 01 | WP01 | Strategic Inception and Project Mandate | Has the relevant authority, specialist or professional adviser reviewed project vision - programme impact where required? | Authority response, compliance checklist, file note and management approval. | King IV governance practice; Companies Act 71 of 2008; project mandate file | Yes / No / N/A + Score 0–5 + Rating
01.086 | 01 | WP01 | Strategic Inception and Project Mandate | Is the decision record for scope mandate - programme impact aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | PMBOK stage-gate governance; board resolution; delegated authority matrix | Yes / No / N/A + Score 0–5 + Rating
01.087 | 01 | WP01 | Strategic Inception and Project Mandate | Have cost, programme and compliance implications of decision authority - programme impact been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | ISO 31000 risk management; stakeholder decision register; project charter | Yes / No / N/A + Score 0–5 + Rating
01.088 | 01 | WP01 | Strategic Inception and Project Mandate | Has the team obtained written confirmation or documented proof for developer appointment - programme impact? | Current certificate/letter/report, version control and document-control entry. | King IV governance practice; Companies Act 71 of 2008; project mandate file | Yes / No / N/A + Score 0–5 + Rating
01.089 | 01 | WP01 | Strategic Inception and Project Mandate | Does the evidence for client objectives - programme impact support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | PMBOK stage-gate governance; board resolution; delegated authority matrix | Yes / No / N/A + Score 0–5 + Rating
01.090 | 01 | WP01 | Strategic Inception and Project Mandate | Have dependencies linked to governance structure - programme impact been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | ISO 31000 risk management; stakeholder decision register; project charter | Yes / No / N/A + Score 0–5 + Rating
01.091 | 01 | WP01 | Strategic Inception and Project Mandate | Has the project team confirmed project vision - risk mitigation in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | King IV governance practice; Companies Act 71 of 2008; project mandate file | Yes / No / N/A + Score 0–5 + Rating
01.092 | 01 | WP01 | Strategic Inception and Project Mandate | Is there a responsible owner, due date and approval route for scope mandate - risk mitigation? | Register entry, supporting drawing/report, approval note and updated risk item. | PMBOK stage-gate governance; board resolution; delegated authority matrix | Yes / No / N/A + Score 0–5 + Rating
01.093 | 01 | WP01 | Strategic Inception and Project Mandate | Has the gate file tested whether decision authority - risk mitigation creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | ISO 31000 risk management; stakeholder decision register; project charter | Yes / No / N/A + Score 0–5 + Rating
01.094 | 01 | WP01 | Strategic Inception and Project Mandate | Are assumptions for developer appointment - risk mitigation documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | King IV governance practice; Companies Act 71 of 2008; project mandate file | Yes / No / N/A + Score 0–5 + Rating
01.095 | 01 | WP01 | Strategic Inception and Project Mandate | Has the relevant authority, specialist or professional adviser reviewed client objectives - risk mitigation where required? | Authority response, compliance checklist, file note and management approval. | PMBOK stage-gate governance; board resolution; delegated authority matrix | Yes / No / N/A + Score 0–5 + Rating
01.096 | 01 | WP01 | Strategic Inception and Project Mandate | Is the decision record for governance structure - risk mitigation aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | ISO 31000 risk management; stakeholder decision register; project charter | Yes / No / N/A + Score 0–5 + Rating
01.097 | 01 | WP01 | Strategic Inception and Project Mandate | Have cost, programme and compliance implications of project vision - stakeholder acceptance been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | King IV governance practice; Companies Act 71 of 2008; project mandate file | Yes / No / N/A + Score 0–5 + Rating
01.098 | 01 | WP01 | Strategic Inception and Project Mandate | Has the team obtained written confirmation or documented proof for scope mandate - stakeholder acceptance? | Current certificate/letter/report, version control and document-control entry. | PMBOK stage-gate governance; board resolution; delegated authority matrix | Yes / No / N/A + Score 0–5 + Rating
01.099 | 01 | WP01 | Strategic Inception and Project Mandate | Does the evidence for decision authority - stakeholder acceptance support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | ISO 31000 risk management; stakeholder decision register; project charter | Yes / No / N/A + Score 0–5 + Rating
01.100 | 01 | WP01 | Strategic Inception and Project Mandate | Have dependencies linked to developer appointment - stakeholder acceptance been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | King IV governance practice; Companies Act 71 of 2008; project mandate file | Yes / No / N/A + Score 0–5 + Rating
02.001 | 02 | WP02 | Site Identification and Opportunity Discovery | Has the project team confirmed R567 exposure - governance approval in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | SPLUMA Act 16 of 2013; municipal land use scheme; title deed/SG diagram | Yes / No / N/A + Score 0–5 + Rating
02.002 | 02 | WP02 | Site Identification and Opportunity Discovery | Is there a responsible owner, due date and approval route for 3 ha site extent - governance approval? | Register entry, supporting drawing/report, approval note and updated risk item. | Deeds Registries Act 47 of 1937; Surveyor-General records; servitude register | Yes / No / N/A + Score 0–5 + Rating
02.003 | 02 | WP02 | Site Identification and Opportunity Discovery | Has the gate file tested whether market gap - governance approval creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | Municipal Planning By-law; wayleave requirements; landowner consent | Yes / No / N/A + Score 0–5 + Rating
02.004 | 02 | WP02 | Site Identification and Opportunity Discovery | Are assumptions for community catchment - governance approval documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | SPLUMA Act 16 of 2013; municipal land use scheme; title deed/SG diagram | Yes / No / N/A + Score 0–5 + Rating
02.005 | 02 | WP02 | Site Identification and Opportunity Discovery | Has the relevant authority, specialist or professional adviser reviewed mobility flows - governance approval where required? | Authority response, compliance checklist, file note and management approval. | Deeds Registries Act 47 of 1937; Surveyor-General records; servitude register | Yes / No / N/A + Score 0–5 + Rating
02.006 | 02 | WP02 | Site Identification and Opportunity Discovery | Is the decision record for competitive landscape - governance approval aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | Municipal Planning By-law; wayleave requirements; landowner consent | Yes / No / N/A + Score 0–5 + Rating
02.007 | 02 | WP02 | Site Identification and Opportunity Discovery | Have cost, programme and compliance implications of R567 exposure - legal authority been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | SPLUMA Act 16 of 2013; municipal land use scheme; title deed/SG diagram | Yes / No / N/A + Score 0–5 + Rating
02.008 | 02 | WP02 | Site Identification and Opportunity Discovery | Has the team obtained written confirmation or documented proof for 3 ha site extent - legal authority? | Current certificate/letter/report, version control and document-control entry. | Deeds Registries Act 47 of 1937; Surveyor-General records; servitude register | Yes / No / N/A + Score 0–5 + Rating
02.009 | 02 | WP02 | Site Identification and Opportunity Discovery | Does the evidence for market gap - legal authority support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | Municipal Planning By-law; wayleave requirements; landowner consent | Yes / No / N/A + Score 0–5 + Rating
02.010 | 02 | WP02 | Site Identification and Opportunity Discovery | Have dependencies linked to community catchment - legal authority been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | SPLUMA Act 16 of 2013; municipal land use scheme; title deed/SG diagram | Yes / No / N/A + Score 0–5 + Rating
02.011 | 02 | WP02 | Site Identification and Opportunity Discovery | Has the project team confirmed mobility flows - legal authority in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | Deeds Registries Act 47 of 1937; Surveyor-General records; servitude register | Yes / No / N/A + Score 0–5 + Rating
02.012 | 02 | WP02 | Site Identification and Opportunity Discovery | Is there a responsible owner, due date and approval route for competitive landscape - legal authority? | Register entry, supporting drawing/report, approval note and updated risk item. | Municipal Planning By-law; wayleave requirements; landowner consent | Yes / No / N/A + Score 0–5 + Rating
02.013 | 02 | WP02 | Site Identification and Opportunity Discovery | Has the gate file tested whether R567 exposure - technical feasibility creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | SPLUMA Act 16 of 2013; municipal land use scheme; title deed/SG diagram | Yes / No / N/A + Score 0–5 + Rating
02.014 | 02 | WP02 | Site Identification and Opportunity Discovery | Are assumptions for 3 ha site extent - technical feasibility documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | Deeds Registries Act 47 of 1937; Surveyor-General records; servitude register | Yes / No / N/A + Score 0–5 + Rating
02.015 | 02 | WP02 | Site Identification and Opportunity Discovery | Has the relevant authority, specialist or professional adviser reviewed market gap - technical feasibility where required? | Authority response, compliance checklist, file note and management approval. | Municipal Planning By-law; wayleave requirements; landowner consent | Yes / No / N/A + Score 0–5 + Rating
02.016 | 02 | WP02 | Site Identification and Opportunity Discovery | Is the decision record for community catchment - technical feasibility aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | SPLUMA Act 16 of 2013; municipal land use scheme; title deed/SG diagram | Yes / No / N/A + Score 0–5 + Rating
02.017 | 02 | WP02 | Site Identification and Opportunity Discovery | Have cost, programme and compliance implications of mobility flows - technical feasibility been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | Deeds Registries Act 47 of 1937; Surveyor-General records; servitude register | Yes / No / N/A + Score 0–5 + Rating
02.018 | 02 | WP02 | Site Identification and Opportunity Discovery | Has the team obtained written confirmation or documented proof for competitive landscape - technical feasibility? | Current certificate/letter/report, version control and document-control entry. | Municipal Planning By-law; wayleave requirements; landowner consent | Yes / No / N/A + Score 0–5 + Rating
02.019 | 02 | WP02 | Site Identification and Opportunity Discovery | Does the evidence for R567 exposure - financial viability support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | SPLUMA Act 16 of 2013; municipal land use scheme; title deed/SG diagram | Yes / No / N/A + Score 0–5 + Rating
02.020 | 02 | WP02 | Site Identification and Opportunity Discovery | Have dependencies linked to 3 ha site extent - financial viability been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | Deeds Registries Act 47 of 1937; Surveyor-General records; servitude register | Yes / No / N/A + Score 0–5 + Rating
02.021 | 02 | WP02 | Site Identification and Opportunity Discovery | Has the project team confirmed market gap - financial viability in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | Municipal Planning By-law; wayleave requirements; landowner consent | Yes / No / N/A + Score 0–5 + Rating
02.022 | 02 | WP02 | Site Identification and Opportunity Discovery | Is there a responsible owner, due date and approval route for community catchment - financial viability? | Register entry, supporting drawing/report, approval note and updated risk item. | SPLUMA Act 16 of 2013; municipal land use scheme; title deed/SG diagram | Yes / No / N/A + Score 0–5 + Rating
02.023 | 02 | WP02 | Site Identification and Opportunity Discovery | Has the gate file tested whether mobility flows - financial viability creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | Deeds Registries Act 47 of 1937; Surveyor-General records; servitude register | Yes / No / N/A + Score 0–5 + Rating
02.024 | 02 | WP02 | Site Identification and Opportunity Discovery | Are assumptions for competitive landscape - financial viability documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | Municipal Planning By-law; wayleave requirements; landowner consent | Yes / No / N/A + Score 0–5 + Rating
02.025 | 02 | WP02 | Site Identification and Opportunity Discovery | Has the relevant authority, specialist or professional adviser reviewed R567 exposure - programme impact where required? | Authority response, compliance checklist, file note and management approval. | SPLUMA Act 16 of 2013; municipal land use scheme; title deed/SG diagram | Yes / No / N/A + Score 0–5 + Rating
02.026 | 02 | WP02 | Site Identification and Opportunity Discovery | Is the decision record for 3 ha site extent - programme impact aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | Deeds Registries Act 47 of 1937; Surveyor-General records; servitude register | Yes / No / N/A + Score 0–5 + Rating
02.027 | 02 | WP02 | Site Identification and Opportunity Discovery | Have cost, programme and compliance implications of market gap - programme impact been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | Municipal Planning By-law; wayleave requirements; landowner consent | Yes / No / N/A + Score 0–5 + Rating
02.028 | 02 | WP02 | Site Identification and Opportunity Discovery | Has the team obtained written confirmation or documented proof for community catchment - programme impact? | Current certificate/letter/report, version control and document-control entry. | SPLUMA Act 16 of 2013; municipal land use scheme; title deed/SG diagram | Yes / No / N/A + Score 0–5 + Rating
02.029 | 02 | WP02 | Site Identification and Opportunity Discovery | Does the evidence for mobility flows - programme impact support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | Deeds Registries Act 47 of 1937; Surveyor-General records; servitude register | Yes / No / N/A + Score 0–5 + Rating
02.030 | 02 | WP02 | Site Identification and Opportunity Discovery | Have dependencies linked to competitive landscape - programme impact been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | Municipal Planning By-law; wayleave requirements; landowner consent | Yes / No / N/A + Score 0–5 + Rating
02.031 | 02 | WP02 | Site Identification and Opportunity Discovery | Has the project team confirmed R567 exposure - risk mitigation in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | SPLUMA Act 16 of 2013; municipal land use scheme; title deed/SG diagram | Yes / No / N/A + Score 0–5 + Rating
02.032 | 02 | WP02 | Site Identification and Opportunity Discovery | Is there a responsible owner, due date and approval route for 3 ha site extent - risk mitigation? | Register entry, supporting drawing/report, approval note and updated risk item. | Deeds Registries Act 47 of 1937; Surveyor-General records; servitude register | Yes / No / N/A + Score 0–5 + Rating
02.033 | 02 | WP02 | Site Identification and Opportunity Discovery | Has the gate file tested whether market gap - risk mitigation creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | Municipal Planning By-law; wayleave requirements; landowner consent | Yes / No / N/A + Score 0–5 + Rating
02.034 | 02 | WP02 | Site Identification and Opportunity Discovery | Are assumptions for community catchment - risk mitigation documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | SPLUMA Act 16 of 2013; municipal land use scheme; title deed/SG diagram | Yes / No / N/A + Score 0–5 + Rating
02.035 | 02 | WP02 | Site Identification and Opportunity Discovery | Has the relevant authority, specialist or professional adviser reviewed mobility flows - risk mitigation where required? | Authority response, compliance checklist, file note and management approval. | Deeds Registries Act 47 of 1937; Surveyor-General records; servitude register | Yes / No / N/A + Score 0–5 + Rating
02.036 | 02 | WP02 | Site Identification and Opportunity Discovery | Is the decision record for competitive landscape - risk mitigation aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | Municipal Planning By-law; wayleave requirements; landowner consent | Yes / No / N/A + Score 0–5 + Rating
02.037 | 02 | WP02 | Site Identification and Opportunity Discovery | Have cost, programme and compliance implications of R567 exposure - stakeholder acceptance been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | SPLUMA Act 16 of 2013; municipal land use scheme; title deed/SG diagram | Yes / No / N/A + Score 0–5 + Rating
02.038 | 02 | WP02 | Site Identification and Opportunity Discovery | Has the team obtained written confirmation or documented proof for 3 ha site extent - stakeholder acceptance? | Current certificate/letter/report, version control and document-control entry. | Deeds Registries Act 47 of 1937; Surveyor-General records; servitude register | Yes / No / N/A + Score 0–5 + Rating
02.039 | 02 | WP02 | Site Identification and Opportunity Discovery | Does the evidence for market gap - stakeholder acceptance support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | Municipal Planning By-law; wayleave requirements; landowner consent | Yes / No / N/A + Score 0–5 + Rating
02.040 | 02 | WP02 | Site Identification and Opportunity Discovery | Have dependencies linked to community catchment - stakeholder acceptance been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | SPLUMA Act 16 of 2013; municipal land use scheme; title deed/SG diagram | Yes / No / N/A + Score 0–5 + Rating
02.041 | 02 | WP02 | Site Identification and Opportunity Discovery | Has the project team confirmed mobility flows - stakeholder acceptance in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | Deeds Registries Act 47 of 1937; Surveyor-General records; servitude register | Yes / No / N/A + Score 0–5 + Rating
02.042 | 02 | WP02 | Site Identification and Opportunity Discovery | Is there a responsible owner, due date and approval route for competitive landscape - stakeholder acceptance? | Register entry, supporting drawing/report, approval note and updated risk item. | Municipal Planning By-law; wayleave requirements; landowner consent | Yes / No / N/A + Score 0–5 + Rating
02.043 | 02 | WP02 | Site Identification and Opportunity Discovery | Has the gate file tested whether R567 exposure - document control creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | SPLUMA Act 16 of 2013; municipal land use scheme; title deed/SG diagram | Yes / No / N/A + Score 0–5 + Rating
02.044 | 02 | WP02 | Site Identification and Opportunity Discovery | Are assumptions for 3 ha site extent - document control documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | Deeds Registries Act 47 of 1937; Surveyor-General records; servitude register | Yes / No / N/A + Score 0–5 + Rating
02.045 | 02 | WP02 | Site Identification and Opportunity Discovery | Has the relevant authority, specialist or professional adviser reviewed market gap - document control where required? | Authority response, compliance checklist, file note and management approval. | Municipal Planning By-law; wayleave requirements; landowner consent | Yes / No / N/A + Score 0–5 + Rating
02.046 | 02 | WP02 | Site Identification and Opportunity Discovery | Is the decision record for community catchment - document control aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | SPLUMA Act 16 of 2013; municipal land use scheme; title deed/SG diagram | Yes / No / N/A + Score 0–5 + Rating
02.047 | 02 | WP02 | Site Identification and Opportunity Discovery | Have cost, programme and compliance implications of mobility flows - document control been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | Deeds Registries Act 47 of 1937; Surveyor-General records; servitude register | Yes / No / N/A + Score 0–5 + Rating
02.048 | 02 | WP02 | Site Identification and Opportunity Discovery | Has the team obtained written confirmation or documented proof for competitive landscape - document control? | Current certificate/letter/report, version control and document-control entry. | Municipal Planning By-law; wayleave requirements; landowner consent | Yes / No / N/A + Score 0–5 + Rating
02.049 | 02 | WP02 | Site Identification and Opportunity Discovery | Does the evidence for R567 exposure - professional certification support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | SPLUMA Act 16 of 2013; municipal land use scheme; title deed/SG diagram | Yes / No / N/A + Score 0–5 + Rating
02.050 | 02 | WP02 | Site Identification and Opportunity Discovery | Have dependencies linked to 3 ha site extent - professional certification been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | Deeds Registries Act 47 of 1937; Surveyor-General records; servitude register | Yes / No / N/A + Score 0–5 + Rating
02.051 | 02 | WP02 | Site Identification and Opportunity Discovery | Has the project team confirmed market gap - professional certification in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | Municipal Planning By-law; wayleave requirements; landowner consent | Yes / No / N/A + Score 0–5 + Rating
02.052 | 02 | WP02 | Site Identification and Opportunity Discovery | Is there a responsible owner, due date and approval route for community catchment - professional certification? | Register entry, supporting drawing/report, approval note and updated risk item. | SPLUMA Act 16 of 2013; municipal land use scheme; title deed/SG diagram | Yes / No / N/A + Score 0–5 + Rating
02.053 | 02 | WP02 | Site Identification and Opportunity Discovery | Has the gate file tested whether mobility flows - professional certification creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | Deeds Registries Act 47 of 1937; Surveyor-General records; servitude register | Yes / No / N/A + Score 0–5 + Rating
02.054 | 02 | WP02 | Site Identification and Opportunity Discovery | Are assumptions for competitive landscape - professional certification documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | Municipal Planning By-law; wayleave requirements; landowner consent | Yes / No / N/A + Score 0–5 + Rating
02.055 | 02 | WP02 | Site Identification and Opportunity Discovery | Has the relevant authority, specialist or professional adviser reviewed R567 exposure - implementation readiness where required? | Authority response, compliance checklist, file note and management approval. | SPLUMA Act 16 of 2013; municipal land use scheme; title deed/SG diagram | Yes / No / N/A + Score 0–5 + Rating
02.056 | 02 | WP02 | Site Identification and Opportunity Discovery | Is the decision record for 3 ha site extent - implementation readiness aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | Deeds Registries Act 47 of 1937; Surveyor-General records; servitude register | Yes / No / N/A + Score 0–5 + Rating
02.057 | 02 | WP02 | Site Identification and Opportunity Discovery | Have cost, programme and compliance implications of market gap - implementation readiness been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | Municipal Planning By-law; wayleave requirements; landowner consent | Yes / No / N/A + Score 0–5 + Rating
02.058 | 02 | WP02 | Site Identification and Opportunity Discovery | Has the team obtained written confirmation or documented proof for community catchment - implementation readiness? | Current certificate/letter/report, version control and document-control entry. | SPLUMA Act 16 of 2013; municipal land use scheme; title deed/SG diagram | Yes / No / N/A + Score 0–5 + Rating
02.059 | 02 | WP02 | Site Identification and Opportunity Discovery | Does the evidence for mobility flows - implementation readiness support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | Deeds Registries Act 47 of 1937; Surveyor-General records; servitude register | Yes / No / N/A + Score 0–5 + Rating
02.060 | 02 | WP02 | Site Identification and Opportunity Discovery | Have dependencies linked to competitive landscape - implementation readiness been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | Municipal Planning By-law; wayleave requirements; landowner consent | Yes / No / N/A + Score 0–5 + Rating
02.061 | 02 | WP02 | Site Identification and Opportunity Discovery | Has the project team confirmed R567 exposure - governance approval in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | SPLUMA Act 16 of 2013; municipal land use scheme; title deed/SG diagram | Yes / No / N/A + Score 0–5 + Rating
02.062 | 02 | WP02 | Site Identification and Opportunity Discovery | Is there a responsible owner, due date and approval route for 3 ha site extent - governance approval? | Register entry, supporting drawing/report, approval note and updated risk item. | Deeds Registries Act 47 of 1937; Surveyor-General records; servitude register | Yes / No / N/A + Score 0–5 + Rating
02.063 | 02 | WP02 | Site Identification and Opportunity Discovery | Has the gate file tested whether market gap - governance approval creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | Municipal Planning By-law; wayleave requirements; landowner consent | Yes / No / N/A + Score 0–5 + Rating
02.064 | 02 | WP02 | Site Identification and Opportunity Discovery | Are assumptions for community catchment - governance approval documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | SPLUMA Act 16 of 2013; municipal land use scheme; title deed/SG diagram | Yes / No / N/A + Score 0–5 + Rating
02.065 | 02 | WP02 | Site Identification and Opportunity Discovery | Has the relevant authority, specialist or professional adviser reviewed mobility flows - governance approval where required? | Authority response, compliance checklist, file note and management approval. | Deeds Registries Act 47 of 1937; Surveyor-General records; servitude register | Yes / No / N/A + Score 0–5 + Rating
02.066 | 02 | WP02 | Site Identification and Opportunity Discovery | Is the decision record for competitive landscape - governance approval aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | Municipal Planning By-law; wayleave requirements; landowner consent | Yes / No / N/A + Score 0–5 + Rating
02.067 | 02 | WP02 | Site Identification and Opportunity Discovery | Have cost, programme and compliance implications of R567 exposure - legal authority been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | SPLUMA Act 16 of 2013; municipal land use scheme; title deed/SG diagram | Yes / No / N/A + Score 0–5 + Rating
02.068 | 02 | WP02 | Site Identification and Opportunity Discovery | Has the team obtained written confirmation or documented proof for 3 ha site extent - legal authority? | Current certificate/letter/report, version control and document-control entry. | Deeds Registries Act 47 of 1937; Surveyor-General records; servitude register | Yes / No / N/A + Score 0–5 + Rating
02.069 | 02 | WP02 | Site Identification and Opportunity Discovery | Does the evidence for market gap - legal authority support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | Municipal Planning By-law; wayleave requirements; landowner consent | Yes / No / N/A + Score 0–5 + Rating
02.070 | 02 | WP02 | Site Identification and Opportunity Discovery | Have dependencies linked to community catchment - legal authority been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | SPLUMA Act 16 of 2013; municipal land use scheme; title deed/SG diagram | Yes / No / N/A + Score 0–5 + Rating
02.071 | 02 | WP02 | Site Identification and Opportunity Discovery | Has the project team confirmed mobility flows - legal authority in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | Deeds Registries Act 47 of 1937; Surveyor-General records; servitude register | Yes / No / N/A + Score 0–5 + Rating
02.072 | 02 | WP02 | Site Identification and Opportunity Discovery | Is there a responsible owner, due date and approval route for competitive landscape - legal authority? | Register entry, supporting drawing/report, approval note and updated risk item. | Municipal Planning By-law; wayleave requirements; landowner consent | Yes / No / N/A + Score 0–5 + Rating
02.073 | 02 | WP02 | Site Identification and Opportunity Discovery | Has the gate file tested whether R567 exposure - technical feasibility creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | SPLUMA Act 16 of 2013; municipal land use scheme; title deed/SG diagram | Yes / No / N/A + Score 0–5 + Rating
02.074 | 02 | WP02 | Site Identification and Opportunity Discovery | Are assumptions for 3 ha site extent - technical feasibility documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | Deeds Registries Act 47 of 1937; Surveyor-General records; servitude register | Yes / No / N/A + Score 0–5 + Rating
02.075 | 02 | WP02 | Site Identification and Opportunity Discovery | Has the relevant authority, specialist or professional adviser reviewed market gap - technical feasibility where required? | Authority response, compliance checklist, file note and management approval. | Municipal Planning By-law; wayleave requirements; landowner consent | Yes / No / N/A + Score 0–5 + Rating
02.076 | 02 | WP02 | Site Identification and Opportunity Discovery | Is the decision record for community catchment - technical feasibility aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | SPLUMA Act 16 of 2013; municipal land use scheme; title deed/SG diagram | Yes / No / N/A + Score 0–5 + Rating
02.077 | 02 | WP02 | Site Identification and Opportunity Discovery | Have cost, programme and compliance implications of mobility flows - technical feasibility been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | Deeds Registries Act 47 of 1937; Surveyor-General records; servitude register | Yes / No / N/A + Score 0–5 + Rating
02.078 | 02 | WP02 | Site Identification and Opportunity Discovery | Has the team obtained written confirmation or documented proof for competitive landscape - technical feasibility? | Current certificate/letter/report, version control and document-control entry. | Municipal Planning By-law; wayleave requirements; landowner consent | Yes / No / N/A + Score 0–5 + Rating
02.079 | 02 | WP02 | Site Identification and Opportunity Discovery | Does the evidence for R567 exposure - financial viability support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | SPLUMA Act 16 of 2013; municipal land use scheme; title deed/SG diagram | Yes / No / N/A + Score 0–5 + Rating
02.080 | 02 | WP02 | Site Identification and Opportunity Discovery | Have dependencies linked to 3 ha site extent - financial viability been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | Deeds Registries Act 47 of 1937; Surveyor-General records; servitude register | Yes / No / N/A + Score 0–5 + Rating
02.081 | 02 | WP02 | Site Identification and Opportunity Discovery | Has the project team confirmed market gap - financial viability in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | Municipal Planning By-law; wayleave requirements; landowner consent | Yes / No / N/A + Score 0–5 + Rating
02.082 | 02 | WP02 | Site Identification and Opportunity Discovery | Is there a responsible owner, due date and approval route for community catchment - financial viability? | Register entry, supporting drawing/report, approval note and updated risk item. | SPLUMA Act 16 of 2013; municipal land use scheme; title deed/SG diagram | Yes / No / N/A + Score 0–5 + Rating
02.083 | 02 | WP02 | Site Identification and Opportunity Discovery | Has the gate file tested whether mobility flows - financial viability creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | Deeds Registries Act 47 of 1937; Surveyor-General records; servitude register | Yes / No / N/A + Score 0–5 + Rating
02.084 | 02 | WP02 | Site Identification and Opportunity Discovery | Are assumptions for competitive landscape - financial viability documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | Municipal Planning By-law; wayleave requirements; landowner consent | Yes / No / N/A + Score 0–5 + Rating
02.085 | 02 | WP02 | Site Identification and Opportunity Discovery | Has the relevant authority, specialist or professional adviser reviewed R567 exposure - programme impact where required? | Authority response, compliance checklist, file note and management approval. | SPLUMA Act 16 of 2013; municipal land use scheme; title deed/SG diagram | Yes / No / N/A + Score 0–5 + Rating
02.086 | 02 | WP02 | Site Identification and Opportunity Discovery | Is the decision record for 3 ha site extent - programme impact aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | Deeds Registries Act 47 of 1937; Surveyor-General records; servitude register | Yes / No / N/A + Score 0–5 + Rating
02.087 | 02 | WP02 | Site Identification and Opportunity Discovery | Have cost, programme and compliance implications of market gap - programme impact been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | Municipal Planning By-law; wayleave requirements; landowner consent | Yes / No / N/A + Score 0–5 + Rating
02.088 | 02 | WP02 | Site Identification and Opportunity Discovery | Has the team obtained written confirmation or documented proof for community catchment - programme impact? | Current certificate/letter/report, version control and document-control entry. | SPLUMA Act 16 of 2013; municipal land use scheme; title deed/SG diagram | Yes / No / N/A + Score 0–5 + Rating
02.089 | 02 | WP02 | Site Identification and Opportunity Discovery | Does the evidence for mobility flows - programme impact support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | Deeds Registries Act 47 of 1937; Surveyor-General records; servitude register | Yes / No / N/A + Score 0–5 + Rating
02.090 | 02 | WP02 | Site Identification and Opportunity Discovery | Have dependencies linked to competitive landscape - programme impact been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | Municipal Planning By-law; wayleave requirements; landowner consent | Yes / No / N/A + Score 0–5 + Rating
02.091 | 02 | WP02 | Site Identification and Opportunity Discovery | Has the project team confirmed R567 exposure - risk mitigation in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | SPLUMA Act 16 of 2013; municipal land use scheme; title deed/SG diagram | Yes / No / N/A + Score 0–5 + Rating
02.092 | 02 | WP02 | Site Identification and Opportunity Discovery | Is there a responsible owner, due date and approval route for 3 ha site extent - risk mitigation? | Register entry, supporting drawing/report, approval note and updated risk item. | Deeds Registries Act 47 of 1937; Surveyor-General records; servitude register | Yes / No / N/A + Score 0–5 + Rating
02.093 | 02 | WP02 | Site Identification and Opportunity Discovery | Has the gate file tested whether market gap - risk mitigation creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | Municipal Planning By-law; wayleave requirements; landowner consent | Yes / No / N/A + Score 0–5 + Rating
02.094 | 02 | WP02 | Site Identification and Opportunity Discovery | Are assumptions for community catchment - risk mitigation documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | SPLUMA Act 16 of 2013; municipal land use scheme; title deed/SG diagram | Yes / No / N/A + Score 0–5 + Rating
02.095 | 02 | WP02 | Site Identification and Opportunity Discovery | Has the relevant authority, specialist or professional adviser reviewed mobility flows - risk mitigation where required? | Authority response, compliance checklist, file note and management approval. | Deeds Registries Act 47 of 1937; Surveyor-General records; servitude register | Yes / No / N/A + Score 0–5 + Rating
02.096 | 02 | WP02 | Site Identification and Opportunity Discovery | Is the decision record for competitive landscape - risk mitigation aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | Municipal Planning By-law; wayleave requirements; landowner consent | Yes / No / N/A + Score 0–5 + Rating
02.097 | 02 | WP02 | Site Identification and Opportunity Discovery | Have cost, programme and compliance implications of R567 exposure - stakeholder acceptance been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | SPLUMA Act 16 of 2013; municipal land use scheme; title deed/SG diagram | Yes / No / N/A + Score 0–5 + Rating
02.098 | 02 | WP02 | Site Identification and Opportunity Discovery | Has the team obtained written confirmation or documented proof for 3 ha site extent - stakeholder acceptance? | Current certificate/letter/report, version control and document-control entry. | Deeds Registries Act 47 of 1937; Surveyor-General records; servitude register | Yes / No / N/A + Score 0–5 + Rating
02.099 | 02 | WP02 | Site Identification and Opportunity Discovery | Does the evidence for market gap - stakeholder acceptance support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | Municipal Planning By-law; wayleave requirements; landowner consent | Yes / No / N/A + Score 0–5 + Rating
02.100 | 02 | WP02 | Site Identification and Opportunity Discovery | Have dependencies linked to community catchment - stakeholder acceptance been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | SPLUMA Act 16 of 2013; municipal land use scheme; title deed/SG diagram | Yes / No / N/A + Score 0–5 + Rating
03.001 | 03 | WP03 | Preliminary Site Screening | Has the project team confirmed ownership confirmation - governance approval in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | SPLUMA Act 16 of 2013; municipal land use scheme; title deed/SG diagram | Yes / No / N/A + Score 0–5 + Rating
03.002 | 03 | WP03 | Preliminary Site Screening | Is there a responsible owner, due date and approval route for servitudes - governance approval? | Register entry, supporting drawing/report, approval note and updated risk item. | Deeds Registries Act 47 of 1937; Surveyor-General records; servitude register | Yes / No / N/A + Score 0–5 + Rating
03.003 | 03 | WP03 | Preliminary Site Screening | Has the gate file tested whether basic zoning position - governance approval creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | Municipal Planning By-law; wayleave requirements; landowner consent | Yes / No / N/A + Score 0–5 + Rating
03.004 | 03 | WP03 | Preliminary Site Screening | Are assumptions for environmental sensitivity - governance approval documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | SPLUMA Act 16 of 2013; municipal land use scheme; title deed/SG diagram | Yes / No / N/A + Score 0–5 + Rating
03.005 | 03 | WP03 | Preliminary Site Screening | Has the relevant authority, specialist or professional adviser reviewed access constraints - governance approval where required? | Authority response, compliance checklist, file note and management approval. | Deeds Registries Act 47 of 1937; Surveyor-General records; servitude register | Yes / No / N/A + Score 0–5 + Rating
03.006 | 03 | WP03 | Preliminary Site Screening | Is the decision record for bulk services proximity - governance approval aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | Municipal Planning By-law; wayleave requirements; landowner consent | Yes / No / N/A + Score 0–5 + Rating
03.007 | 03 | WP03 | Preliminary Site Screening | Have cost, programme and compliance implications of ownership confirmation - legal authority been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | SPLUMA Act 16 of 2013; municipal land use scheme; title deed/SG diagram | Yes / No / N/A + Score 0–5 + Rating
03.008 | 03 | WP03 | Preliminary Site Screening | Has the team obtained written confirmation or documented proof for servitudes - legal authority? | Current certificate/letter/report, version control and document-control entry. | Deeds Registries Act 47 of 1937; Surveyor-General records; servitude register | Yes / No / N/A + Score 0–5 + Rating
03.009 | 03 | WP03 | Preliminary Site Screening | Does the evidence for basic zoning position - legal authority support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | Municipal Planning By-law; wayleave requirements; landowner consent | Yes / No / N/A + Score 0–5 + Rating
03.010 | 03 | WP03 | Preliminary Site Screening | Have dependencies linked to environmental sensitivity - legal authority been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | SPLUMA Act 16 of 2013; municipal land use scheme; title deed/SG diagram | Yes / No / N/A + Score 0–5 + Rating
03.011 | 03 | WP03 | Preliminary Site Screening | Has the project team confirmed access constraints - legal authority in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | Deeds Registries Act 47 of 1937; Surveyor-General records; servitude register | Yes / No / N/A + Score 0–5 + Rating
03.012 | 03 | WP03 | Preliminary Site Screening | Is there a responsible owner, due date and approval route for bulk services proximity - legal authority? | Register entry, supporting drawing/report, approval note and updated risk item. | Municipal Planning By-law; wayleave requirements; landowner consent | Yes / No / N/A + Score 0–5 + Rating
03.013 | 03 | WP03 | Preliminary Site Screening | Has the gate file tested whether ownership confirmation - technical feasibility creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | SPLUMA Act 16 of 2013; municipal land use scheme; title deed/SG diagram | Yes / No / N/A + Score 0–5 + Rating
03.014 | 03 | WP03 | Preliminary Site Screening | Are assumptions for servitudes - technical feasibility documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | Deeds Registries Act 47 of 1937; Surveyor-General records; servitude register | Yes / No / N/A + Score 0–5 + Rating
03.015 | 03 | WP03 | Preliminary Site Screening | Has the relevant authority, specialist or professional adviser reviewed basic zoning position - technical feasibility where required? | Authority response, compliance checklist, file note and management approval. | Municipal Planning By-law; wayleave requirements; landowner consent | Yes / No / N/A + Score 0–5 + Rating
03.016 | 03 | WP03 | Preliminary Site Screening | Is the decision record for environmental sensitivity - technical feasibility aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | SPLUMA Act 16 of 2013; municipal land use scheme; title deed/SG diagram | Yes / No / N/A + Score 0–5 + Rating
03.017 | 03 | WP03 | Preliminary Site Screening | Have cost, programme and compliance implications of access constraints - technical feasibility been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | Deeds Registries Act 47 of 1937; Surveyor-General records; servitude register | Yes / No / N/A + Score 0–5 + Rating
03.018 | 03 | WP03 | Preliminary Site Screening | Has the team obtained written confirmation or documented proof for bulk services proximity - technical feasibility? | Current certificate/letter/report, version control and document-control entry. | Municipal Planning By-law; wayleave requirements; landowner consent | Yes / No / N/A + Score 0–5 + Rating
03.019 | 03 | WP03 | Preliminary Site Screening | Does the evidence for ownership confirmation - financial viability support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | SPLUMA Act 16 of 2013; municipal land use scheme; title deed/SG diagram | Yes / No / N/A + Score 0–5 + Rating
03.020 | 03 | WP03 | Preliminary Site Screening | Have dependencies linked to servitudes - financial viability been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | Deeds Registries Act 47 of 1937; Surveyor-General records; servitude register | Yes / No / N/A + Score 0–5 + Rating
03.021 | 03 | WP03 | Preliminary Site Screening | Has the project team confirmed basic zoning position - financial viability in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | Municipal Planning By-law; wayleave requirements; landowner consent | Yes / No / N/A + Score 0–5 + Rating
03.022 | 03 | WP03 | Preliminary Site Screening | Is there a responsible owner, due date and approval route for environmental sensitivity - financial viability? | Register entry, supporting drawing/report, approval note and updated risk item. | SPLUMA Act 16 of 2013; municipal land use scheme; title deed/SG diagram | Yes / No / N/A + Score 0–5 + Rating
03.023 | 03 | WP03 | Preliminary Site Screening | Has the gate file tested whether access constraints - financial viability creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | Deeds Registries Act 47 of 1937; Surveyor-General records; servitude register | Yes / No / N/A + Score 0–5 + Rating
03.024 | 03 | WP03 | Preliminary Site Screening | Are assumptions for bulk services proximity - financial viability documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | Municipal Planning By-law; wayleave requirements; landowner consent | Yes / No / N/A + Score 0–5 + Rating
03.025 | 03 | WP03 | Preliminary Site Screening | Has the relevant authority, specialist or professional adviser reviewed ownership confirmation - programme impact where required? | Authority response, compliance checklist, file note and management approval. | SPLUMA Act 16 of 2013; municipal land use scheme; title deed/SG diagram | Yes / No / N/A + Score 0–5 + Rating
03.026 | 03 | WP03 | Preliminary Site Screening | Is the decision record for servitudes - programme impact aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | Deeds Registries Act 47 of 1937; Surveyor-General records; servitude register | Yes / No / N/A + Score 0–5 + Rating
03.027 | 03 | WP03 | Preliminary Site Screening | Have cost, programme and compliance implications of basic zoning position - programme impact been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | Municipal Planning By-law; wayleave requirements; landowner consent | Yes / No / N/A + Score 0–5 + Rating
03.028 | 03 | WP03 | Preliminary Site Screening | Has the team obtained written confirmation or documented proof for environmental sensitivity - programme impact? | Current certificate/letter/report, version control and document-control entry. | SPLUMA Act 16 of 2013; municipal land use scheme; title deed/SG diagram | Yes / No / N/A + Score 0–5 + Rating
03.029 | 03 | WP03 | Preliminary Site Screening | Does the evidence for access constraints - programme impact support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | Deeds Registries Act 47 of 1937; Surveyor-General records; servitude register | Yes / No / N/A + Score 0–5 + Rating
03.030 | 03 | WP03 | Preliminary Site Screening | Have dependencies linked to bulk services proximity - programme impact been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | Municipal Planning By-law; wayleave requirements; landowner consent | Yes / No / N/A + Score 0–5 + Rating
03.031 | 03 | WP03 | Preliminary Site Screening | Has the project team confirmed ownership confirmation - risk mitigation in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | SPLUMA Act 16 of 2013; municipal land use scheme; title deed/SG diagram | Yes / No / N/A + Score 0–5 + Rating
03.032 | 03 | WP03 | Preliminary Site Screening | Is there a responsible owner, due date and approval route for servitudes - risk mitigation? | Register entry, supporting drawing/report, approval note and updated risk item. | Deeds Registries Act 47 of 1937; Surveyor-General records; servitude register | Yes / No / N/A + Score 0–5 + Rating
03.033 | 03 | WP03 | Preliminary Site Screening | Has the gate file tested whether basic zoning position - risk mitigation creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | Municipal Planning By-law; wayleave requirements; landowner consent | Yes / No / N/A + Score 0–5 + Rating
03.034 | 03 | WP03 | Preliminary Site Screening | Are assumptions for environmental sensitivity - risk mitigation documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | SPLUMA Act 16 of 2013; municipal land use scheme; title deed/SG diagram | Yes / No / N/A + Score 0–5 + Rating
03.035 | 03 | WP03 | Preliminary Site Screening | Has the relevant authority, specialist or professional adviser reviewed access constraints - risk mitigation where required? | Authority response, compliance checklist, file note and management approval. | Deeds Registries Act 47 of 1937; Surveyor-General records; servitude register | Yes / No / N/A + Score 0–5 + Rating
03.036 | 03 | WP03 | Preliminary Site Screening | Is the decision record for bulk services proximity - risk mitigation aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | Municipal Planning By-law; wayleave requirements; landowner consent | Yes / No / N/A + Score 0–5 + Rating
03.037 | 03 | WP03 | Preliminary Site Screening | Have cost, programme and compliance implications of ownership confirmation - stakeholder acceptance been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | SPLUMA Act 16 of 2013; municipal land use scheme; title deed/SG diagram | Yes / No / N/A + Score 0–5 + Rating
03.038 | 03 | WP03 | Preliminary Site Screening | Has the team obtained written confirmation or documented proof for servitudes - stakeholder acceptance? | Current certificate/letter/report, version control and document-control entry. | Deeds Registries Act 47 of 1937; Surveyor-General records; servitude register | Yes / No / N/A + Score 0–5 + Rating
03.039 | 03 | WP03 | Preliminary Site Screening | Does the evidence for basic zoning position - stakeholder acceptance support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | Municipal Planning By-law; wayleave requirements; landowner consent | Yes / No / N/A + Score 0–5 + Rating
03.040 | 03 | WP03 | Preliminary Site Screening | Have dependencies linked to environmental sensitivity - stakeholder acceptance been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | SPLUMA Act 16 of 2013; municipal land use scheme; title deed/SG diagram | Yes / No / N/A + Score 0–5 + Rating
03.041 | 03 | WP03 | Preliminary Site Screening | Has the project team confirmed access constraints - stakeholder acceptance in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | Deeds Registries Act 47 of 1937; Surveyor-General records; servitude register | Yes / No / N/A + Score 0–5 + Rating
03.042 | 03 | WP03 | Preliminary Site Screening | Is there a responsible owner, due date and approval route for bulk services proximity - stakeholder acceptance? | Register entry, supporting drawing/report, approval note and updated risk item. | Municipal Planning By-law; wayleave requirements; landowner consent | Yes / No / N/A + Score 0–5 + Rating
03.043 | 03 | WP03 | Preliminary Site Screening | Has the gate file tested whether ownership confirmation - document control creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | SPLUMA Act 16 of 2013; municipal land use scheme; title deed/SG diagram | Yes / No / N/A + Score 0–5 + Rating
03.044 | 03 | WP03 | Preliminary Site Screening | Are assumptions for servitudes - document control documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | Deeds Registries Act 47 of 1937; Surveyor-General records; servitude register | Yes / No / N/A + Score 0–5 + Rating
03.045 | 03 | WP03 | Preliminary Site Screening | Has the relevant authority, specialist or professional adviser reviewed basic zoning position - document control where required? | Authority response, compliance checklist, file note and management approval. | Municipal Planning By-law; wayleave requirements; landowner consent | Yes / No / N/A + Score 0–5 + Rating
03.046 | 03 | WP03 | Preliminary Site Screening | Is the decision record for environmental sensitivity - document control aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | SPLUMA Act 16 of 2013; municipal land use scheme; title deed/SG diagram | Yes / No / N/A + Score 0–5 + Rating
03.047 | 03 | WP03 | Preliminary Site Screening | Have cost, programme and compliance implications of access constraints - document control been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | Deeds Registries Act 47 of 1937; Surveyor-General records; servitude register | Yes / No / N/A + Score 0–5 + Rating
03.048 | 03 | WP03 | Preliminary Site Screening | Has the team obtained written confirmation or documented proof for bulk services proximity - document control? | Current certificate/letter/report, version control and document-control entry. | Municipal Planning By-law; wayleave requirements; landowner consent | Yes / No / N/A + Score 0–5 + Rating
03.049 | 03 | WP03 | Preliminary Site Screening | Does the evidence for ownership confirmation - professional certification support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | SPLUMA Act 16 of 2013; municipal land use scheme; title deed/SG diagram | Yes / No / N/A + Score 0–5 + Rating
03.050 | 03 | WP03 | Preliminary Site Screening | Have dependencies linked to servitudes - professional certification been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | Deeds Registries Act 47 of 1937; Surveyor-General records; servitude register | Yes / No / N/A + Score 0–5 + Rating
03.051 | 03 | WP03 | Preliminary Site Screening | Has the project team confirmed basic zoning position - professional certification in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | Municipal Planning By-law; wayleave requirements; landowner consent | Yes / No / N/A + Score 0–5 + Rating
03.052 | 03 | WP03 | Preliminary Site Screening | Is there a responsible owner, due date and approval route for environmental sensitivity - professional certification? | Register entry, supporting drawing/report, approval note and updated risk item. | SPLUMA Act 16 of 2013; municipal land use scheme; title deed/SG diagram | Yes / No / N/A + Score 0–5 + Rating
03.053 | 03 | WP03 | Preliminary Site Screening | Has the gate file tested whether access constraints - professional certification creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | Deeds Registries Act 47 of 1937; Surveyor-General records; servitude register | Yes / No / N/A + Score 0–5 + Rating
03.054 | 03 | WP03 | Preliminary Site Screening | Are assumptions for bulk services proximity - professional certification documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | Municipal Planning By-law; wayleave requirements; landowner consent | Yes / No / N/A + Score 0–5 + Rating
03.055 | 03 | WP03 | Preliminary Site Screening | Has the relevant authority, specialist or professional adviser reviewed ownership confirmation - implementation readiness where required? | Authority response, compliance checklist, file note and management approval. | SPLUMA Act 16 of 2013; municipal land use scheme; title deed/SG diagram | Yes / No / N/A + Score 0–5 + Rating
03.056 | 03 | WP03 | Preliminary Site Screening | Is the decision record for servitudes - implementation readiness aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | Deeds Registries Act 47 of 1937; Surveyor-General records; servitude register | Yes / No / N/A + Score 0–5 + Rating
03.057 | 03 | WP03 | Preliminary Site Screening | Have cost, programme and compliance implications of basic zoning position - implementation readiness been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | Municipal Planning By-law; wayleave requirements; landowner consent | Yes / No / N/A + Score 0–5 + Rating
03.058 | 03 | WP03 | Preliminary Site Screening | Has the team obtained written confirmation or documented proof for environmental sensitivity - implementation readiness? | Current certificate/letter/report, version control and document-control entry. | SPLUMA Act 16 of 2013; municipal land use scheme; title deed/SG diagram | Yes / No / N/A + Score 0–5 + Rating
03.059 | 03 | WP03 | Preliminary Site Screening | Does the evidence for access constraints - implementation readiness support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | Deeds Registries Act 47 of 1937; Surveyor-General records; servitude register | Yes / No / N/A + Score 0–5 + Rating
03.060 | 03 | WP03 | Preliminary Site Screening | Have dependencies linked to bulk services proximity - implementation readiness been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | Municipal Planning By-law; wayleave requirements; landowner consent | Yes / No / N/A + Score 0–5 + Rating
03.061 | 03 | WP03 | Preliminary Site Screening | Has the project team confirmed ownership confirmation - governance approval in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | SPLUMA Act 16 of 2013; municipal land use scheme; title deed/SG diagram | Yes / No / N/A + Score 0–5 + Rating
03.062 | 03 | WP03 | Preliminary Site Screening | Is there a responsible owner, due date and approval route for servitudes - governance approval? | Register entry, supporting drawing/report, approval note and updated risk item. | Deeds Registries Act 47 of 1937; Surveyor-General records; servitude register | Yes / No / N/A + Score 0–5 + Rating
03.063 | 03 | WP03 | Preliminary Site Screening | Has the gate file tested whether basic zoning position - governance approval creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | Municipal Planning By-law; wayleave requirements; landowner consent | Yes / No / N/A + Score 0–5 + Rating
03.064 | 03 | WP03 | Preliminary Site Screening | Are assumptions for environmental sensitivity - governance approval documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | SPLUMA Act 16 of 2013; municipal land use scheme; title deed/SG diagram | Yes / No / N/A + Score 0–5 + Rating
03.065 | 03 | WP03 | Preliminary Site Screening | Has the relevant authority, specialist or professional adviser reviewed access constraints - governance approval where required? | Authority response, compliance checklist, file note and management approval. | Deeds Registries Act 47 of 1937; Surveyor-General records; servitude register | Yes / No / N/A + Score 0–5 + Rating
03.066 | 03 | WP03 | Preliminary Site Screening | Is the decision record for bulk services proximity - governance approval aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | Municipal Planning By-law; wayleave requirements; landowner consent | Yes / No / N/A + Score 0–5 + Rating
03.067 | 03 | WP03 | Preliminary Site Screening | Have cost, programme and compliance implications of ownership confirmation - legal authority been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | SPLUMA Act 16 of 2013; municipal land use scheme; title deed/SG diagram | Yes / No / N/A + Score 0–5 + Rating
03.068 | 03 | WP03 | Preliminary Site Screening | Has the team obtained written confirmation or documented proof for servitudes - legal authority? | Current certificate/letter/report, version control and document-control entry. | Deeds Registries Act 47 of 1937; Surveyor-General records; servitude register | Yes / No / N/A + Score 0–5 + Rating
03.069 | 03 | WP03 | Preliminary Site Screening | Does the evidence for basic zoning position - legal authority support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | Municipal Planning By-law; wayleave requirements; landowner consent | Yes / No / N/A + Score 0–5 + Rating
03.070 | 03 | WP03 | Preliminary Site Screening | Have dependencies linked to environmental sensitivity - legal authority been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | SPLUMA Act 16 of 2013; municipal land use scheme; title deed/SG diagram | Yes / No / N/A + Score 0–5 + Rating
03.071 | 03 | WP03 | Preliminary Site Screening | Has the project team confirmed access constraints - legal authority in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | Deeds Registries Act 47 of 1937; Surveyor-General records; servitude register | Yes / No / N/A + Score 0–5 + Rating
03.072 | 03 | WP03 | Preliminary Site Screening | Is there a responsible owner, due date and approval route for bulk services proximity - legal authority? | Register entry, supporting drawing/report, approval note and updated risk item. | Municipal Planning By-law; wayleave requirements; landowner consent | Yes / No / N/A + Score 0–5 + Rating
03.073 | 03 | WP03 | Preliminary Site Screening | Has the gate file tested whether ownership confirmation - technical feasibility creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | SPLUMA Act 16 of 2013; municipal land use scheme; title deed/SG diagram | Yes / No / N/A + Score 0–5 + Rating
03.074 | 03 | WP03 | Preliminary Site Screening | Are assumptions for servitudes - technical feasibility documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | Deeds Registries Act 47 of 1937; Surveyor-General records; servitude register | Yes / No / N/A + Score 0–5 + Rating
03.075 | 03 | WP03 | Preliminary Site Screening | Has the relevant authority, specialist or professional adviser reviewed basic zoning position - technical feasibility where required? | Authority response, compliance checklist, file note and management approval. | Municipal Planning By-law; wayleave requirements; landowner consent | Yes / No / N/A + Score 0–5 + Rating
03.076 | 03 | WP03 | Preliminary Site Screening | Is the decision record for environmental sensitivity - technical feasibility aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | SPLUMA Act 16 of 2013; municipal land use scheme; title deed/SG diagram | Yes / No / N/A + Score 0–5 + Rating
03.077 | 03 | WP03 | Preliminary Site Screening | Have cost, programme and compliance implications of access constraints - technical feasibility been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | Deeds Registries Act 47 of 1937; Surveyor-General records; servitude register | Yes / No / N/A + Score 0–5 + Rating
03.078 | 03 | WP03 | Preliminary Site Screening | Has the team obtained written confirmation or documented proof for bulk services proximity - technical feasibility? | Current certificate/letter/report, version control and document-control entry. | Municipal Planning By-law; wayleave requirements; landowner consent | Yes / No / N/A + Score 0–5 + Rating
03.079 | 03 | WP03 | Preliminary Site Screening | Does the evidence for ownership confirmation - financial viability support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | SPLUMA Act 16 of 2013; municipal land use scheme; title deed/SG diagram | Yes / No / N/A + Score 0–5 + Rating
03.080 | 03 | WP03 | Preliminary Site Screening | Have dependencies linked to servitudes - financial viability been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | Deeds Registries Act 47 of 1937; Surveyor-General records; servitude register | Yes / No / N/A + Score 0–5 + Rating
03.081 | 03 | WP03 | Preliminary Site Screening | Has the project team confirmed basic zoning position - financial viability in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | Municipal Planning By-law; wayleave requirements; landowner consent | Yes / No / N/A + Score 0–5 + Rating
03.082 | 03 | WP03 | Preliminary Site Screening | Is there a responsible owner, due date and approval route for environmental sensitivity - financial viability? | Register entry, supporting drawing/report, approval note and updated risk item. | SPLUMA Act 16 of 2013; municipal land use scheme; title deed/SG diagram | Yes / No / N/A + Score 0–5 + Rating
03.083 | 03 | WP03 | Preliminary Site Screening | Has the gate file tested whether access constraints - financial viability creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | Deeds Registries Act 47 of 1937; Surveyor-General records; servitude register | Yes / No / N/A + Score 0–5 + Rating
03.084 | 03 | WP03 | Preliminary Site Screening | Are assumptions for bulk services proximity - financial viability documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | Municipal Planning By-law; wayleave requirements; landowner consent | Yes / No / N/A + Score 0–5 + Rating
03.085 | 03 | WP03 | Preliminary Site Screening | Has the relevant authority, specialist or professional adviser reviewed ownership confirmation - programme impact where required? | Authority response, compliance checklist, file note and management approval. | SPLUMA Act 16 of 2013; municipal land use scheme; title deed/SG diagram | Yes / No / N/A + Score 0–5 + Rating
03.086 | 03 | WP03 | Preliminary Site Screening | Is the decision record for servitudes - programme impact aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | Deeds Registries Act 47 of 1937; Surveyor-General records; servitude register | Yes / No / N/A + Score 0–5 + Rating
03.087 | 03 | WP03 | Preliminary Site Screening | Have cost, programme and compliance implications of basic zoning position - programme impact been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | Municipal Planning By-law; wayleave requirements; landowner consent | Yes / No / N/A + Score 0–5 + Rating
03.088 | 03 | WP03 | Preliminary Site Screening | Has the team obtained written confirmation or documented proof for environmental sensitivity - programme impact? | Current certificate/letter/report, version control and document-control entry. | SPLUMA Act 16 of 2013; municipal land use scheme; title deed/SG diagram | Yes / No / N/A + Score 0–5 + Rating
03.089 | 03 | WP03 | Preliminary Site Screening | Does the evidence for access constraints - programme impact support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | Deeds Registries Act 47 of 1937; Surveyor-General records; servitude register | Yes / No / N/A + Score 0–5 + Rating
03.090 | 03 | WP03 | Preliminary Site Screening | Have dependencies linked to bulk services proximity - programme impact been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | Municipal Planning By-law; wayleave requirements; landowner consent | Yes / No / N/A + Score 0–5 + Rating
03.091 | 03 | WP03 | Preliminary Site Screening | Has the project team confirmed ownership confirmation - risk mitigation in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | SPLUMA Act 16 of 2013; municipal land use scheme; title deed/SG diagram | Yes / No / N/A + Score 0–5 + Rating
03.092 | 03 | WP03 | Preliminary Site Screening | Is there a responsible owner, due date and approval route for servitudes - risk mitigation? | Register entry, supporting drawing/report, approval note and updated risk item. | Deeds Registries Act 47 of 1937; Surveyor-General records; servitude register | Yes / No / N/A + Score 0–5 + Rating
03.093 | 03 | WP03 | Preliminary Site Screening | Has the gate file tested whether basic zoning position - risk mitigation creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | Municipal Planning By-law; wayleave requirements; landowner consent | Yes / No / N/A + Score 0–5 + Rating
03.094 | 03 | WP03 | Preliminary Site Screening | Are assumptions for environmental sensitivity - risk mitigation documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | SPLUMA Act 16 of 2013; municipal land use scheme; title deed/SG diagram | Yes / No / N/A + Score 0–5 + Rating
03.095 | 03 | WP03 | Preliminary Site Screening | Has the relevant authority, specialist or professional adviser reviewed access constraints - risk mitigation where required? | Authority response, compliance checklist, file note and management approval. | Deeds Registries Act 47 of 1937; Surveyor-General records; servitude register | Yes / No / N/A + Score 0–5 + Rating
03.096 | 03 | WP03 | Preliminary Site Screening | Is the decision record for bulk services proximity - risk mitigation aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | Municipal Planning By-law; wayleave requirements; landowner consent | Yes / No / N/A + Score 0–5 + Rating
03.097 | 03 | WP03 | Preliminary Site Screening | Have cost, programme and compliance implications of ownership confirmation - stakeholder acceptance been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | SPLUMA Act 16 of 2013; municipal land use scheme; title deed/SG diagram | Yes / No / N/A + Score 0–5 + Rating
03.098 | 03 | WP03 | Preliminary Site Screening | Has the team obtained written confirmation or documented proof for servitudes - stakeholder acceptance? | Current certificate/letter/report, version control and document-control entry. | Deeds Registries Act 47 of 1937; Surveyor-General records; servitude register | Yes / No / N/A + Score 0–5 + Rating
03.099 | 03 | WP03 | Preliminary Site Screening | Does the evidence for basic zoning position - stakeholder acceptance support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | Municipal Planning By-law; wayleave requirements; landowner consent | Yes / No / N/A + Score 0–5 + Rating
03.100 | 03 | WP03 | Preliminary Site Screening | Have dependencies linked to environmental sensitivity - stakeholder acceptance been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | SPLUMA Act 16 of 2013; municipal land use scheme; title deed/SG diagram | Yes / No / N/A + Score 0–5 + Rating
04.001 | 04 | WP04 | Sponsor and Entity Readiness | Has the project team confirmed client capacity - governance approval in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | King IV governance practice; Companies Act 71 of 2008; project mandate file | Yes / No / N/A + Score 0–5 + Rating
04.002 | 04 | WP04 | Sponsor and Entity Readiness | Is there a responsible owner, due date and approval route for corporate documentation - governance approval? | Register entry, supporting drawing/report, approval note and updated risk item. | PMBOK stage-gate governance; board resolution; delegated authority matrix | Yes / No / N/A + Score 0–5 + Rating
04.003 | 04 | WP04 | Sponsor and Entity Readiness | Has the gate file tested whether tax status - governance approval creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | ISO 31000 risk management; stakeholder decision register; project charter | Yes / No / N/A + Score 0–5 + Rating
04.004 | 04 | WP04 | Sponsor and Entity Readiness | Are assumptions for decision-making mandate - governance approval documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | King IV governance practice; Companies Act 71 of 2008; project mandate file | Yes / No / N/A + Score 0–5 + Rating
04.005 | 04 | WP04 | Sponsor and Entity Readiness | Has the relevant authority, specialist or professional adviser reviewed funding preparedness - governance approval where required? | Authority response, compliance checklist, file note and management approval. | PMBOK stage-gate governance; board resolution; delegated authority matrix | Yes / No / N/A + Score 0–5 + Rating
04.006 | 04 | WP04 | Sponsor and Entity Readiness | Is the decision record for legal authority - governance approval aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | ISO 31000 risk management; stakeholder decision register; project charter | Yes / No / N/A + Score 0–5 + Rating
04.007 | 04 | WP04 | Sponsor and Entity Readiness | Have cost, programme and compliance implications of client capacity - legal authority been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | King IV governance practice; Companies Act 71 of 2008; project mandate file | Yes / No / N/A + Score 0–5 + Rating
04.008 | 04 | WP04 | Sponsor and Entity Readiness | Has the team obtained written confirmation or documented proof for corporate documentation - legal authority? | Current certificate/letter/report, version control and document-control entry. | PMBOK stage-gate governance; board resolution; delegated authority matrix | Yes / No / N/A + Score 0–5 + Rating
04.009 | 04 | WP04 | Sponsor and Entity Readiness | Does the evidence for tax status - legal authority support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | ISO 31000 risk management; stakeholder decision register; project charter | Yes / No / N/A + Score 0–5 + Rating
04.010 | 04 | WP04 | Sponsor and Entity Readiness | Have dependencies linked to decision-making mandate - legal authority been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | King IV governance practice; Companies Act 71 of 2008; project mandate file | Yes / No / N/A + Score 0–5 + Rating
04.011 | 04 | WP04 | Sponsor and Entity Readiness | Has the project team confirmed funding preparedness - legal authority in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | PMBOK stage-gate governance; board resolution; delegated authority matrix | Yes / No / N/A + Score 0–5 + Rating
04.012 | 04 | WP04 | Sponsor and Entity Readiness | Is there a responsible owner, due date and approval route for legal authority - legal authority? | Register entry, supporting drawing/report, approval note and updated risk item. | ISO 31000 risk management; stakeholder decision register; project charter | Yes / No / N/A + Score 0–5 + Rating
04.013 | 04 | WP04 | Sponsor and Entity Readiness | Has the gate file tested whether client capacity - technical feasibility creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | King IV governance practice; Companies Act 71 of 2008; project mandate file | Yes / No / N/A + Score 0–5 + Rating
04.014 | 04 | WP04 | Sponsor and Entity Readiness | Are assumptions for corporate documentation - technical feasibility documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | PMBOK stage-gate governance; board resolution; delegated authority matrix | Yes / No / N/A + Score 0–5 + Rating
04.015 | 04 | WP04 | Sponsor and Entity Readiness | Has the relevant authority, specialist or professional adviser reviewed tax status - technical feasibility where required? | Authority response, compliance checklist, file note and management approval. | ISO 31000 risk management; stakeholder decision register; project charter | Yes / No / N/A + Score 0–5 + Rating
04.016 | 04 | WP04 | Sponsor and Entity Readiness | Is the decision record for decision-making mandate - technical feasibility aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | King IV governance practice; Companies Act 71 of 2008; project mandate file | Yes / No / N/A + Score 0–5 + Rating
04.017 | 04 | WP04 | Sponsor and Entity Readiness | Have cost, programme and compliance implications of funding preparedness - technical feasibility been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | PMBOK stage-gate governance; board resolution; delegated authority matrix | Yes / No / N/A + Score 0–5 + Rating
04.018 | 04 | WP04 | Sponsor and Entity Readiness | Has the team obtained written confirmation or documented proof for legal authority - technical feasibility? | Current certificate/letter/report, version control and document-control entry. | ISO 31000 risk management; stakeholder decision register; project charter | Yes / No / N/A + Score 0–5 + Rating
04.019 | 04 | WP04 | Sponsor and Entity Readiness | Does the evidence for client capacity - financial viability support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | King IV governance practice; Companies Act 71 of 2008; project mandate file | Yes / No / N/A + Score 0–5 + Rating
04.020 | 04 | WP04 | Sponsor and Entity Readiness | Have dependencies linked to corporate documentation - financial viability been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | PMBOK stage-gate governance; board resolution; delegated authority matrix | Yes / No / N/A + Score 0–5 + Rating
04.021 | 04 | WP04 | Sponsor and Entity Readiness | Has the project team confirmed tax status - financial viability in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | ISO 31000 risk management; stakeholder decision register; project charter | Yes / No / N/A + Score 0–5 + Rating
04.022 | 04 | WP04 | Sponsor and Entity Readiness | Is there a responsible owner, due date and approval route for decision-making mandate - financial viability? | Register entry, supporting drawing/report, approval note and updated risk item. | King IV governance practice; Companies Act 71 of 2008; project mandate file | Yes / No / N/A + Score 0–5 + Rating
04.023 | 04 | WP04 | Sponsor and Entity Readiness | Has the gate file tested whether funding preparedness - financial viability creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | PMBOK stage-gate governance; board resolution; delegated authority matrix | Yes / No / N/A + Score 0–5 + Rating
04.024 | 04 | WP04 | Sponsor and Entity Readiness | Are assumptions for legal authority - financial viability documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | ISO 31000 risk management; stakeholder decision register; project charter | Yes / No / N/A + Score 0–5 + Rating
04.025 | 04 | WP04 | Sponsor and Entity Readiness | Has the relevant authority, specialist or professional adviser reviewed client capacity - programme impact where required? | Authority response, compliance checklist, file note and management approval. | King IV governance practice; Companies Act 71 of 2008; project mandate file | Yes / No / N/A + Score 0–5 + Rating
04.026 | 04 | WP04 | Sponsor and Entity Readiness | Is the decision record for corporate documentation - programme impact aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | PMBOK stage-gate governance; board resolution; delegated authority matrix | Yes / No / N/A + Score 0–5 + Rating
04.027 | 04 | WP04 | Sponsor and Entity Readiness | Have cost, programme and compliance implications of tax status - programme impact been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | ISO 31000 risk management; stakeholder decision register; project charter | Yes / No / N/A + Score 0–5 + Rating
04.028 | 04 | WP04 | Sponsor and Entity Readiness | Has the team obtained written confirmation or documented proof for decision-making mandate - programme impact? | Current certificate/letter/report, version control and document-control entry. | King IV governance practice; Companies Act 71 of 2008; project mandate file | Yes / No / N/A + Score 0–5 + Rating
04.029 | 04 | WP04 | Sponsor and Entity Readiness | Does the evidence for funding preparedness - programme impact support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | PMBOK stage-gate governance; board resolution; delegated authority matrix | Yes / No / N/A + Score 0–5 + Rating
04.030 | 04 | WP04 | Sponsor and Entity Readiness | Have dependencies linked to legal authority - programme impact been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | ISO 31000 risk management; stakeholder decision register; project charter | Yes / No / N/A + Score 0–5 + Rating
04.031 | 04 | WP04 | Sponsor and Entity Readiness | Has the project team confirmed client capacity - risk mitigation in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | King IV governance practice; Companies Act 71 of 2008; project mandate file | Yes / No / N/A + Score 0–5 + Rating
04.032 | 04 | WP04 | Sponsor and Entity Readiness | Is there a responsible owner, due date and approval route for corporate documentation - risk mitigation? | Register entry, supporting drawing/report, approval note and updated risk item. | PMBOK stage-gate governance; board resolution; delegated authority matrix | Yes / No / N/A + Score 0–5 + Rating
04.033 | 04 | WP04 | Sponsor and Entity Readiness | Has the gate file tested whether tax status - risk mitigation creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | ISO 31000 risk management; stakeholder decision register; project charter | Yes / No / N/A + Score 0–5 + Rating
04.034 | 04 | WP04 | Sponsor and Entity Readiness | Are assumptions for decision-making mandate - risk mitigation documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | King IV governance practice; Companies Act 71 of 2008; project mandate file | Yes / No / N/A + Score 0–5 + Rating
04.035 | 04 | WP04 | Sponsor and Entity Readiness | Has the relevant authority, specialist or professional adviser reviewed funding preparedness - risk mitigation where required? | Authority response, compliance checklist, file note and management approval. | PMBOK stage-gate governance; board resolution; delegated authority matrix | Yes / No / N/A + Score 0–5 + Rating
04.036 | 04 | WP04 | Sponsor and Entity Readiness | Is the decision record for legal authority - risk mitigation aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | ISO 31000 risk management; stakeholder decision register; project charter | Yes / No / N/A + Score 0–5 + Rating
04.037 | 04 | WP04 | Sponsor and Entity Readiness | Have cost, programme and compliance implications of client capacity - stakeholder acceptance been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | King IV governance practice; Companies Act 71 of 2008; project mandate file | Yes / No / N/A + Score 0–5 + Rating
04.038 | 04 | WP04 | Sponsor and Entity Readiness | Has the team obtained written confirmation or documented proof for corporate documentation - stakeholder acceptance? | Current certificate/letter/report, version control and document-control entry. | PMBOK stage-gate governance; board resolution; delegated authority matrix | Yes / No / N/A + Score 0–5 + Rating
04.039 | 04 | WP04 | Sponsor and Entity Readiness | Does the evidence for tax status - stakeholder acceptance support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | ISO 31000 risk management; stakeholder decision register; project charter | Yes / No / N/A + Score 0–5 + Rating
04.040 | 04 | WP04 | Sponsor and Entity Readiness | Have dependencies linked to decision-making mandate - stakeholder acceptance been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | King IV governance practice; Companies Act 71 of 2008; project mandate file | Yes / No / N/A + Score 0–5 + Rating
04.041 | 04 | WP04 | Sponsor and Entity Readiness | Has the project team confirmed funding preparedness - stakeholder acceptance in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | PMBOK stage-gate governance; board resolution; delegated authority matrix | Yes / No / N/A + Score 0–5 + Rating
04.042 | 04 | WP04 | Sponsor and Entity Readiness | Is there a responsible owner, due date and approval route for legal authority - stakeholder acceptance? | Register entry, supporting drawing/report, approval note and updated risk item. | ISO 31000 risk management; stakeholder decision register; project charter | Yes / No / N/A + Score 0–5 + Rating
04.043 | 04 | WP04 | Sponsor and Entity Readiness | Has the gate file tested whether client capacity - document control creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | King IV governance practice; Companies Act 71 of 2008; project mandate file | Yes / No / N/A + Score 0–5 + Rating
04.044 | 04 | WP04 | Sponsor and Entity Readiness | Are assumptions for corporate documentation - document control documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | PMBOK stage-gate governance; board resolution; delegated authority matrix | Yes / No / N/A + Score 0–5 + Rating
04.045 | 04 | WP04 | Sponsor and Entity Readiness | Has the relevant authority, specialist or professional adviser reviewed tax status - document control where required? | Authority response, compliance checklist, file note and management approval. | ISO 31000 risk management; stakeholder decision register; project charter | Yes / No / N/A + Score 0–5 + Rating
04.046 | 04 | WP04 | Sponsor and Entity Readiness | Is the decision record for decision-making mandate - document control aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | King IV governance practice; Companies Act 71 of 2008; project mandate file | Yes / No / N/A + Score 0–5 + Rating
04.047 | 04 | WP04 | Sponsor and Entity Readiness | Have cost, programme and compliance implications of funding preparedness - document control been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | PMBOK stage-gate governance; board resolution; delegated authority matrix | Yes / No / N/A + Score 0–5 + Rating
04.048 | 04 | WP04 | Sponsor and Entity Readiness | Has the team obtained written confirmation or documented proof for legal authority - document control? | Current certificate/letter/report, version control and document-control entry. | ISO 31000 risk management; stakeholder decision register; project charter | Yes / No / N/A + Score 0–5 + Rating
04.049 | 04 | WP04 | Sponsor and Entity Readiness | Does the evidence for client capacity - professional certification support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | King IV governance practice; Companies Act 71 of 2008; project mandate file | Yes / No / N/A + Score 0–5 + Rating
04.050 | 04 | WP04 | Sponsor and Entity Readiness | Have dependencies linked to corporate documentation - professional certification been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | PMBOK stage-gate governance; board resolution; delegated authority matrix | Yes / No / N/A + Score 0–5 + Rating
04.051 | 04 | WP04 | Sponsor and Entity Readiness | Has the project team confirmed tax status - professional certification in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | ISO 31000 risk management; stakeholder decision register; project charter | Yes / No / N/A + Score 0–5 + Rating
04.052 | 04 | WP04 | Sponsor and Entity Readiness | Is there a responsible owner, due date and approval route for decision-making mandate - professional certification? | Register entry, supporting drawing/report, approval note and updated risk item. | King IV governance practice; Companies Act 71 of 2008; project mandate file | Yes / No / N/A + Score 0–5 + Rating
04.053 | 04 | WP04 | Sponsor and Entity Readiness | Has the gate file tested whether funding preparedness - professional certification creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | PMBOK stage-gate governance; board resolution; delegated authority matrix | Yes / No / N/A + Score 0–5 + Rating
04.054 | 04 | WP04 | Sponsor and Entity Readiness | Are assumptions for legal authority - professional certification documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | ISO 31000 risk management; stakeholder decision register; project charter | Yes / No / N/A + Score 0–5 + Rating
04.055 | 04 | WP04 | Sponsor and Entity Readiness | Has the relevant authority, specialist or professional adviser reviewed client capacity - implementation readiness where required? | Authority response, compliance checklist, file note and management approval. | King IV governance practice; Companies Act 71 of 2008; project mandate file | Yes / No / N/A + Score 0–5 + Rating
04.056 | 04 | WP04 | Sponsor and Entity Readiness | Is the decision record for corporate documentation - implementation readiness aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | PMBOK stage-gate governance; board resolution; delegated authority matrix | Yes / No / N/A + Score 0–5 + Rating
04.057 | 04 | WP04 | Sponsor and Entity Readiness | Have cost, programme and compliance implications of tax status - implementation readiness been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | ISO 31000 risk management; stakeholder decision register; project charter | Yes / No / N/A + Score 0–5 + Rating
04.058 | 04 | WP04 | Sponsor and Entity Readiness | Has the team obtained written confirmation or documented proof for decision-making mandate - implementation readiness? | Current certificate/letter/report, version control and document-control entry. | King IV governance practice; Companies Act 71 of 2008; project mandate file | Yes / No / N/A + Score 0–5 + Rating
04.059 | 04 | WP04 | Sponsor and Entity Readiness | Does the evidence for funding preparedness - implementation readiness support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | PMBOK stage-gate governance; board resolution; delegated authority matrix | Yes / No / N/A + Score 0–5 + Rating
04.060 | 04 | WP04 | Sponsor and Entity Readiness | Have dependencies linked to legal authority - implementation readiness been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | ISO 31000 risk management; stakeholder decision register; project charter | Yes / No / N/A + Score 0–5 + Rating
04.061 | 04 | WP04 | Sponsor and Entity Readiness | Has the project team confirmed client capacity - governance approval in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | King IV governance practice; Companies Act 71 of 2008; project mandate file | Yes / No / N/A + Score 0–5 + Rating
04.062 | 04 | WP04 | Sponsor and Entity Readiness | Is there a responsible owner, due date and approval route for corporate documentation - governance approval? | Register entry, supporting drawing/report, approval note and updated risk item. | PMBOK stage-gate governance; board resolution; delegated authority matrix | Yes / No / N/A + Score 0–5 + Rating
04.063 | 04 | WP04 | Sponsor and Entity Readiness | Has the gate file tested whether tax status - governance approval creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | ISO 31000 risk management; stakeholder decision register; project charter | Yes / No / N/A + Score 0–5 + Rating
04.064 | 04 | WP04 | Sponsor and Entity Readiness | Are assumptions for decision-making mandate - governance approval documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | King IV governance practice; Companies Act 71 of 2008; project mandate file | Yes / No / N/A + Score 0–5 + Rating
04.065 | 04 | WP04 | Sponsor and Entity Readiness | Has the relevant authority, specialist or professional adviser reviewed funding preparedness - governance approval where required? | Authority response, compliance checklist, file note and management approval. | PMBOK stage-gate governance; board resolution; delegated authority matrix | Yes / No / N/A + Score 0–5 + Rating
04.066 | 04 | WP04 | Sponsor and Entity Readiness | Is the decision record for legal authority - governance approval aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | ISO 31000 risk management; stakeholder decision register; project charter | Yes / No / N/A + Score 0–5 + Rating
04.067 | 04 | WP04 | Sponsor and Entity Readiness | Have cost, programme and compliance implications of client capacity - legal authority been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | King IV governance practice; Companies Act 71 of 2008; project mandate file | Yes / No / N/A + Score 0–5 + Rating
04.068 | 04 | WP04 | Sponsor and Entity Readiness | Has the team obtained written confirmation or documented proof for corporate documentation - legal authority? | Current certificate/letter/report, version control and document-control entry. | PMBOK stage-gate governance; board resolution; delegated authority matrix | Yes / No / N/A + Score 0–5 + Rating
04.069 | 04 | WP04 | Sponsor and Entity Readiness | Does the evidence for tax status - legal authority support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | ISO 31000 risk management; stakeholder decision register; project charter | Yes / No / N/A + Score 0–5 + Rating
04.070 | 04 | WP04 | Sponsor and Entity Readiness | Have dependencies linked to decision-making mandate - legal authority been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | King IV governance practice; Companies Act 71 of 2008; project mandate file | Yes / No / N/A + Score 0–5 + Rating
04.071 | 04 | WP04 | Sponsor and Entity Readiness | Has the project team confirmed funding preparedness - legal authority in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | PMBOK stage-gate governance; board resolution; delegated authority matrix | Yes / No / N/A + Score 0–5 + Rating
04.072 | 04 | WP04 | Sponsor and Entity Readiness | Is there a responsible owner, due date and approval route for legal authority - legal authority? | Register entry, supporting drawing/report, approval note and updated risk item. | ISO 31000 risk management; stakeholder decision register; project charter | Yes / No / N/A + Score 0–5 + Rating
04.073 | 04 | WP04 | Sponsor and Entity Readiness | Has the gate file tested whether client capacity - technical feasibility creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | King IV governance practice; Companies Act 71 of 2008; project mandate file | Yes / No / N/A + Score 0–5 + Rating
04.074 | 04 | WP04 | Sponsor and Entity Readiness | Are assumptions for corporate documentation - technical feasibility documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | PMBOK stage-gate governance; board resolution; delegated authority matrix | Yes / No / N/A + Score 0–5 + Rating
04.075 | 04 | WP04 | Sponsor and Entity Readiness | Has the relevant authority, specialist or professional adviser reviewed tax status - technical feasibility where required? | Authority response, compliance checklist, file note and management approval. | ISO 31000 risk management; stakeholder decision register; project charter | Yes / No / N/A + Score 0–5 + Rating
04.076 | 04 | WP04 | Sponsor and Entity Readiness | Is the decision record for decision-making mandate - technical feasibility aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | King IV governance practice; Companies Act 71 of 2008; project mandate file | Yes / No / N/A + Score 0–5 + Rating
04.077 | 04 | WP04 | Sponsor and Entity Readiness | Have cost, programme and compliance implications of funding preparedness - technical feasibility been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | PMBOK stage-gate governance; board resolution; delegated authority matrix | Yes / No / N/A + Score 0–5 + Rating
04.078 | 04 | WP04 | Sponsor and Entity Readiness | Has the team obtained written confirmation or documented proof for legal authority - technical feasibility? | Current certificate/letter/report, version control and document-control entry. | ISO 31000 risk management; stakeholder decision register; project charter | Yes / No / N/A + Score 0–5 + Rating
04.079 | 04 | WP04 | Sponsor and Entity Readiness | Does the evidence for client capacity - financial viability support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | King IV governance practice; Companies Act 71 of 2008; project mandate file | Yes / No / N/A + Score 0–5 + Rating
04.080 | 04 | WP04 | Sponsor and Entity Readiness | Have dependencies linked to corporate documentation - financial viability been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | PMBOK stage-gate governance; board resolution; delegated authority matrix | Yes / No / N/A + Score 0–5 + Rating
04.081 | 04 | WP04 | Sponsor and Entity Readiness | Has the project team confirmed tax status - financial viability in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | ISO 31000 risk management; stakeholder decision register; project charter | Yes / No / N/A + Score 0–5 + Rating
04.082 | 04 | WP04 | Sponsor and Entity Readiness | Is there a responsible owner, due date and approval route for decision-making mandate - financial viability? | Register entry, supporting drawing/report, approval note and updated risk item. | King IV governance practice; Companies Act 71 of 2008; project mandate file | Yes / No / N/A + Score 0–5 + Rating
04.083 | 04 | WP04 | Sponsor and Entity Readiness | Has the gate file tested whether funding preparedness - financial viability creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | PMBOK stage-gate governance; board resolution; delegated authority matrix | Yes / No / N/A + Score 0–5 + Rating
04.084 | 04 | WP04 | Sponsor and Entity Readiness | Are assumptions for legal authority - financial viability documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | ISO 31000 risk management; stakeholder decision register; project charter | Yes / No / N/A + Score 0–5 + Rating
04.085 | 04 | WP04 | Sponsor and Entity Readiness | Has the relevant authority, specialist or professional adviser reviewed client capacity - programme impact where required? | Authority response, compliance checklist, file note and management approval. | King IV governance practice; Companies Act 71 of 2008; project mandate file | Yes / No / N/A + Score 0–5 + Rating
04.086 | 04 | WP04 | Sponsor and Entity Readiness | Is the decision record for corporate documentation - programme impact aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | PMBOK stage-gate governance; board resolution; delegated authority matrix | Yes / No / N/A + Score 0–5 + Rating
04.087 | 04 | WP04 | Sponsor and Entity Readiness | Have cost, programme and compliance implications of tax status - programme impact been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | ISO 31000 risk management; stakeholder decision register; project charter | Yes / No / N/A + Score 0–5 + Rating
04.088 | 04 | WP04 | Sponsor and Entity Readiness | Has the team obtained written confirmation or documented proof for decision-making mandate - programme impact? | Current certificate/letter/report, version control and document-control entry. | King IV governance practice; Companies Act 71 of 2008; project mandate file | Yes / No / N/A + Score 0–5 + Rating
04.089 | 04 | WP04 | Sponsor and Entity Readiness | Does the evidence for funding preparedness - programme impact support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | PMBOK stage-gate governance; board resolution; delegated authority matrix | Yes / No / N/A + Score 0–5 + Rating
04.090 | 04 | WP04 | Sponsor and Entity Readiness | Have dependencies linked to legal authority - programme impact been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | ISO 31000 risk management; stakeholder decision register; project charter | Yes / No / N/A + Score 0–5 + Rating
04.091 | 04 | WP04 | Sponsor and Entity Readiness | Has the project team confirmed client capacity - risk mitigation in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | King IV governance practice; Companies Act 71 of 2008; project mandate file | Yes / No / N/A + Score 0–5 + Rating
04.092 | 04 | WP04 | Sponsor and Entity Readiness | Is there a responsible owner, due date and approval route for corporate documentation - risk mitigation? | Register entry, supporting drawing/report, approval note and updated risk item. | PMBOK stage-gate governance; board resolution; delegated authority matrix | Yes / No / N/A + Score 0–5 + Rating
04.093 | 04 | WP04 | Sponsor and Entity Readiness | Has the gate file tested whether tax status - risk mitigation creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | ISO 31000 risk management; stakeholder decision register; project charter | Yes / No / N/A + Score 0–5 + Rating
04.094 | 04 | WP04 | Sponsor and Entity Readiness | Are assumptions for decision-making mandate - risk mitigation documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | King IV governance practice; Companies Act 71 of 2008; project mandate file | Yes / No / N/A + Score 0–5 + Rating
04.095 | 04 | WP04 | Sponsor and Entity Readiness | Has the relevant authority, specialist or professional adviser reviewed funding preparedness - risk mitigation where required? | Authority response, compliance checklist, file note and management approval. | PMBOK stage-gate governance; board resolution; delegated authority matrix | Yes / No / N/A + Score 0–5 + Rating
04.096 | 04 | WP04 | Sponsor and Entity Readiness | Is the decision record for legal authority - risk mitigation aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | ISO 31000 risk management; stakeholder decision register; project charter | Yes / No / N/A + Score 0–5 + Rating
04.097 | 04 | WP04 | Sponsor and Entity Readiness | Have cost, programme and compliance implications of client capacity - stakeholder acceptance been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | King IV governance practice; Companies Act 71 of 2008; project mandate file | Yes / No / N/A + Score 0–5 + Rating
04.098 | 04 | WP04 | Sponsor and Entity Readiness | Has the team obtained written confirmation or documented proof for corporate documentation - stakeholder acceptance? | Current certificate/letter/report, version control and document-control entry. | PMBOK stage-gate governance; board resolution; delegated authority matrix | Yes / No / N/A + Score 0–5 + Rating
04.099 | 04 | WP04 | Sponsor and Entity Readiness | Does the evidence for tax status - stakeholder acceptance support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | ISO 31000 risk management; stakeholder decision register; project charter | Yes / No / N/A + Score 0–5 + Rating
04.100 | 04 | WP04 | Sponsor and Entity Readiness | Have dependencies linked to decision-making mandate - stakeholder acceptance been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | King IV governance practice; Companies Act 71 of 2008; project mandate file | Yes / No / N/A + Score 0–5 + Rating
05.001 | 05 | WP05 | Land Security and Site Control | Has the project team confirmed title deed - governance approval in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | SPLUMA Act 16 of 2013; municipal land use scheme; title deed/SG diagram | Yes / No / N/A + Score 0–5 + Rating
05.002 | 05 | WP05 | Land Security and Site Control | Is there a responsible owner, due date and approval route for landowner consent - governance approval? | Register entry, supporting drawing/report, approval note and updated risk item. | Deeds Registries Act 47 of 1937; Surveyor-General records; servitude register | Yes / No / N/A + Score 0–5 + Rating
05.003 | 05 | WP05 | Land Security and Site Control | Has the gate file tested whether lease or purchase rights - governance approval creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | Municipal Planning By-law; wayleave requirements; landowner consent | Yes / No / N/A + Score 0–5 + Rating
05.004 | 05 | WP05 | Land Security and Site Control | Are assumptions for site boundaries - governance approval documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | SPLUMA Act 16 of 2013; municipal land use scheme; title deed/SG diagram | Yes / No / N/A + Score 0–5 + Rating
05.005 | 05 | WP05 | Land Security and Site Control | Has the relevant authority, specialist or professional adviser reviewed SG diagram - governance approval where required? | Authority response, compliance checklist, file note and management approval. | Deeds Registries Act 47 of 1937; Surveyor-General records; servitude register | Yes / No / N/A + Score 0–5 + Rating
05.006 | 05 | WP05 | Land Security and Site Control | Is the decision record for wayleaves - governance approval aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | Municipal Planning By-law; wayleave requirements; landowner consent | Yes / No / N/A + Score 0–5 + Rating
05.007 | 05 | WP05 | Land Security and Site Control | Have cost, programme and compliance implications of title deed - legal authority been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | SPLUMA Act 16 of 2013; municipal land use scheme; title deed/SG diagram | Yes / No / N/A + Score 0–5 + Rating
05.008 | 05 | WP05 | Land Security and Site Control | Has the team obtained written confirmation or documented proof for landowner consent - legal authority? | Current certificate/letter/report, version control and document-control entry. | Deeds Registries Act 47 of 1937; Surveyor-General records; servitude register | Yes / No / N/A + Score 0–5 + Rating
05.009 | 05 | WP05 | Land Security and Site Control | Does the evidence for lease or purchase rights - legal authority support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | Municipal Planning By-law; wayleave requirements; landowner consent | Yes / No / N/A + Score 0–5 + Rating
05.010 | 05 | WP05 | Land Security and Site Control | Have dependencies linked to site boundaries - legal authority been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | SPLUMA Act 16 of 2013; municipal land use scheme; title deed/SG diagram | Yes / No / N/A + Score 0–5 + Rating
05.011 | 05 | WP05 | Land Security and Site Control | Has the project team confirmed SG diagram - legal authority in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | Deeds Registries Act 47 of 1937; Surveyor-General records; servitude register | Yes / No / N/A + Score 0–5 + Rating
05.012 | 05 | WP05 | Land Security and Site Control | Is there a responsible owner, due date and approval route for wayleaves - legal authority? | Register entry, supporting drawing/report, approval note and updated risk item. | Municipal Planning By-law; wayleave requirements; landowner consent | Yes / No / N/A + Score 0–5 + Rating
05.013 | 05 | WP05 | Land Security and Site Control | Has the gate file tested whether title deed - technical feasibility creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | SPLUMA Act 16 of 2013; municipal land use scheme; title deed/SG diagram | Yes / No / N/A + Score 0–5 + Rating
05.014 | 05 | WP05 | Land Security and Site Control | Are assumptions for landowner consent - technical feasibility documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | Deeds Registries Act 47 of 1937; Surveyor-General records; servitude register | Yes / No / N/A + Score 0–5 + Rating
05.015 | 05 | WP05 | Land Security and Site Control | Has the relevant authority, specialist or professional adviser reviewed lease or purchase rights - technical feasibility where required? | Authority response, compliance checklist, file note and management approval. | Municipal Planning By-law; wayleave requirements; landowner consent | Yes / No / N/A + Score 0–5 + Rating
05.016 | 05 | WP05 | Land Security and Site Control | Is the decision record for site boundaries - technical feasibility aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | SPLUMA Act 16 of 2013; municipal land use scheme; title deed/SG diagram | Yes / No / N/A + Score 0–5 + Rating
05.017 | 05 | WP05 | Land Security and Site Control | Have cost, programme and compliance implications of SG diagram - technical feasibility been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | Deeds Registries Act 47 of 1937; Surveyor-General records; servitude register | Yes / No / N/A + Score 0–5 + Rating
05.018 | 05 | WP05 | Land Security and Site Control | Has the team obtained written confirmation or documented proof for wayleaves - technical feasibility? | Current certificate/letter/report, version control and document-control entry. | Municipal Planning By-law; wayleave requirements; landowner consent | Yes / No / N/A + Score 0–5 + Rating
05.019 | 05 | WP05 | Land Security and Site Control | Does the evidence for title deed - financial viability support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | SPLUMA Act 16 of 2013; municipal land use scheme; title deed/SG diagram | Yes / No / N/A + Score 0–5 + Rating
05.020 | 05 | WP05 | Land Security and Site Control | Have dependencies linked to landowner consent - financial viability been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | Deeds Registries Act 47 of 1937; Surveyor-General records; servitude register | Yes / No / N/A + Score 0–5 + Rating
05.021 | 05 | WP05 | Land Security and Site Control | Has the project team confirmed lease or purchase rights - financial viability in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | Municipal Planning By-law; wayleave requirements; landowner consent | Yes / No / N/A + Score 0–5 + Rating
05.022 | 05 | WP05 | Land Security and Site Control | Is there a responsible owner, due date and approval route for site boundaries - financial viability? | Register entry, supporting drawing/report, approval note and updated risk item. | SPLUMA Act 16 of 2013; municipal land use scheme; title deed/SG diagram | Yes / No / N/A + Score 0–5 + Rating
05.023 | 05 | WP05 | Land Security and Site Control | Has the gate file tested whether SG diagram - financial viability creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | Deeds Registries Act 47 of 1937; Surveyor-General records; servitude register | Yes / No / N/A + Score 0–5 + Rating
05.024 | 05 | WP05 | Land Security and Site Control | Are assumptions for wayleaves - financial viability documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | Municipal Planning By-law; wayleave requirements; landowner consent | Yes / No / N/A + Score 0–5 + Rating
05.025 | 05 | WP05 | Land Security and Site Control | Has the relevant authority, specialist or professional adviser reviewed title deed - programme impact where required? | Authority response, compliance checklist, file note and management approval. | SPLUMA Act 16 of 2013; municipal land use scheme; title deed/SG diagram | Yes / No / N/A + Score 0–5 + Rating
05.026 | 05 | WP05 | Land Security and Site Control | Is the decision record for landowner consent - programme impact aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | Deeds Registries Act 47 of 1937; Surveyor-General records; servitude register | Yes / No / N/A + Score 0–5 + Rating
05.027 | 05 | WP05 | Land Security and Site Control | Have cost, programme and compliance implications of lease or purchase rights - programme impact been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | Municipal Planning By-law; wayleave requirements; landowner consent | Yes / No / N/A + Score 0–5 + Rating
05.028 | 05 | WP05 | Land Security and Site Control | Has the team obtained written confirmation or documented proof for site boundaries - programme impact? | Current certificate/letter/report, version control and document-control entry. | SPLUMA Act 16 of 2013; municipal land use scheme; title deed/SG diagram | Yes / No / N/A + Score 0–5 + Rating
05.029 | 05 | WP05 | Land Security and Site Control | Does the evidence for SG diagram - programme impact support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | Deeds Registries Act 47 of 1937; Surveyor-General records; servitude register | Yes / No / N/A + Score 0–5 + Rating
05.030 | 05 | WP05 | Land Security and Site Control | Have dependencies linked to wayleaves - programme impact been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | Municipal Planning By-law; wayleave requirements; landowner consent | Yes / No / N/A + Score 0–5 + Rating
05.031 | 05 | WP05 | Land Security and Site Control | Has the project team confirmed title deed - risk mitigation in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | SPLUMA Act 16 of 2013; municipal land use scheme; title deed/SG diagram | Yes / No / N/A + Score 0–5 + Rating
05.032 | 05 | WP05 | Land Security and Site Control | Is there a responsible owner, due date and approval route for landowner consent - risk mitigation? | Register entry, supporting drawing/report, approval note and updated risk item. | Deeds Registries Act 47 of 1937; Surveyor-General records; servitude register | Yes / No / N/A + Score 0–5 + Rating
05.033 | 05 | WP05 | Land Security and Site Control | Has the gate file tested whether lease or purchase rights - risk mitigation creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | Municipal Planning By-law; wayleave requirements; landowner consent | Yes / No / N/A + Score 0–5 + Rating
05.034 | 05 | WP05 | Land Security and Site Control | Are assumptions for site boundaries - risk mitigation documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | SPLUMA Act 16 of 2013; municipal land use scheme; title deed/SG diagram | Yes / No / N/A + Score 0–5 + Rating
05.035 | 05 | WP05 | Land Security and Site Control | Has the relevant authority, specialist or professional adviser reviewed SG diagram - risk mitigation where required? | Authority response, compliance checklist, file note and management approval. | Deeds Registries Act 47 of 1937; Surveyor-General records; servitude register | Yes / No / N/A + Score 0–5 + Rating
05.036 | 05 | WP05 | Land Security and Site Control | Is the decision record for wayleaves - risk mitigation aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | Municipal Planning By-law; wayleave requirements; landowner consent | Yes / No / N/A + Score 0–5 + Rating
05.037 | 05 | WP05 | Land Security and Site Control | Have cost, programme and compliance implications of title deed - stakeholder acceptance been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | SPLUMA Act 16 of 2013; municipal land use scheme; title deed/SG diagram | Yes / No / N/A + Score 0–5 + Rating
05.038 | 05 | WP05 | Land Security and Site Control | Has the team obtained written confirmation or documented proof for landowner consent - stakeholder acceptance? | Current certificate/letter/report, version control and document-control entry. | Deeds Registries Act 47 of 1937; Surveyor-General records; servitude register | Yes / No / N/A + Score 0–5 + Rating
05.039 | 05 | WP05 | Land Security and Site Control | Does the evidence for lease or purchase rights - stakeholder acceptance support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | Municipal Planning By-law; wayleave requirements; landowner consent | Yes / No / N/A + Score 0–5 + Rating
05.040 | 05 | WP05 | Land Security and Site Control | Have dependencies linked to site boundaries - stakeholder acceptance been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | SPLUMA Act 16 of 2013; municipal land use scheme; title deed/SG diagram | Yes / No / N/A + Score 0–5 + Rating
05.041 | 05 | WP05 | Land Security and Site Control | Has the project team confirmed SG diagram - stakeholder acceptance in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | Deeds Registries Act 47 of 1937; Surveyor-General records; servitude register | Yes / No / N/A + Score 0–5 + Rating
05.042 | 05 | WP05 | Land Security and Site Control | Is there a responsible owner, due date and approval route for wayleaves - stakeholder acceptance? | Register entry, supporting drawing/report, approval note and updated risk item. | Municipal Planning By-law; wayleave requirements; landowner consent | Yes / No / N/A + Score 0–5 + Rating
05.043 | 05 | WP05 | Land Security and Site Control | Has the gate file tested whether title deed - document control creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | SPLUMA Act 16 of 2013; municipal land use scheme; title deed/SG diagram | Yes / No / N/A + Score 0–5 + Rating
05.044 | 05 | WP05 | Land Security and Site Control | Are assumptions for landowner consent - document control documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | Deeds Registries Act 47 of 1937; Surveyor-General records; servitude register | Yes / No / N/A + Score 0–5 + Rating
05.045 | 05 | WP05 | Land Security and Site Control | Has the relevant authority, specialist or professional adviser reviewed lease or purchase rights - document control where required? | Authority response, compliance checklist, file note and management approval. | Municipal Planning By-law; wayleave requirements; landowner consent | Yes / No / N/A + Score 0–5 + Rating
05.046 | 05 | WP05 | Land Security and Site Control | Is the decision record for site boundaries - document control aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | SPLUMA Act 16 of 2013; municipal land use scheme; title deed/SG diagram | Yes / No / N/A + Score 0–5 + Rating
05.047 | 05 | WP05 | Land Security and Site Control | Have cost, programme and compliance implications of SG diagram - document control been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | Deeds Registries Act 47 of 1937; Surveyor-General records; servitude register | Yes / No / N/A + Score 0–5 + Rating
05.048 | 05 | WP05 | Land Security and Site Control | Has the team obtained written confirmation or documented proof for wayleaves - document control? | Current certificate/letter/report, version control and document-control entry. | Municipal Planning By-law; wayleave requirements; landowner consent | Yes / No / N/A + Score 0–5 + Rating
05.049 | 05 | WP05 | Land Security and Site Control | Does the evidence for title deed - professional certification support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | SPLUMA Act 16 of 2013; municipal land use scheme; title deed/SG diagram | Yes / No / N/A + Score 0–5 + Rating
05.050 | 05 | WP05 | Land Security and Site Control | Have dependencies linked to landowner consent - professional certification been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | Deeds Registries Act 47 of 1937; Surveyor-General records; servitude register | Yes / No / N/A + Score 0–5 + Rating
05.051 | 05 | WP05 | Land Security and Site Control | Has the project team confirmed lease or purchase rights - professional certification in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | Municipal Planning By-law; wayleave requirements; landowner consent | Yes / No / N/A + Score 0–5 + Rating
05.052 | 05 | WP05 | Land Security and Site Control | Is there a responsible owner, due date and approval route for site boundaries - professional certification? | Register entry, supporting drawing/report, approval note and updated risk item. | SPLUMA Act 16 of 2013; municipal land use scheme; title deed/SG diagram | Yes / No / N/A + Score 0–5 + Rating
05.053 | 05 | WP05 | Land Security and Site Control | Has the gate file tested whether SG diagram - professional certification creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | Deeds Registries Act 47 of 1937; Surveyor-General records; servitude register | Yes / No / N/A + Score 0–5 + Rating
05.054 | 05 | WP05 | Land Security and Site Control | Are assumptions for wayleaves - professional certification documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | Municipal Planning By-law; wayleave requirements; landowner consent | Yes / No / N/A + Score 0–5 + Rating
05.055 | 05 | WP05 | Land Security and Site Control | Has the relevant authority, specialist or professional adviser reviewed title deed - implementation readiness where required? | Authority response, compliance checklist, file note and management approval. | SPLUMA Act 16 of 2013; municipal land use scheme; title deed/SG diagram | Yes / No / N/A + Score 0–5 + Rating
05.056 | 05 | WP05 | Land Security and Site Control | Is the decision record for landowner consent - implementation readiness aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | Deeds Registries Act 47 of 1937; Surveyor-General records; servitude register | Yes / No / N/A + Score 0–5 + Rating
05.057 | 05 | WP05 | Land Security and Site Control | Have cost, programme and compliance implications of lease or purchase rights - implementation readiness been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | Municipal Planning By-law; wayleave requirements; landowner consent | Yes / No / N/A + Score 0–5 + Rating
05.058 | 05 | WP05 | Land Security and Site Control | Has the team obtained written confirmation or documented proof for site boundaries - implementation readiness? | Current certificate/letter/report, version control and document-control entry. | SPLUMA Act 16 of 2013; municipal land use scheme; title deed/SG diagram | Yes / No / N/A + Score 0–5 + Rating
05.059 | 05 | WP05 | Land Security and Site Control | Does the evidence for SG diagram - implementation readiness support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | Deeds Registries Act 47 of 1937; Surveyor-General records; servitude register | Yes / No / N/A + Score 0–5 + Rating
05.060 | 05 | WP05 | Land Security and Site Control | Have dependencies linked to wayleaves - implementation readiness been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | Municipal Planning By-law; wayleave requirements; landowner consent | Yes / No / N/A + Score 0–5 + Rating
05.061 | 05 | WP05 | Land Security and Site Control | Has the project team confirmed title deed - governance approval in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | SPLUMA Act 16 of 2013; municipal land use scheme; title deed/SG diagram | Yes / No / N/A + Score 0–5 + Rating
05.062 | 05 | WP05 | Land Security and Site Control | Is there a responsible owner, due date and approval route for landowner consent - governance approval? | Register entry, supporting drawing/report, approval note and updated risk item. | Deeds Registries Act 47 of 1937; Surveyor-General records; servitude register | Yes / No / N/A + Score 0–5 + Rating
05.063 | 05 | WP05 | Land Security and Site Control | Has the gate file tested whether lease or purchase rights - governance approval creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | Municipal Planning By-law; wayleave requirements; landowner consent | Yes / No / N/A + Score 0–5 + Rating
05.064 | 05 | WP05 | Land Security and Site Control | Are assumptions for site boundaries - governance approval documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | SPLUMA Act 16 of 2013; municipal land use scheme; title deed/SG diagram | Yes / No / N/A + Score 0–5 + Rating
05.065 | 05 | WP05 | Land Security and Site Control | Has the relevant authority, specialist or professional adviser reviewed SG diagram - governance approval where required? | Authority response, compliance checklist, file note and management approval. | Deeds Registries Act 47 of 1937; Surveyor-General records; servitude register | Yes / No / N/A + Score 0–5 + Rating
05.066 | 05 | WP05 | Land Security and Site Control | Is the decision record for wayleaves - governance approval aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | Municipal Planning By-law; wayleave requirements; landowner consent | Yes / No / N/A + Score 0–5 + Rating
05.067 | 05 | WP05 | Land Security and Site Control | Have cost, programme and compliance implications of title deed - legal authority been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | SPLUMA Act 16 of 2013; municipal land use scheme; title deed/SG diagram | Yes / No / N/A + Score 0–5 + Rating
05.068 | 05 | WP05 | Land Security and Site Control | Has the team obtained written confirmation or documented proof for landowner consent - legal authority? | Current certificate/letter/report, version control and document-control entry. | Deeds Registries Act 47 of 1937; Surveyor-General records; servitude register | Yes / No / N/A + Score 0–5 + Rating
05.069 | 05 | WP05 | Land Security and Site Control | Does the evidence for lease or purchase rights - legal authority support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | Municipal Planning By-law; wayleave requirements; landowner consent | Yes / No / N/A + Score 0–5 + Rating
05.070 | 05 | WP05 | Land Security and Site Control | Have dependencies linked to site boundaries - legal authority been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | SPLUMA Act 16 of 2013; municipal land use scheme; title deed/SG diagram | Yes / No / N/A + Score 0–5 + Rating
05.071 | 05 | WP05 | Land Security and Site Control | Has the project team confirmed SG diagram - legal authority in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | Deeds Registries Act 47 of 1937; Surveyor-General records; servitude register | Yes / No / N/A + Score 0–5 + Rating
05.072 | 05 | WP05 | Land Security and Site Control | Is there a responsible owner, due date and approval route for wayleaves - legal authority? | Register entry, supporting drawing/report, approval note and updated risk item. | Municipal Planning By-law; wayleave requirements; landowner consent | Yes / No / N/A + Score 0–5 + Rating
05.073 | 05 | WP05 | Land Security and Site Control | Has the gate file tested whether title deed - technical feasibility creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | SPLUMA Act 16 of 2013; municipal land use scheme; title deed/SG diagram | Yes / No / N/A + Score 0–5 + Rating
05.074 | 05 | WP05 | Land Security and Site Control | Are assumptions for landowner consent - technical feasibility documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | Deeds Registries Act 47 of 1937; Surveyor-General records; servitude register | Yes / No / N/A + Score 0–5 + Rating
05.075 | 05 | WP05 | Land Security and Site Control | Has the relevant authority, specialist or professional adviser reviewed lease or purchase rights - technical feasibility where required? | Authority response, compliance checklist, file note and management approval. | Municipal Planning By-law; wayleave requirements; landowner consent | Yes / No / N/A + Score 0–5 + Rating
05.076 | 05 | WP05 | Land Security and Site Control | Is the decision record for site boundaries - technical feasibility aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | SPLUMA Act 16 of 2013; municipal land use scheme; title deed/SG diagram | Yes / No / N/A + Score 0–5 + Rating
05.077 | 05 | WP05 | Land Security and Site Control | Have cost, programme and compliance implications of SG diagram - technical feasibility been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | Deeds Registries Act 47 of 1937; Surveyor-General records; servitude register | Yes / No / N/A + Score 0–5 + Rating
05.078 | 05 | WP05 | Land Security and Site Control | Has the team obtained written confirmation or documented proof for wayleaves - technical feasibility? | Current certificate/letter/report, version control and document-control entry. | Municipal Planning By-law; wayleave requirements; landowner consent | Yes / No / N/A + Score 0–5 + Rating
05.079 | 05 | WP05 | Land Security and Site Control | Does the evidence for title deed - financial viability support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | SPLUMA Act 16 of 2013; municipal land use scheme; title deed/SG diagram | Yes / No / N/A + Score 0–5 + Rating
05.080 | 05 | WP05 | Land Security and Site Control | Have dependencies linked to landowner consent - financial viability been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | Deeds Registries Act 47 of 1937; Surveyor-General records; servitude register | Yes / No / N/A + Score 0–5 + Rating
05.081 | 05 | WP05 | Land Security and Site Control | Has the project team confirmed lease or purchase rights - financial viability in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | Municipal Planning By-law; wayleave requirements; landowner consent | Yes / No / N/A + Score 0–5 + Rating
05.082 | 05 | WP05 | Land Security and Site Control | Is there a responsible owner, due date and approval route for site boundaries - financial viability? | Register entry, supporting drawing/report, approval note and updated risk item. | SPLUMA Act 16 of 2013; municipal land use scheme; title deed/SG diagram | Yes / No / N/A + Score 0–5 + Rating
05.083 | 05 | WP05 | Land Security and Site Control | Has the gate file tested whether SG diagram - financial viability creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | Deeds Registries Act 47 of 1937; Surveyor-General records; servitude register | Yes / No / N/A + Score 0–5 + Rating
05.084 | 05 | WP05 | Land Security and Site Control | Are assumptions for wayleaves - financial viability documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | Municipal Planning By-law; wayleave requirements; landowner consent | Yes / No / N/A + Score 0–5 + Rating
05.085 | 05 | WP05 | Land Security and Site Control | Has the relevant authority, specialist or professional adviser reviewed title deed - programme impact where required? | Authority response, compliance checklist, file note and management approval. | SPLUMA Act 16 of 2013; municipal land use scheme; title deed/SG diagram | Yes / No / N/A + Score 0–5 + Rating
05.086 | 05 | WP05 | Land Security and Site Control | Is the decision record for landowner consent - programme impact aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | Deeds Registries Act 47 of 1937; Surveyor-General records; servitude register | Yes / No / N/A + Score 0–5 + Rating
05.087 | 05 | WP05 | Land Security and Site Control | Have cost, programme and compliance implications of lease or purchase rights - programme impact been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | Municipal Planning By-law; wayleave requirements; landowner consent | Yes / No / N/A + Score 0–5 + Rating
05.088 | 05 | WP05 | Land Security and Site Control | Has the team obtained written confirmation or documented proof for site boundaries - programme impact? | Current certificate/letter/report, version control and document-control entry. | SPLUMA Act 16 of 2013; municipal land use scheme; title deed/SG diagram | Yes / No / N/A + Score 0–5 + Rating
05.089 | 05 | WP05 | Land Security and Site Control | Does the evidence for SG diagram - programme impact support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | Deeds Registries Act 47 of 1937; Surveyor-General records; servitude register | Yes / No / N/A + Score 0–5 + Rating
05.090 | 05 | WP05 | Land Security and Site Control | Have dependencies linked to wayleaves - programme impact been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | Municipal Planning By-law; wayleave requirements; landowner consent | Yes / No / N/A + Score 0–5 + Rating
05.091 | 05 | WP05 | Land Security and Site Control | Has the project team confirmed title deed - risk mitigation in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | SPLUMA Act 16 of 2013; municipal land use scheme; title deed/SG diagram | Yes / No / N/A + Score 0–5 + Rating
05.092 | 05 | WP05 | Land Security and Site Control | Is there a responsible owner, due date and approval route for landowner consent - risk mitigation? | Register entry, supporting drawing/report, approval note and updated risk item. | Deeds Registries Act 47 of 1937; Surveyor-General records; servitude register | Yes / No / N/A + Score 0–5 + Rating
05.093 | 05 | WP05 | Land Security and Site Control | Has the gate file tested whether lease or purchase rights - risk mitigation creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | Municipal Planning By-law; wayleave requirements; landowner consent | Yes / No / N/A + Score 0–5 + Rating
05.094 | 05 | WP05 | Land Security and Site Control | Are assumptions for site boundaries - risk mitigation documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | SPLUMA Act 16 of 2013; municipal land use scheme; title deed/SG diagram | Yes / No / N/A + Score 0–5 + Rating
05.095 | 05 | WP05 | Land Security and Site Control | Has the relevant authority, specialist or professional adviser reviewed SG diagram - risk mitigation where required? | Authority response, compliance checklist, file note and management approval. | Deeds Registries Act 47 of 1937; Surveyor-General records; servitude register | Yes / No / N/A + Score 0–5 + Rating
05.096 | 05 | WP05 | Land Security and Site Control | Is the decision record for wayleaves - risk mitigation aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | Municipal Planning By-law; wayleave requirements; landowner consent | Yes / No / N/A + Score 0–5 + Rating
05.097 | 05 | WP05 | Land Security and Site Control | Have cost, programme and compliance implications of title deed - stakeholder acceptance been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | SPLUMA Act 16 of 2013; municipal land use scheme; title deed/SG diagram | Yes / No / N/A + Score 0–5 + Rating
05.098 | 05 | WP05 | Land Security and Site Control | Has the team obtained written confirmation or documented proof for landowner consent - stakeholder acceptance? | Current certificate/letter/report, version control and document-control entry. | Deeds Registries Act 47 of 1937; Surveyor-General records; servitude register | Yes / No / N/A + Score 0–5 + Rating
05.099 | 05 | WP05 | Land Security and Site Control | Does the evidence for lease or purchase rights - stakeholder acceptance support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | Municipal Planning By-law; wayleave requirements; landowner consent | Yes / No / N/A + Score 0–5 + Rating
05.100 | 05 | WP05 | Land Security and Site Control | Have dependencies linked to site boundaries - stakeholder acceptance been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | SPLUMA Act 16 of 2013; municipal land use scheme; title deed/SG diagram | Yes / No / N/A + Score 0–5 + Rating
06.001 | 06 | WP06 | Feasibility Studies and Market Demand | Has the project team confirmed retail demand - governance approval in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | IFRS/IFRS for SMEs principles; lender due diligence checklist; signed financial model | Yes / No / N/A + Score 0–5 + Rating
06.002 | 06 | WP06 | Feasibility Studies and Market Demand | Is there a responsible owner, due date and approval route for fuel demand - governance approval? | Register entry, supporting drawing/report, approval note and updated risk item. | CIDB/procurement best practice; cost plan; QS measurement and BOQ controls | Yes / No / N/A + Score 0–5 + Rating
06.003 | 06 | WP06 | Feasibility Studies and Market Demand | Has the gate file tested whether Boxer anchor viability - governance approval creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | Treasury-style value-for-money principles; funding term sheet; drawdown controls | Yes / No / N/A + Score 0–5 + Rating
06.004 | 06 | WP06 | Feasibility Studies and Market Demand | Are assumptions for line-shop demand - governance approval documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | IFRS/IFRS for SMEs principles; lender due diligence checklist; signed financial model | Yes / No / N/A + Score 0–5 + Rating
06.005 | 06 | WP06 | Feasibility Studies and Market Demand | Has the relevant authority, specialist or professional adviser reviewed fast-food demand - governance approval where required? | Authority response, compliance checklist, file note and management approval. | CIDB/procurement best practice; cost plan; QS measurement and BOQ controls | Yes / No / N/A + Score 0–5 + Rating
06.006 | 06 | WP06 | Feasibility Studies and Market Demand | Is the decision record for traffic volumes - governance approval aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | Treasury-style value-for-money principles; funding term sheet; drawdown controls | Yes / No / N/A + Score 0–5 + Rating
06.007 | 06 | WP06 | Feasibility Studies and Market Demand | Have cost, programme and compliance implications of retail demand - legal authority been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | IFRS/IFRS for SMEs principles; lender due diligence checklist; signed financial model | Yes / No / N/A + Score 0–5 + Rating
06.008 | 06 | WP06 | Feasibility Studies and Market Demand | Has the team obtained written confirmation or documented proof for fuel demand - legal authority? | Current certificate/letter/report, version control and document-control entry. | CIDB/procurement best practice; cost plan; QS measurement and BOQ controls | Yes / No / N/A + Score 0–5 + Rating
06.009 | 06 | WP06 | Feasibility Studies and Market Demand | Does the evidence for Boxer anchor viability - legal authority support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | Treasury-style value-for-money principles; funding term sheet; drawdown controls | Yes / No / N/A + Score 0–5 + Rating
06.010 | 06 | WP06 | Feasibility Studies and Market Demand | Have dependencies linked to line-shop demand - legal authority been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | IFRS/IFRS for SMEs principles; lender due diligence checklist; signed financial model | Yes / No / N/A + Score 0–5 + Rating
06.011 | 06 | WP06 | Feasibility Studies and Market Demand | Has the project team confirmed fast-food demand - legal authority in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | CIDB/procurement best practice; cost plan; QS measurement and BOQ controls | Yes / No / N/A + Score 0–5 + Rating
06.012 | 06 | WP06 | Feasibility Studies and Market Demand | Is there a responsible owner, due date and approval route for traffic volumes - legal authority? | Register entry, supporting drawing/report, approval note and updated risk item. | Treasury-style value-for-money principles; funding term sheet; drawdown controls | Yes / No / N/A + Score 0–5 + Rating
06.013 | 06 | WP06 | Feasibility Studies and Market Demand | Has the gate file tested whether retail demand - technical feasibility creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | IFRS/IFRS for SMEs principles; lender due diligence checklist; signed financial model | Yes / No / N/A + Score 0–5 + Rating
06.014 | 06 | WP06 | Feasibility Studies and Market Demand | Are assumptions for fuel demand - technical feasibility documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | CIDB/procurement best practice; cost plan; QS measurement and BOQ controls | Yes / No / N/A + Score 0–5 + Rating
06.015 | 06 | WP06 | Feasibility Studies and Market Demand | Has the relevant authority, specialist or professional adviser reviewed Boxer anchor viability - technical feasibility where required? | Authority response, compliance checklist, file note and management approval. | Treasury-style value-for-money principles; funding term sheet; drawdown controls | Yes / No / N/A + Score 0–5 + Rating
06.016 | 06 | WP06 | Feasibility Studies and Market Demand | Is the decision record for line-shop demand - technical feasibility aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | IFRS/IFRS for SMEs principles; lender due diligence checklist; signed financial model | Yes / No / N/A + Score 0–5 + Rating
06.017 | 06 | WP06 | Feasibility Studies and Market Demand | Have cost, programme and compliance implications of fast-food demand - technical feasibility been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | CIDB/procurement best practice; cost plan; QS measurement and BOQ controls | Yes / No / N/A + Score 0–5 + Rating
06.018 | 06 | WP06 | Feasibility Studies and Market Demand | Has the team obtained written confirmation or documented proof for traffic volumes - technical feasibility? | Current certificate/letter/report, version control and document-control entry. | Treasury-style value-for-money principles; funding term sheet; drawdown controls | Yes / No / N/A + Score 0–5 + Rating
06.019 | 06 | WP06 | Feasibility Studies and Market Demand | Does the evidence for retail demand - financial viability support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | IFRS/IFRS for SMEs principles; lender due diligence checklist; signed financial model | Yes / No / N/A + Score 0–5 + Rating
06.020 | 06 | WP06 | Feasibility Studies and Market Demand | Have dependencies linked to fuel demand - financial viability been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | CIDB/procurement best practice; cost plan; QS measurement and BOQ controls | Yes / No / N/A + Score 0–5 + Rating
06.021 | 06 | WP06 | Feasibility Studies and Market Demand | Has the project team confirmed Boxer anchor viability - financial viability in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | Treasury-style value-for-money principles; funding term sheet; drawdown controls | Yes / No / N/A + Score 0–5 + Rating
06.022 | 06 | WP06 | Feasibility Studies and Market Demand | Is there a responsible owner, due date and approval route for line-shop demand - financial viability? | Register entry, supporting drawing/report, approval note and updated risk item. | IFRS/IFRS for SMEs principles; lender due diligence checklist; signed financial model | Yes / No / N/A + Score 0–5 + Rating
06.023 | 06 | WP06 | Feasibility Studies and Market Demand | Has the gate file tested whether fast-food demand - financial viability creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | CIDB/procurement best practice; cost plan; QS measurement and BOQ controls | Yes / No / N/A + Score 0–5 + Rating
06.024 | 06 | WP06 | Feasibility Studies and Market Demand | Are assumptions for traffic volumes - financial viability documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | Treasury-style value-for-money principles; funding term sheet; drawdown controls | Yes / No / N/A + Score 0–5 + Rating
06.025 | 06 | WP06 | Feasibility Studies and Market Demand | Has the relevant authority, specialist or professional adviser reviewed retail demand - programme impact where required? | Authority response, compliance checklist, file note and management approval. | IFRS/IFRS for SMEs principles; lender due diligence checklist; signed financial model | Yes / No / N/A + Score 0–5 + Rating
06.026 | 06 | WP06 | Feasibility Studies and Market Demand | Is the decision record for fuel demand - programme impact aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | CIDB/procurement best practice; cost plan; QS measurement and BOQ controls | Yes / No / N/A + Score 0–5 + Rating
06.027 | 06 | WP06 | Feasibility Studies and Market Demand | Have cost, programme and compliance implications of Boxer anchor viability - programme impact been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | Treasury-style value-for-money principles; funding term sheet; drawdown controls | Yes / No / N/A + Score 0–5 + Rating
06.028 | 06 | WP06 | Feasibility Studies and Market Demand | Has the team obtained written confirmation or documented proof for line-shop demand - programme impact? | Current certificate/letter/report, version control and document-control entry. | IFRS/IFRS for SMEs principles; lender due diligence checklist; signed financial model | Yes / No / N/A + Score 0–5 + Rating
06.029 | 06 | WP06 | Feasibility Studies and Market Demand | Does the evidence for fast-food demand - programme impact support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | CIDB/procurement best practice; cost plan; QS measurement and BOQ controls | Yes / No / N/A + Score 0–5 + Rating
06.030 | 06 | WP06 | Feasibility Studies and Market Demand | Have dependencies linked to traffic volumes - programme impact been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | Treasury-style value-for-money principles; funding term sheet; drawdown controls | Yes / No / N/A + Score 0–5 + Rating
06.031 | 06 | WP06 | Feasibility Studies and Market Demand | Has the project team confirmed retail demand - risk mitigation in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | IFRS/IFRS for SMEs principles; lender due diligence checklist; signed financial model | Yes / No / N/A + Score 0–5 + Rating
06.032 | 06 | WP06 | Feasibility Studies and Market Demand | Is there a responsible owner, due date and approval route for fuel demand - risk mitigation? | Register entry, supporting drawing/report, approval note and updated risk item. | CIDB/procurement best practice; cost plan; QS measurement and BOQ controls | Yes / No / N/A + Score 0–5 + Rating
06.033 | 06 | WP06 | Feasibility Studies and Market Demand | Has the gate file tested whether Boxer anchor viability - risk mitigation creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | Treasury-style value-for-money principles; funding term sheet; drawdown controls | Yes / No / N/A + Score 0–5 + Rating
06.034 | 06 | WP06 | Feasibility Studies and Market Demand | Are assumptions for line-shop demand - risk mitigation documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | IFRS/IFRS for SMEs principles; lender due diligence checklist; signed financial model | Yes / No / N/A + Score 0–5 + Rating
06.035 | 06 | WP06 | Feasibility Studies and Market Demand | Has the relevant authority, specialist or professional adviser reviewed fast-food demand - risk mitigation where required? | Authority response, compliance checklist, file note and management approval. | CIDB/procurement best practice; cost plan; QS measurement and BOQ controls | Yes / No / N/A + Score 0–5 + Rating
06.036 | 06 | WP06 | Feasibility Studies and Market Demand | Is the decision record for traffic volumes - risk mitigation aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | Treasury-style value-for-money principles; funding term sheet; drawdown controls | Yes / No / N/A + Score 0–5 + Rating
06.037 | 06 | WP06 | Feasibility Studies and Market Demand | Have cost, programme and compliance implications of retail demand - stakeholder acceptance been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | IFRS/IFRS for SMEs principles; lender due diligence checklist; signed financial model | Yes / No / N/A + Score 0–5 + Rating
06.038 | 06 | WP06 | Feasibility Studies and Market Demand | Has the team obtained written confirmation or documented proof for fuel demand - stakeholder acceptance? | Current certificate/letter/report, version control and document-control entry. | CIDB/procurement best practice; cost plan; QS measurement and BOQ controls | Yes / No / N/A + Score 0–5 + Rating
06.039 | 06 | WP06 | Feasibility Studies and Market Demand | Does the evidence for Boxer anchor viability - stakeholder acceptance support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | Treasury-style value-for-money principles; funding term sheet; drawdown controls | Yes / No / N/A + Score 0–5 + Rating
06.040 | 06 | WP06 | Feasibility Studies and Market Demand | Have dependencies linked to line-shop demand - stakeholder acceptance been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | IFRS/IFRS for SMEs principles; lender due diligence checklist; signed financial model | Yes / No / N/A + Score 0–5 + Rating
06.041 | 06 | WP06 | Feasibility Studies and Market Demand | Has the project team confirmed fast-food demand - stakeholder acceptance in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | CIDB/procurement best practice; cost plan; QS measurement and BOQ controls | Yes / No / N/A + Score 0–5 + Rating
06.042 | 06 | WP06 | Feasibility Studies and Market Demand | Is there a responsible owner, due date and approval route for traffic volumes - stakeholder acceptance? | Register entry, supporting drawing/report, approval note and updated risk item. | Treasury-style value-for-money principles; funding term sheet; drawdown controls | Yes / No / N/A + Score 0–5 + Rating
06.043 | 06 | WP06 | Feasibility Studies and Market Demand | Has the gate file tested whether retail demand - document control creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | IFRS/IFRS for SMEs principles; lender due diligence checklist; signed financial model | Yes / No / N/A + Score 0–5 + Rating
06.044 | 06 | WP06 | Feasibility Studies and Market Demand | Are assumptions for fuel demand - document control documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | CIDB/procurement best practice; cost plan; QS measurement and BOQ controls | Yes / No / N/A + Score 0–5 + Rating
06.045 | 06 | WP06 | Feasibility Studies and Market Demand | Has the relevant authority, specialist or professional adviser reviewed Boxer anchor viability - document control where required? | Authority response, compliance checklist, file note and management approval. | Treasury-style value-for-money principles; funding term sheet; drawdown controls | Yes / No / N/A + Score 0–5 + Rating
06.046 | 06 | WP06 | Feasibility Studies and Market Demand | Is the decision record for line-shop demand - document control aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | IFRS/IFRS for SMEs principles; lender due diligence checklist; signed financial model | Yes / No / N/A + Score 0–5 + Rating
06.047 | 06 | WP06 | Feasibility Studies and Market Demand | Have cost, programme and compliance implications of fast-food demand - document control been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | CIDB/procurement best practice; cost plan; QS measurement and BOQ controls | Yes / No / N/A + Score 0–5 + Rating
06.048 | 06 | WP06 | Feasibility Studies and Market Demand | Has the team obtained written confirmation or documented proof for traffic volumes - document control? | Current certificate/letter/report, version control and document-control entry. | Treasury-style value-for-money principles; funding term sheet; drawdown controls | Yes / No / N/A + Score 0–5 + Rating
06.049 | 06 | WP06 | Feasibility Studies and Market Demand | Does the evidence for retail demand - professional certification support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | IFRS/IFRS for SMEs principles; lender due diligence checklist; signed financial model | Yes / No / N/A + Score 0–5 + Rating
06.050 | 06 | WP06 | Feasibility Studies and Market Demand | Have dependencies linked to fuel demand - professional certification been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | CIDB/procurement best practice; cost plan; QS measurement and BOQ controls | Yes / No / N/A + Score 0–5 + Rating
06.051 | 06 | WP06 | Feasibility Studies and Market Demand | Has the project team confirmed Boxer anchor viability - professional certification in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | Treasury-style value-for-money principles; funding term sheet; drawdown controls | Yes / No / N/A + Score 0–5 + Rating
06.052 | 06 | WP06 | Feasibility Studies and Market Demand | Is there a responsible owner, due date and approval route for line-shop demand - professional certification? | Register entry, supporting drawing/report, approval note and updated risk item. | IFRS/IFRS for SMEs principles; lender due diligence checklist; signed financial model | Yes / No / N/A + Score 0–5 + Rating
06.053 | 06 | WP06 | Feasibility Studies and Market Demand | Has the gate file tested whether fast-food demand - professional certification creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | CIDB/procurement best practice; cost plan; QS measurement and BOQ controls | Yes / No / N/A + Score 0–5 + Rating
06.054 | 06 | WP06 | Feasibility Studies and Market Demand | Are assumptions for traffic volumes - professional certification documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | Treasury-style value-for-money principles; funding term sheet; drawdown controls | Yes / No / N/A + Score 0–5 + Rating
06.055 | 06 | WP06 | Feasibility Studies and Market Demand | Has the relevant authority, specialist or professional adviser reviewed retail demand - implementation readiness where required? | Authority response, compliance checklist, file note and management approval. | IFRS/IFRS for SMEs principles; lender due diligence checklist; signed financial model | Yes / No / N/A + Score 0–5 + Rating
06.056 | 06 | WP06 | Feasibility Studies and Market Demand | Is the decision record for fuel demand - implementation readiness aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | CIDB/procurement best practice; cost plan; QS measurement and BOQ controls | Yes / No / N/A + Score 0–5 + Rating
06.057 | 06 | WP06 | Feasibility Studies and Market Demand | Have cost, programme and compliance implications of Boxer anchor viability - implementation readiness been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | Treasury-style value-for-money principles; funding term sheet; drawdown controls | Yes / No / N/A + Score 0–5 + Rating
06.058 | 06 | WP06 | Feasibility Studies and Market Demand | Has the team obtained written confirmation or documented proof for line-shop demand - implementation readiness? | Current certificate/letter/report, version control and document-control entry. | IFRS/IFRS for SMEs principles; lender due diligence checklist; signed financial model | Yes / No / N/A + Score 0–5 + Rating
06.059 | 06 | WP06 | Feasibility Studies and Market Demand | Does the evidence for fast-food demand - implementation readiness support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | CIDB/procurement best practice; cost plan; QS measurement and BOQ controls | Yes / No / N/A + Score 0–5 + Rating
06.060 | 06 | WP06 | Feasibility Studies and Market Demand | Have dependencies linked to traffic volumes - implementation readiness been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | Treasury-style value-for-money principles; funding term sheet; drawdown controls | Yes / No / N/A + Score 0–5 + Rating
06.061 | 06 | WP06 | Feasibility Studies and Market Demand | Has the project team confirmed retail demand - governance approval in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | IFRS/IFRS for SMEs principles; lender due diligence checklist; signed financial model | Yes / No / N/A + Score 0–5 + Rating
06.062 | 06 | WP06 | Feasibility Studies and Market Demand | Is there a responsible owner, due date and approval route for fuel demand - governance approval? | Register entry, supporting drawing/report, approval note and updated risk item. | CIDB/procurement best practice; cost plan; QS measurement and BOQ controls | Yes / No / N/A + Score 0–5 + Rating
06.063 | 06 | WP06 | Feasibility Studies and Market Demand | Has the gate file tested whether Boxer anchor viability - governance approval creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | Treasury-style value-for-money principles; funding term sheet; drawdown controls | Yes / No / N/A + Score 0–5 + Rating
06.064 | 06 | WP06 | Feasibility Studies and Market Demand | Are assumptions for line-shop demand - governance approval documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | IFRS/IFRS for SMEs principles; lender due diligence checklist; signed financial model | Yes / No / N/A + Score 0–5 + Rating
06.065 | 06 | WP06 | Feasibility Studies and Market Demand | Has the relevant authority, specialist or professional adviser reviewed fast-food demand - governance approval where required? | Authority response, compliance checklist, file note and management approval. | CIDB/procurement best practice; cost plan; QS measurement and BOQ controls | Yes / No / N/A + Score 0–5 + Rating
06.066 | 06 | WP06 | Feasibility Studies and Market Demand | Is the decision record for traffic volumes - governance approval aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | Treasury-style value-for-money principles; funding term sheet; drawdown controls | Yes / No / N/A + Score 0–5 + Rating
06.067 | 06 | WP06 | Feasibility Studies and Market Demand | Have cost, programme and compliance implications of retail demand - legal authority been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | IFRS/IFRS for SMEs principles; lender due diligence checklist; signed financial model | Yes / No / N/A + Score 0–5 + Rating
06.068 | 06 | WP06 | Feasibility Studies and Market Demand | Has the team obtained written confirmation or documented proof for fuel demand - legal authority? | Current certificate/letter/report, version control and document-control entry. | CIDB/procurement best practice; cost plan; QS measurement and BOQ controls | Yes / No / N/A + Score 0–5 + Rating
06.069 | 06 | WP06 | Feasibility Studies and Market Demand | Does the evidence for Boxer anchor viability - legal authority support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | Treasury-style value-for-money principles; funding term sheet; drawdown controls | Yes / No / N/A + Score 0–5 + Rating
06.070 | 06 | WP06 | Feasibility Studies and Market Demand | Have dependencies linked to line-shop demand - legal authority been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | IFRS/IFRS for SMEs principles; lender due diligence checklist; signed financial model | Yes / No / N/A + Score 0–5 + Rating
06.071 | 06 | WP06 | Feasibility Studies and Market Demand | Has the project team confirmed fast-food demand - legal authority in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | CIDB/procurement best practice; cost plan; QS measurement and BOQ controls | Yes / No / N/A + Score 0–5 + Rating
06.072 | 06 | WP06 | Feasibility Studies and Market Demand | Is there a responsible owner, due date and approval route for traffic volumes - legal authority? | Register entry, supporting drawing/report, approval note and updated risk item. | Treasury-style value-for-money principles; funding term sheet; drawdown controls | Yes / No / N/A + Score 0–5 + Rating
06.073 | 06 | WP06 | Feasibility Studies and Market Demand | Has the gate file tested whether retail demand - technical feasibility creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | IFRS/IFRS for SMEs principles; lender due diligence checklist; signed financial model | Yes / No / N/A + Score 0–5 + Rating
06.074 | 06 | WP06 | Feasibility Studies and Market Demand | Are assumptions for fuel demand - technical feasibility documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | CIDB/procurement best practice; cost plan; QS measurement and BOQ controls | Yes / No / N/A + Score 0–5 + Rating
06.075 | 06 | WP06 | Feasibility Studies and Market Demand | Has the relevant authority, specialist or professional adviser reviewed Boxer anchor viability - technical feasibility where required? | Authority response, compliance checklist, file note and management approval. | Treasury-style value-for-money principles; funding term sheet; drawdown controls | Yes / No / N/A + Score 0–5 + Rating
06.076 | 06 | WP06 | Feasibility Studies and Market Demand | Is the decision record for line-shop demand - technical feasibility aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | IFRS/IFRS for SMEs principles; lender due diligence checklist; signed financial model | Yes / No / N/A + Score 0–5 + Rating
06.077 | 06 | WP06 | Feasibility Studies and Market Demand | Have cost, programme and compliance implications of fast-food demand - technical feasibility been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | CIDB/procurement best practice; cost plan; QS measurement and BOQ controls | Yes / No / N/A + Score 0–5 + Rating
06.078 | 06 | WP06 | Feasibility Studies and Market Demand | Has the team obtained written confirmation or documented proof for traffic volumes - technical feasibility? | Current certificate/letter/report, version control and document-control entry. | Treasury-style value-for-money principles; funding term sheet; drawdown controls | Yes / No / N/A + Score 0–5 + Rating
06.079 | 06 | WP06 | Feasibility Studies and Market Demand | Does the evidence for retail demand - financial viability support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | IFRS/IFRS for SMEs principles; lender due diligence checklist; signed financial model | Yes / No / N/A + Score 0–5 + Rating
06.080 | 06 | WP06 | Feasibility Studies and Market Demand | Have dependencies linked to fuel demand - financial viability been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | CIDB/procurement best practice; cost plan; QS measurement and BOQ controls | Yes / No / N/A + Score 0–5 + Rating
06.081 | 06 | WP06 | Feasibility Studies and Market Demand | Has the project team confirmed Boxer anchor viability - financial viability in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | Treasury-style value-for-money principles; funding term sheet; drawdown controls | Yes / No / N/A + Score 0–5 + Rating
06.082 | 06 | WP06 | Feasibility Studies and Market Demand | Is there a responsible owner, due date and approval route for line-shop demand - financial viability? | Register entry, supporting drawing/report, approval note and updated risk item. | IFRS/IFRS for SMEs principles; lender due diligence checklist; signed financial model | Yes / No / N/A + Score 0–5 + Rating
06.083 | 06 | WP06 | Feasibility Studies and Market Demand | Has the gate file tested whether fast-food demand - financial viability creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | CIDB/procurement best practice; cost plan; QS measurement and BOQ controls | Yes / No / N/A + Score 0–5 + Rating
06.084 | 06 | WP06 | Feasibility Studies and Market Demand | Are assumptions for traffic volumes - financial viability documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | Treasury-style value-for-money principles; funding term sheet; drawdown controls | Yes / No / N/A + Score 0–5 + Rating
06.085 | 06 | WP06 | Feasibility Studies and Market Demand | Has the relevant authority, specialist or professional adviser reviewed retail demand - programme impact where required? | Authority response, compliance checklist, file note and management approval. | IFRS/IFRS for SMEs principles; lender due diligence checklist; signed financial model | Yes / No / N/A + Score 0–5 + Rating
06.086 | 06 | WP06 | Feasibility Studies and Market Demand | Is the decision record for fuel demand - programme impact aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | CIDB/procurement best practice; cost plan; QS measurement and BOQ controls | Yes / No / N/A + Score 0–5 + Rating
06.087 | 06 | WP06 | Feasibility Studies and Market Demand | Have cost, programme and compliance implications of Boxer anchor viability - programme impact been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | Treasury-style value-for-money principles; funding term sheet; drawdown controls | Yes / No / N/A + Score 0–5 + Rating
06.088 | 06 | WP06 | Feasibility Studies and Market Demand | Has the team obtained written confirmation or documented proof for line-shop demand - programme impact? | Current certificate/letter/report, version control and document-control entry. | IFRS/IFRS for SMEs principles; lender due diligence checklist; signed financial model | Yes / No / N/A + Score 0–5 + Rating
06.089 | 06 | WP06 | Feasibility Studies and Market Demand | Does the evidence for fast-food demand - programme impact support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | CIDB/procurement best practice; cost plan; QS measurement and BOQ controls | Yes / No / N/A + Score 0–5 + Rating
06.090 | 06 | WP06 | Feasibility Studies and Market Demand | Have dependencies linked to traffic volumes - programme impact been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | Treasury-style value-for-money principles; funding term sheet; drawdown controls | Yes / No / N/A + Score 0–5 + Rating
06.091 | 06 | WP06 | Feasibility Studies and Market Demand | Has the project team confirmed retail demand - risk mitigation in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | IFRS/IFRS for SMEs principles; lender due diligence checklist; signed financial model | Yes / No / N/A + Score 0–5 + Rating
06.092 | 06 | WP06 | Feasibility Studies and Market Demand | Is there a responsible owner, due date and approval route for fuel demand - risk mitigation? | Register entry, supporting drawing/report, approval note and updated risk item. | CIDB/procurement best practice; cost plan; QS measurement and BOQ controls | Yes / No / N/A + Score 0–5 + Rating
06.093 | 06 | WP06 | Feasibility Studies and Market Demand | Has the gate file tested whether Boxer anchor viability - risk mitigation creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | Treasury-style value-for-money principles; funding term sheet; drawdown controls | Yes / No / N/A + Score 0–5 + Rating
06.094 | 06 | WP06 | Feasibility Studies and Market Demand | Are assumptions for line-shop demand - risk mitigation documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | IFRS/IFRS for SMEs principles; lender due diligence checklist; signed financial model | Yes / No / N/A + Score 0–5 + Rating
06.095 | 06 | WP06 | Feasibility Studies and Market Demand | Has the relevant authority, specialist or professional adviser reviewed fast-food demand - risk mitigation where required? | Authority response, compliance checklist, file note and management approval. | CIDB/procurement best practice; cost plan; QS measurement and BOQ controls | Yes / No / N/A + Score 0–5 + Rating
06.096 | 06 | WP06 | Feasibility Studies and Market Demand | Is the decision record for traffic volumes - risk mitigation aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | Treasury-style value-for-money principles; funding term sheet; drawdown controls | Yes / No / N/A + Score 0–5 + Rating
06.097 | 06 | WP06 | Feasibility Studies and Market Demand | Have cost, programme and compliance implications of retail demand - stakeholder acceptance been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | IFRS/IFRS for SMEs principles; lender due diligence checklist; signed financial model | Yes / No / N/A + Score 0–5 + Rating
06.098 | 06 | WP06 | Feasibility Studies and Market Demand | Has the team obtained written confirmation or documented proof for fuel demand - stakeholder acceptance? | Current certificate/letter/report, version control and document-control entry. | CIDB/procurement best practice; cost plan; QS measurement and BOQ controls | Yes / No / N/A + Score 0–5 + Rating
06.099 | 06 | WP06 | Feasibility Studies and Market Demand | Does the evidence for Boxer anchor viability - stakeholder acceptance support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | Treasury-style value-for-money principles; funding term sheet; drawdown controls | Yes / No / N/A + Score 0–5 + Rating
06.100 | 06 | WP06 | Feasibility Studies and Market Demand | Have dependencies linked to line-shop demand - stakeholder acceptance been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | IFRS/IFRS for SMEs principles; lender due diligence checklist; signed financial model | Yes / No / N/A + Score 0–5 + Rating
07.001 | 07 | WP07 | Traffic, Access and Mobility Feasibility | Has the project team confirmed R567 entrance - governance approval in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | SANRAL/road authority access requirements; TMH/TRH road design guidance | Yes / No / N/A + Score 0–5 + Rating
07.002 | 07 | WP07 | Traffic, Access and Mobility Feasibility | Is there a responsible owner, due date and approval route for turning lanes - governance approval? | Register entry, supporting drawing/report, approval note and updated risk item. | Municipal roads and stormwater standards; traffic impact assessment | Yes / No / N/A + Score 0–5 + Rating
07.003 | 07 | WP07 | Traffic, Access and Mobility Feasibility | Has the gate file tested whether sight distances - governance approval creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | SANS 10400-S access; pedestrian safety and universal access principles | Yes / No / N/A + Score 0–5 + Rating
07.004 | 07 | WP07 | Traffic, Access and Mobility Feasibility | Are assumptions for heavy vehicle movement - governance approval documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | SANRAL/road authority access requirements; TMH/TRH road design guidance | Yes / No / N/A + Score 0–5 + Rating
07.005 | 07 | WP07 | Traffic, Access and Mobility Feasibility | Has the relevant authority, specialist or professional adviser reviewed pedestrian safety - governance approval where required? | Authority response, compliance checklist, file note and management approval. | Municipal roads and stormwater standards; traffic impact assessment | Yes / No / N/A + Score 0–5 + Rating
07.006 | 07 | WP07 | Traffic, Access and Mobility Feasibility | Is the decision record for public transport interface - governance approval aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | SANS 10400-S access; pedestrian safety and universal access principles | Yes / No / N/A + Score 0–5 + Rating
07.007 | 07 | WP07 | Traffic, Access and Mobility Feasibility | Have cost, programme and compliance implications of R567 entrance - legal authority been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | SANRAL/road authority access requirements; TMH/TRH road design guidance | Yes / No / N/A + Score 0–5 + Rating
07.008 | 07 | WP07 | Traffic, Access and Mobility Feasibility | Has the team obtained written confirmation or documented proof for turning lanes - legal authority? | Current certificate/letter/report, version control and document-control entry. | Municipal roads and stormwater standards; traffic impact assessment | Yes / No / N/A + Score 0–5 + Rating
07.009 | 07 | WP07 | Traffic, Access and Mobility Feasibility | Does the evidence for sight distances - legal authority support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | SANS 10400-S access; pedestrian safety and universal access principles | Yes / No / N/A + Score 0–5 + Rating
07.010 | 07 | WP07 | Traffic, Access and Mobility Feasibility | Have dependencies linked to heavy vehicle movement - legal authority been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | SANRAL/road authority access requirements; TMH/TRH road design guidance | Yes / No / N/A + Score 0–5 + Rating
07.011 | 07 | WP07 | Traffic, Access and Mobility Feasibility | Has the project team confirmed pedestrian safety - legal authority in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | Municipal roads and stormwater standards; traffic impact assessment | Yes / No / N/A + Score 0–5 + Rating
07.012 | 07 | WP07 | Traffic, Access and Mobility Feasibility | Is there a responsible owner, due date and approval route for public transport interface - legal authority? | Register entry, supporting drawing/report, approval note and updated risk item. | SANS 10400-S access; pedestrian safety and universal access principles | Yes / No / N/A + Score 0–5 + Rating
07.013 | 07 | WP07 | Traffic, Access and Mobility Feasibility | Has the gate file tested whether R567 entrance - technical feasibility creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | SANRAL/road authority access requirements; TMH/TRH road design guidance | Yes / No / N/A + Score 0–5 + Rating
07.014 | 07 | WP07 | Traffic, Access and Mobility Feasibility | Are assumptions for turning lanes - technical feasibility documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | Municipal roads and stormwater standards; traffic impact assessment | Yes / No / N/A + Score 0–5 + Rating
07.015 | 07 | WP07 | Traffic, Access and Mobility Feasibility | Has the relevant authority, specialist or professional adviser reviewed sight distances - technical feasibility where required? | Authority response, compliance checklist, file note and management approval. | SANS 10400-S access; pedestrian safety and universal access principles | Yes / No / N/A + Score 0–5 + Rating
07.016 | 07 | WP07 | Traffic, Access and Mobility Feasibility | Is the decision record for heavy vehicle movement - technical feasibility aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | SANRAL/road authority access requirements; TMH/TRH road design guidance | Yes / No / N/A + Score 0–5 + Rating
07.017 | 07 | WP07 | Traffic, Access and Mobility Feasibility | Have cost, programme and compliance implications of pedestrian safety - technical feasibility been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | Municipal roads and stormwater standards; traffic impact assessment | Yes / No / N/A + Score 0–5 + Rating
07.018 | 07 | WP07 | Traffic, Access and Mobility Feasibility | Has the team obtained written confirmation or documented proof for public transport interface - technical feasibility? | Current certificate/letter/report, version control and document-control entry. | SANS 10400-S access; pedestrian safety and universal access principles | Yes / No / N/A + Score 0–5 + Rating
07.019 | 07 | WP07 | Traffic, Access and Mobility Feasibility | Does the evidence for R567 entrance - financial viability support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | SANRAL/road authority access requirements; TMH/TRH road design guidance | Yes / No / N/A + Score 0–5 + Rating
07.020 | 07 | WP07 | Traffic, Access and Mobility Feasibility | Have dependencies linked to turning lanes - financial viability been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | Municipal roads and stormwater standards; traffic impact assessment | Yes / No / N/A + Score 0–5 + Rating
07.021 | 07 | WP07 | Traffic, Access and Mobility Feasibility | Has the project team confirmed sight distances - financial viability in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | SANS 10400-S access; pedestrian safety and universal access principles | Yes / No / N/A + Score 0–5 + Rating
07.022 | 07 | WP07 | Traffic, Access and Mobility Feasibility | Is there a responsible owner, due date and approval route for heavy vehicle movement - financial viability? | Register entry, supporting drawing/report, approval note and updated risk item. | SANRAL/road authority access requirements; TMH/TRH road design guidance | Yes / No / N/A + Score 0–5 + Rating
07.023 | 07 | WP07 | Traffic, Access and Mobility Feasibility | Has the gate file tested whether pedestrian safety - financial viability creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | Municipal roads and stormwater standards; traffic impact assessment | Yes / No / N/A + Score 0–5 + Rating
07.024 | 07 | WP07 | Traffic, Access and Mobility Feasibility | Are assumptions for public transport interface - financial viability documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | SANS 10400-S access; pedestrian safety and universal access principles | Yes / No / N/A + Score 0–5 + Rating
07.025 | 07 | WP07 | Traffic, Access and Mobility Feasibility | Has the relevant authority, specialist or professional adviser reviewed R567 entrance - programme impact where required? | Authority response, compliance checklist, file note and management approval. | SANRAL/road authority access requirements; TMH/TRH road design guidance | Yes / No / N/A + Score 0–5 + Rating
07.026 | 07 | WP07 | Traffic, Access and Mobility Feasibility | Is the decision record for turning lanes - programme impact aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | Municipal roads and stormwater standards; traffic impact assessment | Yes / No / N/A + Score 0–5 + Rating
07.027 | 07 | WP07 | Traffic, Access and Mobility Feasibility | Have cost, programme and compliance implications of sight distances - programme impact been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | SANS 10400-S access; pedestrian safety and universal access principles | Yes / No / N/A + Score 0–5 + Rating
07.028 | 07 | WP07 | Traffic, Access and Mobility Feasibility | Has the team obtained written confirmation or documented proof for heavy vehicle movement - programme impact? | Current certificate/letter/report, version control and document-control entry. | SANRAL/road authority access requirements; TMH/TRH road design guidance | Yes / No / N/A + Score 0–5 + Rating
07.029 | 07 | WP07 | Traffic, Access and Mobility Feasibility | Does the evidence for pedestrian safety - programme impact support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | Municipal roads and stormwater standards; traffic impact assessment | Yes / No / N/A + Score 0–5 + Rating
07.030 | 07 | WP07 | Traffic, Access and Mobility Feasibility | Have dependencies linked to public transport interface - programme impact been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | SANS 10400-S access; pedestrian safety and universal access principles | Yes / No / N/A + Score 0–5 + Rating
07.031 | 07 | WP07 | Traffic, Access and Mobility Feasibility | Has the project team confirmed R567 entrance - risk mitigation in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | SANRAL/road authority access requirements; TMH/TRH road design guidance | Yes / No / N/A + Score 0–5 + Rating
07.032 | 07 | WP07 | Traffic, Access and Mobility Feasibility | Is there a responsible owner, due date and approval route for turning lanes - risk mitigation? | Register entry, supporting drawing/report, approval note and updated risk item. | Municipal roads and stormwater standards; traffic impact assessment | Yes / No / N/A + Score 0–5 + Rating
07.033 | 07 | WP07 | Traffic, Access and Mobility Feasibility | Has the gate file tested whether sight distances - risk mitigation creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | SANS 10400-S access; pedestrian safety and universal access principles | Yes / No / N/A + Score 0–5 + Rating
07.034 | 07 | WP07 | Traffic, Access and Mobility Feasibility | Are assumptions for heavy vehicle movement - risk mitigation documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | SANRAL/road authority access requirements; TMH/TRH road design guidance | Yes / No / N/A + Score 0–5 + Rating
07.035 | 07 | WP07 | Traffic, Access and Mobility Feasibility | Has the relevant authority, specialist or professional adviser reviewed pedestrian safety - risk mitigation where required? | Authority response, compliance checklist, file note and management approval. | Municipal roads and stormwater standards; traffic impact assessment | Yes / No / N/A + Score 0–5 + Rating
07.036 | 07 | WP07 | Traffic, Access and Mobility Feasibility | Is the decision record for public transport interface - risk mitigation aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | SANS 10400-S access; pedestrian safety and universal access principles | Yes / No / N/A + Score 0–5 + Rating
07.037 | 07 | WP07 | Traffic, Access and Mobility Feasibility | Have cost, programme and compliance implications of R567 entrance - stakeholder acceptance been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | SANRAL/road authority access requirements; TMH/TRH road design guidance | Yes / No / N/A + Score 0–5 + Rating
07.038 | 07 | WP07 | Traffic, Access and Mobility Feasibility | Has the team obtained written confirmation or documented proof for turning lanes - stakeholder acceptance? | Current certificate/letter/report, version control and document-control entry. | Municipal roads and stormwater standards; traffic impact assessment | Yes / No / N/A + Score 0–5 + Rating
07.039 | 07 | WP07 | Traffic, Access and Mobility Feasibility | Does the evidence for sight distances - stakeholder acceptance support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | SANS 10400-S access; pedestrian safety and universal access principles | Yes / No / N/A + Score 0–5 + Rating
07.040 | 07 | WP07 | Traffic, Access and Mobility Feasibility | Have dependencies linked to heavy vehicle movement - stakeholder acceptance been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | SANRAL/road authority access requirements; TMH/TRH road design guidance | Yes / No / N/A + Score 0–5 + Rating
07.041 | 07 | WP07 | Traffic, Access and Mobility Feasibility | Has the project team confirmed pedestrian safety - stakeholder acceptance in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | Municipal roads and stormwater standards; traffic impact assessment | Yes / No / N/A + Score 0–5 + Rating
07.042 | 07 | WP07 | Traffic, Access and Mobility Feasibility | Is there a responsible owner, due date and approval route for public transport interface - stakeholder acceptance? | Register entry, supporting drawing/report, approval note and updated risk item. | SANS 10400-S access; pedestrian safety and universal access principles | Yes / No / N/A + Score 0–5 + Rating
07.043 | 07 | WP07 | Traffic, Access and Mobility Feasibility | Has the gate file tested whether R567 entrance - document control creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | SANRAL/road authority access requirements; TMH/TRH road design guidance | Yes / No / N/A + Score 0–5 + Rating
07.044 | 07 | WP07 | Traffic, Access and Mobility Feasibility | Are assumptions for turning lanes - document control documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | Municipal roads and stormwater standards; traffic impact assessment | Yes / No / N/A + Score 0–5 + Rating
07.045 | 07 | WP07 | Traffic, Access and Mobility Feasibility | Has the relevant authority, specialist or professional adviser reviewed sight distances - document control where required? | Authority response, compliance checklist, file note and management approval. | SANS 10400-S access; pedestrian safety and universal access principles | Yes / No / N/A + Score 0–5 + Rating
07.046 | 07 | WP07 | Traffic, Access and Mobility Feasibility | Is the decision record for heavy vehicle movement - document control aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | SANRAL/road authority access requirements; TMH/TRH road design guidance | Yes / No / N/A + Score 0–5 + Rating
07.047 | 07 | WP07 | Traffic, Access and Mobility Feasibility | Have cost, programme and compliance implications of pedestrian safety - document control been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | Municipal roads and stormwater standards; traffic impact assessment | Yes / No / N/A + Score 0–5 + Rating
07.048 | 07 | WP07 | Traffic, Access and Mobility Feasibility | Has the team obtained written confirmation or documented proof for public transport interface - document control? | Current certificate/letter/report, version control and document-control entry. | SANS 10400-S access; pedestrian safety and universal access principles | Yes / No / N/A + Score 0–5 + Rating
07.049 | 07 | WP07 | Traffic, Access and Mobility Feasibility | Does the evidence for R567 entrance - professional certification support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | SANRAL/road authority access requirements; TMH/TRH road design guidance | Yes / No / N/A + Score 0–5 + Rating
07.050 | 07 | WP07 | Traffic, Access and Mobility Feasibility | Have dependencies linked to turning lanes - professional certification been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | Municipal roads and stormwater standards; traffic impact assessment | Yes / No / N/A + Score 0–5 + Rating
07.051 | 07 | WP07 | Traffic, Access and Mobility Feasibility | Has the project team confirmed sight distances - professional certification in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | SANS 10400-S access; pedestrian safety and universal access principles | Yes / No / N/A + Score 0–5 + Rating
07.052 | 07 | WP07 | Traffic, Access and Mobility Feasibility | Is there a responsible owner, due date and approval route for heavy vehicle movement - professional certification? | Register entry, supporting drawing/report, approval note and updated risk item. | SANRAL/road authority access requirements; TMH/TRH road design guidance | Yes / No / N/A + Score 0–5 + Rating
07.053 | 07 | WP07 | Traffic, Access and Mobility Feasibility | Has the gate file tested whether pedestrian safety - professional certification creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | Municipal roads and stormwater standards; traffic impact assessment | Yes / No / N/A + Score 0–5 + Rating
07.054 | 07 | WP07 | Traffic, Access and Mobility Feasibility | Are assumptions for public transport interface - professional certification documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | SANS 10400-S access; pedestrian safety and universal access principles | Yes / No / N/A + Score 0–5 + Rating
07.055 | 07 | WP07 | Traffic, Access and Mobility Feasibility | Has the relevant authority, specialist or professional adviser reviewed R567 entrance - implementation readiness where required? | Authority response, compliance checklist, file note and management approval. | SANRAL/road authority access requirements; TMH/TRH road design guidance | Yes / No / N/A + Score 0–5 + Rating
07.056 | 07 | WP07 | Traffic, Access and Mobility Feasibility | Is the decision record for turning lanes - implementation readiness aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | Municipal roads and stormwater standards; traffic impact assessment | Yes / No / N/A + Score 0–5 + Rating
07.057 | 07 | WP07 | Traffic, Access and Mobility Feasibility | Have cost, programme and compliance implications of sight distances - implementation readiness been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | SANS 10400-S access; pedestrian safety and universal access principles | Yes / No / N/A + Score 0–5 + Rating
07.058 | 07 | WP07 | Traffic, Access and Mobility Feasibility | Has the team obtained written confirmation or documented proof for heavy vehicle movement - implementation readiness? | Current certificate/letter/report, version control and document-control entry. | SANRAL/road authority access requirements; TMH/TRH road design guidance | Yes / No / N/A + Score 0–5 + Rating
07.059 | 07 | WP07 | Traffic, Access and Mobility Feasibility | Does the evidence for pedestrian safety - implementation readiness support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | Municipal roads and stormwater standards; traffic impact assessment | Yes / No / N/A + Score 0–5 + Rating
07.060 | 07 | WP07 | Traffic, Access and Mobility Feasibility | Have dependencies linked to public transport interface - implementation readiness been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | SANS 10400-S access; pedestrian safety and universal access principles | Yes / No / N/A + Score 0–5 + Rating
07.061 | 07 | WP07 | Traffic, Access and Mobility Feasibility | Has the project team confirmed R567 entrance - governance approval in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | SANRAL/road authority access requirements; TMH/TRH road design guidance | Yes / No / N/A + Score 0–5 + Rating
07.062 | 07 | WP07 | Traffic, Access and Mobility Feasibility | Is there a responsible owner, due date and approval route for turning lanes - governance approval? | Register entry, supporting drawing/report, approval note and updated risk item. | Municipal roads and stormwater standards; traffic impact assessment | Yes / No / N/A + Score 0–5 + Rating
07.063 | 07 | WP07 | Traffic, Access and Mobility Feasibility | Has the gate file tested whether sight distances - governance approval creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | SANS 10400-S access; pedestrian safety and universal access principles | Yes / No / N/A + Score 0–5 + Rating
07.064 | 07 | WP07 | Traffic, Access and Mobility Feasibility | Are assumptions for heavy vehicle movement - governance approval documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | SANRAL/road authority access requirements; TMH/TRH road design guidance | Yes / No / N/A + Score 0–5 + Rating
07.065 | 07 | WP07 | Traffic, Access and Mobility Feasibility | Has the relevant authority, specialist or professional adviser reviewed pedestrian safety - governance approval where required? | Authority response, compliance checklist, file note and management approval. | Municipal roads and stormwater standards; traffic impact assessment | Yes / No / N/A + Score 0–5 + Rating
07.066 | 07 | WP07 | Traffic, Access and Mobility Feasibility | Is the decision record for public transport interface - governance approval aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | SANS 10400-S access; pedestrian safety and universal access principles | Yes / No / N/A + Score 0–5 + Rating
07.067 | 07 | WP07 | Traffic, Access and Mobility Feasibility | Have cost, programme and compliance implications of R567 entrance - legal authority been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | SANRAL/road authority access requirements; TMH/TRH road design guidance | Yes / No / N/A + Score 0–5 + Rating
07.068 | 07 | WP07 | Traffic, Access and Mobility Feasibility | Has the team obtained written confirmation or documented proof for turning lanes - legal authority? | Current certificate/letter/report, version control and document-control entry. | Municipal roads and stormwater standards; traffic impact assessment | Yes / No / N/A + Score 0–5 + Rating
07.069 | 07 | WP07 | Traffic, Access and Mobility Feasibility | Does the evidence for sight distances - legal authority support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | SANS 10400-S access; pedestrian safety and universal access principles | Yes / No / N/A + Score 0–5 + Rating
07.070 | 07 | WP07 | Traffic, Access and Mobility Feasibility | Have dependencies linked to heavy vehicle movement - legal authority been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | SANRAL/road authority access requirements; TMH/TRH road design guidance | Yes / No / N/A + Score 0–5 + Rating
07.071 | 07 | WP07 | Traffic, Access and Mobility Feasibility | Has the project team confirmed pedestrian safety - legal authority in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | Municipal roads and stormwater standards; traffic impact assessment | Yes / No / N/A + Score 0–5 + Rating
07.072 | 07 | WP07 | Traffic, Access and Mobility Feasibility | Is there a responsible owner, due date and approval route for public transport interface - legal authority? | Register entry, supporting drawing/report, approval note and updated risk item. | SANS 10400-S access; pedestrian safety and universal access principles | Yes / No / N/A + Score 0–5 + Rating
07.073 | 07 | WP07 | Traffic, Access and Mobility Feasibility | Has the gate file tested whether R567 entrance - technical feasibility creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | SANRAL/road authority access requirements; TMH/TRH road design guidance | Yes / No / N/A + Score 0–5 + Rating
07.074 | 07 | WP07 | Traffic, Access and Mobility Feasibility | Are assumptions for turning lanes - technical feasibility documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | Municipal roads and stormwater standards; traffic impact assessment | Yes / No / N/A + Score 0–5 + Rating
07.075 | 07 | WP07 | Traffic, Access and Mobility Feasibility | Has the relevant authority, specialist or professional adviser reviewed sight distances - technical feasibility where required? | Authority response, compliance checklist, file note and management approval. | SANS 10400-S access; pedestrian safety and universal access principles | Yes / No / N/A + Score 0–5 + Rating
07.076 | 07 | WP07 | Traffic, Access and Mobility Feasibility | Is the decision record for heavy vehicle movement - technical feasibility aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | SANRAL/road authority access requirements; TMH/TRH road design guidance | Yes / No / N/A + Score 0–5 + Rating
07.077 | 07 | WP07 | Traffic, Access and Mobility Feasibility | Have cost, programme and compliance implications of pedestrian safety - technical feasibility been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | Municipal roads and stormwater standards; traffic impact assessment | Yes / No / N/A + Score 0–5 + Rating
07.078 | 07 | WP07 | Traffic, Access and Mobility Feasibility | Has the team obtained written confirmation or documented proof for public transport interface - technical feasibility? | Current certificate/letter/report, version control and document-control entry. | SANS 10400-S access; pedestrian safety and universal access principles | Yes / No / N/A + Score 0–5 + Rating
07.079 | 07 | WP07 | Traffic, Access and Mobility Feasibility | Does the evidence for R567 entrance - financial viability support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | SANRAL/road authority access requirements; TMH/TRH road design guidance | Yes / No / N/A + Score 0–5 + Rating
07.080 | 07 | WP07 | Traffic, Access and Mobility Feasibility | Have dependencies linked to turning lanes - financial viability been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | Municipal roads and stormwater standards; traffic impact assessment | Yes / No / N/A + Score 0–5 + Rating
07.081 | 07 | WP07 | Traffic, Access and Mobility Feasibility | Has the project team confirmed sight distances - financial viability in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | SANS 10400-S access; pedestrian safety and universal access principles | Yes / No / N/A + Score 0–5 + Rating
07.082 | 07 | WP07 | Traffic, Access and Mobility Feasibility | Is there a responsible owner, due date and approval route for heavy vehicle movement - financial viability? | Register entry, supporting drawing/report, approval note and updated risk item. | SANRAL/road authority access requirements; TMH/TRH road design guidance | Yes / No / N/A + Score 0–5 + Rating
07.083 | 07 | WP07 | Traffic, Access and Mobility Feasibility | Has the gate file tested whether pedestrian safety - financial viability creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | Municipal roads and stormwater standards; traffic impact assessment | Yes / No / N/A + Score 0–5 + Rating
07.084 | 07 | WP07 | Traffic, Access and Mobility Feasibility | Are assumptions for public transport interface - financial viability documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | SANS 10400-S access; pedestrian safety and universal access principles | Yes / No / N/A + Score 0–5 + Rating
07.085 | 07 | WP07 | Traffic, Access and Mobility Feasibility | Has the relevant authority, specialist or professional adviser reviewed R567 entrance - programme impact where required? | Authority response, compliance checklist, file note and management approval. | SANRAL/road authority access requirements; TMH/TRH road design guidance | Yes / No / N/A + Score 0–5 + Rating
07.086 | 07 | WP07 | Traffic, Access and Mobility Feasibility | Is the decision record for turning lanes - programme impact aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | Municipal roads and stormwater standards; traffic impact assessment | Yes / No / N/A + Score 0–5 + Rating
07.087 | 07 | WP07 | Traffic, Access and Mobility Feasibility | Have cost, programme and compliance implications of sight distances - programme impact been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | SANS 10400-S access; pedestrian safety and universal access principles | Yes / No / N/A + Score 0–5 + Rating
07.088 | 07 | WP07 | Traffic, Access and Mobility Feasibility | Has the team obtained written confirmation or documented proof for heavy vehicle movement - programme impact? | Current certificate/letter/report, version control and document-control entry. | SANRAL/road authority access requirements; TMH/TRH road design guidance | Yes / No / N/A + Score 0–5 + Rating
07.089 | 07 | WP07 | Traffic, Access and Mobility Feasibility | Does the evidence for pedestrian safety - programme impact support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | Municipal roads and stormwater standards; traffic impact assessment | Yes / No / N/A + Score 0–5 + Rating
07.090 | 07 | WP07 | Traffic, Access and Mobility Feasibility | Have dependencies linked to public transport interface - programme impact been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | SANS 10400-S access; pedestrian safety and universal access principles | Yes / No / N/A + Score 0–5 + Rating
07.091 | 07 | WP07 | Traffic, Access and Mobility Feasibility | Has the project team confirmed R567 entrance - risk mitigation in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | SANRAL/road authority access requirements; TMH/TRH road design guidance | Yes / No / N/A + Score 0–5 + Rating
07.092 | 07 | WP07 | Traffic, Access and Mobility Feasibility | Is there a responsible owner, due date and approval route for turning lanes - risk mitigation? | Register entry, supporting drawing/report, approval note and updated risk item. | Municipal roads and stormwater standards; traffic impact assessment | Yes / No / N/A + Score 0–5 + Rating
07.093 | 07 | WP07 | Traffic, Access and Mobility Feasibility | Has the gate file tested whether sight distances - risk mitigation creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | SANS 10400-S access; pedestrian safety and universal access principles | Yes / No / N/A + Score 0–5 + Rating
07.094 | 07 | WP07 | Traffic, Access and Mobility Feasibility | Are assumptions for heavy vehicle movement - risk mitigation documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | SANRAL/road authority access requirements; TMH/TRH road design guidance | Yes / No / N/A + Score 0–5 + Rating
07.095 | 07 | WP07 | Traffic, Access and Mobility Feasibility | Has the relevant authority, specialist or professional adviser reviewed pedestrian safety - risk mitigation where required? | Authority response, compliance checklist, file note and management approval. | Municipal roads and stormwater standards; traffic impact assessment | Yes / No / N/A + Score 0–5 + Rating
07.096 | 07 | WP07 | Traffic, Access and Mobility Feasibility | Is the decision record for public transport interface - risk mitigation aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | SANS 10400-S access; pedestrian safety and universal access principles | Yes / No / N/A + Score 0–5 + Rating
07.097 | 07 | WP07 | Traffic, Access and Mobility Feasibility | Have cost, programme and compliance implications of R567 entrance - stakeholder acceptance been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | SANRAL/road authority access requirements; TMH/TRH road design guidance | Yes / No / N/A + Score 0–5 + Rating
07.098 | 07 | WP07 | Traffic, Access and Mobility Feasibility | Has the team obtained written confirmation or documented proof for turning lanes - stakeholder acceptance? | Current certificate/letter/report, version control and document-control entry. | Municipal roads and stormwater standards; traffic impact assessment | Yes / No / N/A + Score 0–5 + Rating
07.099 | 07 | WP07 | Traffic, Access and Mobility Feasibility | Does the evidence for sight distances - stakeholder acceptance support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | SANS 10400-S access; pedestrian safety and universal access principles | Yes / No / N/A + Score 0–5 + Rating
07.100 | 07 | WP07 | Traffic, Access and Mobility Feasibility | Have dependencies linked to heavy vehicle movement - stakeholder acceptance been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | SANRAL/road authority access requirements; TMH/TRH road design guidance | Yes / No / N/A + Score 0–5 + Rating
08.001 | 08 | WP08 | Bulk Services and Infrastructure Feasibility | Has the project team confirmed water supply - governance approval in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
08.002 | 08 | WP08 | Bulk Services and Infrastructure Feasibility | Is there a responsible owner, due date and approval route for sewer capacity - governance approval? | Register entry, supporting drawing/report, approval note and updated risk item. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
08.003 | 08 | WP08 | Bulk Services and Infrastructure Feasibility | Has the gate file tested whether stormwater discharge - governance approval creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
08.004 | 08 | WP08 | Bulk Services and Infrastructure Feasibility | Are assumptions for electrical capacity - governance approval documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
08.005 | 08 | WP08 | Bulk Services and Infrastructure Feasibility | Has the relevant authority, specialist or professional adviser reviewed fire water - governance approval where required? | Authority response, compliance checklist, file note and management approval. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
08.006 | 08 | WP08 | Bulk Services and Infrastructure Feasibility | Is the decision record for ICT services - governance approval aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
08.007 | 08 | WP08 | Bulk Services and Infrastructure Feasibility | Have cost, programme and compliance implications of water supply - legal authority been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
08.008 | 08 | WP08 | Bulk Services and Infrastructure Feasibility | Has the team obtained written confirmation or documented proof for sewer capacity - legal authority? | Current certificate/letter/report, version control and document-control entry. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
08.009 | 08 | WP08 | Bulk Services and Infrastructure Feasibility | Does the evidence for stormwater discharge - legal authority support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
08.010 | 08 | WP08 | Bulk Services and Infrastructure Feasibility | Have dependencies linked to electrical capacity - legal authority been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
08.011 | 08 | WP08 | Bulk Services and Infrastructure Feasibility | Has the project team confirmed fire water - legal authority in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
08.012 | 08 | WP08 | Bulk Services and Infrastructure Feasibility | Is there a responsible owner, due date and approval route for ICT services - legal authority? | Register entry, supporting drawing/report, approval note and updated risk item. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
08.013 | 08 | WP08 | Bulk Services and Infrastructure Feasibility | Has the gate file tested whether water supply - technical feasibility creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
08.014 | 08 | WP08 | Bulk Services and Infrastructure Feasibility | Are assumptions for sewer capacity - technical feasibility documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
08.015 | 08 | WP08 | Bulk Services and Infrastructure Feasibility | Has the relevant authority, specialist or professional adviser reviewed stormwater discharge - technical feasibility where required? | Authority response, compliance checklist, file note and management approval. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
08.016 | 08 | WP08 | Bulk Services and Infrastructure Feasibility | Is the decision record for electrical capacity - technical feasibility aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
08.017 | 08 | WP08 | Bulk Services and Infrastructure Feasibility | Have cost, programme and compliance implications of fire water - technical feasibility been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
08.018 | 08 | WP08 | Bulk Services and Infrastructure Feasibility | Has the team obtained written confirmation or documented proof for ICT services - technical feasibility? | Current certificate/letter/report, version control and document-control entry. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
08.019 | 08 | WP08 | Bulk Services and Infrastructure Feasibility | Does the evidence for water supply - financial viability support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
08.020 | 08 | WP08 | Bulk Services and Infrastructure Feasibility | Have dependencies linked to sewer capacity - financial viability been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
08.021 | 08 | WP08 | Bulk Services and Infrastructure Feasibility | Has the project team confirmed stormwater discharge - financial viability in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
08.022 | 08 | WP08 | Bulk Services and Infrastructure Feasibility | Is there a responsible owner, due date and approval route for electrical capacity - financial viability? | Register entry, supporting drawing/report, approval note and updated risk item. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
08.023 | 08 | WP08 | Bulk Services and Infrastructure Feasibility | Has the gate file tested whether fire water - financial viability creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
08.024 | 08 | WP08 | Bulk Services and Infrastructure Feasibility | Are assumptions for ICT services - financial viability documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
08.025 | 08 | WP08 | Bulk Services and Infrastructure Feasibility | Has the relevant authority, specialist or professional adviser reviewed water supply - programme impact where required? | Authority response, compliance checklist, file note and management approval. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
08.026 | 08 | WP08 | Bulk Services and Infrastructure Feasibility | Is the decision record for sewer capacity - programme impact aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
08.027 | 08 | WP08 | Bulk Services and Infrastructure Feasibility | Have cost, programme and compliance implications of stormwater discharge - programme impact been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
08.028 | 08 | WP08 | Bulk Services and Infrastructure Feasibility | Has the team obtained written confirmation or documented proof for electrical capacity - programme impact? | Current certificate/letter/report, version control and document-control entry. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
08.029 | 08 | WP08 | Bulk Services and Infrastructure Feasibility | Does the evidence for fire water - programme impact support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
08.030 | 08 | WP08 | Bulk Services and Infrastructure Feasibility | Have dependencies linked to ICT services - programme impact been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
08.031 | 08 | WP08 | Bulk Services and Infrastructure Feasibility | Has the project team confirmed water supply - risk mitigation in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
08.032 | 08 | WP08 | Bulk Services and Infrastructure Feasibility | Is there a responsible owner, due date and approval route for sewer capacity - risk mitigation? | Register entry, supporting drawing/report, approval note and updated risk item. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
08.033 | 08 | WP08 | Bulk Services and Infrastructure Feasibility | Has the gate file tested whether stormwater discharge - risk mitigation creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
08.034 | 08 | WP08 | Bulk Services and Infrastructure Feasibility | Are assumptions for electrical capacity - risk mitigation documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
08.035 | 08 | WP08 | Bulk Services and Infrastructure Feasibility | Has the relevant authority, specialist or professional adviser reviewed fire water - risk mitigation where required? | Authority response, compliance checklist, file note and management approval. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
08.036 | 08 | WP08 | Bulk Services and Infrastructure Feasibility | Is the decision record for ICT services - risk mitigation aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
08.037 | 08 | WP08 | Bulk Services and Infrastructure Feasibility | Have cost, programme and compliance implications of water supply - stakeholder acceptance been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
08.038 | 08 | WP08 | Bulk Services and Infrastructure Feasibility | Has the team obtained written confirmation or documented proof for sewer capacity - stakeholder acceptance? | Current certificate/letter/report, version control and document-control entry. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
08.039 | 08 | WP08 | Bulk Services and Infrastructure Feasibility | Does the evidence for stormwater discharge - stakeholder acceptance support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
08.040 | 08 | WP08 | Bulk Services and Infrastructure Feasibility | Have dependencies linked to electrical capacity - stakeholder acceptance been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
08.041 | 08 | WP08 | Bulk Services and Infrastructure Feasibility | Has the project team confirmed fire water - stakeholder acceptance in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
08.042 | 08 | WP08 | Bulk Services and Infrastructure Feasibility | Is there a responsible owner, due date and approval route for ICT services - stakeholder acceptance? | Register entry, supporting drawing/report, approval note and updated risk item. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
08.043 | 08 | WP08 | Bulk Services and Infrastructure Feasibility | Has the gate file tested whether water supply - document control creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
08.044 | 08 | WP08 | Bulk Services and Infrastructure Feasibility | Are assumptions for sewer capacity - document control documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
08.045 | 08 | WP08 | Bulk Services and Infrastructure Feasibility | Has the relevant authority, specialist or professional adviser reviewed stormwater discharge - document control where required? | Authority response, compliance checklist, file note and management approval. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
08.046 | 08 | WP08 | Bulk Services and Infrastructure Feasibility | Is the decision record for electrical capacity - document control aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
08.047 | 08 | WP08 | Bulk Services and Infrastructure Feasibility | Have cost, programme and compliance implications of fire water - document control been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
08.048 | 08 | WP08 | Bulk Services and Infrastructure Feasibility | Has the team obtained written confirmation or documented proof for ICT services - document control? | Current certificate/letter/report, version control and document-control entry. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
08.049 | 08 | WP08 | Bulk Services and Infrastructure Feasibility | Does the evidence for water supply - professional certification support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
08.050 | 08 | WP08 | Bulk Services and Infrastructure Feasibility | Have dependencies linked to sewer capacity - professional certification been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
08.051 | 08 | WP08 | Bulk Services and Infrastructure Feasibility | Has the project team confirmed stormwater discharge - professional certification in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
08.052 | 08 | WP08 | Bulk Services and Infrastructure Feasibility | Is there a responsible owner, due date and approval route for electrical capacity - professional certification? | Register entry, supporting drawing/report, approval note and updated risk item. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
08.053 | 08 | WP08 | Bulk Services and Infrastructure Feasibility | Has the gate file tested whether fire water - professional certification creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
08.054 | 08 | WP08 | Bulk Services and Infrastructure Feasibility | Are assumptions for ICT services - professional certification documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
08.055 | 08 | WP08 | Bulk Services and Infrastructure Feasibility | Has the relevant authority, specialist or professional adviser reviewed water supply - implementation readiness where required? | Authority response, compliance checklist, file note and management approval. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
08.056 | 08 | WP08 | Bulk Services and Infrastructure Feasibility | Is the decision record for sewer capacity - implementation readiness aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
08.057 | 08 | WP08 | Bulk Services and Infrastructure Feasibility | Have cost, programme and compliance implications of stormwater discharge - implementation readiness been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
08.058 | 08 | WP08 | Bulk Services and Infrastructure Feasibility | Has the team obtained written confirmation or documented proof for electrical capacity - implementation readiness? | Current certificate/letter/report, version control and document-control entry. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
08.059 | 08 | WP08 | Bulk Services and Infrastructure Feasibility | Does the evidence for fire water - implementation readiness support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
08.060 | 08 | WP08 | Bulk Services and Infrastructure Feasibility | Have dependencies linked to ICT services - implementation readiness been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
08.061 | 08 | WP08 | Bulk Services and Infrastructure Feasibility | Has the project team confirmed water supply - governance approval in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
08.062 | 08 | WP08 | Bulk Services and Infrastructure Feasibility | Is there a responsible owner, due date and approval route for sewer capacity - governance approval? | Register entry, supporting drawing/report, approval note and updated risk item. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
08.063 | 08 | WP08 | Bulk Services and Infrastructure Feasibility | Has the gate file tested whether stormwater discharge - governance approval creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
08.064 | 08 | WP08 | Bulk Services and Infrastructure Feasibility | Are assumptions for electrical capacity - governance approval documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
08.065 | 08 | WP08 | Bulk Services and Infrastructure Feasibility | Has the relevant authority, specialist or professional adviser reviewed fire water - governance approval where required? | Authority response, compliance checklist, file note and management approval. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
08.066 | 08 | WP08 | Bulk Services and Infrastructure Feasibility | Is the decision record for ICT services - governance approval aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
08.067 | 08 | WP08 | Bulk Services and Infrastructure Feasibility | Have cost, programme and compliance implications of water supply - legal authority been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
08.068 | 08 | WP08 | Bulk Services and Infrastructure Feasibility | Has the team obtained written confirmation or documented proof for sewer capacity - legal authority? | Current certificate/letter/report, version control and document-control entry. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
08.069 | 08 | WP08 | Bulk Services and Infrastructure Feasibility | Does the evidence for stormwater discharge - legal authority support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
08.070 | 08 | WP08 | Bulk Services and Infrastructure Feasibility | Have dependencies linked to electrical capacity - legal authority been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
08.071 | 08 | WP08 | Bulk Services and Infrastructure Feasibility | Has the project team confirmed fire water - legal authority in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
08.072 | 08 | WP08 | Bulk Services and Infrastructure Feasibility | Is there a responsible owner, due date and approval route for ICT services - legal authority? | Register entry, supporting drawing/report, approval note and updated risk item. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
08.073 | 08 | WP08 | Bulk Services and Infrastructure Feasibility | Has the gate file tested whether water supply - technical feasibility creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
08.074 | 08 | WP08 | Bulk Services and Infrastructure Feasibility | Are assumptions for sewer capacity - technical feasibility documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
08.075 | 08 | WP08 | Bulk Services and Infrastructure Feasibility | Has the relevant authority, specialist or professional adviser reviewed stormwater discharge - technical feasibility where required? | Authority response, compliance checklist, file note and management approval. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
08.076 | 08 | WP08 | Bulk Services and Infrastructure Feasibility | Is the decision record for electrical capacity - technical feasibility aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
08.077 | 08 | WP08 | Bulk Services and Infrastructure Feasibility | Have cost, programme and compliance implications of fire water - technical feasibility been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
08.078 | 08 | WP08 | Bulk Services and Infrastructure Feasibility | Has the team obtained written confirmation or documented proof for ICT services - technical feasibility? | Current certificate/letter/report, version control and document-control entry. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
08.079 | 08 | WP08 | Bulk Services and Infrastructure Feasibility | Does the evidence for water supply - financial viability support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
08.080 | 08 | WP08 | Bulk Services and Infrastructure Feasibility | Have dependencies linked to sewer capacity - financial viability been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
08.081 | 08 | WP08 | Bulk Services and Infrastructure Feasibility | Has the project team confirmed stormwater discharge - financial viability in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
08.082 | 08 | WP08 | Bulk Services and Infrastructure Feasibility | Is there a responsible owner, due date and approval route for electrical capacity - financial viability? | Register entry, supporting drawing/report, approval note and updated risk item. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
08.083 | 08 | WP08 | Bulk Services and Infrastructure Feasibility | Has the gate file tested whether fire water - financial viability creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
08.084 | 08 | WP08 | Bulk Services and Infrastructure Feasibility | Are assumptions for ICT services - financial viability documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
08.085 | 08 | WP08 | Bulk Services and Infrastructure Feasibility | Has the relevant authority, specialist or professional adviser reviewed water supply - programme impact where required? | Authority response, compliance checklist, file note and management approval. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
08.086 | 08 | WP08 | Bulk Services and Infrastructure Feasibility | Is the decision record for sewer capacity - programme impact aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
08.087 | 08 | WP08 | Bulk Services and Infrastructure Feasibility | Have cost, programme and compliance implications of stormwater discharge - programme impact been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
08.088 | 08 | WP08 | Bulk Services and Infrastructure Feasibility | Has the team obtained written confirmation or documented proof for electrical capacity - programme impact? | Current certificate/letter/report, version control and document-control entry. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
08.089 | 08 | WP08 | Bulk Services and Infrastructure Feasibility | Does the evidence for fire water - programme impact support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
08.090 | 08 | WP08 | Bulk Services and Infrastructure Feasibility | Have dependencies linked to ICT services - programme impact been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
08.091 | 08 | WP08 | Bulk Services and Infrastructure Feasibility | Has the project team confirmed water supply - risk mitigation in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
08.092 | 08 | WP08 | Bulk Services and Infrastructure Feasibility | Is there a responsible owner, due date and approval route for sewer capacity - risk mitigation? | Register entry, supporting drawing/report, approval note and updated risk item. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
08.093 | 08 | WP08 | Bulk Services and Infrastructure Feasibility | Has the gate file tested whether stormwater discharge - risk mitigation creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
08.094 | 08 | WP08 | Bulk Services and Infrastructure Feasibility | Are assumptions for electrical capacity - risk mitigation documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
08.095 | 08 | WP08 | Bulk Services and Infrastructure Feasibility | Has the relevant authority, specialist or professional adviser reviewed fire water - risk mitigation where required? | Authority response, compliance checklist, file note and management approval. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
08.096 | 08 | WP08 | Bulk Services and Infrastructure Feasibility | Is the decision record for ICT services - risk mitigation aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
08.097 | 08 | WP08 | Bulk Services and Infrastructure Feasibility | Have cost, programme and compliance implications of water supply - stakeholder acceptance been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
08.098 | 08 | WP08 | Bulk Services and Infrastructure Feasibility | Has the team obtained written confirmation or documented proof for sewer capacity - stakeholder acceptance? | Current certificate/letter/report, version control and document-control entry. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
08.099 | 08 | WP08 | Bulk Services and Infrastructure Feasibility | Does the evidence for stormwater discharge - stakeholder acceptance support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
08.100 | 08 | WP08 | Bulk Services and Infrastructure Feasibility | Have dependencies linked to electrical capacity - stakeholder acceptance been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
09.001 | 09 | WP09 | Environmental Screening and Scoping | Has the project team confirmed NEMA triggers - governance approval in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | NEMA Act 107 of 1998; EIA Regulations, 2014; DFFE screening requirements | Yes / No / N/A + Score 0–5 + Rating
09.002 | 09 | WP09 | Environmental Screening and Scoping | Is there a responsible owner, due date and approval route for wetland sensitivity - governance approval? | Register entry, supporting drawing/report, approval note and updated risk item. | National Water Act 36 of 1998; biodiversity and wetland specialist guidance | Yes / No / N/A + Score 0–5 + Rating
09.003 | 09 | WP09 | Environmental Screening and Scoping | Has the gate file tested whether biodiversity risk - governance approval creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | NHRA Act 25 of 1999; public participation record; EMPr controls | Yes / No / N/A + Score 0–5 + Rating
09.004 | 09 | WP09 | Environmental Screening and Scoping | Are assumptions for heritage risk - governance approval documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | NEMA Act 107 of 1998; EIA Regulations, 2014; DFFE screening requirements | Yes / No / N/A + Score 0–5 + Rating
09.005 | 09 | WP09 | Environmental Screening and Scoping | Has the relevant authority, specialist or professional adviser reviewed groundwater risk - governance approval where required? | Authority response, compliance checklist, file note and management approval. | National Water Act 36 of 1998; biodiversity and wetland specialist guidance | Yes / No / N/A + Score 0–5 + Rating
09.006 | 09 | WP09 | Environmental Screening and Scoping | Is the decision record for noise sources - governance approval aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | NHRA Act 25 of 1999; public participation record; EMPr controls | Yes / No / N/A + Score 0–5 + Rating
09.007 | 09 | WP09 | Environmental Screening and Scoping | Have cost, programme and compliance implications of NEMA triggers - legal authority been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | NEMA Act 107 of 1998; EIA Regulations, 2014; DFFE screening requirements | Yes / No / N/A + Score 0–5 + Rating
09.008 | 09 | WP09 | Environmental Screening and Scoping | Has the team obtained written confirmation or documented proof for wetland sensitivity - legal authority? | Current certificate/letter/report, version control and document-control entry. | National Water Act 36 of 1998; biodiversity and wetland specialist guidance | Yes / No / N/A + Score 0–5 + Rating
09.009 | 09 | WP09 | Environmental Screening and Scoping | Does the evidence for biodiversity risk - legal authority support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | NHRA Act 25 of 1999; public participation record; EMPr controls | Yes / No / N/A + Score 0–5 + Rating
09.010 | 09 | WP09 | Environmental Screening and Scoping | Have dependencies linked to heritage risk - legal authority been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | NEMA Act 107 of 1998; EIA Regulations, 2014; DFFE screening requirements | Yes / No / N/A + Score 0–5 + Rating
09.011 | 09 | WP09 | Environmental Screening and Scoping | Has the project team confirmed groundwater risk - legal authority in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | National Water Act 36 of 1998; biodiversity and wetland specialist guidance | Yes / No / N/A + Score 0–5 + Rating
09.012 | 09 | WP09 | Environmental Screening and Scoping | Is there a responsible owner, due date and approval route for noise sources - legal authority? | Register entry, supporting drawing/report, approval note and updated risk item. | NHRA Act 25 of 1999; public participation record; EMPr controls | Yes / No / N/A + Score 0–5 + Rating
09.013 | 09 | WP09 | Environmental Screening and Scoping | Has the gate file tested whether NEMA triggers - technical feasibility creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | NEMA Act 107 of 1998; EIA Regulations, 2014; DFFE screening requirements | Yes / No / N/A + Score 0–5 + Rating
09.014 | 09 | WP09 | Environmental Screening and Scoping | Are assumptions for wetland sensitivity - technical feasibility documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | National Water Act 36 of 1998; biodiversity and wetland specialist guidance | Yes / No / N/A + Score 0–5 + Rating
09.015 | 09 | WP09 | Environmental Screening and Scoping | Has the relevant authority, specialist or professional adviser reviewed biodiversity risk - technical feasibility where required? | Authority response, compliance checklist, file note and management approval. | NHRA Act 25 of 1999; public participation record; EMPr controls | Yes / No / N/A + Score 0–5 + Rating
09.016 | 09 | WP09 | Environmental Screening and Scoping | Is the decision record for heritage risk - technical feasibility aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | NEMA Act 107 of 1998; EIA Regulations, 2014; DFFE screening requirements | Yes / No / N/A + Score 0–5 + Rating
09.017 | 09 | WP09 | Environmental Screening and Scoping | Have cost, programme and compliance implications of groundwater risk - technical feasibility been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | National Water Act 36 of 1998; biodiversity and wetland specialist guidance | Yes / No / N/A + Score 0–5 + Rating
09.018 | 09 | WP09 | Environmental Screening and Scoping | Has the team obtained written confirmation or documented proof for noise sources - technical feasibility? | Current certificate/letter/report, version control and document-control entry. | NHRA Act 25 of 1999; public participation record; EMPr controls | Yes / No / N/A + Score 0–5 + Rating
09.019 | 09 | WP09 | Environmental Screening and Scoping | Does the evidence for NEMA triggers - financial viability support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | NEMA Act 107 of 1998; EIA Regulations, 2014; DFFE screening requirements | Yes / No / N/A + Score 0–5 + Rating
09.020 | 09 | WP09 | Environmental Screening and Scoping | Have dependencies linked to wetland sensitivity - financial viability been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | National Water Act 36 of 1998; biodiversity and wetland specialist guidance | Yes / No / N/A + Score 0–5 + Rating
09.021 | 09 | WP09 | Environmental Screening and Scoping | Has the project team confirmed biodiversity risk - financial viability in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | NHRA Act 25 of 1999; public participation record; EMPr controls | Yes / No / N/A + Score 0–5 + Rating
09.022 | 09 | WP09 | Environmental Screening and Scoping | Is there a responsible owner, due date and approval route for heritage risk - financial viability? | Register entry, supporting drawing/report, approval note and updated risk item. | NEMA Act 107 of 1998; EIA Regulations, 2014; DFFE screening requirements | Yes / No / N/A + Score 0–5 + Rating
09.023 | 09 | WP09 | Environmental Screening and Scoping | Has the gate file tested whether groundwater risk - financial viability creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | National Water Act 36 of 1998; biodiversity and wetland specialist guidance | Yes / No / N/A + Score 0–5 + Rating
09.024 | 09 | WP09 | Environmental Screening and Scoping | Are assumptions for noise sources - financial viability documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | NHRA Act 25 of 1999; public participation record; EMPr controls | Yes / No / N/A + Score 0–5 + Rating
09.025 | 09 | WP09 | Environmental Screening and Scoping | Has the relevant authority, specialist or professional adviser reviewed NEMA triggers - programme impact where required? | Authority response, compliance checklist, file note and management approval. | NEMA Act 107 of 1998; EIA Regulations, 2014; DFFE screening requirements | Yes / No / N/A + Score 0–5 + Rating
09.026 | 09 | WP09 | Environmental Screening and Scoping | Is the decision record for wetland sensitivity - programme impact aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | National Water Act 36 of 1998; biodiversity and wetland specialist guidance | Yes / No / N/A + Score 0–5 + Rating
09.027 | 09 | WP09 | Environmental Screening and Scoping | Have cost, programme and compliance implications of biodiversity risk - programme impact been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | NHRA Act 25 of 1999; public participation record; EMPr controls | Yes / No / N/A + Score 0–5 + Rating
09.028 | 09 | WP09 | Environmental Screening and Scoping | Has the team obtained written confirmation or documented proof for heritage risk - programme impact? | Current certificate/letter/report, version control and document-control entry. | NEMA Act 107 of 1998; EIA Regulations, 2014; DFFE screening requirements | Yes / No / N/A + Score 0–5 + Rating
09.029 | 09 | WP09 | Environmental Screening and Scoping | Does the evidence for groundwater risk - programme impact support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | National Water Act 36 of 1998; biodiversity and wetland specialist guidance | Yes / No / N/A + Score 0–5 + Rating
09.030 | 09 | WP09 | Environmental Screening and Scoping | Have dependencies linked to noise sources - programme impact been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | NHRA Act 25 of 1999; public participation record; EMPr controls | Yes / No / N/A + Score 0–5 + Rating
09.031 | 09 | WP09 | Environmental Screening and Scoping | Has the project team confirmed NEMA triggers - risk mitigation in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | NEMA Act 107 of 1998; EIA Regulations, 2014; DFFE screening requirements | Yes / No / N/A + Score 0–5 + Rating
09.032 | 09 | WP09 | Environmental Screening and Scoping | Is there a responsible owner, due date and approval route for wetland sensitivity - risk mitigation? | Register entry, supporting drawing/report, approval note and updated risk item. | National Water Act 36 of 1998; biodiversity and wetland specialist guidance | Yes / No / N/A + Score 0–5 + Rating
09.033 | 09 | WP09 | Environmental Screening and Scoping | Has the gate file tested whether biodiversity risk - risk mitigation creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | NHRA Act 25 of 1999; public participation record; EMPr controls | Yes / No / N/A + Score 0–5 + Rating
09.034 | 09 | WP09 | Environmental Screening and Scoping | Are assumptions for heritage risk - risk mitigation documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | NEMA Act 107 of 1998; EIA Regulations, 2014; DFFE screening requirements | Yes / No / N/A + Score 0–5 + Rating
09.035 | 09 | WP09 | Environmental Screening and Scoping | Has the relevant authority, specialist or professional adviser reviewed groundwater risk - risk mitigation where required? | Authority response, compliance checklist, file note and management approval. | National Water Act 36 of 1998; biodiversity and wetland specialist guidance | Yes / No / N/A + Score 0–5 + Rating
09.036 | 09 | WP09 | Environmental Screening and Scoping | Is the decision record for noise sources - risk mitigation aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | NHRA Act 25 of 1999; public participation record; EMPr controls | Yes / No / N/A + Score 0–5 + Rating
09.037 | 09 | WP09 | Environmental Screening and Scoping | Have cost, programme and compliance implications of NEMA triggers - stakeholder acceptance been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | NEMA Act 107 of 1998; EIA Regulations, 2014; DFFE screening requirements | Yes / No / N/A + Score 0–5 + Rating
09.038 | 09 | WP09 | Environmental Screening and Scoping | Has the team obtained written confirmation or documented proof for wetland sensitivity - stakeholder acceptance? | Current certificate/letter/report, version control and document-control entry. | National Water Act 36 of 1998; biodiversity and wetland specialist guidance | Yes / No / N/A + Score 0–5 + Rating
09.039 | 09 | WP09 | Environmental Screening and Scoping | Does the evidence for biodiversity risk - stakeholder acceptance support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | NHRA Act 25 of 1999; public participation record; EMPr controls | Yes / No / N/A + Score 0–5 + Rating
09.040 | 09 | WP09 | Environmental Screening and Scoping | Have dependencies linked to heritage risk - stakeholder acceptance been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | NEMA Act 107 of 1998; EIA Regulations, 2014; DFFE screening requirements | Yes / No / N/A + Score 0–5 + Rating
09.041 | 09 | WP09 | Environmental Screening and Scoping | Has the project team confirmed groundwater risk - stakeholder acceptance in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | National Water Act 36 of 1998; biodiversity and wetland specialist guidance | Yes / No / N/A + Score 0–5 + Rating
09.042 | 09 | WP09 | Environmental Screening and Scoping | Is there a responsible owner, due date and approval route for noise sources - stakeholder acceptance? | Register entry, supporting drawing/report, approval note and updated risk item. | NHRA Act 25 of 1999; public participation record; EMPr controls | Yes / No / N/A + Score 0–5 + Rating
09.043 | 09 | WP09 | Environmental Screening and Scoping | Has the gate file tested whether NEMA triggers - document control creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | NEMA Act 107 of 1998; EIA Regulations, 2014; DFFE screening requirements | Yes / No / N/A + Score 0–5 + Rating
09.044 | 09 | WP09 | Environmental Screening and Scoping | Are assumptions for wetland sensitivity - document control documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | National Water Act 36 of 1998; biodiversity and wetland specialist guidance | Yes / No / N/A + Score 0–5 + Rating
09.045 | 09 | WP09 | Environmental Screening and Scoping | Has the relevant authority, specialist or professional adviser reviewed biodiversity risk - document control where required? | Authority response, compliance checklist, file note and management approval. | NHRA Act 25 of 1999; public participation record; EMPr controls | Yes / No / N/A + Score 0–5 + Rating
09.046 | 09 | WP09 | Environmental Screening and Scoping | Is the decision record for heritage risk - document control aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | NEMA Act 107 of 1998; EIA Regulations, 2014; DFFE screening requirements | Yes / No / N/A + Score 0–5 + Rating
09.047 | 09 | WP09 | Environmental Screening and Scoping | Have cost, programme and compliance implications of groundwater risk - document control been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | National Water Act 36 of 1998; biodiversity and wetland specialist guidance | Yes / No / N/A + Score 0–5 + Rating
09.048 | 09 | WP09 | Environmental Screening and Scoping | Has the team obtained written confirmation or documented proof for noise sources - document control? | Current certificate/letter/report, version control and document-control entry. | NHRA Act 25 of 1999; public participation record; EMPr controls | Yes / No / N/A + Score 0–5 + Rating
09.049 | 09 | WP09 | Environmental Screening and Scoping | Does the evidence for NEMA triggers - professional certification support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | NEMA Act 107 of 1998; EIA Regulations, 2014; DFFE screening requirements | Yes / No / N/A + Score 0–5 + Rating
09.050 | 09 | WP09 | Environmental Screening and Scoping | Have dependencies linked to wetland sensitivity - professional certification been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | National Water Act 36 of 1998; biodiversity and wetland specialist guidance | Yes / No / N/A + Score 0–5 + Rating
09.051 | 09 | WP09 | Environmental Screening and Scoping | Has the project team confirmed biodiversity risk - professional certification in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | NHRA Act 25 of 1999; public participation record; EMPr controls | Yes / No / N/A + Score 0–5 + Rating
09.052 | 09 | WP09 | Environmental Screening and Scoping | Is there a responsible owner, due date and approval route for heritage risk - professional certification? | Register entry, supporting drawing/report, approval note and updated risk item. | NEMA Act 107 of 1998; EIA Regulations, 2014; DFFE screening requirements | Yes / No / N/A + Score 0–5 + Rating
09.053 | 09 | WP09 | Environmental Screening and Scoping | Has the gate file tested whether groundwater risk - professional certification creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | National Water Act 36 of 1998; biodiversity and wetland specialist guidance | Yes / No / N/A + Score 0–5 + Rating
09.054 | 09 | WP09 | Environmental Screening and Scoping | Are assumptions for noise sources - professional certification documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | NHRA Act 25 of 1999; public participation record; EMPr controls | Yes / No / N/A + Score 0–5 + Rating
09.055 | 09 | WP09 | Environmental Screening and Scoping | Has the relevant authority, specialist or professional adviser reviewed NEMA triggers - implementation readiness where required? | Authority response, compliance checklist, file note and management approval. | NEMA Act 107 of 1998; EIA Regulations, 2014; DFFE screening requirements | Yes / No / N/A + Score 0–5 + Rating
09.056 | 09 | WP09 | Environmental Screening and Scoping | Is the decision record for wetland sensitivity - implementation readiness aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | National Water Act 36 of 1998; biodiversity and wetland specialist guidance | Yes / No / N/A + Score 0–5 + Rating
09.057 | 09 | WP09 | Environmental Screening and Scoping | Have cost, programme and compliance implications of biodiversity risk - implementation readiness been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | NHRA Act 25 of 1999; public participation record; EMPr controls | Yes / No / N/A + Score 0–5 + Rating
09.058 | 09 | WP09 | Environmental Screening and Scoping | Has the team obtained written confirmation or documented proof for heritage risk - implementation readiness? | Current certificate/letter/report, version control and document-control entry. | NEMA Act 107 of 1998; EIA Regulations, 2014; DFFE screening requirements | Yes / No / N/A + Score 0–5 + Rating
09.059 | 09 | WP09 | Environmental Screening and Scoping | Does the evidence for groundwater risk - implementation readiness support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | National Water Act 36 of 1998; biodiversity and wetland specialist guidance | Yes / No / N/A + Score 0–5 + Rating
09.060 | 09 | WP09 | Environmental Screening and Scoping | Have dependencies linked to noise sources - implementation readiness been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | NHRA Act 25 of 1999; public participation record; EMPr controls | Yes / No / N/A + Score 0–5 + Rating
09.061 | 09 | WP09 | Environmental Screening and Scoping | Has the project team confirmed NEMA triggers - governance approval in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | NEMA Act 107 of 1998; EIA Regulations, 2014; DFFE screening requirements | Yes / No / N/A + Score 0–5 + Rating
09.062 | 09 | WP09 | Environmental Screening and Scoping | Is there a responsible owner, due date and approval route for wetland sensitivity - governance approval? | Register entry, supporting drawing/report, approval note and updated risk item. | National Water Act 36 of 1998; biodiversity and wetland specialist guidance | Yes / No / N/A + Score 0–5 + Rating
09.063 | 09 | WP09 | Environmental Screening and Scoping | Has the gate file tested whether biodiversity risk - governance approval creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | NHRA Act 25 of 1999; public participation record; EMPr controls | Yes / No / N/A + Score 0–5 + Rating
09.064 | 09 | WP09 | Environmental Screening and Scoping | Are assumptions for heritage risk - governance approval documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | NEMA Act 107 of 1998; EIA Regulations, 2014; DFFE screening requirements | Yes / No / N/A + Score 0–5 + Rating
09.065 | 09 | WP09 | Environmental Screening and Scoping | Has the relevant authority, specialist or professional adviser reviewed groundwater risk - governance approval where required? | Authority response, compliance checklist, file note and management approval. | National Water Act 36 of 1998; biodiversity and wetland specialist guidance | Yes / No / N/A + Score 0–5 + Rating
09.066 | 09 | WP09 | Environmental Screening and Scoping | Is the decision record for noise sources - governance approval aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | NHRA Act 25 of 1999; public participation record; EMPr controls | Yes / No / N/A + Score 0–5 + Rating
09.067 | 09 | WP09 | Environmental Screening and Scoping | Have cost, programme and compliance implications of NEMA triggers - legal authority been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | NEMA Act 107 of 1998; EIA Regulations, 2014; DFFE screening requirements | Yes / No / N/A + Score 0–5 + Rating
09.068 | 09 | WP09 | Environmental Screening and Scoping | Has the team obtained written confirmation or documented proof for wetland sensitivity - legal authority? | Current certificate/letter/report, version control and document-control entry. | National Water Act 36 of 1998; biodiversity and wetland specialist guidance | Yes / No / N/A + Score 0–5 + Rating
09.069 | 09 | WP09 | Environmental Screening and Scoping | Does the evidence for biodiversity risk - legal authority support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | NHRA Act 25 of 1999; public participation record; EMPr controls | Yes / No / N/A + Score 0–5 + Rating
09.070 | 09 | WP09 | Environmental Screening and Scoping | Have dependencies linked to heritage risk - legal authority been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | NEMA Act 107 of 1998; EIA Regulations, 2014; DFFE screening requirements | Yes / No / N/A + Score 0–5 + Rating
09.071 | 09 | WP09 | Environmental Screening and Scoping | Has the project team confirmed groundwater risk - legal authority in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | National Water Act 36 of 1998; biodiversity and wetland specialist guidance | Yes / No / N/A + Score 0–5 + Rating
09.072 | 09 | WP09 | Environmental Screening and Scoping | Is there a responsible owner, due date and approval route for noise sources - legal authority? | Register entry, supporting drawing/report, approval note and updated risk item. | NHRA Act 25 of 1999; public participation record; EMPr controls | Yes / No / N/A + Score 0–5 + Rating
09.073 | 09 | WP09 | Environmental Screening and Scoping | Has the gate file tested whether NEMA triggers - technical feasibility creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | NEMA Act 107 of 1998; EIA Regulations, 2014; DFFE screening requirements | Yes / No / N/A + Score 0–5 + Rating
09.074 | 09 | WP09 | Environmental Screening and Scoping | Are assumptions for wetland sensitivity - technical feasibility documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | National Water Act 36 of 1998; biodiversity and wetland specialist guidance | Yes / No / N/A + Score 0–5 + Rating
09.075 | 09 | WP09 | Environmental Screening and Scoping | Has the relevant authority, specialist or professional adviser reviewed biodiversity risk - technical feasibility where required? | Authority response, compliance checklist, file note and management approval. | NHRA Act 25 of 1999; public participation record; EMPr controls | Yes / No / N/A + Score 0–5 + Rating
09.076 | 09 | WP09 | Environmental Screening and Scoping | Is the decision record for heritage risk - technical feasibility aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | NEMA Act 107 of 1998; EIA Regulations, 2014; DFFE screening requirements | Yes / No / N/A + Score 0–5 + Rating
09.077 | 09 | WP09 | Environmental Screening and Scoping | Have cost, programme and compliance implications of groundwater risk - technical feasibility been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | National Water Act 36 of 1998; biodiversity and wetland specialist guidance | Yes / No / N/A + Score 0–5 + Rating
09.078 | 09 | WP09 | Environmental Screening and Scoping | Has the team obtained written confirmation or documented proof for noise sources - technical feasibility? | Current certificate/letter/report, version control and document-control entry. | NHRA Act 25 of 1999; public participation record; EMPr controls | Yes / No / N/A + Score 0–5 + Rating
09.079 | 09 | WP09 | Environmental Screening and Scoping | Does the evidence for NEMA triggers - financial viability support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | NEMA Act 107 of 1998; EIA Regulations, 2014; DFFE screening requirements | Yes / No / N/A + Score 0–5 + Rating
09.080 | 09 | WP09 | Environmental Screening and Scoping | Have dependencies linked to wetland sensitivity - financial viability been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | National Water Act 36 of 1998; biodiversity and wetland specialist guidance | Yes / No / N/A + Score 0–5 + Rating
09.081 | 09 | WP09 | Environmental Screening and Scoping | Has the project team confirmed biodiversity risk - financial viability in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | NHRA Act 25 of 1999; public participation record; EMPr controls | Yes / No / N/A + Score 0–5 + Rating
09.082 | 09 | WP09 | Environmental Screening and Scoping | Is there a responsible owner, due date and approval route for heritage risk - financial viability? | Register entry, supporting drawing/report, approval note and updated risk item. | NEMA Act 107 of 1998; EIA Regulations, 2014; DFFE screening requirements | Yes / No / N/A + Score 0–5 + Rating
09.083 | 09 | WP09 | Environmental Screening and Scoping | Has the gate file tested whether groundwater risk - financial viability creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | National Water Act 36 of 1998; biodiversity and wetland specialist guidance | Yes / No / N/A + Score 0–5 + Rating
09.084 | 09 | WP09 | Environmental Screening and Scoping | Are assumptions for noise sources - financial viability documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | NHRA Act 25 of 1999; public participation record; EMPr controls | Yes / No / N/A + Score 0–5 + Rating
09.085 | 09 | WP09 | Environmental Screening and Scoping | Has the relevant authority, specialist or professional adviser reviewed NEMA triggers - programme impact where required? | Authority response, compliance checklist, file note and management approval. | NEMA Act 107 of 1998; EIA Regulations, 2014; DFFE screening requirements | Yes / No / N/A + Score 0–5 + Rating
09.086 | 09 | WP09 | Environmental Screening and Scoping | Is the decision record for wetland sensitivity - programme impact aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | National Water Act 36 of 1998; biodiversity and wetland specialist guidance | Yes / No / N/A + Score 0–5 + Rating
09.087 | 09 | WP09 | Environmental Screening and Scoping | Have cost, programme and compliance implications of biodiversity risk - programme impact been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | NHRA Act 25 of 1999; public participation record; EMPr controls | Yes / No / N/A + Score 0–5 + Rating
09.088 | 09 | WP09 | Environmental Screening and Scoping | Has the team obtained written confirmation or documented proof for heritage risk - programme impact? | Current certificate/letter/report, version control and document-control entry. | NEMA Act 107 of 1998; EIA Regulations, 2014; DFFE screening requirements | Yes / No / N/A + Score 0–5 + Rating
09.089 | 09 | WP09 | Environmental Screening and Scoping | Does the evidence for groundwater risk - programme impact support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | National Water Act 36 of 1998; biodiversity and wetland specialist guidance | Yes / No / N/A + Score 0–5 + Rating
09.090 | 09 | WP09 | Environmental Screening and Scoping | Have dependencies linked to noise sources - programme impact been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | NHRA Act 25 of 1999; public participation record; EMPr controls | Yes / No / N/A + Score 0–5 + Rating
09.091 | 09 | WP09 | Environmental Screening and Scoping | Has the project team confirmed NEMA triggers - risk mitigation in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | NEMA Act 107 of 1998; EIA Regulations, 2014; DFFE screening requirements | Yes / No / N/A + Score 0–5 + Rating
09.092 | 09 | WP09 | Environmental Screening and Scoping | Is there a responsible owner, due date and approval route for wetland sensitivity - risk mitigation? | Register entry, supporting drawing/report, approval note and updated risk item. | National Water Act 36 of 1998; biodiversity and wetland specialist guidance | Yes / No / N/A + Score 0–5 + Rating
09.093 | 09 | WP09 | Environmental Screening and Scoping | Has the gate file tested whether biodiversity risk - risk mitigation creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | NHRA Act 25 of 1999; public participation record; EMPr controls | Yes / No / N/A + Score 0–5 + Rating
09.094 | 09 | WP09 | Environmental Screening and Scoping | Are assumptions for heritage risk - risk mitigation documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | NEMA Act 107 of 1998; EIA Regulations, 2014; DFFE screening requirements | Yes / No / N/A + Score 0–5 + Rating
09.095 | 09 | WP09 | Environmental Screening and Scoping | Has the relevant authority, specialist or professional adviser reviewed groundwater risk - risk mitigation where required? | Authority response, compliance checklist, file note and management approval. | National Water Act 36 of 1998; biodiversity and wetland specialist guidance | Yes / No / N/A + Score 0–5 + Rating
09.096 | 09 | WP09 | Environmental Screening and Scoping | Is the decision record for noise sources - risk mitigation aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | NHRA Act 25 of 1999; public participation record; EMPr controls | Yes / No / N/A + Score 0–5 + Rating
09.097 | 09 | WP09 | Environmental Screening and Scoping | Have cost, programme and compliance implications of NEMA triggers - stakeholder acceptance been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | NEMA Act 107 of 1998; EIA Regulations, 2014; DFFE screening requirements | Yes / No / N/A + Score 0–5 + Rating
09.098 | 09 | WP09 | Environmental Screening and Scoping | Has the team obtained written confirmation or documented proof for wetland sensitivity - stakeholder acceptance? | Current certificate/letter/report, version control and document-control entry. | National Water Act 36 of 1998; biodiversity and wetland specialist guidance | Yes / No / N/A + Score 0–5 + Rating
09.099 | 09 | WP09 | Environmental Screening and Scoping | Does the evidence for biodiversity risk - stakeholder acceptance support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | NHRA Act 25 of 1999; public participation record; EMPr controls | Yes / No / N/A + Score 0–5 + Rating
09.100 | 09 | WP09 | Environmental Screening and Scoping | Have dependencies linked to heritage risk - stakeholder acceptance been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | NEMA Act 107 of 1998; EIA Regulations, 2014; DFFE screening requirements | Yes / No / N/A + Score 0–5 + Rating
10.001 | 10 | WP10 | Land Use Rights and Zoning | Has the project team confirmed current agricultural zoning - governance approval in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | SPLUMA Act 16 of 2013; municipal land use scheme; title deed/SG diagram | Yes / No / N/A + Score 0–5 + Rating
10.002 | 10 | WP10 | Land Use Rights and Zoning | Is there a responsible owner, due date and approval route for rezoning pathway - governance approval? | Register entry, supporting drawing/report, approval note and updated risk item. | Deeds Registries Act 47 of 1937; Surveyor-General records; servitude register | Yes / No / N/A + Score 0–5 + Rating
10.003 | 10 | WP10 | Land Use Rights and Zoning | Has the gate file tested whether consent use - governance approval creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | Municipal Planning By-law; wayleave requirements; landowner consent | Yes / No / N/A + Score 0–5 + Rating
10.004 | 10 | WP10 | Land Use Rights and Zoning | Are assumptions for site development plan - governance approval documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | SPLUMA Act 16 of 2013; municipal land use scheme; title deed/SG diagram | Yes / No / N/A + Score 0–5 + Rating
10.005 | 10 | WP10 | Land Use Rights and Zoning | Has the relevant authority, specialist or professional adviser reviewed parking compliance - governance approval where required? | Authority response, compliance checklist, file note and management approval. | Deeds Registries Act 47 of 1937; Surveyor-General records; servitude register | Yes / No / N/A + Score 0–5 + Rating
10.006 | 10 | WP10 | Land Use Rights and Zoning | Is the decision record for FAR and coverage - governance approval aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | Municipal Planning By-law; wayleave requirements; landowner consent | Yes / No / N/A + Score 0–5 + Rating
10.007 | 10 | WP10 | Land Use Rights and Zoning | Have cost, programme and compliance implications of current agricultural zoning - legal authority been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | SPLUMA Act 16 of 2013; municipal land use scheme; title deed/SG diagram | Yes / No / N/A + Score 0–5 + Rating
10.008 | 10 | WP10 | Land Use Rights and Zoning | Has the team obtained written confirmation or documented proof for rezoning pathway - legal authority? | Current certificate/letter/report, version control and document-control entry. | Deeds Registries Act 47 of 1937; Surveyor-General records; servitude register | Yes / No / N/A + Score 0–5 + Rating
10.009 | 10 | WP10 | Land Use Rights and Zoning | Does the evidence for consent use - legal authority support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | Municipal Planning By-law; wayleave requirements; landowner consent | Yes / No / N/A + Score 0–5 + Rating
10.010 | 10 | WP10 | Land Use Rights and Zoning | Have dependencies linked to site development plan - legal authority been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | SPLUMA Act 16 of 2013; municipal land use scheme; title deed/SG diagram | Yes / No / N/A + Score 0–5 + Rating
10.011 | 10 | WP10 | Land Use Rights and Zoning | Has the project team confirmed parking compliance - legal authority in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | Deeds Registries Act 47 of 1937; Surveyor-General records; servitude register | Yes / No / N/A + Score 0–5 + Rating
10.012 | 10 | WP10 | Land Use Rights and Zoning | Is there a responsible owner, due date and approval route for FAR and coverage - legal authority? | Register entry, supporting drawing/report, approval note and updated risk item. | Municipal Planning By-law; wayleave requirements; landowner consent | Yes / No / N/A + Score 0–5 + Rating
10.013 | 10 | WP10 | Land Use Rights and Zoning | Has the gate file tested whether current agricultural zoning - technical feasibility creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | SPLUMA Act 16 of 2013; municipal land use scheme; title deed/SG diagram | Yes / No / N/A + Score 0–5 + Rating
10.014 | 10 | WP10 | Land Use Rights and Zoning | Are assumptions for rezoning pathway - technical feasibility documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | Deeds Registries Act 47 of 1937; Surveyor-General records; servitude register | Yes / No / N/A + Score 0–5 + Rating
10.015 | 10 | WP10 | Land Use Rights and Zoning | Has the relevant authority, specialist or professional adviser reviewed consent use - technical feasibility where required? | Authority response, compliance checklist, file note and management approval. | Municipal Planning By-law; wayleave requirements; landowner consent | Yes / No / N/A + Score 0–5 + Rating
10.016 | 10 | WP10 | Land Use Rights and Zoning | Is the decision record for site development plan - technical feasibility aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | SPLUMA Act 16 of 2013; municipal land use scheme; title deed/SG diagram | Yes / No / N/A + Score 0–5 + Rating
10.017 | 10 | WP10 | Land Use Rights and Zoning | Have cost, programme and compliance implications of parking compliance - technical feasibility been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | Deeds Registries Act 47 of 1937; Surveyor-General records; servitude register | Yes / No / N/A + Score 0–5 + Rating
10.018 | 10 | WP10 | Land Use Rights and Zoning | Has the team obtained written confirmation or documented proof for FAR and coverage - technical feasibility? | Current certificate/letter/report, version control and document-control entry. | Municipal Planning By-law; wayleave requirements; landowner consent | Yes / No / N/A + Score 0–5 + Rating
10.019 | 10 | WP10 | Land Use Rights and Zoning | Does the evidence for current agricultural zoning - financial viability support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | SPLUMA Act 16 of 2013; municipal land use scheme; title deed/SG diagram | Yes / No / N/A + Score 0–5 + Rating
10.020 | 10 | WP10 | Land Use Rights and Zoning | Have dependencies linked to rezoning pathway - financial viability been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | Deeds Registries Act 47 of 1937; Surveyor-General records; servitude register | Yes / No / N/A + Score 0–5 + Rating
10.021 | 10 | WP10 | Land Use Rights and Zoning | Has the project team confirmed consent use - financial viability in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | Municipal Planning By-law; wayleave requirements; landowner consent | Yes / No / N/A + Score 0–5 + Rating
10.022 | 10 | WP10 | Land Use Rights and Zoning | Is there a responsible owner, due date and approval route for site development plan - financial viability? | Register entry, supporting drawing/report, approval note and updated risk item. | SPLUMA Act 16 of 2013; municipal land use scheme; title deed/SG diagram | Yes / No / N/A + Score 0–5 + Rating
10.023 | 10 | WP10 | Land Use Rights and Zoning | Has the gate file tested whether parking compliance - financial viability creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | Deeds Registries Act 47 of 1937; Surveyor-General records; servitude register | Yes / No / N/A + Score 0–5 + Rating
10.024 | 10 | WP10 | Land Use Rights and Zoning | Are assumptions for FAR and coverage - financial viability documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | Municipal Planning By-law; wayleave requirements; landowner consent | Yes / No / N/A + Score 0–5 + Rating
10.025 | 10 | WP10 | Land Use Rights and Zoning | Has the relevant authority, specialist or professional adviser reviewed current agricultural zoning - programme impact where required? | Authority response, compliance checklist, file note and management approval. | SPLUMA Act 16 of 2013; municipal land use scheme; title deed/SG diagram | Yes / No / N/A + Score 0–5 + Rating
10.026 | 10 | WP10 | Land Use Rights and Zoning | Is the decision record for rezoning pathway - programme impact aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | Deeds Registries Act 47 of 1937; Surveyor-General records; servitude register | Yes / No / N/A + Score 0–5 + Rating
10.027 | 10 | WP10 | Land Use Rights and Zoning | Have cost, programme and compliance implications of consent use - programme impact been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | Municipal Planning By-law; wayleave requirements; landowner consent | Yes / No / N/A + Score 0–5 + Rating
10.028 | 10 | WP10 | Land Use Rights and Zoning | Has the team obtained written confirmation or documented proof for site development plan - programme impact? | Current certificate/letter/report, version control and document-control entry. | SPLUMA Act 16 of 2013; municipal land use scheme; title deed/SG diagram | Yes / No / N/A + Score 0–5 + Rating
10.029 | 10 | WP10 | Land Use Rights and Zoning | Does the evidence for parking compliance - programme impact support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | Deeds Registries Act 47 of 1937; Surveyor-General records; servitude register | Yes / No / N/A + Score 0–5 + Rating
10.030 | 10 | WP10 | Land Use Rights and Zoning | Have dependencies linked to FAR and coverage - programme impact been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | Municipal Planning By-law; wayleave requirements; landowner consent | Yes / No / N/A + Score 0–5 + Rating
10.031 | 10 | WP10 | Land Use Rights and Zoning | Has the project team confirmed current agricultural zoning - risk mitigation in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | SPLUMA Act 16 of 2013; municipal land use scheme; title deed/SG diagram | Yes / No / N/A + Score 0–5 + Rating
10.032 | 10 | WP10 | Land Use Rights and Zoning | Is there a responsible owner, due date and approval route for rezoning pathway - risk mitigation? | Register entry, supporting drawing/report, approval note and updated risk item. | Deeds Registries Act 47 of 1937; Surveyor-General records; servitude register | Yes / No / N/A + Score 0–5 + Rating
10.033 | 10 | WP10 | Land Use Rights and Zoning | Has the gate file tested whether consent use - risk mitigation creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | Municipal Planning By-law; wayleave requirements; landowner consent | Yes / No / N/A + Score 0–5 + Rating
10.034 | 10 | WP10 | Land Use Rights and Zoning | Are assumptions for site development plan - risk mitigation documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | SPLUMA Act 16 of 2013; municipal land use scheme; title deed/SG diagram | Yes / No / N/A + Score 0–5 + Rating
10.035 | 10 | WP10 | Land Use Rights and Zoning | Has the relevant authority, specialist or professional adviser reviewed parking compliance - risk mitigation where required? | Authority response, compliance checklist, file note and management approval. | Deeds Registries Act 47 of 1937; Surveyor-General records; servitude register | Yes / No / N/A + Score 0–5 + Rating
10.036 | 10 | WP10 | Land Use Rights and Zoning | Is the decision record for FAR and coverage - risk mitigation aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | Municipal Planning By-law; wayleave requirements; landowner consent | Yes / No / N/A + Score 0–5 + Rating
10.037 | 10 | WP10 | Land Use Rights and Zoning | Have cost, programme and compliance implications of current agricultural zoning - stakeholder acceptance been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | SPLUMA Act 16 of 2013; municipal land use scheme; title deed/SG diagram | Yes / No / N/A + Score 0–5 + Rating
10.038 | 10 | WP10 | Land Use Rights and Zoning | Has the team obtained written confirmation or documented proof for rezoning pathway - stakeholder acceptance? | Current certificate/letter/report, version control and document-control entry. | Deeds Registries Act 47 of 1937; Surveyor-General records; servitude register | Yes / No / N/A + Score 0–5 + Rating
10.039 | 10 | WP10 | Land Use Rights and Zoning | Does the evidence for consent use - stakeholder acceptance support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | Municipal Planning By-law; wayleave requirements; landowner consent | Yes / No / N/A + Score 0–5 + Rating
10.040 | 10 | WP10 | Land Use Rights and Zoning | Have dependencies linked to site development plan - stakeholder acceptance been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | SPLUMA Act 16 of 2013; municipal land use scheme; title deed/SG diagram | Yes / No / N/A + Score 0–5 + Rating
10.041 | 10 | WP10 | Land Use Rights and Zoning | Has the project team confirmed parking compliance - stakeholder acceptance in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | Deeds Registries Act 47 of 1937; Surveyor-General records; servitude register | Yes / No / N/A + Score 0–5 + Rating
10.042 | 10 | WP10 | Land Use Rights and Zoning | Is there a responsible owner, due date and approval route for FAR and coverage - stakeholder acceptance? | Register entry, supporting drawing/report, approval note and updated risk item. | Municipal Planning By-law; wayleave requirements; landowner consent | Yes / No / N/A + Score 0–5 + Rating
10.043 | 10 | WP10 | Land Use Rights and Zoning | Has the gate file tested whether current agricultural zoning - document control creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | SPLUMA Act 16 of 2013; municipal land use scheme; title deed/SG diagram | Yes / No / N/A + Score 0–5 + Rating
10.044 | 10 | WP10 | Land Use Rights and Zoning | Are assumptions for rezoning pathway - document control documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | Deeds Registries Act 47 of 1937; Surveyor-General records; servitude register | Yes / No / N/A + Score 0–5 + Rating
10.045 | 10 | WP10 | Land Use Rights and Zoning | Has the relevant authority, specialist or professional adviser reviewed consent use - document control where required? | Authority response, compliance checklist, file note and management approval. | Municipal Planning By-law; wayleave requirements; landowner consent | Yes / No / N/A + Score 0–5 + Rating
10.046 | 10 | WP10 | Land Use Rights and Zoning | Is the decision record for site development plan - document control aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | SPLUMA Act 16 of 2013; municipal land use scheme; title deed/SG diagram | Yes / No / N/A + Score 0–5 + Rating
10.047 | 10 | WP10 | Land Use Rights and Zoning | Have cost, programme and compliance implications of parking compliance - document control been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | Deeds Registries Act 47 of 1937; Surveyor-General records; servitude register | Yes / No / N/A + Score 0–5 + Rating
10.048 | 10 | WP10 | Land Use Rights and Zoning | Has the team obtained written confirmation or documented proof for FAR and coverage - document control? | Current certificate/letter/report, version control and document-control entry. | Municipal Planning By-law; wayleave requirements; landowner consent | Yes / No / N/A + Score 0–5 + Rating
10.049 | 10 | WP10 | Land Use Rights and Zoning | Does the evidence for current agricultural zoning - professional certification support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | SPLUMA Act 16 of 2013; municipal land use scheme; title deed/SG diagram | Yes / No / N/A + Score 0–5 + Rating
10.050 | 10 | WP10 | Land Use Rights and Zoning | Have dependencies linked to rezoning pathway - professional certification been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | Deeds Registries Act 47 of 1937; Surveyor-General records; servitude register | Yes / No / N/A + Score 0–5 + Rating
10.051 | 10 | WP10 | Land Use Rights and Zoning | Has the project team confirmed consent use - professional certification in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | Municipal Planning By-law; wayleave requirements; landowner consent | Yes / No / N/A + Score 0–5 + Rating
10.052 | 10 | WP10 | Land Use Rights and Zoning | Is there a responsible owner, due date and approval route for site development plan - professional certification? | Register entry, supporting drawing/report, approval note and updated risk item. | SPLUMA Act 16 of 2013; municipal land use scheme; title deed/SG diagram | Yes / No / N/A + Score 0–5 + Rating
10.053 | 10 | WP10 | Land Use Rights and Zoning | Has the gate file tested whether parking compliance - professional certification creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | Deeds Registries Act 47 of 1937; Surveyor-General records; servitude register | Yes / No / N/A + Score 0–5 + Rating
10.054 | 10 | WP10 | Land Use Rights and Zoning | Are assumptions for FAR and coverage - professional certification documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | Municipal Planning By-law; wayleave requirements; landowner consent | Yes / No / N/A + Score 0–5 + Rating
10.055 | 10 | WP10 | Land Use Rights and Zoning | Has the relevant authority, specialist or professional adviser reviewed current agricultural zoning - implementation readiness where required? | Authority response, compliance checklist, file note and management approval. | SPLUMA Act 16 of 2013; municipal land use scheme; title deed/SG diagram | Yes / No / N/A + Score 0–5 + Rating
10.056 | 10 | WP10 | Land Use Rights and Zoning | Is the decision record for rezoning pathway - implementation readiness aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | Deeds Registries Act 47 of 1937; Surveyor-General records; servitude register | Yes / No / N/A + Score 0–5 + Rating
10.057 | 10 | WP10 | Land Use Rights and Zoning | Have cost, programme and compliance implications of consent use - implementation readiness been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | Municipal Planning By-law; wayleave requirements; landowner consent | Yes / No / N/A + Score 0–5 + Rating
10.058 | 10 | WP10 | Land Use Rights and Zoning | Has the team obtained written confirmation or documented proof for site development plan - implementation readiness? | Current certificate/letter/report, version control and document-control entry. | SPLUMA Act 16 of 2013; municipal land use scheme; title deed/SG diagram | Yes / No / N/A + Score 0–5 + Rating
10.059 | 10 | WP10 | Land Use Rights and Zoning | Does the evidence for parking compliance - implementation readiness support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | Deeds Registries Act 47 of 1937; Surveyor-General records; servitude register | Yes / No / N/A + Score 0–5 + Rating
10.060 | 10 | WP10 | Land Use Rights and Zoning | Have dependencies linked to FAR and coverage - implementation readiness been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | Municipal Planning By-law; wayleave requirements; landowner consent | Yes / No / N/A + Score 0–5 + Rating
10.061 | 10 | WP10 | Land Use Rights and Zoning | Has the project team confirmed current agricultural zoning - governance approval in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | SPLUMA Act 16 of 2013; municipal land use scheme; title deed/SG diagram | Yes / No / N/A + Score 0–5 + Rating
10.062 | 10 | WP10 | Land Use Rights and Zoning | Is there a responsible owner, due date and approval route for rezoning pathway - governance approval? | Register entry, supporting drawing/report, approval note and updated risk item. | Deeds Registries Act 47 of 1937; Surveyor-General records; servitude register | Yes / No / N/A + Score 0–5 + Rating
10.063 | 10 | WP10 | Land Use Rights and Zoning | Has the gate file tested whether consent use - governance approval creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | Municipal Planning By-law; wayleave requirements; landowner consent | Yes / No / N/A + Score 0–5 + Rating
10.064 | 10 | WP10 | Land Use Rights and Zoning | Are assumptions for site development plan - governance approval documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | SPLUMA Act 16 of 2013; municipal land use scheme; title deed/SG diagram | Yes / No / N/A + Score 0–5 + Rating
10.065 | 10 | WP10 | Land Use Rights and Zoning | Has the relevant authority, specialist or professional adviser reviewed parking compliance - governance approval where required? | Authority response, compliance checklist, file note and management approval. | Deeds Registries Act 47 of 1937; Surveyor-General records; servitude register | Yes / No / N/A + Score 0–5 + Rating
10.066 | 10 | WP10 | Land Use Rights and Zoning | Is the decision record for FAR and coverage - governance approval aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | Municipal Planning By-law; wayleave requirements; landowner consent | Yes / No / N/A + Score 0–5 + Rating
10.067 | 10 | WP10 | Land Use Rights and Zoning | Have cost, programme and compliance implications of current agricultural zoning - legal authority been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | SPLUMA Act 16 of 2013; municipal land use scheme; title deed/SG diagram | Yes / No / N/A + Score 0–5 + Rating
10.068 | 10 | WP10 | Land Use Rights and Zoning | Has the team obtained written confirmation or documented proof for rezoning pathway - legal authority? | Current certificate/letter/report, version control and document-control entry. | Deeds Registries Act 47 of 1937; Surveyor-General records; servitude register | Yes / No / N/A + Score 0–5 + Rating
10.069 | 10 | WP10 | Land Use Rights and Zoning | Does the evidence for consent use - legal authority support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | Municipal Planning By-law; wayleave requirements; landowner consent | Yes / No / N/A + Score 0–5 + Rating
10.070 | 10 | WP10 | Land Use Rights and Zoning | Have dependencies linked to site development plan - legal authority been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | SPLUMA Act 16 of 2013; municipal land use scheme; title deed/SG diagram | Yes / No / N/A + Score 0–5 + Rating
10.071 | 10 | WP10 | Land Use Rights and Zoning | Has the project team confirmed parking compliance - legal authority in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | Deeds Registries Act 47 of 1937; Surveyor-General records; servitude register | Yes / No / N/A + Score 0–5 + Rating
10.072 | 10 | WP10 | Land Use Rights and Zoning | Is there a responsible owner, due date and approval route for FAR and coverage - legal authority? | Register entry, supporting drawing/report, approval note and updated risk item. | Municipal Planning By-law; wayleave requirements; landowner consent | Yes / No / N/A + Score 0–5 + Rating
10.073 | 10 | WP10 | Land Use Rights and Zoning | Has the gate file tested whether current agricultural zoning - technical feasibility creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | SPLUMA Act 16 of 2013; municipal land use scheme; title deed/SG diagram | Yes / No / N/A + Score 0–5 + Rating
10.074 | 10 | WP10 | Land Use Rights and Zoning | Are assumptions for rezoning pathway - technical feasibility documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | Deeds Registries Act 47 of 1937; Surveyor-General records; servitude register | Yes / No / N/A + Score 0–5 + Rating
10.075 | 10 | WP10 | Land Use Rights and Zoning | Has the relevant authority, specialist or professional adviser reviewed consent use - technical feasibility where required? | Authority response, compliance checklist, file note and management approval. | Municipal Planning By-law; wayleave requirements; landowner consent | Yes / No / N/A + Score 0–5 + Rating
10.076 | 10 | WP10 | Land Use Rights and Zoning | Is the decision record for site development plan - technical feasibility aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | SPLUMA Act 16 of 2013; municipal land use scheme; title deed/SG diagram | Yes / No / N/A + Score 0–5 + Rating
10.077 | 10 | WP10 | Land Use Rights and Zoning | Have cost, programme and compliance implications of parking compliance - technical feasibility been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | Deeds Registries Act 47 of 1937; Surveyor-General records; servitude register | Yes / No / N/A + Score 0–5 + Rating
10.078 | 10 | WP10 | Land Use Rights and Zoning | Has the team obtained written confirmation or documented proof for FAR and coverage - technical feasibility? | Current certificate/letter/report, version control and document-control entry. | Municipal Planning By-law; wayleave requirements; landowner consent | Yes / No / N/A + Score 0–5 + Rating
10.079 | 10 | WP10 | Land Use Rights and Zoning | Does the evidence for current agricultural zoning - financial viability support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | SPLUMA Act 16 of 2013; municipal land use scheme; title deed/SG diagram | Yes / No / N/A + Score 0–5 + Rating
10.080 | 10 | WP10 | Land Use Rights and Zoning | Have dependencies linked to rezoning pathway - financial viability been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | Deeds Registries Act 47 of 1937; Surveyor-General records; servitude register | Yes / No / N/A + Score 0–5 + Rating
10.081 | 10 | WP10 | Land Use Rights and Zoning | Has the project team confirmed consent use - financial viability in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | Municipal Planning By-law; wayleave requirements; landowner consent | Yes / No / N/A + Score 0–5 + Rating
10.082 | 10 | WP10 | Land Use Rights and Zoning | Is there a responsible owner, due date and approval route for site development plan - financial viability? | Register entry, supporting drawing/report, approval note and updated risk item. | SPLUMA Act 16 of 2013; municipal land use scheme; title deed/SG diagram | Yes / No / N/A + Score 0–5 + Rating
10.083 | 10 | WP10 | Land Use Rights and Zoning | Has the gate file tested whether parking compliance - financial viability creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | Deeds Registries Act 47 of 1937; Surveyor-General records; servitude register | Yes / No / N/A + Score 0–5 + Rating
10.084 | 10 | WP10 | Land Use Rights and Zoning | Are assumptions for FAR and coverage - financial viability documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | Municipal Planning By-law; wayleave requirements; landowner consent | Yes / No / N/A + Score 0–5 + Rating
10.085 | 10 | WP10 | Land Use Rights and Zoning | Has the relevant authority, specialist or professional adviser reviewed current agricultural zoning - programme impact where required? | Authority response, compliance checklist, file note and management approval. | SPLUMA Act 16 of 2013; municipal land use scheme; title deed/SG diagram | Yes / No / N/A + Score 0–5 + Rating
10.086 | 10 | WP10 | Land Use Rights and Zoning | Is the decision record for rezoning pathway - programme impact aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | Deeds Registries Act 47 of 1937; Surveyor-General records; servitude register | Yes / No / N/A + Score 0–5 + Rating
10.087 | 10 | WP10 | Land Use Rights and Zoning | Have cost, programme and compliance implications of consent use - programme impact been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | Municipal Planning By-law; wayleave requirements; landowner consent | Yes / No / N/A + Score 0–5 + Rating
10.088 | 10 | WP10 | Land Use Rights and Zoning | Has the team obtained written confirmation or documented proof for site development plan - programme impact? | Current certificate/letter/report, version control and document-control entry. | SPLUMA Act 16 of 2013; municipal land use scheme; title deed/SG diagram | Yes / No / N/A + Score 0–5 + Rating
10.089 | 10 | WP10 | Land Use Rights and Zoning | Does the evidence for parking compliance - programme impact support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | Deeds Registries Act 47 of 1937; Surveyor-General records; servitude register | Yes / No / N/A + Score 0–5 + Rating
10.090 | 10 | WP10 | Land Use Rights and Zoning | Have dependencies linked to FAR and coverage - programme impact been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | Municipal Planning By-law; wayleave requirements; landowner consent | Yes / No / N/A + Score 0–5 + Rating
10.091 | 10 | WP10 | Land Use Rights and Zoning | Has the project team confirmed current agricultural zoning - risk mitigation in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | SPLUMA Act 16 of 2013; municipal land use scheme; title deed/SG diagram | Yes / No / N/A + Score 0–5 + Rating
10.092 | 10 | WP10 | Land Use Rights and Zoning | Is there a responsible owner, due date and approval route for rezoning pathway - risk mitigation? | Register entry, supporting drawing/report, approval note and updated risk item. | Deeds Registries Act 47 of 1937; Surveyor-General records; servitude register | Yes / No / N/A + Score 0–5 + Rating
10.093 | 10 | WP10 | Land Use Rights and Zoning | Has the gate file tested whether consent use - risk mitigation creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | Municipal Planning By-law; wayleave requirements; landowner consent | Yes / No / N/A + Score 0–5 + Rating
10.094 | 10 | WP10 | Land Use Rights and Zoning | Are assumptions for site development plan - risk mitigation documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | SPLUMA Act 16 of 2013; municipal land use scheme; title deed/SG diagram | Yes / No / N/A + Score 0–5 + Rating
10.095 | 10 | WP10 | Land Use Rights and Zoning | Has the relevant authority, specialist or professional adviser reviewed parking compliance - risk mitigation where required? | Authority response, compliance checklist, file note and management approval. | Deeds Registries Act 47 of 1937; Surveyor-General records; servitude register | Yes / No / N/A + Score 0–5 + Rating
10.096 | 10 | WP10 | Land Use Rights and Zoning | Is the decision record for FAR and coverage - risk mitigation aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | Municipal Planning By-law; wayleave requirements; landowner consent | Yes / No / N/A + Score 0–5 + Rating
10.097 | 10 | WP10 | Land Use Rights and Zoning | Have cost, programme and compliance implications of current agricultural zoning - stakeholder acceptance been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | SPLUMA Act 16 of 2013; municipal land use scheme; title deed/SG diagram | Yes / No / N/A + Score 0–5 + Rating
10.098 | 10 | WP10 | Land Use Rights and Zoning | Has the team obtained written confirmation or documented proof for rezoning pathway - stakeholder acceptance? | Current certificate/letter/report, version control and document-control entry. | Deeds Registries Act 47 of 1937; Surveyor-General records; servitude register | Yes / No / N/A + Score 0–5 + Rating
10.099 | 10 | WP10 | Land Use Rights and Zoning | Does the evidence for consent use - stakeholder acceptance support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | Municipal Planning By-law; wayleave requirements; landowner consent | Yes / No / N/A + Score 0–5 + Rating
10.100 | 10 | WP10 | Land Use Rights and Zoning | Have dependencies linked to site development plan - stakeholder acceptance been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | SPLUMA Act 16 of 2013; municipal land use scheme; title deed/SG diagram | Yes / No / N/A + Score 0–5 + Rating
11.001 | 11 | WP11 | Environmental Authorisation - Estimated 10 Months | Has the project team confirmed screening report - governance approval in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | NEMA Act 107 of 1998; EIA Regulations, 2014; DFFE screening requirements | Yes / No / N/A + Score 0–5 + Rating
11.002 | 11 | WP11 | Environmental Authorisation - Estimated 10 Months | Is there a responsible owner, due date and approval route for specialist studies - governance approval? | Register entry, supporting drawing/report, approval note and updated risk item. | National Water Act 36 of 1998; biodiversity and wetland specialist guidance | Yes / No / N/A + Score 0–5 + Rating
11.003 | 11 | WP11 | Environmental Authorisation - Estimated 10 Months | Has the gate file tested whether draft BAR or EIA - governance approval creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | NHRA Act 25 of 1999; public participation record; EMPr controls | Yes / No / N/A + Score 0–5 + Rating
11.004 | 11 | WP11 | Environmental Authorisation - Estimated 10 Months | Are assumptions for public participation - governance approval documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | NEMA Act 107 of 1998; EIA Regulations, 2014; DFFE screening requirements | Yes / No / N/A + Score 0–5 + Rating
11.005 | 11 | WP11 | Environmental Authorisation - Estimated 10 Months | Has the relevant authority, specialist or professional adviser reviewed authority comments - governance approval where required? | Authority response, compliance checklist, file note and management approval. | National Water Act 36 of 1998; biodiversity and wetland specialist guidance | Yes / No / N/A + Score 0–5 + Rating
11.006 | 11 | WP11 | Environmental Authorisation - Estimated 10 Months | Is the decision record for EMPr - governance approval aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | NHRA Act 25 of 1999; public participation record; EMPr controls | Yes / No / N/A + Score 0–5 + Rating
11.007 | 11 | WP11 | Environmental Authorisation - Estimated 10 Months | Have cost, programme and compliance implications of screening report - legal authority been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | NEMA Act 107 of 1998; EIA Regulations, 2014; DFFE screening requirements | Yes / No / N/A + Score 0–5 + Rating
11.008 | 11 | WP11 | Environmental Authorisation - Estimated 10 Months | Has the team obtained written confirmation or documented proof for specialist studies - legal authority? | Current certificate/letter/report, version control and document-control entry. | National Water Act 36 of 1998; biodiversity and wetland specialist guidance | Yes / No / N/A + Score 0–5 + Rating
11.009 | 11 | WP11 | Environmental Authorisation - Estimated 10 Months | Does the evidence for draft BAR or EIA - legal authority support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | NHRA Act 25 of 1999; public participation record; EMPr controls | Yes / No / N/A + Score 0–5 + Rating
11.010 | 11 | WP11 | Environmental Authorisation - Estimated 10 Months | Have dependencies linked to public participation - legal authority been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | NEMA Act 107 of 1998; EIA Regulations, 2014; DFFE screening requirements | Yes / No / N/A + Score 0–5 + Rating
11.011 | 11 | WP11 | Environmental Authorisation - Estimated 10 Months | Has the project team confirmed authority comments - legal authority in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | National Water Act 36 of 1998; biodiversity and wetland specialist guidance | Yes / No / N/A + Score 0–5 + Rating
11.012 | 11 | WP11 | Environmental Authorisation - Estimated 10 Months | Is there a responsible owner, due date and approval route for EMPr - legal authority? | Register entry, supporting drawing/report, approval note and updated risk item. | NHRA Act 25 of 1999; public participation record; EMPr controls | Yes / No / N/A + Score 0–5 + Rating
11.013 | 11 | WP11 | Environmental Authorisation - Estimated 10 Months | Has the gate file tested whether screening report - technical feasibility creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | NEMA Act 107 of 1998; EIA Regulations, 2014; DFFE screening requirements | Yes / No / N/A + Score 0–5 + Rating
11.014 | 11 | WP11 | Environmental Authorisation - Estimated 10 Months | Are assumptions for specialist studies - technical feasibility documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | National Water Act 36 of 1998; biodiversity and wetland specialist guidance | Yes / No / N/A + Score 0–5 + Rating
11.015 | 11 | WP11 | Environmental Authorisation - Estimated 10 Months | Has the relevant authority, specialist or professional adviser reviewed draft BAR or EIA - technical feasibility where required? | Authority response, compliance checklist, file note and management approval. | NHRA Act 25 of 1999; public participation record; EMPr controls | Yes / No / N/A + Score 0–5 + Rating
11.016 | 11 | WP11 | Environmental Authorisation - Estimated 10 Months | Is the decision record for public participation - technical feasibility aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | NEMA Act 107 of 1998; EIA Regulations, 2014; DFFE screening requirements | Yes / No / N/A + Score 0–5 + Rating
11.017 | 11 | WP11 | Environmental Authorisation - Estimated 10 Months | Have cost, programme and compliance implications of authority comments - technical feasibility been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | National Water Act 36 of 1998; biodiversity and wetland specialist guidance | Yes / No / N/A + Score 0–5 + Rating
11.018 | 11 | WP11 | Environmental Authorisation - Estimated 10 Months | Has the team obtained written confirmation or documented proof for EMPr - technical feasibility? | Current certificate/letter/report, version control and document-control entry. | NHRA Act 25 of 1999; public participation record; EMPr controls | Yes / No / N/A + Score 0–5 + Rating
11.019 | 11 | WP11 | Environmental Authorisation - Estimated 10 Months | Does the evidence for screening report - financial viability support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | NEMA Act 107 of 1998; EIA Regulations, 2014; DFFE screening requirements | Yes / No / N/A + Score 0–5 + Rating
11.020 | 11 | WP11 | Environmental Authorisation - Estimated 10 Months | Have dependencies linked to specialist studies - financial viability been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | National Water Act 36 of 1998; biodiversity and wetland specialist guidance | Yes / No / N/A + Score 0–5 + Rating
11.021 | 11 | WP11 | Environmental Authorisation - Estimated 10 Months | Has the project team confirmed draft BAR or EIA - financial viability in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | NHRA Act 25 of 1999; public participation record; EMPr controls | Yes / No / N/A + Score 0–5 + Rating
11.022 | 11 | WP11 | Environmental Authorisation - Estimated 10 Months | Is there a responsible owner, due date and approval route for public participation - financial viability? | Register entry, supporting drawing/report, approval note and updated risk item. | NEMA Act 107 of 1998; EIA Regulations, 2014; DFFE screening requirements | Yes / No / N/A + Score 0–5 + Rating
11.023 | 11 | WP11 | Environmental Authorisation - Estimated 10 Months | Has the gate file tested whether authority comments - financial viability creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | National Water Act 36 of 1998; biodiversity and wetland specialist guidance | Yes / No / N/A + Score 0–5 + Rating
11.024 | 11 | WP11 | Environmental Authorisation - Estimated 10 Months | Are assumptions for EMPr - financial viability documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | NHRA Act 25 of 1999; public participation record; EMPr controls | Yes / No / N/A + Score 0–5 + Rating
11.025 | 11 | WP11 | Environmental Authorisation - Estimated 10 Months | Has the relevant authority, specialist or professional adviser reviewed screening report - programme impact where required? | Authority response, compliance checklist, file note and management approval. | NEMA Act 107 of 1998; EIA Regulations, 2014; DFFE screening requirements | Yes / No / N/A + Score 0–5 + Rating
11.026 | 11 | WP11 | Environmental Authorisation - Estimated 10 Months | Is the decision record for specialist studies - programme impact aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | National Water Act 36 of 1998; biodiversity and wetland specialist guidance | Yes / No / N/A + Score 0–5 + Rating
11.027 | 11 | WP11 | Environmental Authorisation - Estimated 10 Months | Have cost, programme and compliance implications of draft BAR or EIA - programme impact been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | NHRA Act 25 of 1999; public participation record; EMPr controls | Yes / No / N/A + Score 0–5 + Rating
11.028 | 11 | WP11 | Environmental Authorisation - Estimated 10 Months | Has the team obtained written confirmation or documented proof for public participation - programme impact? | Current certificate/letter/report, version control and document-control entry. | NEMA Act 107 of 1998; EIA Regulations, 2014; DFFE screening requirements | Yes / No / N/A + Score 0–5 + Rating
11.029 | 11 | WP11 | Environmental Authorisation - Estimated 10 Months | Does the evidence for authority comments - programme impact support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | National Water Act 36 of 1998; biodiversity and wetland specialist guidance | Yes / No / N/A + Score 0–5 + Rating
11.030 | 11 | WP11 | Environmental Authorisation - Estimated 10 Months | Have dependencies linked to EMPr - programme impact been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | NHRA Act 25 of 1999; public participation record; EMPr controls | Yes / No / N/A + Score 0–5 + Rating
11.031 | 11 | WP11 | Environmental Authorisation - Estimated 10 Months | Has the project team confirmed screening report - risk mitigation in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | NEMA Act 107 of 1998; EIA Regulations, 2014; DFFE screening requirements | Yes / No / N/A + Score 0–5 + Rating
11.032 | 11 | WP11 | Environmental Authorisation - Estimated 10 Months | Is there a responsible owner, due date and approval route for specialist studies - risk mitigation? | Register entry, supporting drawing/report, approval note and updated risk item. | National Water Act 36 of 1998; biodiversity and wetland specialist guidance | Yes / No / N/A + Score 0–5 + Rating
11.033 | 11 | WP11 | Environmental Authorisation - Estimated 10 Months | Has the gate file tested whether draft BAR or EIA - risk mitigation creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | NHRA Act 25 of 1999; public participation record; EMPr controls | Yes / No / N/A + Score 0–5 + Rating
11.034 | 11 | WP11 | Environmental Authorisation - Estimated 10 Months | Are assumptions for public participation - risk mitigation documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | NEMA Act 107 of 1998; EIA Regulations, 2014; DFFE screening requirements | Yes / No / N/A + Score 0–5 + Rating
11.035 | 11 | WP11 | Environmental Authorisation - Estimated 10 Months | Has the relevant authority, specialist or professional adviser reviewed authority comments - risk mitigation where required? | Authority response, compliance checklist, file note and management approval. | National Water Act 36 of 1998; biodiversity and wetland specialist guidance | Yes / No / N/A + Score 0–5 + Rating
11.036 | 11 | WP11 | Environmental Authorisation - Estimated 10 Months | Is the decision record for EMPr - risk mitigation aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | NHRA Act 25 of 1999; public participation record; EMPr controls | Yes / No / N/A + Score 0–5 + Rating
11.037 | 11 | WP11 | Environmental Authorisation - Estimated 10 Months | Have cost, programme and compliance implications of screening report - stakeholder acceptance been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | NEMA Act 107 of 1998; EIA Regulations, 2014; DFFE screening requirements | Yes / No / N/A + Score 0–5 + Rating
11.038 | 11 | WP11 | Environmental Authorisation - Estimated 10 Months | Has the team obtained written confirmation or documented proof for specialist studies - stakeholder acceptance? | Current certificate/letter/report, version control and document-control entry. | National Water Act 36 of 1998; biodiversity and wetland specialist guidance | Yes / No / N/A + Score 0–5 + Rating
11.039 | 11 | WP11 | Environmental Authorisation - Estimated 10 Months | Does the evidence for draft BAR or EIA - stakeholder acceptance support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | NHRA Act 25 of 1999; public participation record; EMPr controls | Yes / No / N/A + Score 0–5 + Rating
11.040 | 11 | WP11 | Environmental Authorisation - Estimated 10 Months | Have dependencies linked to public participation - stakeholder acceptance been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | NEMA Act 107 of 1998; EIA Regulations, 2014; DFFE screening requirements | Yes / No / N/A + Score 0–5 + Rating
11.041 | 11 | WP11 | Environmental Authorisation - Estimated 10 Months | Has the project team confirmed authority comments - stakeholder acceptance in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | National Water Act 36 of 1998; biodiversity and wetland specialist guidance | Yes / No / N/A + Score 0–5 + Rating
11.042 | 11 | WP11 | Environmental Authorisation - Estimated 10 Months | Is there a responsible owner, due date and approval route for EMPr - stakeholder acceptance? | Register entry, supporting drawing/report, approval note and updated risk item. | NHRA Act 25 of 1999; public participation record; EMPr controls | Yes / No / N/A + Score 0–5 + Rating
11.043 | 11 | WP11 | Environmental Authorisation - Estimated 10 Months | Has the gate file tested whether screening report - document control creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | NEMA Act 107 of 1998; EIA Regulations, 2014; DFFE screening requirements | Yes / No / N/A + Score 0–5 + Rating
11.044 | 11 | WP11 | Environmental Authorisation - Estimated 10 Months | Are assumptions for specialist studies - document control documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | National Water Act 36 of 1998; biodiversity and wetland specialist guidance | Yes / No / N/A + Score 0–5 + Rating
11.045 | 11 | WP11 | Environmental Authorisation - Estimated 10 Months | Has the relevant authority, specialist or professional adviser reviewed draft BAR or EIA - document control where required? | Authority response, compliance checklist, file note and management approval. | NHRA Act 25 of 1999; public participation record; EMPr controls | Yes / No / N/A + Score 0–5 + Rating
11.046 | 11 | WP11 | Environmental Authorisation - Estimated 10 Months | Is the decision record for public participation - document control aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | NEMA Act 107 of 1998; EIA Regulations, 2014; DFFE screening requirements | Yes / No / N/A + Score 0–5 + Rating
11.047 | 11 | WP11 | Environmental Authorisation - Estimated 10 Months | Have cost, programme and compliance implications of authority comments - document control been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | National Water Act 36 of 1998; biodiversity and wetland specialist guidance | Yes / No / N/A + Score 0–5 + Rating
11.048 | 11 | WP11 | Environmental Authorisation - Estimated 10 Months | Has the team obtained written confirmation or documented proof for EMPr - document control? | Current certificate/letter/report, version control and document-control entry. | NHRA Act 25 of 1999; public participation record; EMPr controls | Yes / No / N/A + Score 0–5 + Rating
11.049 | 11 | WP11 | Environmental Authorisation - Estimated 10 Months | Does the evidence for screening report - professional certification support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | NEMA Act 107 of 1998; EIA Regulations, 2014; DFFE screening requirements | Yes / No / N/A + Score 0–5 + Rating
11.050 | 11 | WP11 | Environmental Authorisation - Estimated 10 Months | Have dependencies linked to specialist studies - professional certification been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | National Water Act 36 of 1998; biodiversity and wetland specialist guidance | Yes / No / N/A + Score 0–5 + Rating
11.051 | 11 | WP11 | Environmental Authorisation - Estimated 10 Months | Has the project team confirmed draft BAR or EIA - professional certification in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | NHRA Act 25 of 1999; public participation record; EMPr controls | Yes / No / N/A + Score 0–5 + Rating
11.052 | 11 | WP11 | Environmental Authorisation - Estimated 10 Months | Is there a responsible owner, due date and approval route for public participation - professional certification? | Register entry, supporting drawing/report, approval note and updated risk item. | NEMA Act 107 of 1998; EIA Regulations, 2014; DFFE screening requirements | Yes / No / N/A + Score 0–5 + Rating
11.053 | 11 | WP11 | Environmental Authorisation - Estimated 10 Months | Has the gate file tested whether authority comments - professional certification creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | National Water Act 36 of 1998; biodiversity and wetland specialist guidance | Yes / No / N/A + Score 0–5 + Rating
11.054 | 11 | WP11 | Environmental Authorisation - Estimated 10 Months | Are assumptions for EMPr - professional certification documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | NHRA Act 25 of 1999; public participation record; EMPr controls | Yes / No / N/A + Score 0–5 + Rating
11.055 | 11 | WP11 | Environmental Authorisation - Estimated 10 Months | Has the relevant authority, specialist or professional adviser reviewed screening report - implementation readiness where required? | Authority response, compliance checklist, file note and management approval. | NEMA Act 107 of 1998; EIA Regulations, 2014; DFFE screening requirements | Yes / No / N/A + Score 0–5 + Rating
11.056 | 11 | WP11 | Environmental Authorisation - Estimated 10 Months | Is the decision record for specialist studies - implementation readiness aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | National Water Act 36 of 1998; biodiversity and wetland specialist guidance | Yes / No / N/A + Score 0–5 + Rating
11.057 | 11 | WP11 | Environmental Authorisation - Estimated 10 Months | Have cost, programme and compliance implications of draft BAR or EIA - implementation readiness been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | NHRA Act 25 of 1999; public participation record; EMPr controls | Yes / No / N/A + Score 0–5 + Rating
11.058 | 11 | WP11 | Environmental Authorisation - Estimated 10 Months | Has the team obtained written confirmation or documented proof for public participation - implementation readiness? | Current certificate/letter/report, version control and document-control entry. | NEMA Act 107 of 1998; EIA Regulations, 2014; DFFE screening requirements | Yes / No / N/A + Score 0–5 + Rating
11.059 | 11 | WP11 | Environmental Authorisation - Estimated 10 Months | Does the evidence for authority comments - implementation readiness support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | National Water Act 36 of 1998; biodiversity and wetland specialist guidance | Yes / No / N/A + Score 0–5 + Rating
11.060 | 11 | WP11 | Environmental Authorisation - Estimated 10 Months | Have dependencies linked to EMPr - implementation readiness been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | NHRA Act 25 of 1999; public participation record; EMPr controls | Yes / No / N/A + Score 0–5 + Rating
11.061 | 11 | WP11 | Environmental Authorisation - Estimated 10 Months | Has the project team confirmed screening report - governance approval in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | NEMA Act 107 of 1998; EIA Regulations, 2014; DFFE screening requirements | Yes / No / N/A + Score 0–5 + Rating
11.062 | 11 | WP11 | Environmental Authorisation - Estimated 10 Months | Is there a responsible owner, due date and approval route for specialist studies - governance approval? | Register entry, supporting drawing/report, approval note and updated risk item. | National Water Act 36 of 1998; biodiversity and wetland specialist guidance | Yes / No / N/A + Score 0–5 + Rating
11.063 | 11 | WP11 | Environmental Authorisation - Estimated 10 Months | Has the gate file tested whether draft BAR or EIA - governance approval creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | NHRA Act 25 of 1999; public participation record; EMPr controls | Yes / No / N/A + Score 0–5 + Rating
11.064 | 11 | WP11 | Environmental Authorisation - Estimated 10 Months | Are assumptions for public participation - governance approval documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | NEMA Act 107 of 1998; EIA Regulations, 2014; DFFE screening requirements | Yes / No / N/A + Score 0–5 + Rating
11.065 | 11 | WP11 | Environmental Authorisation - Estimated 10 Months | Has the relevant authority, specialist or professional adviser reviewed authority comments - governance approval where required? | Authority response, compliance checklist, file note and management approval. | National Water Act 36 of 1998; biodiversity and wetland specialist guidance | Yes / No / N/A + Score 0–5 + Rating
11.066 | 11 | WP11 | Environmental Authorisation - Estimated 10 Months | Is the decision record for EMPr - governance approval aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | NHRA Act 25 of 1999; public participation record; EMPr controls | Yes / No / N/A + Score 0–5 + Rating
11.067 | 11 | WP11 | Environmental Authorisation - Estimated 10 Months | Have cost, programme and compliance implications of screening report - legal authority been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | NEMA Act 107 of 1998; EIA Regulations, 2014; DFFE screening requirements | Yes / No / N/A + Score 0–5 + Rating
11.068 | 11 | WP11 | Environmental Authorisation - Estimated 10 Months | Has the team obtained written confirmation or documented proof for specialist studies - legal authority? | Current certificate/letter/report, version control and document-control entry. | National Water Act 36 of 1998; biodiversity and wetland specialist guidance | Yes / No / N/A + Score 0–5 + Rating
11.069 | 11 | WP11 | Environmental Authorisation - Estimated 10 Months | Does the evidence for draft BAR or EIA - legal authority support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | NHRA Act 25 of 1999; public participation record; EMPr controls | Yes / No / N/A + Score 0–5 + Rating
11.070 | 11 | WP11 | Environmental Authorisation - Estimated 10 Months | Have dependencies linked to public participation - legal authority been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | NEMA Act 107 of 1998; EIA Regulations, 2014; DFFE screening requirements | Yes / No / N/A + Score 0–5 + Rating
11.071 | 11 | WP11 | Environmental Authorisation - Estimated 10 Months | Has the project team confirmed authority comments - legal authority in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | National Water Act 36 of 1998; biodiversity and wetland specialist guidance | Yes / No / N/A + Score 0–5 + Rating
11.072 | 11 | WP11 | Environmental Authorisation - Estimated 10 Months | Is there a responsible owner, due date and approval route for EMPr - legal authority? | Register entry, supporting drawing/report, approval note and updated risk item. | NHRA Act 25 of 1999; public participation record; EMPr controls | Yes / No / N/A + Score 0–5 + Rating
11.073 | 11 | WP11 | Environmental Authorisation - Estimated 10 Months | Has the gate file tested whether screening report - technical feasibility creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | NEMA Act 107 of 1998; EIA Regulations, 2014; DFFE screening requirements | Yes / No / N/A + Score 0–5 + Rating
11.074 | 11 | WP11 | Environmental Authorisation - Estimated 10 Months | Are assumptions for specialist studies - technical feasibility documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | National Water Act 36 of 1998; biodiversity and wetland specialist guidance | Yes / No / N/A + Score 0–5 + Rating
11.075 | 11 | WP11 | Environmental Authorisation - Estimated 10 Months | Has the relevant authority, specialist or professional adviser reviewed draft BAR or EIA - technical feasibility where required? | Authority response, compliance checklist, file note and management approval. | NHRA Act 25 of 1999; public participation record; EMPr controls | Yes / No / N/A + Score 0–5 + Rating
11.076 | 11 | WP11 | Environmental Authorisation - Estimated 10 Months | Is the decision record for public participation - technical feasibility aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | NEMA Act 107 of 1998; EIA Regulations, 2014; DFFE screening requirements | Yes / No / N/A + Score 0–5 + Rating
11.077 | 11 | WP11 | Environmental Authorisation - Estimated 10 Months | Have cost, programme and compliance implications of authority comments - technical feasibility been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | National Water Act 36 of 1998; biodiversity and wetland specialist guidance | Yes / No / N/A + Score 0–5 + Rating
11.078 | 11 | WP11 | Environmental Authorisation - Estimated 10 Months | Has the team obtained written confirmation or documented proof for EMPr - technical feasibility? | Current certificate/letter/report, version control and document-control entry. | NHRA Act 25 of 1999; public participation record; EMPr controls | Yes / No / N/A + Score 0–5 + Rating
11.079 | 11 | WP11 | Environmental Authorisation - Estimated 10 Months | Does the evidence for screening report - financial viability support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | NEMA Act 107 of 1998; EIA Regulations, 2014; DFFE screening requirements | Yes / No / N/A + Score 0–5 + Rating
11.080 | 11 | WP11 | Environmental Authorisation - Estimated 10 Months | Have dependencies linked to specialist studies - financial viability been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | National Water Act 36 of 1998; biodiversity and wetland specialist guidance | Yes / No / N/A + Score 0–5 + Rating
11.081 | 11 | WP11 | Environmental Authorisation - Estimated 10 Months | Has the project team confirmed draft BAR or EIA - financial viability in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | NHRA Act 25 of 1999; public participation record; EMPr controls | Yes / No / N/A + Score 0–5 + Rating
11.082 | 11 | WP11 | Environmental Authorisation - Estimated 10 Months | Is there a responsible owner, due date and approval route for public participation - financial viability? | Register entry, supporting drawing/report, approval note and updated risk item. | NEMA Act 107 of 1998; EIA Regulations, 2014; DFFE screening requirements | Yes / No / N/A + Score 0–5 + Rating
11.083 | 11 | WP11 | Environmental Authorisation - Estimated 10 Months | Has the gate file tested whether authority comments - financial viability creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | National Water Act 36 of 1998; biodiversity and wetland specialist guidance | Yes / No / N/A + Score 0–5 + Rating
11.084 | 11 | WP11 | Environmental Authorisation - Estimated 10 Months | Are assumptions for EMPr - financial viability documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | NHRA Act 25 of 1999; public participation record; EMPr controls | Yes / No / N/A + Score 0–5 + Rating
11.085 | 11 | WP11 | Environmental Authorisation - Estimated 10 Months | Has the relevant authority, specialist or professional adviser reviewed screening report - programme impact where required? | Authority response, compliance checklist, file note and management approval. | NEMA Act 107 of 1998; EIA Regulations, 2014; DFFE screening requirements | Yes / No / N/A + Score 0–5 + Rating
11.086 | 11 | WP11 | Environmental Authorisation - Estimated 10 Months | Is the decision record for specialist studies - programme impact aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | National Water Act 36 of 1998; biodiversity and wetland specialist guidance | Yes / No / N/A + Score 0–5 + Rating
11.087 | 11 | WP11 | Environmental Authorisation - Estimated 10 Months | Have cost, programme and compliance implications of draft BAR or EIA - programme impact been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | NHRA Act 25 of 1999; public participation record; EMPr controls | Yes / No / N/A + Score 0–5 + Rating
11.088 | 11 | WP11 | Environmental Authorisation - Estimated 10 Months | Has the team obtained written confirmation or documented proof for public participation - programme impact? | Current certificate/letter/report, version control and document-control entry. | NEMA Act 107 of 1998; EIA Regulations, 2014; DFFE screening requirements | Yes / No / N/A + Score 0–5 + Rating
11.089 | 11 | WP11 | Environmental Authorisation - Estimated 10 Months | Does the evidence for authority comments - programme impact support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | National Water Act 36 of 1998; biodiversity and wetland specialist guidance | Yes / No / N/A + Score 0–5 + Rating
11.090 | 11 | WP11 | Environmental Authorisation - Estimated 10 Months | Have dependencies linked to EMPr - programme impact been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | NHRA Act 25 of 1999; public participation record; EMPr controls | Yes / No / N/A + Score 0–5 + Rating
11.091 | 11 | WP11 | Environmental Authorisation - Estimated 10 Months | Has the project team confirmed screening report - risk mitigation in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | NEMA Act 107 of 1998; EIA Regulations, 2014; DFFE screening requirements | Yes / No / N/A + Score 0–5 + Rating
11.092 | 11 | WP11 | Environmental Authorisation - Estimated 10 Months | Is there a responsible owner, due date and approval route for specialist studies - risk mitigation? | Register entry, supporting drawing/report, approval note and updated risk item. | National Water Act 36 of 1998; biodiversity and wetland specialist guidance | Yes / No / N/A + Score 0–5 + Rating
11.093 | 11 | WP11 | Environmental Authorisation - Estimated 10 Months | Has the gate file tested whether draft BAR or EIA - risk mitigation creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | NHRA Act 25 of 1999; public participation record; EMPr controls | Yes / No / N/A + Score 0–5 + Rating
11.094 | 11 | WP11 | Environmental Authorisation - Estimated 10 Months | Are assumptions for public participation - risk mitigation documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | NEMA Act 107 of 1998; EIA Regulations, 2014; DFFE screening requirements | Yes / No / N/A + Score 0–5 + Rating
11.095 | 11 | WP11 | Environmental Authorisation - Estimated 10 Months | Has the relevant authority, specialist or professional adviser reviewed authority comments - risk mitigation where required? | Authority response, compliance checklist, file note and management approval. | National Water Act 36 of 1998; biodiversity and wetland specialist guidance | Yes / No / N/A + Score 0–5 + Rating
11.096 | 11 | WP11 | Environmental Authorisation - Estimated 10 Months | Is the decision record for EMPr - risk mitigation aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | NHRA Act 25 of 1999; public participation record; EMPr controls | Yes / No / N/A + Score 0–5 + Rating
11.097 | 11 | WP11 | Environmental Authorisation - Estimated 10 Months | Have cost, programme and compliance implications of screening report - stakeholder acceptance been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | NEMA Act 107 of 1998; EIA Regulations, 2014; DFFE screening requirements | Yes / No / N/A + Score 0–5 + Rating
11.098 | 11 | WP11 | Environmental Authorisation - Estimated 10 Months | Has the team obtained written confirmation or documented proof for specialist studies - stakeholder acceptance? | Current certificate/letter/report, version control and document-control entry. | National Water Act 36 of 1998; biodiversity and wetland specialist guidance | Yes / No / N/A + Score 0–5 + Rating
11.099 | 11 | WP11 | Environmental Authorisation - Estimated 10 Months | Does the evidence for draft BAR or EIA - stakeholder acceptance support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | NHRA Act 25 of 1999; public participation record; EMPr controls | Yes / No / N/A + Score 0–5 + Rating
11.100 | 11 | WP11 | Environmental Authorisation - Estimated 10 Months | Have dependencies linked to public participation - stakeholder acceptance been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | NEMA Act 107 of 1998; EIA Regulations, 2014; DFFE screening requirements | Yes / No / N/A + Score 0–5 + Rating
12.001 | 12 | WP12 | Stakeholder Mapping and Public Participation | Has the project team confirmed municipality - governance approval in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | King IV governance practice; Companies Act 71 of 2008; project mandate file | Yes / No / N/A + Score 0–5 + Rating
12.002 | 12 | WP12 | Stakeholder Mapping and Public Participation | Is there a responsible owner, due date and approval route for road authority - governance approval? | Register entry, supporting drawing/report, approval note and updated risk item. | PMBOK stage-gate governance; board resolution; delegated authority matrix | Yes / No / N/A + Score 0–5 + Rating
12.003 | 12 | WP12 | Stakeholder Mapping and Public Participation | Has the gate file tested whether DMRE - governance approval creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | ISO 31000 risk management; stakeholder decision register; project charter | Yes / No / N/A + Score 0–5 + Rating
12.004 | 12 | WP12 | Stakeholder Mapping and Public Participation | Are assumptions for environmental authority - governance approval documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | King IV governance practice; Companies Act 71 of 2008; project mandate file | Yes / No / N/A + Score 0–5 + Rating
12.005 | 12 | WP12 | Stakeholder Mapping and Public Participation | Has the relevant authority, specialist or professional adviser reviewed community leaders - governance approval where required? | Authority response, compliance checklist, file note and management approval. | PMBOK stage-gate governance; board resolution; delegated authority matrix | Yes / No / N/A + Score 0–5 + Rating
12.006 | 12 | WP12 | Stakeholder Mapping and Public Participation | Is the decision record for neighbouring landowners - governance approval aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | ISO 31000 risk management; stakeholder decision register; project charter | Yes / No / N/A + Score 0–5 + Rating
12.007 | 12 | WP12 | Stakeholder Mapping and Public Participation | Have cost, programme and compliance implications of municipality - legal authority been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | King IV governance practice; Companies Act 71 of 2008; project mandate file | Yes / No / N/A + Score 0–5 + Rating
12.008 | 12 | WP12 | Stakeholder Mapping and Public Participation | Has the team obtained written confirmation or documented proof for road authority - legal authority? | Current certificate/letter/report, version control and document-control entry. | PMBOK stage-gate governance; board resolution; delegated authority matrix | Yes / No / N/A + Score 0–5 + Rating
12.009 | 12 | WP12 | Stakeholder Mapping and Public Participation | Does the evidence for DMRE - legal authority support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | ISO 31000 risk management; stakeholder decision register; project charter | Yes / No / N/A + Score 0–5 + Rating
12.010 | 12 | WP12 | Stakeholder Mapping and Public Participation | Have dependencies linked to environmental authority - legal authority been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | King IV governance practice; Companies Act 71 of 2008; project mandate file | Yes / No / N/A + Score 0–5 + Rating
12.011 | 12 | WP12 | Stakeholder Mapping and Public Participation | Has the project team confirmed community leaders - legal authority in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | PMBOK stage-gate governance; board resolution; delegated authority matrix | Yes / No / N/A + Score 0–5 + Rating
12.012 | 12 | WP12 | Stakeholder Mapping and Public Participation | Is there a responsible owner, due date and approval route for neighbouring landowners - legal authority? | Register entry, supporting drawing/report, approval note and updated risk item. | ISO 31000 risk management; stakeholder decision register; project charter | Yes / No / N/A + Score 0–5 + Rating
12.013 | 12 | WP12 | Stakeholder Mapping and Public Participation | Has the gate file tested whether municipality - technical feasibility creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | King IV governance practice; Companies Act 71 of 2008; project mandate file | Yes / No / N/A + Score 0–5 + Rating
12.014 | 12 | WP12 | Stakeholder Mapping and Public Participation | Are assumptions for road authority - technical feasibility documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | PMBOK stage-gate governance; board resolution; delegated authority matrix | Yes / No / N/A + Score 0–5 + Rating
12.015 | 12 | WP12 | Stakeholder Mapping and Public Participation | Has the relevant authority, specialist or professional adviser reviewed DMRE - technical feasibility where required? | Authority response, compliance checklist, file note and management approval. | ISO 31000 risk management; stakeholder decision register; project charter | Yes / No / N/A + Score 0–5 + Rating
12.016 | 12 | WP12 | Stakeholder Mapping and Public Participation | Is the decision record for environmental authority - technical feasibility aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | King IV governance practice; Companies Act 71 of 2008; project mandate file | Yes / No / N/A + Score 0–5 + Rating
12.017 | 12 | WP12 | Stakeholder Mapping and Public Participation | Have cost, programme and compliance implications of community leaders - technical feasibility been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | PMBOK stage-gate governance; board resolution; delegated authority matrix | Yes / No / N/A + Score 0–5 + Rating
12.018 | 12 | WP12 | Stakeholder Mapping and Public Participation | Has the team obtained written confirmation or documented proof for neighbouring landowners - technical feasibility? | Current certificate/letter/report, version control and document-control entry. | ISO 31000 risk management; stakeholder decision register; project charter | Yes / No / N/A + Score 0–5 + Rating
12.019 | 12 | WP12 | Stakeholder Mapping and Public Participation | Does the evidence for municipality - financial viability support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | King IV governance practice; Companies Act 71 of 2008; project mandate file | Yes / No / N/A + Score 0–5 + Rating
12.020 | 12 | WP12 | Stakeholder Mapping and Public Participation | Have dependencies linked to road authority - financial viability been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | PMBOK stage-gate governance; board resolution; delegated authority matrix | Yes / No / N/A + Score 0–5 + Rating
12.021 | 12 | WP12 | Stakeholder Mapping and Public Participation | Has the project team confirmed DMRE - financial viability in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | ISO 31000 risk management; stakeholder decision register; project charter | Yes / No / N/A + Score 0–5 + Rating
12.022 | 12 | WP12 | Stakeholder Mapping and Public Participation | Is there a responsible owner, due date and approval route for environmental authority - financial viability? | Register entry, supporting drawing/report, approval note and updated risk item. | King IV governance practice; Companies Act 71 of 2008; project mandate file | Yes / No / N/A + Score 0–5 + Rating
12.023 | 12 | WP12 | Stakeholder Mapping and Public Participation | Has the gate file tested whether community leaders - financial viability creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | PMBOK stage-gate governance; board resolution; delegated authority matrix | Yes / No / N/A + Score 0–5 + Rating
12.024 | 12 | WP12 | Stakeholder Mapping and Public Participation | Are assumptions for neighbouring landowners - financial viability documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | ISO 31000 risk management; stakeholder decision register; project charter | Yes / No / N/A + Score 0–5 + Rating
12.025 | 12 | WP12 | Stakeholder Mapping and Public Participation | Has the relevant authority, specialist or professional adviser reviewed municipality - programme impact where required? | Authority response, compliance checklist, file note and management approval. | King IV governance practice; Companies Act 71 of 2008; project mandate file | Yes / No / N/A + Score 0–5 + Rating
12.026 | 12 | WP12 | Stakeholder Mapping and Public Participation | Is the decision record for road authority - programme impact aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | PMBOK stage-gate governance; board resolution; delegated authority matrix | Yes / No / N/A + Score 0–5 + Rating
12.027 | 12 | WP12 | Stakeholder Mapping and Public Participation | Have cost, programme and compliance implications of DMRE - programme impact been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | ISO 31000 risk management; stakeholder decision register; project charter | Yes / No / N/A + Score 0–5 + Rating
12.028 | 12 | WP12 | Stakeholder Mapping and Public Participation | Has the team obtained written confirmation or documented proof for environmental authority - programme impact? | Current certificate/letter/report, version control and document-control entry. | King IV governance practice; Companies Act 71 of 2008; project mandate file | Yes / No / N/A + Score 0–5 + Rating
12.029 | 12 | WP12 | Stakeholder Mapping and Public Participation | Does the evidence for community leaders - programme impact support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | PMBOK stage-gate governance; board resolution; delegated authority matrix | Yes / No / N/A + Score 0–5 + Rating
12.030 | 12 | WP12 | Stakeholder Mapping and Public Participation | Have dependencies linked to neighbouring landowners - programme impact been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | ISO 31000 risk management; stakeholder decision register; project charter | Yes / No / N/A + Score 0–5 + Rating
12.031 | 12 | WP12 | Stakeholder Mapping and Public Participation | Has the project team confirmed municipality - risk mitigation in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | King IV governance practice; Companies Act 71 of 2008; project mandate file | Yes / No / N/A + Score 0–5 + Rating
12.032 | 12 | WP12 | Stakeholder Mapping and Public Participation | Is there a responsible owner, due date and approval route for road authority - risk mitigation? | Register entry, supporting drawing/report, approval note and updated risk item. | PMBOK stage-gate governance; board resolution; delegated authority matrix | Yes / No / N/A + Score 0–5 + Rating
12.033 | 12 | WP12 | Stakeholder Mapping and Public Participation | Has the gate file tested whether DMRE - risk mitigation creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | ISO 31000 risk management; stakeholder decision register; project charter | Yes / No / N/A + Score 0–5 + Rating
12.034 | 12 | WP12 | Stakeholder Mapping and Public Participation | Are assumptions for environmental authority - risk mitigation documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | King IV governance practice; Companies Act 71 of 2008; project mandate file | Yes / No / N/A + Score 0–5 + Rating
12.035 | 12 | WP12 | Stakeholder Mapping and Public Participation | Has the relevant authority, specialist or professional adviser reviewed community leaders - risk mitigation where required? | Authority response, compliance checklist, file note and management approval. | PMBOK stage-gate governance; board resolution; delegated authority matrix | Yes / No / N/A + Score 0–5 + Rating
12.036 | 12 | WP12 | Stakeholder Mapping and Public Participation | Is the decision record for neighbouring landowners - risk mitigation aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | ISO 31000 risk management; stakeholder decision register; project charter | Yes / No / N/A + Score 0–5 + Rating
12.037 | 12 | WP12 | Stakeholder Mapping and Public Participation | Have cost, programme and compliance implications of municipality - stakeholder acceptance been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | King IV governance practice; Companies Act 71 of 2008; project mandate file | Yes / No / N/A + Score 0–5 + Rating
12.038 | 12 | WP12 | Stakeholder Mapping and Public Participation | Has the team obtained written confirmation or documented proof for road authority - stakeholder acceptance? | Current certificate/letter/report, version control and document-control entry. | PMBOK stage-gate governance; board resolution; delegated authority matrix | Yes / No / N/A + Score 0–5 + Rating
12.039 | 12 | WP12 | Stakeholder Mapping and Public Participation | Does the evidence for DMRE - stakeholder acceptance support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | ISO 31000 risk management; stakeholder decision register; project charter | Yes / No / N/A + Score 0–5 + Rating
12.040 | 12 | WP12 | Stakeholder Mapping and Public Participation | Have dependencies linked to environmental authority - stakeholder acceptance been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | King IV governance practice; Companies Act 71 of 2008; project mandate file | Yes / No / N/A + Score 0–5 + Rating
12.041 | 12 | WP12 | Stakeholder Mapping and Public Participation | Has the project team confirmed community leaders - stakeholder acceptance in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | PMBOK stage-gate governance; board resolution; delegated authority matrix | Yes / No / N/A + Score 0–5 + Rating
12.042 | 12 | WP12 | Stakeholder Mapping and Public Participation | Is there a responsible owner, due date and approval route for neighbouring landowners - stakeholder acceptance? | Register entry, supporting drawing/report, approval note and updated risk item. | ISO 31000 risk management; stakeholder decision register; project charter | Yes / No / N/A + Score 0–5 + Rating
12.043 | 12 | WP12 | Stakeholder Mapping and Public Participation | Has the gate file tested whether municipality - document control creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | King IV governance practice; Companies Act 71 of 2008; project mandate file | Yes / No / N/A + Score 0–5 + Rating
12.044 | 12 | WP12 | Stakeholder Mapping and Public Participation | Are assumptions for road authority - document control documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | PMBOK stage-gate governance; board resolution; delegated authority matrix | Yes / No / N/A + Score 0–5 + Rating
12.045 | 12 | WP12 | Stakeholder Mapping and Public Participation | Has the relevant authority, specialist or professional adviser reviewed DMRE - document control where required? | Authority response, compliance checklist, file note and management approval. | ISO 31000 risk management; stakeholder decision register; project charter | Yes / No / N/A + Score 0–5 + Rating
12.046 | 12 | WP12 | Stakeholder Mapping and Public Participation | Is the decision record for environmental authority - document control aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | King IV governance practice; Companies Act 71 of 2008; project mandate file | Yes / No / N/A + Score 0–5 + Rating
12.047 | 12 | WP12 | Stakeholder Mapping and Public Participation | Have cost, programme and compliance implications of community leaders - document control been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | PMBOK stage-gate governance; board resolution; delegated authority matrix | Yes / No / N/A + Score 0–5 + Rating
12.048 | 12 | WP12 | Stakeholder Mapping and Public Participation | Has the team obtained written confirmation or documented proof for neighbouring landowners - document control? | Current certificate/letter/report, version control and document-control entry. | ISO 31000 risk management; stakeholder decision register; project charter | Yes / No / N/A + Score 0–5 + Rating
12.049 | 12 | WP12 | Stakeholder Mapping and Public Participation | Does the evidence for municipality - professional certification support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | King IV governance practice; Companies Act 71 of 2008; project mandate file | Yes / No / N/A + Score 0–5 + Rating
12.050 | 12 | WP12 | Stakeholder Mapping and Public Participation | Have dependencies linked to road authority - professional certification been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | PMBOK stage-gate governance; board resolution; delegated authority matrix | Yes / No / N/A + Score 0–5 + Rating
12.051 | 12 | WP12 | Stakeholder Mapping and Public Participation | Has the project team confirmed DMRE - professional certification in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | ISO 31000 risk management; stakeholder decision register; project charter | Yes / No / N/A + Score 0–5 + Rating
12.052 | 12 | WP12 | Stakeholder Mapping and Public Participation | Is there a responsible owner, due date and approval route for environmental authority - professional certification? | Register entry, supporting drawing/report, approval note and updated risk item. | King IV governance practice; Companies Act 71 of 2008; project mandate file | Yes / No / N/A + Score 0–5 + Rating
12.053 | 12 | WP12 | Stakeholder Mapping and Public Participation | Has the gate file tested whether community leaders - professional certification creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | PMBOK stage-gate governance; board resolution; delegated authority matrix | Yes / No / N/A + Score 0–5 + Rating
12.054 | 12 | WP12 | Stakeholder Mapping and Public Participation | Are assumptions for neighbouring landowners - professional certification documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | ISO 31000 risk management; stakeholder decision register; project charter | Yes / No / N/A + Score 0–5 + Rating
12.055 | 12 | WP12 | Stakeholder Mapping and Public Participation | Has the relevant authority, specialist or professional adviser reviewed municipality - implementation readiness where required? | Authority response, compliance checklist, file note and management approval. | King IV governance practice; Companies Act 71 of 2008; project mandate file | Yes / No / N/A + Score 0–5 + Rating
12.056 | 12 | WP12 | Stakeholder Mapping and Public Participation | Is the decision record for road authority - implementation readiness aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | PMBOK stage-gate governance; board resolution; delegated authority matrix | Yes / No / N/A + Score 0–5 + Rating
12.057 | 12 | WP12 | Stakeholder Mapping and Public Participation | Have cost, programme and compliance implications of DMRE - implementation readiness been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | ISO 31000 risk management; stakeholder decision register; project charter | Yes / No / N/A + Score 0–5 + Rating
12.058 | 12 | WP12 | Stakeholder Mapping and Public Participation | Has the team obtained written confirmation or documented proof for environmental authority - implementation readiness? | Current certificate/letter/report, version control and document-control entry. | King IV governance practice; Companies Act 71 of 2008; project mandate file | Yes / No / N/A + Score 0–5 + Rating
12.059 | 12 | WP12 | Stakeholder Mapping and Public Participation | Does the evidence for community leaders - implementation readiness support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | PMBOK stage-gate governance; board resolution; delegated authority matrix | Yes / No / N/A + Score 0–5 + Rating
12.060 | 12 | WP12 | Stakeholder Mapping and Public Participation | Have dependencies linked to neighbouring landowners - implementation readiness been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | ISO 31000 risk management; stakeholder decision register; project charter | Yes / No / N/A + Score 0–5 + Rating
12.061 | 12 | WP12 | Stakeholder Mapping and Public Participation | Has the project team confirmed municipality - governance approval in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | King IV governance practice; Companies Act 71 of 2008; project mandate file | Yes / No / N/A + Score 0–5 + Rating
12.062 | 12 | WP12 | Stakeholder Mapping and Public Participation | Is there a responsible owner, due date and approval route for road authority - governance approval? | Register entry, supporting drawing/report, approval note and updated risk item. | PMBOK stage-gate governance; board resolution; delegated authority matrix | Yes / No / N/A + Score 0–5 + Rating
12.063 | 12 | WP12 | Stakeholder Mapping and Public Participation | Has the gate file tested whether DMRE - governance approval creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | ISO 31000 risk management; stakeholder decision register; project charter | Yes / No / N/A + Score 0–5 + Rating
12.064 | 12 | WP12 | Stakeholder Mapping and Public Participation | Are assumptions for environmental authority - governance approval documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | King IV governance practice; Companies Act 71 of 2008; project mandate file | Yes / No / N/A + Score 0–5 + Rating
12.065 | 12 | WP12 | Stakeholder Mapping and Public Participation | Has the relevant authority, specialist or professional adviser reviewed community leaders - governance approval where required? | Authority response, compliance checklist, file note and management approval. | PMBOK stage-gate governance; board resolution; delegated authority matrix | Yes / No / N/A + Score 0–5 + Rating
12.066 | 12 | WP12 | Stakeholder Mapping and Public Participation | Is the decision record for neighbouring landowners - governance approval aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | ISO 31000 risk management; stakeholder decision register; project charter | Yes / No / N/A + Score 0–5 + Rating
12.067 | 12 | WP12 | Stakeholder Mapping and Public Participation | Have cost, programme and compliance implications of municipality - legal authority been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | King IV governance practice; Companies Act 71 of 2008; project mandate file | Yes / No / N/A + Score 0–5 + Rating
12.068 | 12 | WP12 | Stakeholder Mapping and Public Participation | Has the team obtained written confirmation or documented proof for road authority - legal authority? | Current certificate/letter/report, version control and document-control entry. | PMBOK stage-gate governance; board resolution; delegated authority matrix | Yes / No / N/A + Score 0–5 + Rating
12.069 | 12 | WP12 | Stakeholder Mapping and Public Participation | Does the evidence for DMRE - legal authority support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | ISO 31000 risk management; stakeholder decision register; project charter | Yes / No / N/A + Score 0–5 + Rating
12.070 | 12 | WP12 | Stakeholder Mapping and Public Participation | Have dependencies linked to environmental authority - legal authority been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | King IV governance practice; Companies Act 71 of 2008; project mandate file | Yes / No / N/A + Score 0–5 + Rating
12.071 | 12 | WP12 | Stakeholder Mapping and Public Participation | Has the project team confirmed community leaders - legal authority in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | PMBOK stage-gate governance; board resolution; delegated authority matrix | Yes / No / N/A + Score 0–5 + Rating
12.072 | 12 | WP12 | Stakeholder Mapping and Public Participation | Is there a responsible owner, due date and approval route for neighbouring landowners - legal authority? | Register entry, supporting drawing/report, approval note and updated risk item. | ISO 31000 risk management; stakeholder decision register; project charter | Yes / No / N/A + Score 0–5 + Rating
12.073 | 12 | WP12 | Stakeholder Mapping and Public Participation | Has the gate file tested whether municipality - technical feasibility creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | King IV governance practice; Companies Act 71 of 2008; project mandate file | Yes / No / N/A + Score 0–5 + Rating
12.074 | 12 | WP12 | Stakeholder Mapping and Public Participation | Are assumptions for road authority - technical feasibility documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | PMBOK stage-gate governance; board resolution; delegated authority matrix | Yes / No / N/A + Score 0–5 + Rating
12.075 | 12 | WP12 | Stakeholder Mapping and Public Participation | Has the relevant authority, specialist or professional adviser reviewed DMRE - technical feasibility where required? | Authority response, compliance checklist, file note and management approval. | ISO 31000 risk management; stakeholder decision register; project charter | Yes / No / N/A + Score 0–5 + Rating
12.076 | 12 | WP12 | Stakeholder Mapping and Public Participation | Is the decision record for environmental authority - technical feasibility aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | King IV governance practice; Companies Act 71 of 2008; project mandate file | Yes / No / N/A + Score 0–5 + Rating
12.077 | 12 | WP12 | Stakeholder Mapping and Public Participation | Have cost, programme and compliance implications of community leaders - technical feasibility been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | PMBOK stage-gate governance; board resolution; delegated authority matrix | Yes / No / N/A + Score 0–5 + Rating
12.078 | 12 | WP12 | Stakeholder Mapping and Public Participation | Has the team obtained written confirmation or documented proof for neighbouring landowners - technical feasibility? | Current certificate/letter/report, version control and document-control entry. | ISO 31000 risk management; stakeholder decision register; project charter | Yes / No / N/A + Score 0–5 + Rating
12.079 | 12 | WP12 | Stakeholder Mapping and Public Participation | Does the evidence for municipality - financial viability support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | King IV governance practice; Companies Act 71 of 2008; project mandate file | Yes / No / N/A + Score 0–5 + Rating
12.080 | 12 | WP12 | Stakeholder Mapping and Public Participation | Have dependencies linked to road authority - financial viability been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | PMBOK stage-gate governance; board resolution; delegated authority matrix | Yes / No / N/A + Score 0–5 + Rating
12.081 | 12 | WP12 | Stakeholder Mapping and Public Participation | Has the project team confirmed DMRE - financial viability in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | ISO 31000 risk management; stakeholder decision register; project charter | Yes / No / N/A + Score 0–5 + Rating
12.082 | 12 | WP12 | Stakeholder Mapping and Public Participation | Is there a responsible owner, due date and approval route for environmental authority - financial viability? | Register entry, supporting drawing/report, approval note and updated risk item. | King IV governance practice; Companies Act 71 of 2008; project mandate file | Yes / No / N/A + Score 0–5 + Rating
12.083 | 12 | WP12 | Stakeholder Mapping and Public Participation | Has the gate file tested whether community leaders - financial viability creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | PMBOK stage-gate governance; board resolution; delegated authority matrix | Yes / No / N/A + Score 0–5 + Rating
12.084 | 12 | WP12 | Stakeholder Mapping and Public Participation | Are assumptions for neighbouring landowners - financial viability documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | ISO 31000 risk management; stakeholder decision register; project charter | Yes / No / N/A + Score 0–5 + Rating
12.085 | 12 | WP12 | Stakeholder Mapping and Public Participation | Has the relevant authority, specialist or professional adviser reviewed municipality - programme impact where required? | Authority response, compliance checklist, file note and management approval. | King IV governance practice; Companies Act 71 of 2008; project mandate file | Yes / No / N/A + Score 0–5 + Rating
12.086 | 12 | WP12 | Stakeholder Mapping and Public Participation | Is the decision record for road authority - programme impact aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | PMBOK stage-gate governance; board resolution; delegated authority matrix | Yes / No / N/A + Score 0–5 + Rating
12.087 | 12 | WP12 | Stakeholder Mapping and Public Participation | Have cost, programme and compliance implications of DMRE - programme impact been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | ISO 31000 risk management; stakeholder decision register; project charter | Yes / No / N/A + Score 0–5 + Rating
12.088 | 12 | WP12 | Stakeholder Mapping and Public Participation | Has the team obtained written confirmation or documented proof for environmental authority - programme impact? | Current certificate/letter/report, version control and document-control entry. | King IV governance practice; Companies Act 71 of 2008; project mandate file | Yes / No / N/A + Score 0–5 + Rating
12.089 | 12 | WP12 | Stakeholder Mapping and Public Participation | Does the evidence for community leaders - programme impact support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | PMBOK stage-gate governance; board resolution; delegated authority matrix | Yes / No / N/A + Score 0–5 + Rating
12.090 | 12 | WP12 | Stakeholder Mapping and Public Participation | Have dependencies linked to neighbouring landowners - programme impact been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | ISO 31000 risk management; stakeholder decision register; project charter | Yes / No / N/A + Score 0–5 + Rating
12.091 | 12 | WP12 | Stakeholder Mapping and Public Participation | Has the project team confirmed municipality - risk mitigation in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | King IV governance practice; Companies Act 71 of 2008; project mandate file | Yes / No / N/A + Score 0–5 + Rating
12.092 | 12 | WP12 | Stakeholder Mapping and Public Participation | Is there a responsible owner, due date and approval route for road authority - risk mitigation? | Register entry, supporting drawing/report, approval note and updated risk item. | PMBOK stage-gate governance; board resolution; delegated authority matrix | Yes / No / N/A + Score 0–5 + Rating
12.093 | 12 | WP12 | Stakeholder Mapping and Public Participation | Has the gate file tested whether DMRE - risk mitigation creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | ISO 31000 risk management; stakeholder decision register; project charter | Yes / No / N/A + Score 0–5 + Rating
12.094 | 12 | WP12 | Stakeholder Mapping and Public Participation | Are assumptions for environmental authority - risk mitigation documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | King IV governance practice; Companies Act 71 of 2008; project mandate file | Yes / No / N/A + Score 0–5 + Rating
12.095 | 12 | WP12 | Stakeholder Mapping and Public Participation | Has the relevant authority, specialist or professional adviser reviewed community leaders - risk mitigation where required? | Authority response, compliance checklist, file note and management approval. | PMBOK stage-gate governance; board resolution; delegated authority matrix | Yes / No / N/A + Score 0–5 + Rating
12.096 | 12 | WP12 | Stakeholder Mapping and Public Participation | Is the decision record for neighbouring landowners - risk mitigation aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | ISO 31000 risk management; stakeholder decision register; project charter | Yes / No / N/A + Score 0–5 + Rating
12.097 | 12 | WP12 | Stakeholder Mapping and Public Participation | Have cost, programme and compliance implications of municipality - stakeholder acceptance been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | King IV governance practice; Companies Act 71 of 2008; project mandate file | Yes / No / N/A + Score 0–5 + Rating
12.098 | 12 | WP12 | Stakeholder Mapping and Public Participation | Has the team obtained written confirmation or documented proof for road authority - stakeholder acceptance? | Current certificate/letter/report, version control and document-control entry. | PMBOK stage-gate governance; board resolution; delegated authority matrix | Yes / No / N/A + Score 0–5 + Rating
12.099 | 12 | WP12 | Stakeholder Mapping and Public Participation | Does the evidence for DMRE - stakeholder acceptance support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | ISO 31000 risk management; stakeholder decision register; project charter | Yes / No / N/A + Score 0–5 + Rating
12.100 | 12 | WP12 | Stakeholder Mapping and Public Participation | Have dependencies linked to environmental authority - stakeholder acceptance been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | King IV governance practice; Companies Act 71 of 2008; project mandate file | Yes / No / N/A + Score 0–5 + Rating
13.001 | 13 | WP13 | Concept Development | Has the project team confirmed site layout - governance approval in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
13.002 | 13 | WP13 | Concept Development | Is there a responsible owner, due date and approval route for Boxer store placement - governance approval? | Register entry, supporting drawing/report, approval note and updated risk item. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
13.003 | 13 | WP13 | Concept Development | Has the gate file tested whether fuel forecourt interface - governance approval creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
13.004 | 13 | WP13 | Concept Development | Are assumptions for line-shop frontage - governance approval documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
13.005 | 13 | WP13 | Concept Development | Has the relevant authority, specialist or professional adviser reviewed QSR positioning - governance approval where required? | Authority response, compliance checklist, file note and management approval. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
13.006 | 13 | WP13 | Concept Development | Is the decision record for parking concept - governance approval aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
13.007 | 13 | WP13 | Concept Development | Have cost, programme and compliance implications of site layout - legal authority been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
13.008 | 13 | WP13 | Concept Development | Has the team obtained written confirmation or documented proof for Boxer store placement - legal authority? | Current certificate/letter/report, version control and document-control entry. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
13.009 | 13 | WP13 | Concept Development | Does the evidence for fuel forecourt interface - legal authority support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
13.010 | 13 | WP13 | Concept Development | Have dependencies linked to line-shop frontage - legal authority been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
13.011 | 13 | WP13 | Concept Development | Has the project team confirmed QSR positioning - legal authority in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
13.012 | 13 | WP13 | Concept Development | Is there a responsible owner, due date and approval route for parking concept - legal authority? | Register entry, supporting drawing/report, approval note and updated risk item. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
13.013 | 13 | WP13 | Concept Development | Has the gate file tested whether site layout - technical feasibility creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
13.014 | 13 | WP13 | Concept Development | Are assumptions for Boxer store placement - technical feasibility documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
13.015 | 13 | WP13 | Concept Development | Has the relevant authority, specialist or professional adviser reviewed fuel forecourt interface - technical feasibility where required? | Authority response, compliance checklist, file note and management approval. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
13.016 | 13 | WP13 | Concept Development | Is the decision record for line-shop frontage - technical feasibility aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
13.017 | 13 | WP13 | Concept Development | Have cost, programme and compliance implications of QSR positioning - technical feasibility been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
13.018 | 13 | WP13 | Concept Development | Has the team obtained written confirmation or documented proof for parking concept - technical feasibility? | Current certificate/letter/report, version control and document-control entry. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
13.019 | 13 | WP13 | Concept Development | Does the evidence for site layout - financial viability support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
13.020 | 13 | WP13 | Concept Development | Have dependencies linked to Boxer store placement - financial viability been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
13.021 | 13 | WP13 | Concept Development | Has the project team confirmed fuel forecourt interface - financial viability in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
13.022 | 13 | WP13 | Concept Development | Is there a responsible owner, due date and approval route for line-shop frontage - financial viability? | Register entry, supporting drawing/report, approval note and updated risk item. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
13.023 | 13 | WP13 | Concept Development | Has the gate file tested whether QSR positioning - financial viability creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
13.024 | 13 | WP13 | Concept Development | Are assumptions for parking concept - financial viability documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
13.025 | 13 | WP13 | Concept Development | Has the relevant authority, specialist or professional adviser reviewed site layout - programme impact where required? | Authority response, compliance checklist, file note and management approval. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
13.026 | 13 | WP13 | Concept Development | Is the decision record for Boxer store placement - programme impact aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
13.027 | 13 | WP13 | Concept Development | Have cost, programme and compliance implications of fuel forecourt interface - programme impact been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
13.028 | 13 | WP13 | Concept Development | Has the team obtained written confirmation or documented proof for line-shop frontage - programme impact? | Current certificate/letter/report, version control and document-control entry. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
13.029 | 13 | WP13 | Concept Development | Does the evidence for QSR positioning - programme impact support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
13.030 | 13 | WP13 | Concept Development | Have dependencies linked to parking concept - programme impact been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
13.031 | 13 | WP13 | Concept Development | Has the project team confirmed site layout - risk mitigation in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
13.032 | 13 | WP13 | Concept Development | Is there a responsible owner, due date and approval route for Boxer store placement - risk mitigation? | Register entry, supporting drawing/report, approval note and updated risk item. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
13.033 | 13 | WP13 | Concept Development | Has the gate file tested whether fuel forecourt interface - risk mitigation creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
13.034 | 13 | WP13 | Concept Development | Are assumptions for line-shop frontage - risk mitigation documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
13.035 | 13 | WP13 | Concept Development | Has the relevant authority, specialist or professional adviser reviewed QSR positioning - risk mitigation where required? | Authority response, compliance checklist, file note and management approval. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
13.036 | 13 | WP13 | Concept Development | Is the decision record for parking concept - risk mitigation aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
13.037 | 13 | WP13 | Concept Development | Have cost, programme and compliance implications of site layout - stakeholder acceptance been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
13.038 | 13 | WP13 | Concept Development | Has the team obtained written confirmation or documented proof for Boxer store placement - stakeholder acceptance? | Current certificate/letter/report, version control and document-control entry. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
13.039 | 13 | WP13 | Concept Development | Does the evidence for fuel forecourt interface - stakeholder acceptance support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
13.040 | 13 | WP13 | Concept Development | Have dependencies linked to line-shop frontage - stakeholder acceptance been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
13.041 | 13 | WP13 | Concept Development | Has the project team confirmed QSR positioning - stakeholder acceptance in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
13.042 | 13 | WP13 | Concept Development | Is there a responsible owner, due date and approval route for parking concept - stakeholder acceptance? | Register entry, supporting drawing/report, approval note and updated risk item. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
13.043 | 13 | WP13 | Concept Development | Has the gate file tested whether site layout - document control creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
13.044 | 13 | WP13 | Concept Development | Are assumptions for Boxer store placement - document control documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
13.045 | 13 | WP13 | Concept Development | Has the relevant authority, specialist or professional adviser reviewed fuel forecourt interface - document control where required? | Authority response, compliance checklist, file note and management approval. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
13.046 | 13 | WP13 | Concept Development | Is the decision record for line-shop frontage - document control aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
13.047 | 13 | WP13 | Concept Development | Have cost, programme and compliance implications of QSR positioning - document control been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
13.048 | 13 | WP13 | Concept Development | Has the team obtained written confirmation or documented proof for parking concept - document control? | Current certificate/letter/report, version control and document-control entry. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
13.049 | 13 | WP13 | Concept Development | Does the evidence for site layout - professional certification support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
13.050 | 13 | WP13 | Concept Development | Have dependencies linked to Boxer store placement - professional certification been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
13.051 | 13 | WP13 | Concept Development | Has the project team confirmed fuel forecourt interface - professional certification in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
13.052 | 13 | WP13 | Concept Development | Is there a responsible owner, due date and approval route for line-shop frontage - professional certification? | Register entry, supporting drawing/report, approval note and updated risk item. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
13.053 | 13 | WP13 | Concept Development | Has the gate file tested whether QSR positioning - professional certification creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
13.054 | 13 | WP13 | Concept Development | Are assumptions for parking concept - professional certification documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
13.055 | 13 | WP13 | Concept Development | Has the relevant authority, specialist or professional adviser reviewed site layout - implementation readiness where required? | Authority response, compliance checklist, file note and management approval. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
13.056 | 13 | WP13 | Concept Development | Is the decision record for Boxer store placement - implementation readiness aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
13.057 | 13 | WP13 | Concept Development | Have cost, programme and compliance implications of fuel forecourt interface - implementation readiness been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
13.058 | 13 | WP13 | Concept Development | Has the team obtained written confirmation or documented proof for line-shop frontage - implementation readiness? | Current certificate/letter/report, version control and document-control entry. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
13.059 | 13 | WP13 | Concept Development | Does the evidence for QSR positioning - implementation readiness support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
13.060 | 13 | WP13 | Concept Development | Have dependencies linked to parking concept - implementation readiness been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
13.061 | 13 | WP13 | Concept Development | Has the project team confirmed site layout - governance approval in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
13.062 | 13 | WP13 | Concept Development | Is there a responsible owner, due date and approval route for Boxer store placement - governance approval? | Register entry, supporting drawing/report, approval note and updated risk item. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
13.063 | 13 | WP13 | Concept Development | Has the gate file tested whether fuel forecourt interface - governance approval creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
13.064 | 13 | WP13 | Concept Development | Are assumptions for line-shop frontage - governance approval documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
13.065 | 13 | WP13 | Concept Development | Has the relevant authority, specialist or professional adviser reviewed QSR positioning - governance approval where required? | Authority response, compliance checklist, file note and management approval. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
13.066 | 13 | WP13 | Concept Development | Is the decision record for parking concept - governance approval aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
13.067 | 13 | WP13 | Concept Development | Have cost, programme and compliance implications of site layout - legal authority been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
13.068 | 13 | WP13 | Concept Development | Has the team obtained written confirmation or documented proof for Boxer store placement - legal authority? | Current certificate/letter/report, version control and document-control entry. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
13.069 | 13 | WP13 | Concept Development | Does the evidence for fuel forecourt interface - legal authority support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
13.070 | 13 | WP13 | Concept Development | Have dependencies linked to line-shop frontage - legal authority been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
13.071 | 13 | WP13 | Concept Development | Has the project team confirmed QSR positioning - legal authority in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
13.072 | 13 | WP13 | Concept Development | Is there a responsible owner, due date and approval route for parking concept - legal authority? | Register entry, supporting drawing/report, approval note and updated risk item. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
13.073 | 13 | WP13 | Concept Development | Has the gate file tested whether site layout - technical feasibility creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
13.074 | 13 | WP13 | Concept Development | Are assumptions for Boxer store placement - technical feasibility documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
13.075 | 13 | WP13 | Concept Development | Has the relevant authority, specialist or professional adviser reviewed fuel forecourt interface - technical feasibility where required? | Authority response, compliance checklist, file note and management approval. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
13.076 | 13 | WP13 | Concept Development | Is the decision record for line-shop frontage - technical feasibility aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
13.077 | 13 | WP13 | Concept Development | Have cost, programme and compliance implications of QSR positioning - technical feasibility been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
13.078 | 13 | WP13 | Concept Development | Has the team obtained written confirmation or documented proof for parking concept - technical feasibility? | Current certificate/letter/report, version control and document-control entry. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
13.079 | 13 | WP13 | Concept Development | Does the evidence for site layout - financial viability support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
13.080 | 13 | WP13 | Concept Development | Have dependencies linked to Boxer store placement - financial viability been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
13.081 | 13 | WP13 | Concept Development | Has the project team confirmed fuel forecourt interface - financial viability in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
13.082 | 13 | WP13 | Concept Development | Is there a responsible owner, due date and approval route for line-shop frontage - financial viability? | Register entry, supporting drawing/report, approval note and updated risk item. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
13.083 | 13 | WP13 | Concept Development | Has the gate file tested whether QSR positioning - financial viability creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
13.084 | 13 | WP13 | Concept Development | Are assumptions for parking concept - financial viability documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
13.085 | 13 | WP13 | Concept Development | Has the relevant authority, specialist or professional adviser reviewed site layout - programme impact where required? | Authority response, compliance checklist, file note and management approval. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
13.086 | 13 | WP13 | Concept Development | Is the decision record for Boxer store placement - programme impact aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
13.087 | 13 | WP13 | Concept Development | Have cost, programme and compliance implications of fuel forecourt interface - programme impact been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
13.088 | 13 | WP13 | Concept Development | Has the team obtained written confirmation or documented proof for line-shop frontage - programme impact? | Current certificate/letter/report, version control and document-control entry. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
13.089 | 13 | WP13 | Concept Development | Does the evidence for QSR positioning - programme impact support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
13.090 | 13 | WP13 | Concept Development | Have dependencies linked to parking concept - programme impact been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
13.091 | 13 | WP13 | Concept Development | Has the project team confirmed site layout - risk mitigation in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
13.092 | 13 | WP13 | Concept Development | Is there a responsible owner, due date and approval route for Boxer store placement - risk mitigation? | Register entry, supporting drawing/report, approval note and updated risk item. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
13.093 | 13 | WP13 | Concept Development | Has the gate file tested whether fuel forecourt interface - risk mitigation creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
13.094 | 13 | WP13 | Concept Development | Are assumptions for line-shop frontage - risk mitigation documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
13.095 | 13 | WP13 | Concept Development | Has the relevant authority, specialist or professional adviser reviewed QSR positioning - risk mitigation where required? | Authority response, compliance checklist, file note and management approval. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
13.096 | 13 | WP13 | Concept Development | Is the decision record for parking concept - risk mitigation aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
13.097 | 13 | WP13 | Concept Development | Have cost, programme and compliance implications of site layout - stakeholder acceptance been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
13.098 | 13 | WP13 | Concept Development | Has the team obtained written confirmation or documented proof for Boxer store placement - stakeholder acceptance? | Current certificate/letter/report, version control and document-control entry. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
13.099 | 13 | WP13 | Concept Development | Does the evidence for fuel forecourt interface - stakeholder acceptance support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
13.100 | 13 | WP13 | Concept Development | Have dependencies linked to line-shop frontage - stakeholder acceptance been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
14.001 | 14 | WP14 | Retail Masterplanning and GLA Strategy | Has the project team confirmed anchor GLA - governance approval in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
14.002 | 14 | WP14 | Retail Masterplanning and GLA Strategy | Is there a responsible owner, due date and approval route for line-shop GLA - governance approval? | Register entry, supporting drawing/report, approval note and updated risk item. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
14.003 | 14 | WP14 | Retail Masterplanning and GLA Strategy | Has the gate file tested whether QSR GLA - governance approval creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
14.004 | 14 | WP14 | Retail Masterplanning and GLA Strategy | Are assumptions for forecourt convenience offer - governance approval documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
14.005 | 14 | WP14 | Retail Masterplanning and GLA Strategy | Has the relevant authority, specialist or professional adviser reviewed back-of-house allocation - governance approval where required? | Authority response, compliance checklist, file note and management approval. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
14.006 | 14 | WP14 | Retail Masterplanning and GLA Strategy | Is the decision record for loading areas - governance approval aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
14.007 | 14 | WP14 | Retail Masterplanning and GLA Strategy | Have cost, programme and compliance implications of anchor GLA - legal authority been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
14.008 | 14 | WP14 | Retail Masterplanning and GLA Strategy | Has the team obtained written confirmation or documented proof for line-shop GLA - legal authority? | Current certificate/letter/report, version control and document-control entry. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
14.009 | 14 | WP14 | Retail Masterplanning and GLA Strategy | Does the evidence for QSR GLA - legal authority support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
14.010 | 14 | WP14 | Retail Masterplanning and GLA Strategy | Have dependencies linked to forecourt convenience offer - legal authority been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
14.011 | 14 | WP14 | Retail Masterplanning and GLA Strategy | Has the project team confirmed back-of-house allocation - legal authority in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
14.012 | 14 | WP14 | Retail Masterplanning and GLA Strategy | Is there a responsible owner, due date and approval route for loading areas - legal authority? | Register entry, supporting drawing/report, approval note and updated risk item. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
14.013 | 14 | WP14 | Retail Masterplanning and GLA Strategy | Has the gate file tested whether anchor GLA - technical feasibility creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
14.014 | 14 | WP14 | Retail Masterplanning and GLA Strategy | Are assumptions for line-shop GLA - technical feasibility documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
14.015 | 14 | WP14 | Retail Masterplanning and GLA Strategy | Has the relevant authority, specialist or professional adviser reviewed QSR GLA - technical feasibility where required? | Authority response, compliance checklist, file note and management approval. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
14.016 | 14 | WP14 | Retail Masterplanning and GLA Strategy | Is the decision record for forecourt convenience offer - technical feasibility aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
14.017 | 14 | WP14 | Retail Masterplanning and GLA Strategy | Have cost, programme and compliance implications of back-of-house allocation - technical feasibility been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
14.018 | 14 | WP14 | Retail Masterplanning and GLA Strategy | Has the team obtained written confirmation or documented proof for loading areas - technical feasibility? | Current certificate/letter/report, version control and document-control entry. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
14.019 | 14 | WP14 | Retail Masterplanning and GLA Strategy | Does the evidence for anchor GLA - financial viability support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
14.020 | 14 | WP14 | Retail Masterplanning and GLA Strategy | Have dependencies linked to line-shop GLA - financial viability been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
14.021 | 14 | WP14 | Retail Masterplanning and GLA Strategy | Has the project team confirmed QSR GLA - financial viability in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
14.022 | 14 | WP14 | Retail Masterplanning and GLA Strategy | Is there a responsible owner, due date and approval route for forecourt convenience offer - financial viability? | Register entry, supporting drawing/report, approval note and updated risk item. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
14.023 | 14 | WP14 | Retail Masterplanning and GLA Strategy | Has the gate file tested whether back-of-house allocation - financial viability creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
14.024 | 14 | WP14 | Retail Masterplanning and GLA Strategy | Are assumptions for loading areas - financial viability documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
14.025 | 14 | WP14 | Retail Masterplanning and GLA Strategy | Has the relevant authority, specialist or professional adviser reviewed anchor GLA - programme impact where required? | Authority response, compliance checklist, file note and management approval. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
14.026 | 14 | WP14 | Retail Masterplanning and GLA Strategy | Is the decision record for line-shop GLA - programme impact aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
14.027 | 14 | WP14 | Retail Masterplanning and GLA Strategy | Have cost, programme and compliance implications of QSR GLA - programme impact been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
14.028 | 14 | WP14 | Retail Masterplanning and GLA Strategy | Has the team obtained written confirmation or documented proof for forecourt convenience offer - programme impact? | Current certificate/letter/report, version control and document-control entry. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
14.029 | 14 | WP14 | Retail Masterplanning and GLA Strategy | Does the evidence for back-of-house allocation - programme impact support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
14.030 | 14 | WP14 | Retail Masterplanning and GLA Strategy | Have dependencies linked to loading areas - programme impact been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
14.031 | 14 | WP14 | Retail Masterplanning and GLA Strategy | Has the project team confirmed anchor GLA - risk mitigation in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
14.032 | 14 | WP14 | Retail Masterplanning and GLA Strategy | Is there a responsible owner, due date and approval route for line-shop GLA - risk mitigation? | Register entry, supporting drawing/report, approval note and updated risk item. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
14.033 | 14 | WP14 | Retail Masterplanning and GLA Strategy | Has the gate file tested whether QSR GLA - risk mitigation creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
14.034 | 14 | WP14 | Retail Masterplanning and GLA Strategy | Are assumptions for forecourt convenience offer - risk mitigation documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
14.035 | 14 | WP14 | Retail Masterplanning and GLA Strategy | Has the relevant authority, specialist or professional adviser reviewed back-of-house allocation - risk mitigation where required? | Authority response, compliance checklist, file note and management approval. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
14.036 | 14 | WP14 | Retail Masterplanning and GLA Strategy | Is the decision record for loading areas - risk mitigation aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
14.037 | 14 | WP14 | Retail Masterplanning and GLA Strategy | Have cost, programme and compliance implications of anchor GLA - stakeholder acceptance been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
14.038 | 14 | WP14 | Retail Masterplanning and GLA Strategy | Has the team obtained written confirmation or documented proof for line-shop GLA - stakeholder acceptance? | Current certificate/letter/report, version control and document-control entry. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
14.039 | 14 | WP14 | Retail Masterplanning and GLA Strategy | Does the evidence for QSR GLA - stakeholder acceptance support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
14.040 | 14 | WP14 | Retail Masterplanning and GLA Strategy | Have dependencies linked to forecourt convenience offer - stakeholder acceptance been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
14.041 | 14 | WP14 | Retail Masterplanning and GLA Strategy | Has the project team confirmed back-of-house allocation - stakeholder acceptance in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
14.042 | 14 | WP14 | Retail Masterplanning and GLA Strategy | Is there a responsible owner, due date and approval route for loading areas - stakeholder acceptance? | Register entry, supporting drawing/report, approval note and updated risk item. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
14.043 | 14 | WP14 | Retail Masterplanning and GLA Strategy | Has the gate file tested whether anchor GLA - document control creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
14.044 | 14 | WP14 | Retail Masterplanning and GLA Strategy | Are assumptions for line-shop GLA - document control documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
14.045 | 14 | WP14 | Retail Masterplanning and GLA Strategy | Has the relevant authority, specialist or professional adviser reviewed QSR GLA - document control where required? | Authority response, compliance checklist, file note and management approval. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
14.046 | 14 | WP14 | Retail Masterplanning and GLA Strategy | Is the decision record for forecourt convenience offer - document control aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
14.047 | 14 | WP14 | Retail Masterplanning and GLA Strategy | Have cost, programme and compliance implications of back-of-house allocation - document control been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
14.048 | 14 | WP14 | Retail Masterplanning and GLA Strategy | Has the team obtained written confirmation or documented proof for loading areas - document control? | Current certificate/letter/report, version control and document-control entry. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
14.049 | 14 | WP14 | Retail Masterplanning and GLA Strategy | Does the evidence for anchor GLA - professional certification support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
14.050 | 14 | WP14 | Retail Masterplanning and GLA Strategy | Have dependencies linked to line-shop GLA - professional certification been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
14.051 | 14 | WP14 | Retail Masterplanning and GLA Strategy | Has the project team confirmed QSR GLA - professional certification in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
14.052 | 14 | WP14 | Retail Masterplanning and GLA Strategy | Is there a responsible owner, due date and approval route for forecourt convenience offer - professional certification? | Register entry, supporting drawing/report, approval note and updated risk item. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
14.053 | 14 | WP14 | Retail Masterplanning and GLA Strategy | Has the gate file tested whether back-of-house allocation - professional certification creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
14.054 | 14 | WP14 | Retail Masterplanning and GLA Strategy | Are assumptions for loading areas - professional certification documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
14.055 | 14 | WP14 | Retail Masterplanning and GLA Strategy | Has the relevant authority, specialist or professional adviser reviewed anchor GLA - implementation readiness where required? | Authority response, compliance checklist, file note and management approval. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
14.056 | 14 | WP14 | Retail Masterplanning and GLA Strategy | Is the decision record for line-shop GLA - implementation readiness aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
14.057 | 14 | WP14 | Retail Masterplanning and GLA Strategy | Have cost, programme and compliance implications of QSR GLA - implementation readiness been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
14.058 | 14 | WP14 | Retail Masterplanning and GLA Strategy | Has the team obtained written confirmation or documented proof for forecourt convenience offer - implementation readiness? | Current certificate/letter/report, version control and document-control entry. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
14.059 | 14 | WP14 | Retail Masterplanning and GLA Strategy | Does the evidence for back-of-house allocation - implementation readiness support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
14.060 | 14 | WP14 | Retail Masterplanning and GLA Strategy | Have dependencies linked to loading areas - implementation readiness been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
14.061 | 14 | WP14 | Retail Masterplanning and GLA Strategy | Has the project team confirmed anchor GLA - governance approval in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
14.062 | 14 | WP14 | Retail Masterplanning and GLA Strategy | Is there a responsible owner, due date and approval route for line-shop GLA - governance approval? | Register entry, supporting drawing/report, approval note and updated risk item. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
14.063 | 14 | WP14 | Retail Masterplanning and GLA Strategy | Has the gate file tested whether QSR GLA - governance approval creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
14.064 | 14 | WP14 | Retail Masterplanning and GLA Strategy | Are assumptions for forecourt convenience offer - governance approval documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
14.065 | 14 | WP14 | Retail Masterplanning and GLA Strategy | Has the relevant authority, specialist or professional adviser reviewed back-of-house allocation - governance approval where required? | Authority response, compliance checklist, file note and management approval. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
14.066 | 14 | WP14 | Retail Masterplanning and GLA Strategy | Is the decision record for loading areas - governance approval aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
14.067 | 14 | WP14 | Retail Masterplanning and GLA Strategy | Have cost, programme and compliance implications of anchor GLA - legal authority been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
14.068 | 14 | WP14 | Retail Masterplanning and GLA Strategy | Has the team obtained written confirmation or documented proof for line-shop GLA - legal authority? | Current certificate/letter/report, version control and document-control entry. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
14.069 | 14 | WP14 | Retail Masterplanning and GLA Strategy | Does the evidence for QSR GLA - legal authority support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
14.070 | 14 | WP14 | Retail Masterplanning and GLA Strategy | Have dependencies linked to forecourt convenience offer - legal authority been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
14.071 | 14 | WP14 | Retail Masterplanning and GLA Strategy | Has the project team confirmed back-of-house allocation - legal authority in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
14.072 | 14 | WP14 | Retail Masterplanning and GLA Strategy | Is there a responsible owner, due date and approval route for loading areas - legal authority? | Register entry, supporting drawing/report, approval note and updated risk item. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
14.073 | 14 | WP14 | Retail Masterplanning and GLA Strategy | Has the gate file tested whether anchor GLA - technical feasibility creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
14.074 | 14 | WP14 | Retail Masterplanning and GLA Strategy | Are assumptions for line-shop GLA - technical feasibility documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
14.075 | 14 | WP14 | Retail Masterplanning and GLA Strategy | Has the relevant authority, specialist or professional adviser reviewed QSR GLA - technical feasibility where required? | Authority response, compliance checklist, file note and management approval. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
14.076 | 14 | WP14 | Retail Masterplanning and GLA Strategy | Is the decision record for forecourt convenience offer - technical feasibility aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
14.077 | 14 | WP14 | Retail Masterplanning and GLA Strategy | Have cost, programme and compliance implications of back-of-house allocation - technical feasibility been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
14.078 | 14 | WP14 | Retail Masterplanning and GLA Strategy | Has the team obtained written confirmation or documented proof for loading areas - technical feasibility? | Current certificate/letter/report, version control and document-control entry. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
14.079 | 14 | WP14 | Retail Masterplanning and GLA Strategy | Does the evidence for anchor GLA - financial viability support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
14.080 | 14 | WP14 | Retail Masterplanning and GLA Strategy | Have dependencies linked to line-shop GLA - financial viability been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
14.081 | 14 | WP14 | Retail Masterplanning and GLA Strategy | Has the project team confirmed QSR GLA - financial viability in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
14.082 | 14 | WP14 | Retail Masterplanning and GLA Strategy | Is there a responsible owner, due date and approval route for forecourt convenience offer - financial viability? | Register entry, supporting drawing/report, approval note and updated risk item. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
14.083 | 14 | WP14 | Retail Masterplanning and GLA Strategy | Has the gate file tested whether back-of-house allocation - financial viability creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
14.084 | 14 | WP14 | Retail Masterplanning and GLA Strategy | Are assumptions for loading areas - financial viability documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
14.085 | 14 | WP14 | Retail Masterplanning and GLA Strategy | Has the relevant authority, specialist or professional adviser reviewed anchor GLA - programme impact where required? | Authority response, compliance checklist, file note and management approval. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
14.086 | 14 | WP14 | Retail Masterplanning and GLA Strategy | Is the decision record for line-shop GLA - programme impact aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
14.087 | 14 | WP14 | Retail Masterplanning and GLA Strategy | Have cost, programme and compliance implications of QSR GLA - programme impact been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
14.088 | 14 | WP14 | Retail Masterplanning and GLA Strategy | Has the team obtained written confirmation or documented proof for forecourt convenience offer - programme impact? | Current certificate/letter/report, version control and document-control entry. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
14.089 | 14 | WP14 | Retail Masterplanning and GLA Strategy | Does the evidence for back-of-house allocation - programme impact support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
14.090 | 14 | WP14 | Retail Masterplanning and GLA Strategy | Have dependencies linked to loading areas - programme impact been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
14.091 | 14 | WP14 | Retail Masterplanning and GLA Strategy | Has the project team confirmed anchor GLA - risk mitigation in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
14.092 | 14 | WP14 | Retail Masterplanning and GLA Strategy | Is there a responsible owner, due date and approval route for line-shop GLA - risk mitigation? | Register entry, supporting drawing/report, approval note and updated risk item. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
14.093 | 14 | WP14 | Retail Masterplanning and GLA Strategy | Has the gate file tested whether QSR GLA - risk mitigation creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
14.094 | 14 | WP14 | Retail Masterplanning and GLA Strategy | Are assumptions for forecourt convenience offer - risk mitigation documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
14.095 | 14 | WP14 | Retail Masterplanning and GLA Strategy | Has the relevant authority, specialist or professional adviser reviewed back-of-house allocation - risk mitigation where required? | Authority response, compliance checklist, file note and management approval. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
14.096 | 14 | WP14 | Retail Masterplanning and GLA Strategy | Is the decision record for loading areas - risk mitigation aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
14.097 | 14 | WP14 | Retail Masterplanning and GLA Strategy | Have cost, programme and compliance implications of anchor GLA - stakeholder acceptance been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
14.098 | 14 | WP14 | Retail Masterplanning and GLA Strategy | Has the team obtained written confirmation or documented proof for line-shop GLA - stakeholder acceptance? | Current certificate/letter/report, version control and document-control entry. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
14.099 | 14 | WP14 | Retail Masterplanning and GLA Strategy | Does the evidence for QSR GLA - stakeholder acceptance support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
14.100 | 14 | WP14 | Retail Masterplanning and GLA Strategy | Have dependencies linked to forecourt convenience offer - stakeholder acceptance been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
15.001 | 15 | WP15 | Boxer Superstores Anchor Alignment | Has the project team confirmed Boxer specifications - governance approval in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
15.002 | 15 | WP15 | Boxer Superstores Anchor Alignment | Is there a responsible owner, due date and approval route for anchor lease principles - governance approval? | Register entry, supporting drawing/report, approval note and updated risk item. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
15.003 | 15 | WP15 | Boxer Superstores Anchor Alignment | Has the gate file tested whether loading requirements - governance approval creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
15.004 | 15 | WP15 | Boxer Superstores Anchor Alignment | Are assumptions for store footprint - governance approval documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
15.005 | 15 | WP15 | Boxer Superstores Anchor Alignment | Has the relevant authority, specialist or professional adviser reviewed service yard - governance approval where required? | Authority response, compliance checklist, file note and management approval. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
15.006 | 15 | WP15 | Boxer Superstores Anchor Alignment | Is the decision record for delivery windows - governance approval aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
15.007 | 15 | WP15 | Boxer Superstores Anchor Alignment | Have cost, programme and compliance implications of Boxer specifications - legal authority been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
15.008 | 15 | WP15 | Boxer Superstores Anchor Alignment | Has the team obtained written confirmation or documented proof for anchor lease principles - legal authority? | Current certificate/letter/report, version control and document-control entry. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
15.009 | 15 | WP15 | Boxer Superstores Anchor Alignment | Does the evidence for loading requirements - legal authority support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
15.010 | 15 | WP15 | Boxer Superstores Anchor Alignment | Have dependencies linked to store footprint - legal authority been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
15.011 | 15 | WP15 | Boxer Superstores Anchor Alignment | Has the project team confirmed service yard - legal authority in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
15.012 | 15 | WP15 | Boxer Superstores Anchor Alignment | Is there a responsible owner, due date and approval route for delivery windows - legal authority? | Register entry, supporting drawing/report, approval note and updated risk item. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
15.013 | 15 | WP15 | Boxer Superstores Anchor Alignment | Has the gate file tested whether Boxer specifications - technical feasibility creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
15.014 | 15 | WP15 | Boxer Superstores Anchor Alignment | Are assumptions for anchor lease principles - technical feasibility documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
15.015 | 15 | WP15 | Boxer Superstores Anchor Alignment | Has the relevant authority, specialist or professional adviser reviewed loading requirements - technical feasibility where required? | Authority response, compliance checklist, file note and management approval. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
15.016 | 15 | WP15 | Boxer Superstores Anchor Alignment | Is the decision record for store footprint - technical feasibility aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
15.017 | 15 | WP15 | Boxer Superstores Anchor Alignment | Have cost, programme and compliance implications of service yard - technical feasibility been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
15.018 | 15 | WP15 | Boxer Superstores Anchor Alignment | Has the team obtained written confirmation or documented proof for delivery windows - technical feasibility? | Current certificate/letter/report, version control and document-control entry. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
15.019 | 15 | WP15 | Boxer Superstores Anchor Alignment | Does the evidence for Boxer specifications - financial viability support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
15.020 | 15 | WP15 | Boxer Superstores Anchor Alignment | Have dependencies linked to anchor lease principles - financial viability been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
15.021 | 15 | WP15 | Boxer Superstores Anchor Alignment | Has the project team confirmed loading requirements - financial viability in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
15.022 | 15 | WP15 | Boxer Superstores Anchor Alignment | Is there a responsible owner, due date and approval route for store footprint - financial viability? | Register entry, supporting drawing/report, approval note and updated risk item. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
15.023 | 15 | WP15 | Boxer Superstores Anchor Alignment | Has the gate file tested whether service yard - financial viability creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
15.024 | 15 | WP15 | Boxer Superstores Anchor Alignment | Are assumptions for delivery windows - financial viability documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
15.025 | 15 | WP15 | Boxer Superstores Anchor Alignment | Has the relevant authority, specialist or professional adviser reviewed Boxer specifications - programme impact where required? | Authority response, compliance checklist, file note and management approval. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
15.026 | 15 | WP15 | Boxer Superstores Anchor Alignment | Is the decision record for anchor lease principles - programme impact aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
15.027 | 15 | WP15 | Boxer Superstores Anchor Alignment | Have cost, programme and compliance implications of loading requirements - programme impact been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
15.028 | 15 | WP15 | Boxer Superstores Anchor Alignment | Has the team obtained written confirmation or documented proof for store footprint - programme impact? | Current certificate/letter/report, version control and document-control entry. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
15.029 | 15 | WP15 | Boxer Superstores Anchor Alignment | Does the evidence for service yard - programme impact support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
15.030 | 15 | WP15 | Boxer Superstores Anchor Alignment | Have dependencies linked to delivery windows - programme impact been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
15.031 | 15 | WP15 | Boxer Superstores Anchor Alignment | Has the project team confirmed Boxer specifications - risk mitigation in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
15.032 | 15 | WP15 | Boxer Superstores Anchor Alignment | Is there a responsible owner, due date and approval route for anchor lease principles - risk mitigation? | Register entry, supporting drawing/report, approval note and updated risk item. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
15.033 | 15 | WP15 | Boxer Superstores Anchor Alignment | Has the gate file tested whether loading requirements - risk mitigation creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
15.034 | 15 | WP15 | Boxer Superstores Anchor Alignment | Are assumptions for store footprint - risk mitigation documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
15.035 | 15 | WP15 | Boxer Superstores Anchor Alignment | Has the relevant authority, specialist or professional adviser reviewed service yard - risk mitigation where required? | Authority response, compliance checklist, file note and management approval. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
15.036 | 15 | WP15 | Boxer Superstores Anchor Alignment | Is the decision record for delivery windows - risk mitigation aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
15.037 | 15 | WP15 | Boxer Superstores Anchor Alignment | Have cost, programme and compliance implications of Boxer specifications - stakeholder acceptance been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
15.038 | 15 | WP15 | Boxer Superstores Anchor Alignment | Has the team obtained written confirmation or documented proof for anchor lease principles - stakeholder acceptance? | Current certificate/letter/report, version control and document-control entry. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
15.039 | 15 | WP15 | Boxer Superstores Anchor Alignment | Does the evidence for loading requirements - stakeholder acceptance support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
15.040 | 15 | WP15 | Boxer Superstores Anchor Alignment | Have dependencies linked to store footprint - stakeholder acceptance been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
15.041 | 15 | WP15 | Boxer Superstores Anchor Alignment | Has the project team confirmed service yard - stakeholder acceptance in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
15.042 | 15 | WP15 | Boxer Superstores Anchor Alignment | Is there a responsible owner, due date and approval route for delivery windows - stakeholder acceptance? | Register entry, supporting drawing/report, approval note and updated risk item. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
15.043 | 15 | WP15 | Boxer Superstores Anchor Alignment | Has the gate file tested whether Boxer specifications - document control creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
15.044 | 15 | WP15 | Boxer Superstores Anchor Alignment | Are assumptions for anchor lease principles - document control documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
15.045 | 15 | WP15 | Boxer Superstores Anchor Alignment | Has the relevant authority, specialist or professional adviser reviewed loading requirements - document control where required? | Authority response, compliance checklist, file note and management approval. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
15.046 | 15 | WP15 | Boxer Superstores Anchor Alignment | Is the decision record for store footprint - document control aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
15.047 | 15 | WP15 | Boxer Superstores Anchor Alignment | Have cost, programme and compliance implications of service yard - document control been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
15.048 | 15 | WP15 | Boxer Superstores Anchor Alignment | Has the team obtained written confirmation or documented proof for delivery windows - document control? | Current certificate/letter/report, version control and document-control entry. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
15.049 | 15 | WP15 | Boxer Superstores Anchor Alignment | Does the evidence for Boxer specifications - professional certification support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
15.050 | 15 | WP15 | Boxer Superstores Anchor Alignment | Have dependencies linked to anchor lease principles - professional certification been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
15.051 | 15 | WP15 | Boxer Superstores Anchor Alignment | Has the project team confirmed loading requirements - professional certification in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
15.052 | 15 | WP15 | Boxer Superstores Anchor Alignment | Is there a responsible owner, due date and approval route for store footprint - professional certification? | Register entry, supporting drawing/report, approval note and updated risk item. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
15.053 | 15 | WP15 | Boxer Superstores Anchor Alignment | Has the gate file tested whether service yard - professional certification creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
15.054 | 15 | WP15 | Boxer Superstores Anchor Alignment | Are assumptions for delivery windows - professional certification documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
15.055 | 15 | WP15 | Boxer Superstores Anchor Alignment | Has the relevant authority, specialist or professional adviser reviewed Boxer specifications - implementation readiness where required? | Authority response, compliance checklist, file note and management approval. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
15.056 | 15 | WP15 | Boxer Superstores Anchor Alignment | Is the decision record for anchor lease principles - implementation readiness aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
15.057 | 15 | WP15 | Boxer Superstores Anchor Alignment | Have cost, programme and compliance implications of loading requirements - implementation readiness been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
15.058 | 15 | WP15 | Boxer Superstores Anchor Alignment | Has the team obtained written confirmation or documented proof for store footprint - implementation readiness? | Current certificate/letter/report, version control and document-control entry. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
15.059 | 15 | WP15 | Boxer Superstores Anchor Alignment | Does the evidence for service yard - implementation readiness support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
15.060 | 15 | WP15 | Boxer Superstores Anchor Alignment | Have dependencies linked to delivery windows - implementation readiness been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
15.061 | 15 | WP15 | Boxer Superstores Anchor Alignment | Has the project team confirmed Boxer specifications - governance approval in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
15.062 | 15 | WP15 | Boxer Superstores Anchor Alignment | Is there a responsible owner, due date and approval route for anchor lease principles - governance approval? | Register entry, supporting drawing/report, approval note and updated risk item. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
15.063 | 15 | WP15 | Boxer Superstores Anchor Alignment | Has the gate file tested whether loading requirements - governance approval creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
15.064 | 15 | WP15 | Boxer Superstores Anchor Alignment | Are assumptions for store footprint - governance approval documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
15.065 | 15 | WP15 | Boxer Superstores Anchor Alignment | Has the relevant authority, specialist or professional adviser reviewed service yard - governance approval where required? | Authority response, compliance checklist, file note and management approval. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
15.066 | 15 | WP15 | Boxer Superstores Anchor Alignment | Is the decision record for delivery windows - governance approval aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
15.067 | 15 | WP15 | Boxer Superstores Anchor Alignment | Have cost, programme and compliance implications of Boxer specifications - legal authority been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
15.068 | 15 | WP15 | Boxer Superstores Anchor Alignment | Has the team obtained written confirmation or documented proof for anchor lease principles - legal authority? | Current certificate/letter/report, version control and document-control entry. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
15.069 | 15 | WP15 | Boxer Superstores Anchor Alignment | Does the evidence for loading requirements - legal authority support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
15.070 | 15 | WP15 | Boxer Superstores Anchor Alignment | Have dependencies linked to store footprint - legal authority been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
15.071 | 15 | WP15 | Boxer Superstores Anchor Alignment | Has the project team confirmed service yard - legal authority in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
15.072 | 15 | WP15 | Boxer Superstores Anchor Alignment | Is there a responsible owner, due date and approval route for delivery windows - legal authority? | Register entry, supporting drawing/report, approval note and updated risk item. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
15.073 | 15 | WP15 | Boxer Superstores Anchor Alignment | Has the gate file tested whether Boxer specifications - technical feasibility creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
15.074 | 15 | WP15 | Boxer Superstores Anchor Alignment | Are assumptions for anchor lease principles - technical feasibility documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
15.075 | 15 | WP15 | Boxer Superstores Anchor Alignment | Has the relevant authority, specialist or professional adviser reviewed loading requirements - technical feasibility where required? | Authority response, compliance checklist, file note and management approval. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
15.076 | 15 | WP15 | Boxer Superstores Anchor Alignment | Is the decision record for store footprint - technical feasibility aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
15.077 | 15 | WP15 | Boxer Superstores Anchor Alignment | Have cost, programme and compliance implications of service yard - technical feasibility been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
15.078 | 15 | WP15 | Boxer Superstores Anchor Alignment | Has the team obtained written confirmation or documented proof for delivery windows - technical feasibility? | Current certificate/letter/report, version control and document-control entry. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
15.079 | 15 | WP15 | Boxer Superstores Anchor Alignment | Does the evidence for Boxer specifications - financial viability support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
15.080 | 15 | WP15 | Boxer Superstores Anchor Alignment | Have dependencies linked to anchor lease principles - financial viability been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
15.081 | 15 | WP15 | Boxer Superstores Anchor Alignment | Has the project team confirmed loading requirements - financial viability in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
15.082 | 15 | WP15 | Boxer Superstores Anchor Alignment | Is there a responsible owner, due date and approval route for store footprint - financial viability? | Register entry, supporting drawing/report, approval note and updated risk item. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
15.083 | 15 | WP15 | Boxer Superstores Anchor Alignment | Has the gate file tested whether service yard - financial viability creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
15.084 | 15 | WP15 | Boxer Superstores Anchor Alignment | Are assumptions for delivery windows - financial viability documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
15.085 | 15 | WP15 | Boxer Superstores Anchor Alignment | Has the relevant authority, specialist or professional adviser reviewed Boxer specifications - programme impact where required? | Authority response, compliance checklist, file note and management approval. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
15.086 | 15 | WP15 | Boxer Superstores Anchor Alignment | Is the decision record for anchor lease principles - programme impact aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
15.087 | 15 | WP15 | Boxer Superstores Anchor Alignment | Have cost, programme and compliance implications of loading requirements - programme impact been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
15.088 | 15 | WP15 | Boxer Superstores Anchor Alignment | Has the team obtained written confirmation or documented proof for store footprint - programme impact? | Current certificate/letter/report, version control and document-control entry. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
15.089 | 15 | WP15 | Boxer Superstores Anchor Alignment | Does the evidence for service yard - programme impact support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
15.090 | 15 | WP15 | Boxer Superstores Anchor Alignment | Have dependencies linked to delivery windows - programme impact been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
15.091 | 15 | WP15 | Boxer Superstores Anchor Alignment | Has the project team confirmed Boxer specifications - risk mitigation in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
15.092 | 15 | WP15 | Boxer Superstores Anchor Alignment | Is there a responsible owner, due date and approval route for anchor lease principles - risk mitigation? | Register entry, supporting drawing/report, approval note and updated risk item. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
15.093 | 15 | WP15 | Boxer Superstores Anchor Alignment | Has the gate file tested whether loading requirements - risk mitigation creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
15.094 | 15 | WP15 | Boxer Superstores Anchor Alignment | Are assumptions for store footprint - risk mitigation documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
15.095 | 15 | WP15 | Boxer Superstores Anchor Alignment | Has the relevant authority, specialist or professional adviser reviewed service yard - risk mitigation where required? | Authority response, compliance checklist, file note and management approval. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
15.096 | 15 | WP15 | Boxer Superstores Anchor Alignment | Is the decision record for delivery windows - risk mitigation aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
15.097 | 15 | WP15 | Boxer Superstores Anchor Alignment | Have cost, programme and compliance implications of Boxer specifications - stakeholder acceptance been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
15.098 | 15 | WP15 | Boxer Superstores Anchor Alignment | Has the team obtained written confirmation or documented proof for anchor lease principles - stakeholder acceptance? | Current certificate/letter/report, version control and document-control entry. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
15.099 | 15 | WP15 | Boxer Superstores Anchor Alignment | Does the evidence for loading requirements - stakeholder acceptance support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
15.100 | 15 | WP15 | Boxer Superstores Anchor Alignment | Have dependencies linked to store footprint - stakeholder acceptance been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
16.001 | 16 | WP16 | Tenant Acquisition Strategy | Has the project team confirmed target tenant list - governance approval in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
16.002 | 16 | WP16 | Tenant Acquisition Strategy | Is there a responsible owner, due date and approval route for leasing brochure - governance approval? | Register entry, supporting drawing/report, approval note and updated risk item. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
16.003 | 16 | WP16 | Tenant Acquisition Strategy | Has the gate file tested whether anchor-led positioning - governance approval creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
16.004 | 16 | WP16 | Tenant Acquisition Strategy | Are assumptions for rental assumptions - governance approval documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
16.005 | 16 | WP16 | Tenant Acquisition Strategy | Has the relevant authority, specialist or professional adviser reviewed tenant due diligence - governance approval where required? | Authority response, compliance checklist, file note and management approval. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
16.006 | 16 | WP16 | Tenant Acquisition Strategy | Is the decision record for letters of intent - governance approval aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
16.007 | 16 | WP16 | Tenant Acquisition Strategy | Have cost, programme and compliance implications of target tenant list - legal authority been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
16.008 | 16 | WP16 | Tenant Acquisition Strategy | Has the team obtained written confirmation or documented proof for leasing brochure - legal authority? | Current certificate/letter/report, version control and document-control entry. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
16.009 | 16 | WP16 | Tenant Acquisition Strategy | Does the evidence for anchor-led positioning - legal authority support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
16.010 | 16 | WP16 | Tenant Acquisition Strategy | Have dependencies linked to rental assumptions - legal authority been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
16.011 | 16 | WP16 | Tenant Acquisition Strategy | Has the project team confirmed tenant due diligence - legal authority in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
16.012 | 16 | WP16 | Tenant Acquisition Strategy | Is there a responsible owner, due date and approval route for letters of intent - legal authority? | Register entry, supporting drawing/report, approval note and updated risk item. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
16.013 | 16 | WP16 | Tenant Acquisition Strategy | Has the gate file tested whether target tenant list - technical feasibility creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
16.014 | 16 | WP16 | Tenant Acquisition Strategy | Are assumptions for leasing brochure - technical feasibility documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
16.015 | 16 | WP16 | Tenant Acquisition Strategy | Has the relevant authority, specialist or professional adviser reviewed anchor-led positioning - technical feasibility where required? | Authority response, compliance checklist, file note and management approval. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
16.016 | 16 | WP16 | Tenant Acquisition Strategy | Is the decision record for rental assumptions - technical feasibility aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
16.017 | 16 | WP16 | Tenant Acquisition Strategy | Have cost, programme and compliance implications of tenant due diligence - technical feasibility been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
16.018 | 16 | WP16 | Tenant Acquisition Strategy | Has the team obtained written confirmation or documented proof for letters of intent - technical feasibility? | Current certificate/letter/report, version control and document-control entry. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
16.019 | 16 | WP16 | Tenant Acquisition Strategy | Does the evidence for target tenant list - financial viability support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
16.020 | 16 | WP16 | Tenant Acquisition Strategy | Have dependencies linked to leasing brochure - financial viability been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
16.021 | 16 | WP16 | Tenant Acquisition Strategy | Has the project team confirmed anchor-led positioning - financial viability in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
16.022 | 16 | WP16 | Tenant Acquisition Strategy | Is there a responsible owner, due date and approval route for rental assumptions - financial viability? | Register entry, supporting drawing/report, approval note and updated risk item. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
16.023 | 16 | WP16 | Tenant Acquisition Strategy | Has the gate file tested whether tenant due diligence - financial viability creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
16.024 | 16 | WP16 | Tenant Acquisition Strategy | Are assumptions for letters of intent - financial viability documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
16.025 | 16 | WP16 | Tenant Acquisition Strategy | Has the relevant authority, specialist or professional adviser reviewed target tenant list - programme impact where required? | Authority response, compliance checklist, file note and management approval. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
16.026 | 16 | WP16 | Tenant Acquisition Strategy | Is the decision record for leasing brochure - programme impact aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
16.027 | 16 | WP16 | Tenant Acquisition Strategy | Have cost, programme and compliance implications of anchor-led positioning - programme impact been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
16.028 | 16 | WP16 | Tenant Acquisition Strategy | Has the team obtained written confirmation or documented proof for rental assumptions - programme impact? | Current certificate/letter/report, version control and document-control entry. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
16.029 | 16 | WP16 | Tenant Acquisition Strategy | Does the evidence for tenant due diligence - programme impact support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
16.030 | 16 | WP16 | Tenant Acquisition Strategy | Have dependencies linked to letters of intent - programme impact been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
16.031 | 16 | WP16 | Tenant Acquisition Strategy | Has the project team confirmed target tenant list - risk mitigation in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
16.032 | 16 | WP16 | Tenant Acquisition Strategy | Is there a responsible owner, due date and approval route for leasing brochure - risk mitigation? | Register entry, supporting drawing/report, approval note and updated risk item. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
16.033 | 16 | WP16 | Tenant Acquisition Strategy | Has the gate file tested whether anchor-led positioning - risk mitigation creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
16.034 | 16 | WP16 | Tenant Acquisition Strategy | Are assumptions for rental assumptions - risk mitigation documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
16.035 | 16 | WP16 | Tenant Acquisition Strategy | Has the relevant authority, specialist or professional adviser reviewed tenant due diligence - risk mitigation where required? | Authority response, compliance checklist, file note and management approval. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
16.036 | 16 | WP16 | Tenant Acquisition Strategy | Is the decision record for letters of intent - risk mitigation aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
16.037 | 16 | WP16 | Tenant Acquisition Strategy | Have cost, programme and compliance implications of target tenant list - stakeholder acceptance been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
16.038 | 16 | WP16 | Tenant Acquisition Strategy | Has the team obtained written confirmation or documented proof for leasing brochure - stakeholder acceptance? | Current certificate/letter/report, version control and document-control entry. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
16.039 | 16 | WP16 | Tenant Acquisition Strategy | Does the evidence for anchor-led positioning - stakeholder acceptance support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
16.040 | 16 | WP16 | Tenant Acquisition Strategy | Have dependencies linked to rental assumptions - stakeholder acceptance been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
16.041 | 16 | WP16 | Tenant Acquisition Strategy | Has the project team confirmed tenant due diligence - stakeholder acceptance in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
16.042 | 16 | WP16 | Tenant Acquisition Strategy | Is there a responsible owner, due date and approval route for letters of intent - stakeholder acceptance? | Register entry, supporting drawing/report, approval note and updated risk item. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
16.043 | 16 | WP16 | Tenant Acquisition Strategy | Has the gate file tested whether target tenant list - document control creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
16.044 | 16 | WP16 | Tenant Acquisition Strategy | Are assumptions for leasing brochure - document control documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
16.045 | 16 | WP16 | Tenant Acquisition Strategy | Has the relevant authority, specialist or professional adviser reviewed anchor-led positioning - document control where required? | Authority response, compliance checklist, file note and management approval. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
16.046 | 16 | WP16 | Tenant Acquisition Strategy | Is the decision record for rental assumptions - document control aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
16.047 | 16 | WP16 | Tenant Acquisition Strategy | Have cost, programme and compliance implications of tenant due diligence - document control been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
16.048 | 16 | WP16 | Tenant Acquisition Strategy | Has the team obtained written confirmation or documented proof for letters of intent - document control? | Current certificate/letter/report, version control and document-control entry. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
16.049 | 16 | WP16 | Tenant Acquisition Strategy | Does the evidence for target tenant list - professional certification support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
16.050 | 16 | WP16 | Tenant Acquisition Strategy | Have dependencies linked to leasing brochure - professional certification been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
16.051 | 16 | WP16 | Tenant Acquisition Strategy | Has the project team confirmed anchor-led positioning - professional certification in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
16.052 | 16 | WP16 | Tenant Acquisition Strategy | Is there a responsible owner, due date and approval route for rental assumptions - professional certification? | Register entry, supporting drawing/report, approval note and updated risk item. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
16.053 | 16 | WP16 | Tenant Acquisition Strategy | Has the gate file tested whether tenant due diligence - professional certification creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
16.054 | 16 | WP16 | Tenant Acquisition Strategy | Are assumptions for letters of intent - professional certification documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
16.055 | 16 | WP16 | Tenant Acquisition Strategy | Has the relevant authority, specialist or professional adviser reviewed target tenant list - implementation readiness where required? | Authority response, compliance checklist, file note and management approval. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
16.056 | 16 | WP16 | Tenant Acquisition Strategy | Is the decision record for leasing brochure - implementation readiness aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
16.057 | 16 | WP16 | Tenant Acquisition Strategy | Have cost, programme and compliance implications of anchor-led positioning - implementation readiness been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
16.058 | 16 | WP16 | Tenant Acquisition Strategy | Has the team obtained written confirmation or documented proof for rental assumptions - implementation readiness? | Current certificate/letter/report, version control and document-control entry. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
16.059 | 16 | WP16 | Tenant Acquisition Strategy | Does the evidence for tenant due diligence - implementation readiness support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
16.060 | 16 | WP16 | Tenant Acquisition Strategy | Have dependencies linked to letters of intent - implementation readiness been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
16.061 | 16 | WP16 | Tenant Acquisition Strategy | Has the project team confirmed target tenant list - governance approval in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
16.062 | 16 | WP16 | Tenant Acquisition Strategy | Is there a responsible owner, due date and approval route for leasing brochure - governance approval? | Register entry, supporting drawing/report, approval note and updated risk item. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
16.063 | 16 | WP16 | Tenant Acquisition Strategy | Has the gate file tested whether anchor-led positioning - governance approval creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
16.064 | 16 | WP16 | Tenant Acquisition Strategy | Are assumptions for rental assumptions - governance approval documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
16.065 | 16 | WP16 | Tenant Acquisition Strategy | Has the relevant authority, specialist or professional adviser reviewed tenant due diligence - governance approval where required? | Authority response, compliance checklist, file note and management approval. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
16.066 | 16 | WP16 | Tenant Acquisition Strategy | Is the decision record for letters of intent - governance approval aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
16.067 | 16 | WP16 | Tenant Acquisition Strategy | Have cost, programme and compliance implications of target tenant list - legal authority been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
16.068 | 16 | WP16 | Tenant Acquisition Strategy | Has the team obtained written confirmation or documented proof for leasing brochure - legal authority? | Current certificate/letter/report, version control and document-control entry. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
16.069 | 16 | WP16 | Tenant Acquisition Strategy | Does the evidence for anchor-led positioning - legal authority support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
16.070 | 16 | WP16 | Tenant Acquisition Strategy | Have dependencies linked to rental assumptions - legal authority been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
16.071 | 16 | WP16 | Tenant Acquisition Strategy | Has the project team confirmed tenant due diligence - legal authority in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
16.072 | 16 | WP16 | Tenant Acquisition Strategy | Is there a responsible owner, due date and approval route for letters of intent - legal authority? | Register entry, supporting drawing/report, approval note and updated risk item. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
16.073 | 16 | WP16 | Tenant Acquisition Strategy | Has the gate file tested whether target tenant list - technical feasibility creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
16.074 | 16 | WP16 | Tenant Acquisition Strategy | Are assumptions for leasing brochure - technical feasibility documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
16.075 | 16 | WP16 | Tenant Acquisition Strategy | Has the relevant authority, specialist or professional adviser reviewed anchor-led positioning - technical feasibility where required? | Authority response, compliance checklist, file note and management approval. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
16.076 | 16 | WP16 | Tenant Acquisition Strategy | Is the decision record for rental assumptions - technical feasibility aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
16.077 | 16 | WP16 | Tenant Acquisition Strategy | Have cost, programme and compliance implications of tenant due diligence - technical feasibility been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
16.078 | 16 | WP16 | Tenant Acquisition Strategy | Has the team obtained written confirmation or documented proof for letters of intent - technical feasibility? | Current certificate/letter/report, version control and document-control entry. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
16.079 | 16 | WP16 | Tenant Acquisition Strategy | Does the evidence for target tenant list - financial viability support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
16.080 | 16 | WP16 | Tenant Acquisition Strategy | Have dependencies linked to leasing brochure - financial viability been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
16.081 | 16 | WP16 | Tenant Acquisition Strategy | Has the project team confirmed anchor-led positioning - financial viability in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
16.082 | 16 | WP16 | Tenant Acquisition Strategy | Is there a responsible owner, due date and approval route for rental assumptions - financial viability? | Register entry, supporting drawing/report, approval note and updated risk item. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
16.083 | 16 | WP16 | Tenant Acquisition Strategy | Has the gate file tested whether tenant due diligence - financial viability creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
16.084 | 16 | WP16 | Tenant Acquisition Strategy | Are assumptions for letters of intent - financial viability documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
16.085 | 16 | WP16 | Tenant Acquisition Strategy | Has the relevant authority, specialist or professional adviser reviewed target tenant list - programme impact where required? | Authority response, compliance checklist, file note and management approval. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
16.086 | 16 | WP16 | Tenant Acquisition Strategy | Is the decision record for leasing brochure - programme impact aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
16.087 | 16 | WP16 | Tenant Acquisition Strategy | Have cost, programme and compliance implications of anchor-led positioning - programme impact been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
16.088 | 16 | WP16 | Tenant Acquisition Strategy | Has the team obtained written confirmation or documented proof for rental assumptions - programme impact? | Current certificate/letter/report, version control and document-control entry. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
16.089 | 16 | WP16 | Tenant Acquisition Strategy | Does the evidence for tenant due diligence - programme impact support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
16.090 | 16 | WP16 | Tenant Acquisition Strategy | Have dependencies linked to letters of intent - programme impact been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
16.091 | 16 | WP16 | Tenant Acquisition Strategy | Has the project team confirmed target tenant list - risk mitigation in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
16.092 | 16 | WP16 | Tenant Acquisition Strategy | Is there a responsible owner, due date and approval route for leasing brochure - risk mitigation? | Register entry, supporting drawing/report, approval note and updated risk item. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
16.093 | 16 | WP16 | Tenant Acquisition Strategy | Has the gate file tested whether anchor-led positioning - risk mitigation creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
16.094 | 16 | WP16 | Tenant Acquisition Strategy | Are assumptions for rental assumptions - risk mitigation documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
16.095 | 16 | WP16 | Tenant Acquisition Strategy | Has the relevant authority, specialist or professional adviser reviewed tenant due diligence - risk mitigation where required? | Authority response, compliance checklist, file note and management approval. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
16.096 | 16 | WP16 | Tenant Acquisition Strategy | Is the decision record for letters of intent - risk mitigation aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
16.097 | 16 | WP16 | Tenant Acquisition Strategy | Have cost, programme and compliance implications of target tenant list - stakeholder acceptance been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
16.098 | 16 | WP16 | Tenant Acquisition Strategy | Has the team obtained written confirmation or documented proof for leasing brochure - stakeholder acceptance? | Current certificate/letter/report, version control and document-control entry. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
16.099 | 16 | WP16 | Tenant Acquisition Strategy | Does the evidence for anchor-led positioning - stakeholder acceptance support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
16.100 | 16 | WP16 | Tenant Acquisition Strategy | Have dependencies linked to rental assumptions - stakeholder acceptance been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
17.001 | 17 | WP17 | Line-Shop Tenant Mix and Leasing | Has the project team confirmed pharmacy option - governance approval in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
17.002 | 17 | WP17 | Line-Shop Tenant Mix and Leasing | Is there a responsible owner, due date and approval route for cellular tenant - governance approval? | Register entry, supporting drawing/report, approval note and updated risk item. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
17.003 | 17 | WP17 | Line-Shop Tenant Mix and Leasing | Has the gate file tested whether banking/ATM - governance approval creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
17.004 | 17 | WP17 | Line-Shop Tenant Mix and Leasing | Are assumptions for bakery or deli - governance approval documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
17.005 | 17 | WP17 | Line-Shop Tenant Mix and Leasing | Has the relevant authority, specialist or professional adviser reviewed local enterprise - governance approval where required? | Authority response, compliance checklist, file note and management approval. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
17.006 | 17 | WP17 | Line-Shop Tenant Mix and Leasing | Is the decision record for beauty or personal care - governance approval aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
17.007 | 17 | WP17 | Line-Shop Tenant Mix and Leasing | Have cost, programme and compliance implications of pharmacy option - legal authority been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
17.008 | 17 | WP17 | Line-Shop Tenant Mix and Leasing | Has the team obtained written confirmation or documented proof for cellular tenant - legal authority? | Current certificate/letter/report, version control and document-control entry. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
17.009 | 17 | WP17 | Line-Shop Tenant Mix and Leasing | Does the evidence for banking/ATM - legal authority support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
17.010 | 17 | WP17 | Line-Shop Tenant Mix and Leasing | Have dependencies linked to bakery or deli - legal authority been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
17.011 | 17 | WP17 | Line-Shop Tenant Mix and Leasing | Has the project team confirmed local enterprise - legal authority in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
17.012 | 17 | WP17 | Line-Shop Tenant Mix and Leasing | Is there a responsible owner, due date and approval route for beauty or personal care - legal authority? | Register entry, supporting drawing/report, approval note and updated risk item. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
17.013 | 17 | WP17 | Line-Shop Tenant Mix and Leasing | Has the gate file tested whether pharmacy option - technical feasibility creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
17.014 | 17 | WP17 | Line-Shop Tenant Mix and Leasing | Are assumptions for cellular tenant - technical feasibility documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
17.015 | 17 | WP17 | Line-Shop Tenant Mix and Leasing | Has the relevant authority, specialist or professional adviser reviewed banking/ATM - technical feasibility where required? | Authority response, compliance checklist, file note and management approval. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
17.016 | 17 | WP17 | Line-Shop Tenant Mix and Leasing | Is the decision record for bakery or deli - technical feasibility aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
17.017 | 17 | WP17 | Line-Shop Tenant Mix and Leasing | Have cost, programme and compliance implications of local enterprise - technical feasibility been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
17.018 | 17 | WP17 | Line-Shop Tenant Mix and Leasing | Has the team obtained written confirmation or documented proof for beauty or personal care - technical feasibility? | Current certificate/letter/report, version control and document-control entry. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
17.019 | 17 | WP17 | Line-Shop Tenant Mix and Leasing | Does the evidence for pharmacy option - financial viability support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
17.020 | 17 | WP17 | Line-Shop Tenant Mix and Leasing | Have dependencies linked to cellular tenant - financial viability been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
17.021 | 17 | WP17 | Line-Shop Tenant Mix and Leasing | Has the project team confirmed banking/ATM - financial viability in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
17.022 | 17 | WP17 | Line-Shop Tenant Mix and Leasing | Is there a responsible owner, due date and approval route for bakery or deli - financial viability? | Register entry, supporting drawing/report, approval note and updated risk item. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
17.023 | 17 | WP17 | Line-Shop Tenant Mix and Leasing | Has the gate file tested whether local enterprise - financial viability creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
17.024 | 17 | WP17 | Line-Shop Tenant Mix and Leasing | Are assumptions for beauty or personal care - financial viability documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
17.025 | 17 | WP17 | Line-Shop Tenant Mix and Leasing | Has the relevant authority, specialist or professional adviser reviewed pharmacy option - programme impact where required? | Authority response, compliance checklist, file note and management approval. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
17.026 | 17 | WP17 | Line-Shop Tenant Mix and Leasing | Is the decision record for cellular tenant - programme impact aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
17.027 | 17 | WP17 | Line-Shop Tenant Mix and Leasing | Have cost, programme and compliance implications of banking/ATM - programme impact been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
17.028 | 17 | WP17 | Line-Shop Tenant Mix and Leasing | Has the team obtained written confirmation or documented proof for bakery or deli - programme impact? | Current certificate/letter/report, version control and document-control entry. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
17.029 | 17 | WP17 | Line-Shop Tenant Mix and Leasing | Does the evidence for local enterprise - programme impact support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
17.030 | 17 | WP17 | Line-Shop Tenant Mix and Leasing | Have dependencies linked to beauty or personal care - programme impact been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
17.031 | 17 | WP17 | Line-Shop Tenant Mix and Leasing | Has the project team confirmed pharmacy option - risk mitigation in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
17.032 | 17 | WP17 | Line-Shop Tenant Mix and Leasing | Is there a responsible owner, due date and approval route for cellular tenant - risk mitigation? | Register entry, supporting drawing/report, approval note and updated risk item. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
17.033 | 17 | WP17 | Line-Shop Tenant Mix and Leasing | Has the gate file tested whether banking/ATM - risk mitigation creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
17.034 | 17 | WP17 | Line-Shop Tenant Mix and Leasing | Are assumptions for bakery or deli - risk mitigation documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
17.035 | 17 | WP17 | Line-Shop Tenant Mix and Leasing | Has the relevant authority, specialist or professional adviser reviewed local enterprise - risk mitigation where required? | Authority response, compliance checklist, file note and management approval. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
17.036 | 17 | WP17 | Line-Shop Tenant Mix and Leasing | Is the decision record for beauty or personal care - risk mitigation aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
17.037 | 17 | WP17 | Line-Shop Tenant Mix and Leasing | Have cost, programme and compliance implications of pharmacy option - stakeholder acceptance been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
17.038 | 17 | WP17 | Line-Shop Tenant Mix and Leasing | Has the team obtained written confirmation or documented proof for cellular tenant - stakeholder acceptance? | Current certificate/letter/report, version control and document-control entry. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
17.039 | 17 | WP17 | Line-Shop Tenant Mix and Leasing | Does the evidence for banking/ATM - stakeholder acceptance support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
17.040 | 17 | WP17 | Line-Shop Tenant Mix and Leasing | Have dependencies linked to bakery or deli - stakeholder acceptance been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
17.041 | 17 | WP17 | Line-Shop Tenant Mix and Leasing | Has the project team confirmed local enterprise - stakeholder acceptance in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
17.042 | 17 | WP17 | Line-Shop Tenant Mix and Leasing | Is there a responsible owner, due date and approval route for beauty or personal care - stakeholder acceptance? | Register entry, supporting drawing/report, approval note and updated risk item. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
17.043 | 17 | WP17 | Line-Shop Tenant Mix and Leasing | Has the gate file tested whether pharmacy option - document control creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
17.044 | 17 | WP17 | Line-Shop Tenant Mix and Leasing | Are assumptions for cellular tenant - document control documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
17.045 | 17 | WP17 | Line-Shop Tenant Mix and Leasing | Has the relevant authority, specialist or professional adviser reviewed banking/ATM - document control where required? | Authority response, compliance checklist, file note and management approval. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
17.046 | 17 | WP17 | Line-Shop Tenant Mix and Leasing | Is the decision record for bakery or deli - document control aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
17.047 | 17 | WP17 | Line-Shop Tenant Mix and Leasing | Have cost, programme and compliance implications of local enterprise - document control been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
17.048 | 17 | WP17 | Line-Shop Tenant Mix and Leasing | Has the team obtained written confirmation or documented proof for beauty or personal care - document control? | Current certificate/letter/report, version control and document-control entry. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
17.049 | 17 | WP17 | Line-Shop Tenant Mix and Leasing | Does the evidence for pharmacy option - professional certification support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
17.050 | 17 | WP17 | Line-Shop Tenant Mix and Leasing | Have dependencies linked to cellular tenant - professional certification been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
17.051 | 17 | WP17 | Line-Shop Tenant Mix and Leasing | Has the project team confirmed banking/ATM - professional certification in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
17.052 | 17 | WP17 | Line-Shop Tenant Mix and Leasing | Is there a responsible owner, due date and approval route for bakery or deli - professional certification? | Register entry, supporting drawing/report, approval note and updated risk item. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
17.053 | 17 | WP17 | Line-Shop Tenant Mix and Leasing | Has the gate file tested whether local enterprise - professional certification creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
17.054 | 17 | WP17 | Line-Shop Tenant Mix and Leasing | Are assumptions for beauty or personal care - professional certification documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
17.055 | 17 | WP17 | Line-Shop Tenant Mix and Leasing | Has the relevant authority, specialist or professional adviser reviewed pharmacy option - implementation readiness where required? | Authority response, compliance checklist, file note and management approval. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
17.056 | 17 | WP17 | Line-Shop Tenant Mix and Leasing | Is the decision record for cellular tenant - implementation readiness aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
17.057 | 17 | WP17 | Line-Shop Tenant Mix and Leasing | Have cost, programme and compliance implications of banking/ATM - implementation readiness been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
17.058 | 17 | WP17 | Line-Shop Tenant Mix and Leasing | Has the team obtained written confirmation or documented proof for bakery or deli - implementation readiness? | Current certificate/letter/report, version control and document-control entry. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
17.059 | 17 | WP17 | Line-Shop Tenant Mix and Leasing | Does the evidence for local enterprise - implementation readiness support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
17.060 | 17 | WP17 | Line-Shop Tenant Mix and Leasing | Have dependencies linked to beauty or personal care - implementation readiness been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
17.061 | 17 | WP17 | Line-Shop Tenant Mix and Leasing | Has the project team confirmed pharmacy option - governance approval in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
17.062 | 17 | WP17 | Line-Shop Tenant Mix and Leasing | Is there a responsible owner, due date and approval route for cellular tenant - governance approval? | Register entry, supporting drawing/report, approval note and updated risk item. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
17.063 | 17 | WP17 | Line-Shop Tenant Mix and Leasing | Has the gate file tested whether banking/ATM - governance approval creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
17.064 | 17 | WP17 | Line-Shop Tenant Mix and Leasing | Are assumptions for bakery or deli - governance approval documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
17.065 | 17 | WP17 | Line-Shop Tenant Mix and Leasing | Has the relevant authority, specialist or professional adviser reviewed local enterprise - governance approval where required? | Authority response, compliance checklist, file note and management approval. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
17.066 | 17 | WP17 | Line-Shop Tenant Mix and Leasing | Is the decision record for beauty or personal care - governance approval aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
17.067 | 17 | WP17 | Line-Shop Tenant Mix and Leasing | Have cost, programme and compliance implications of pharmacy option - legal authority been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
17.068 | 17 | WP17 | Line-Shop Tenant Mix and Leasing | Has the team obtained written confirmation or documented proof for cellular tenant - legal authority? | Current certificate/letter/report, version control and document-control entry. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
17.069 | 17 | WP17 | Line-Shop Tenant Mix and Leasing | Does the evidence for banking/ATM - legal authority support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
17.070 | 17 | WP17 | Line-Shop Tenant Mix and Leasing | Have dependencies linked to bakery or deli - legal authority been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
17.071 | 17 | WP17 | Line-Shop Tenant Mix and Leasing | Has the project team confirmed local enterprise - legal authority in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
17.072 | 17 | WP17 | Line-Shop Tenant Mix and Leasing | Is there a responsible owner, due date and approval route for beauty or personal care - legal authority? | Register entry, supporting drawing/report, approval note and updated risk item. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
17.073 | 17 | WP17 | Line-Shop Tenant Mix and Leasing | Has the gate file tested whether pharmacy option - technical feasibility creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
17.074 | 17 | WP17 | Line-Shop Tenant Mix and Leasing | Are assumptions for cellular tenant - technical feasibility documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
17.075 | 17 | WP17 | Line-Shop Tenant Mix and Leasing | Has the relevant authority, specialist or professional adviser reviewed banking/ATM - technical feasibility where required? | Authority response, compliance checklist, file note and management approval. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
17.076 | 17 | WP17 | Line-Shop Tenant Mix and Leasing | Is the decision record for bakery or deli - technical feasibility aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
17.077 | 17 | WP17 | Line-Shop Tenant Mix and Leasing | Have cost, programme and compliance implications of local enterprise - technical feasibility been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
17.078 | 17 | WP17 | Line-Shop Tenant Mix and Leasing | Has the team obtained written confirmation or documented proof for beauty or personal care - technical feasibility? | Current certificate/letter/report, version control and document-control entry. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
17.079 | 17 | WP17 | Line-Shop Tenant Mix and Leasing | Does the evidence for pharmacy option - financial viability support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
17.080 | 17 | WP17 | Line-Shop Tenant Mix and Leasing | Have dependencies linked to cellular tenant - financial viability been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
17.081 | 17 | WP17 | Line-Shop Tenant Mix and Leasing | Has the project team confirmed banking/ATM - financial viability in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
17.082 | 17 | WP17 | Line-Shop Tenant Mix and Leasing | Is there a responsible owner, due date and approval route for bakery or deli - financial viability? | Register entry, supporting drawing/report, approval note and updated risk item. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
17.083 | 17 | WP17 | Line-Shop Tenant Mix and Leasing | Has the gate file tested whether local enterprise - financial viability creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
17.084 | 17 | WP17 | Line-Shop Tenant Mix and Leasing | Are assumptions for beauty or personal care - financial viability documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
17.085 | 17 | WP17 | Line-Shop Tenant Mix and Leasing | Has the relevant authority, specialist or professional adviser reviewed pharmacy option - programme impact where required? | Authority response, compliance checklist, file note and management approval. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
17.086 | 17 | WP17 | Line-Shop Tenant Mix and Leasing | Is the decision record for cellular tenant - programme impact aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
17.087 | 17 | WP17 | Line-Shop Tenant Mix and Leasing | Have cost, programme and compliance implications of banking/ATM - programme impact been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
17.088 | 17 | WP17 | Line-Shop Tenant Mix and Leasing | Has the team obtained written confirmation or documented proof for bakery or deli - programme impact? | Current certificate/letter/report, version control and document-control entry. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
17.089 | 17 | WP17 | Line-Shop Tenant Mix and Leasing | Does the evidence for local enterprise - programme impact support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
17.090 | 17 | WP17 | Line-Shop Tenant Mix and Leasing | Have dependencies linked to beauty or personal care - programme impact been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
17.091 | 17 | WP17 | Line-Shop Tenant Mix and Leasing | Has the project team confirmed pharmacy option - risk mitigation in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
17.092 | 17 | WP17 | Line-Shop Tenant Mix and Leasing | Is there a responsible owner, due date and approval route for cellular tenant - risk mitigation? | Register entry, supporting drawing/report, approval note and updated risk item. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
17.093 | 17 | WP17 | Line-Shop Tenant Mix and Leasing | Has the gate file tested whether banking/ATM - risk mitigation creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
17.094 | 17 | WP17 | Line-Shop Tenant Mix and Leasing | Are assumptions for bakery or deli - risk mitigation documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
17.095 | 17 | WP17 | Line-Shop Tenant Mix and Leasing | Has the relevant authority, specialist or professional adviser reviewed local enterprise - risk mitigation where required? | Authority response, compliance checklist, file note and management approval. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
17.096 | 17 | WP17 | Line-Shop Tenant Mix and Leasing | Is the decision record for beauty or personal care - risk mitigation aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
17.097 | 17 | WP17 | Line-Shop Tenant Mix and Leasing | Have cost, programme and compliance implications of pharmacy option - stakeholder acceptance been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
17.098 | 17 | WP17 | Line-Shop Tenant Mix and Leasing | Has the team obtained written confirmation or documented proof for cellular tenant - stakeholder acceptance? | Current certificate/letter/report, version control and document-control entry. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
17.099 | 17 | WP17 | Line-Shop Tenant Mix and Leasing | Does the evidence for banking/ATM - stakeholder acceptance support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
17.100 | 17 | WP17 | Line-Shop Tenant Mix and Leasing | Have dependencies linked to bakery or deli - stakeholder acceptance been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
18.001 | 18 | WP18 | Fast-Food Chain Restaurant Acquisition | Has the project team confirmed brand targeting - governance approval in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
18.002 | 18 | WP18 | Fast-Food Chain Restaurant Acquisition | Is there a responsible owner, due date and approval route for drive-through feasibility - governance approval? | Register entry, supporting drawing/report, approval note and updated risk item. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
18.003 | 18 | WP18 | Fast-Food Chain Restaurant Acquisition | Has the gate file tested whether kitchen extraction - governance approval creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
18.004 | 18 | WP18 | Fast-Food Chain Restaurant Acquisition | Are assumptions for grease traps - governance approval documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
18.005 | 18 | WP18 | Fast-Food Chain Restaurant Acquisition | Has the relevant authority, specialist or professional adviser reviewed delivery access - governance approval where required? | Authority response, compliance checklist, file note and management approval. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
18.006 | 18 | WP18 | Fast-Food Chain Restaurant Acquisition | Is the decision record for seating areas - governance approval aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
18.007 | 18 | WP18 | Fast-Food Chain Restaurant Acquisition | Have cost, programme and compliance implications of brand targeting - legal authority been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
18.008 | 18 | WP18 | Fast-Food Chain Restaurant Acquisition | Has the team obtained written confirmation or documented proof for drive-through feasibility - legal authority? | Current certificate/letter/report, version control and document-control entry. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
18.009 | 18 | WP18 | Fast-Food Chain Restaurant Acquisition | Does the evidence for kitchen extraction - legal authority support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
18.010 | 18 | WP18 | Fast-Food Chain Restaurant Acquisition | Have dependencies linked to grease traps - legal authority been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
18.011 | 18 | WP18 | Fast-Food Chain Restaurant Acquisition | Has the project team confirmed delivery access - legal authority in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
18.012 | 18 | WP18 | Fast-Food Chain Restaurant Acquisition | Is there a responsible owner, due date and approval route for seating areas - legal authority? | Register entry, supporting drawing/report, approval note and updated risk item. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
18.013 | 18 | WP18 | Fast-Food Chain Restaurant Acquisition | Has the gate file tested whether brand targeting - technical feasibility creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
18.014 | 18 | WP18 | Fast-Food Chain Restaurant Acquisition | Are assumptions for drive-through feasibility - technical feasibility documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
18.015 | 18 | WP18 | Fast-Food Chain Restaurant Acquisition | Has the relevant authority, specialist or professional adviser reviewed kitchen extraction - technical feasibility where required? | Authority response, compliance checklist, file note and management approval. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
18.016 | 18 | WP18 | Fast-Food Chain Restaurant Acquisition | Is the decision record for grease traps - technical feasibility aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
18.017 | 18 | WP18 | Fast-Food Chain Restaurant Acquisition | Have cost, programme and compliance implications of delivery access - technical feasibility been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
18.018 | 18 | WP18 | Fast-Food Chain Restaurant Acquisition | Has the team obtained written confirmation or documented proof for seating areas - technical feasibility? | Current certificate/letter/report, version control and document-control entry. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
18.019 | 18 | WP18 | Fast-Food Chain Restaurant Acquisition | Does the evidence for brand targeting - financial viability support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
18.020 | 18 | WP18 | Fast-Food Chain Restaurant Acquisition | Have dependencies linked to drive-through feasibility - financial viability been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
18.021 | 18 | WP18 | Fast-Food Chain Restaurant Acquisition | Has the project team confirmed kitchen extraction - financial viability in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
18.022 | 18 | WP18 | Fast-Food Chain Restaurant Acquisition | Is there a responsible owner, due date and approval route for grease traps - financial viability? | Register entry, supporting drawing/report, approval note and updated risk item. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
18.023 | 18 | WP18 | Fast-Food Chain Restaurant Acquisition | Has the gate file tested whether delivery access - financial viability creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
18.024 | 18 | WP18 | Fast-Food Chain Restaurant Acquisition | Are assumptions for seating areas - financial viability documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
18.025 | 18 | WP18 | Fast-Food Chain Restaurant Acquisition | Has the relevant authority, specialist or professional adviser reviewed brand targeting - programme impact where required? | Authority response, compliance checklist, file note and management approval. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
18.026 | 18 | WP18 | Fast-Food Chain Restaurant Acquisition | Is the decision record for drive-through feasibility - programme impact aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
18.027 | 18 | WP18 | Fast-Food Chain Restaurant Acquisition | Have cost, programme and compliance implications of kitchen extraction - programme impact been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
18.028 | 18 | WP18 | Fast-Food Chain Restaurant Acquisition | Has the team obtained written confirmation or documented proof for grease traps - programme impact? | Current certificate/letter/report, version control and document-control entry. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
18.029 | 18 | WP18 | Fast-Food Chain Restaurant Acquisition | Does the evidence for delivery access - programme impact support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
18.030 | 18 | WP18 | Fast-Food Chain Restaurant Acquisition | Have dependencies linked to seating areas - programme impact been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
18.031 | 18 | WP18 | Fast-Food Chain Restaurant Acquisition | Has the project team confirmed brand targeting - risk mitigation in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
18.032 | 18 | WP18 | Fast-Food Chain Restaurant Acquisition | Is there a responsible owner, due date and approval route for drive-through feasibility - risk mitigation? | Register entry, supporting drawing/report, approval note and updated risk item. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
18.033 | 18 | WP18 | Fast-Food Chain Restaurant Acquisition | Has the gate file tested whether kitchen extraction - risk mitigation creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
18.034 | 18 | WP18 | Fast-Food Chain Restaurant Acquisition | Are assumptions for grease traps - risk mitigation documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
18.035 | 18 | WP18 | Fast-Food Chain Restaurant Acquisition | Has the relevant authority, specialist or professional adviser reviewed delivery access - risk mitigation where required? | Authority response, compliance checklist, file note and management approval. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
18.036 | 18 | WP18 | Fast-Food Chain Restaurant Acquisition | Is the decision record for seating areas - risk mitigation aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
18.037 | 18 | WP18 | Fast-Food Chain Restaurant Acquisition | Have cost, programme and compliance implications of brand targeting - stakeholder acceptance been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
18.038 | 18 | WP18 | Fast-Food Chain Restaurant Acquisition | Has the team obtained written confirmation or documented proof for drive-through feasibility - stakeholder acceptance? | Current certificate/letter/report, version control and document-control entry. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
18.039 | 18 | WP18 | Fast-Food Chain Restaurant Acquisition | Does the evidence for kitchen extraction - stakeholder acceptance support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
18.040 | 18 | WP18 | Fast-Food Chain Restaurant Acquisition | Have dependencies linked to grease traps - stakeholder acceptance been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
18.041 | 18 | WP18 | Fast-Food Chain Restaurant Acquisition | Has the project team confirmed delivery access - stakeholder acceptance in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
18.042 | 18 | WP18 | Fast-Food Chain Restaurant Acquisition | Is there a responsible owner, due date and approval route for seating areas - stakeholder acceptance? | Register entry, supporting drawing/report, approval note and updated risk item. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
18.043 | 18 | WP18 | Fast-Food Chain Restaurant Acquisition | Has the gate file tested whether brand targeting - document control creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
18.044 | 18 | WP18 | Fast-Food Chain Restaurant Acquisition | Are assumptions for drive-through feasibility - document control documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
18.045 | 18 | WP18 | Fast-Food Chain Restaurant Acquisition | Has the relevant authority, specialist or professional adviser reviewed kitchen extraction - document control where required? | Authority response, compliance checklist, file note and management approval. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
18.046 | 18 | WP18 | Fast-Food Chain Restaurant Acquisition | Is the decision record for grease traps - document control aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
18.047 | 18 | WP18 | Fast-Food Chain Restaurant Acquisition | Have cost, programme and compliance implications of delivery access - document control been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
18.048 | 18 | WP18 | Fast-Food Chain Restaurant Acquisition | Has the team obtained written confirmation or documented proof for seating areas - document control? | Current certificate/letter/report, version control and document-control entry. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
18.049 | 18 | WP18 | Fast-Food Chain Restaurant Acquisition | Does the evidence for brand targeting - professional certification support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
18.050 | 18 | WP18 | Fast-Food Chain Restaurant Acquisition | Have dependencies linked to drive-through feasibility - professional certification been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
18.051 | 18 | WP18 | Fast-Food Chain Restaurant Acquisition | Has the project team confirmed kitchen extraction - professional certification in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
18.052 | 18 | WP18 | Fast-Food Chain Restaurant Acquisition | Is there a responsible owner, due date and approval route for grease traps - professional certification? | Register entry, supporting drawing/report, approval note and updated risk item. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
18.053 | 18 | WP18 | Fast-Food Chain Restaurant Acquisition | Has the gate file tested whether delivery access - professional certification creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
18.054 | 18 | WP18 | Fast-Food Chain Restaurant Acquisition | Are assumptions for seating areas - professional certification documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
18.055 | 18 | WP18 | Fast-Food Chain Restaurant Acquisition | Has the relevant authority, specialist or professional adviser reviewed brand targeting - implementation readiness where required? | Authority response, compliance checklist, file note and management approval. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
18.056 | 18 | WP18 | Fast-Food Chain Restaurant Acquisition | Is the decision record for drive-through feasibility - implementation readiness aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
18.057 | 18 | WP18 | Fast-Food Chain Restaurant Acquisition | Have cost, programme and compliance implications of kitchen extraction - implementation readiness been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
18.058 | 18 | WP18 | Fast-Food Chain Restaurant Acquisition | Has the team obtained written confirmation or documented proof for grease traps - implementation readiness? | Current certificate/letter/report, version control and document-control entry. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
18.059 | 18 | WP18 | Fast-Food Chain Restaurant Acquisition | Does the evidence for delivery access - implementation readiness support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
18.060 | 18 | WP18 | Fast-Food Chain Restaurant Acquisition | Have dependencies linked to seating areas - implementation readiness been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
18.061 | 18 | WP18 | Fast-Food Chain Restaurant Acquisition | Has the project team confirmed brand targeting - governance approval in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
18.062 | 18 | WP18 | Fast-Food Chain Restaurant Acquisition | Is there a responsible owner, due date and approval route for drive-through feasibility - governance approval? | Register entry, supporting drawing/report, approval note and updated risk item. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
18.063 | 18 | WP18 | Fast-Food Chain Restaurant Acquisition | Has the gate file tested whether kitchen extraction - governance approval creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
18.064 | 18 | WP18 | Fast-Food Chain Restaurant Acquisition | Are assumptions for grease traps - governance approval documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
18.065 | 18 | WP18 | Fast-Food Chain Restaurant Acquisition | Has the relevant authority, specialist or professional adviser reviewed delivery access - governance approval where required? | Authority response, compliance checklist, file note and management approval. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
18.066 | 18 | WP18 | Fast-Food Chain Restaurant Acquisition | Is the decision record for seating areas - governance approval aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
18.067 | 18 | WP18 | Fast-Food Chain Restaurant Acquisition | Have cost, programme and compliance implications of brand targeting - legal authority been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
18.068 | 18 | WP18 | Fast-Food Chain Restaurant Acquisition | Has the team obtained written confirmation or documented proof for drive-through feasibility - legal authority? | Current certificate/letter/report, version control and document-control entry. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
18.069 | 18 | WP18 | Fast-Food Chain Restaurant Acquisition | Does the evidence for kitchen extraction - legal authority support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
18.070 | 18 | WP18 | Fast-Food Chain Restaurant Acquisition | Have dependencies linked to grease traps - legal authority been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
18.071 | 18 | WP18 | Fast-Food Chain Restaurant Acquisition | Has the project team confirmed delivery access - legal authority in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
18.072 | 18 | WP18 | Fast-Food Chain Restaurant Acquisition | Is there a responsible owner, due date and approval route for seating areas - legal authority? | Register entry, supporting drawing/report, approval note and updated risk item. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
18.073 | 18 | WP18 | Fast-Food Chain Restaurant Acquisition | Has the gate file tested whether brand targeting - technical feasibility creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
18.074 | 18 | WP18 | Fast-Food Chain Restaurant Acquisition | Are assumptions for drive-through feasibility - technical feasibility documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
18.075 | 18 | WP18 | Fast-Food Chain Restaurant Acquisition | Has the relevant authority, specialist or professional adviser reviewed kitchen extraction - technical feasibility where required? | Authority response, compliance checklist, file note and management approval. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
18.076 | 18 | WP18 | Fast-Food Chain Restaurant Acquisition | Is the decision record for grease traps - technical feasibility aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
18.077 | 18 | WP18 | Fast-Food Chain Restaurant Acquisition | Have cost, programme and compliance implications of delivery access - technical feasibility been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
18.078 | 18 | WP18 | Fast-Food Chain Restaurant Acquisition | Has the team obtained written confirmation or documented proof for seating areas - technical feasibility? | Current certificate/letter/report, version control and document-control entry. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
18.079 | 18 | WP18 | Fast-Food Chain Restaurant Acquisition | Does the evidence for brand targeting - financial viability support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
18.080 | 18 | WP18 | Fast-Food Chain Restaurant Acquisition | Have dependencies linked to drive-through feasibility - financial viability been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
18.081 | 18 | WP18 | Fast-Food Chain Restaurant Acquisition | Has the project team confirmed kitchen extraction - financial viability in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
18.082 | 18 | WP18 | Fast-Food Chain Restaurant Acquisition | Is there a responsible owner, due date and approval route for grease traps - financial viability? | Register entry, supporting drawing/report, approval note and updated risk item. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
18.083 | 18 | WP18 | Fast-Food Chain Restaurant Acquisition | Has the gate file tested whether delivery access - financial viability creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
18.084 | 18 | WP18 | Fast-Food Chain Restaurant Acquisition | Are assumptions for seating areas - financial viability documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
18.085 | 18 | WP18 | Fast-Food Chain Restaurant Acquisition | Has the relevant authority, specialist or professional adviser reviewed brand targeting - programme impact where required? | Authority response, compliance checklist, file note and management approval. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
18.086 | 18 | WP18 | Fast-Food Chain Restaurant Acquisition | Is the decision record for drive-through feasibility - programme impact aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
18.087 | 18 | WP18 | Fast-Food Chain Restaurant Acquisition | Have cost, programme and compliance implications of kitchen extraction - programme impact been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
18.088 | 18 | WP18 | Fast-Food Chain Restaurant Acquisition | Has the team obtained written confirmation or documented proof for grease traps - programme impact? | Current certificate/letter/report, version control and document-control entry. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
18.089 | 18 | WP18 | Fast-Food Chain Restaurant Acquisition | Does the evidence for delivery access - programme impact support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
18.090 | 18 | WP18 | Fast-Food Chain Restaurant Acquisition | Have dependencies linked to seating areas - programme impact been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
18.091 | 18 | WP18 | Fast-Food Chain Restaurant Acquisition | Has the project team confirmed brand targeting - risk mitigation in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
18.092 | 18 | WP18 | Fast-Food Chain Restaurant Acquisition | Is there a responsible owner, due date and approval route for drive-through feasibility - risk mitigation? | Register entry, supporting drawing/report, approval note and updated risk item. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
18.093 | 18 | WP18 | Fast-Food Chain Restaurant Acquisition | Has the gate file tested whether kitchen extraction - risk mitigation creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
18.094 | 18 | WP18 | Fast-Food Chain Restaurant Acquisition | Are assumptions for grease traps - risk mitigation documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
18.095 | 18 | WP18 | Fast-Food Chain Restaurant Acquisition | Has the relevant authority, specialist or professional adviser reviewed delivery access - risk mitigation where required? | Authority response, compliance checklist, file note and management approval. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
18.096 | 18 | WP18 | Fast-Food Chain Restaurant Acquisition | Is the decision record for seating areas - risk mitigation aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
18.097 | 18 | WP18 | Fast-Food Chain Restaurant Acquisition | Have cost, programme and compliance implications of brand targeting - stakeholder acceptance been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
18.098 | 18 | WP18 | Fast-Food Chain Restaurant Acquisition | Has the team obtained written confirmation or documented proof for drive-through feasibility - stakeholder acceptance? | Current certificate/letter/report, version control and document-control entry. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
18.099 | 18 | WP18 | Fast-Food Chain Restaurant Acquisition | Does the evidence for kitchen extraction - stakeholder acceptance support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
18.100 | 18 | WP18 | Fast-Food Chain Restaurant Acquisition | Have dependencies linked to grease traps - stakeholder acceptance been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
19.001 | 19 | WP19 | Fuel Partner and Forecourt Coordination | Has the project team confirmed TotalEnergies standards - governance approval in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
19.002 | 19 | WP19 | Fuel Partner and Forecourt Coordination | Is there a responsible owner, due date and approval route for forecourt layout - governance approval? | Register entry, supporting drawing/report, approval note and updated risk item. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
19.003 | 19 | WP19 | Fuel Partner and Forecourt Coordination | Has the gate file tested whether tank farm - governance approval creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
19.004 | 19 | WP19 | Fuel Partner and Forecourt Coordination | Are assumptions for fuel logistics - governance approval documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
19.005 | 19 | WP19 | Fuel Partner and Forecourt Coordination | Has the relevant authority, specialist or professional adviser reviewed C-store integration - governance approval where required? | Authority response, compliance checklist, file note and management approval. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
19.006 | 19 | WP19 | Fuel Partner and Forecourt Coordination | Is the decision record for brand signage - governance approval aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
19.007 | 19 | WP19 | Fuel Partner and Forecourt Coordination | Have cost, programme and compliance implications of TotalEnergies standards - legal authority been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
19.008 | 19 | WP19 | Fuel Partner and Forecourt Coordination | Has the team obtained written confirmation or documented proof for forecourt layout - legal authority? | Current certificate/letter/report, version control and document-control entry. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
19.009 | 19 | WP19 | Fuel Partner and Forecourt Coordination | Does the evidence for tank farm - legal authority support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
19.010 | 19 | WP19 | Fuel Partner and Forecourt Coordination | Have dependencies linked to fuel logistics - legal authority been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
19.011 | 19 | WP19 | Fuel Partner and Forecourt Coordination | Has the project team confirmed C-store integration - legal authority in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
19.012 | 19 | WP19 | Fuel Partner and Forecourt Coordination | Is there a responsible owner, due date and approval route for brand signage - legal authority? | Register entry, supporting drawing/report, approval note and updated risk item. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
19.013 | 19 | WP19 | Fuel Partner and Forecourt Coordination | Has the gate file tested whether TotalEnergies standards - technical feasibility creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
19.014 | 19 | WP19 | Fuel Partner and Forecourt Coordination | Are assumptions for forecourt layout - technical feasibility documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
19.015 | 19 | WP19 | Fuel Partner and Forecourt Coordination | Has the relevant authority, specialist or professional adviser reviewed tank farm - technical feasibility where required? | Authority response, compliance checklist, file note and management approval. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
19.016 | 19 | WP19 | Fuel Partner and Forecourt Coordination | Is the decision record for fuel logistics - technical feasibility aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
19.017 | 19 | WP19 | Fuel Partner and Forecourt Coordination | Have cost, programme and compliance implications of C-store integration - technical feasibility been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
19.018 | 19 | WP19 | Fuel Partner and Forecourt Coordination | Has the team obtained written confirmation or documented proof for brand signage - technical feasibility? | Current certificate/letter/report, version control and document-control entry. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
19.019 | 19 | WP19 | Fuel Partner and Forecourt Coordination | Does the evidence for TotalEnergies standards - financial viability support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
19.020 | 19 | WP19 | Fuel Partner and Forecourt Coordination | Have dependencies linked to forecourt layout - financial viability been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
19.021 | 19 | WP19 | Fuel Partner and Forecourt Coordination | Has the project team confirmed tank farm - financial viability in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
19.022 | 19 | WP19 | Fuel Partner and Forecourt Coordination | Is there a responsible owner, due date and approval route for fuel logistics - financial viability? | Register entry, supporting drawing/report, approval note and updated risk item. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
19.023 | 19 | WP19 | Fuel Partner and Forecourt Coordination | Has the gate file tested whether C-store integration - financial viability creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
19.024 | 19 | WP19 | Fuel Partner and Forecourt Coordination | Are assumptions for brand signage - financial viability documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
19.025 | 19 | WP19 | Fuel Partner and Forecourt Coordination | Has the relevant authority, specialist or professional adviser reviewed TotalEnergies standards - programme impact where required? | Authority response, compliance checklist, file note and management approval. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
19.026 | 19 | WP19 | Fuel Partner and Forecourt Coordination | Is the decision record for forecourt layout - programme impact aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
19.027 | 19 | WP19 | Fuel Partner and Forecourt Coordination | Have cost, programme and compliance implications of tank farm - programme impact been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
19.028 | 19 | WP19 | Fuel Partner and Forecourt Coordination | Has the team obtained written confirmation or documented proof for fuel logistics - programme impact? | Current certificate/letter/report, version control and document-control entry. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
19.029 | 19 | WP19 | Fuel Partner and Forecourt Coordination | Does the evidence for C-store integration - programme impact support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
19.030 | 19 | WP19 | Fuel Partner and Forecourt Coordination | Have dependencies linked to brand signage - programme impact been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
19.031 | 19 | WP19 | Fuel Partner and Forecourt Coordination | Has the project team confirmed TotalEnergies standards - risk mitigation in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
19.032 | 19 | WP19 | Fuel Partner and Forecourt Coordination | Is there a responsible owner, due date and approval route for forecourt layout - risk mitigation? | Register entry, supporting drawing/report, approval note and updated risk item. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
19.033 | 19 | WP19 | Fuel Partner and Forecourt Coordination | Has the gate file tested whether tank farm - risk mitigation creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
19.034 | 19 | WP19 | Fuel Partner and Forecourt Coordination | Are assumptions for fuel logistics - risk mitigation documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
19.035 | 19 | WP19 | Fuel Partner and Forecourt Coordination | Has the relevant authority, specialist or professional adviser reviewed C-store integration - risk mitigation where required? | Authority response, compliance checklist, file note and management approval. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
19.036 | 19 | WP19 | Fuel Partner and Forecourt Coordination | Is the decision record for brand signage - risk mitigation aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
19.037 | 19 | WP19 | Fuel Partner and Forecourt Coordination | Have cost, programme and compliance implications of TotalEnergies standards - stakeholder acceptance been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
19.038 | 19 | WP19 | Fuel Partner and Forecourt Coordination | Has the team obtained written confirmation or documented proof for forecourt layout - stakeholder acceptance? | Current certificate/letter/report, version control and document-control entry. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
19.039 | 19 | WP19 | Fuel Partner and Forecourt Coordination | Does the evidence for tank farm - stakeholder acceptance support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
19.040 | 19 | WP19 | Fuel Partner and Forecourt Coordination | Have dependencies linked to fuel logistics - stakeholder acceptance been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
19.041 | 19 | WP19 | Fuel Partner and Forecourt Coordination | Has the project team confirmed C-store integration - stakeholder acceptance in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
19.042 | 19 | WP19 | Fuel Partner and Forecourt Coordination | Is there a responsible owner, due date and approval route for brand signage - stakeholder acceptance? | Register entry, supporting drawing/report, approval note and updated risk item. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
19.043 | 19 | WP19 | Fuel Partner and Forecourt Coordination | Has the gate file tested whether TotalEnergies standards - document control creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
19.044 | 19 | WP19 | Fuel Partner and Forecourt Coordination | Are assumptions for forecourt layout - document control documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
19.045 | 19 | WP19 | Fuel Partner and Forecourt Coordination | Has the relevant authority, specialist or professional adviser reviewed tank farm - document control where required? | Authority response, compliance checklist, file note and management approval. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
19.046 | 19 | WP19 | Fuel Partner and Forecourt Coordination | Is the decision record for fuel logistics - document control aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
19.047 | 19 | WP19 | Fuel Partner and Forecourt Coordination | Have cost, programme and compliance implications of C-store integration - document control been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
19.048 | 19 | WP19 | Fuel Partner and Forecourt Coordination | Has the team obtained written confirmation or documented proof for brand signage - document control? | Current certificate/letter/report, version control and document-control entry. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
19.049 | 19 | WP19 | Fuel Partner and Forecourt Coordination | Does the evidence for TotalEnergies standards - professional certification support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
19.050 | 19 | WP19 | Fuel Partner and Forecourt Coordination | Have dependencies linked to forecourt layout - professional certification been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
19.051 | 19 | WP19 | Fuel Partner and Forecourt Coordination | Has the project team confirmed tank farm - professional certification in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
19.052 | 19 | WP19 | Fuel Partner and Forecourt Coordination | Is there a responsible owner, due date and approval route for fuel logistics - professional certification? | Register entry, supporting drawing/report, approval note and updated risk item. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
19.053 | 19 | WP19 | Fuel Partner and Forecourt Coordination | Has the gate file tested whether C-store integration - professional certification creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
19.054 | 19 | WP19 | Fuel Partner and Forecourt Coordination | Are assumptions for brand signage - professional certification documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
19.055 | 19 | WP19 | Fuel Partner and Forecourt Coordination | Has the relevant authority, specialist or professional adviser reviewed TotalEnergies standards - implementation readiness where required? | Authority response, compliance checklist, file note and management approval. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
19.056 | 19 | WP19 | Fuel Partner and Forecourt Coordination | Is the decision record for forecourt layout - implementation readiness aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
19.057 | 19 | WP19 | Fuel Partner and Forecourt Coordination | Have cost, programme and compliance implications of tank farm - implementation readiness been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
19.058 | 19 | WP19 | Fuel Partner and Forecourt Coordination | Has the team obtained written confirmation or documented proof for fuel logistics - implementation readiness? | Current certificate/letter/report, version control and document-control entry. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
19.059 | 19 | WP19 | Fuel Partner and Forecourt Coordination | Does the evidence for C-store integration - implementation readiness support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
19.060 | 19 | WP19 | Fuel Partner and Forecourt Coordination | Have dependencies linked to brand signage - implementation readiness been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
19.061 | 19 | WP19 | Fuel Partner and Forecourt Coordination | Has the project team confirmed TotalEnergies standards - governance approval in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
19.062 | 19 | WP19 | Fuel Partner and Forecourt Coordination | Is there a responsible owner, due date and approval route for forecourt layout - governance approval? | Register entry, supporting drawing/report, approval note and updated risk item. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
19.063 | 19 | WP19 | Fuel Partner and Forecourt Coordination | Has the gate file tested whether tank farm - governance approval creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
19.064 | 19 | WP19 | Fuel Partner and Forecourt Coordination | Are assumptions for fuel logistics - governance approval documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
19.065 | 19 | WP19 | Fuel Partner and Forecourt Coordination | Has the relevant authority, specialist or professional adviser reviewed C-store integration - governance approval where required? | Authority response, compliance checklist, file note and management approval. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
19.066 | 19 | WP19 | Fuel Partner and Forecourt Coordination | Is the decision record for brand signage - governance approval aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
19.067 | 19 | WP19 | Fuel Partner and Forecourt Coordination | Have cost, programme and compliance implications of TotalEnergies standards - legal authority been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
19.068 | 19 | WP19 | Fuel Partner and Forecourt Coordination | Has the team obtained written confirmation or documented proof for forecourt layout - legal authority? | Current certificate/letter/report, version control and document-control entry. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
19.069 | 19 | WP19 | Fuel Partner and Forecourt Coordination | Does the evidence for tank farm - legal authority support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
19.070 | 19 | WP19 | Fuel Partner and Forecourt Coordination | Have dependencies linked to fuel logistics - legal authority been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
19.071 | 19 | WP19 | Fuel Partner and Forecourt Coordination | Has the project team confirmed C-store integration - legal authority in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
19.072 | 19 | WP19 | Fuel Partner and Forecourt Coordination | Is there a responsible owner, due date and approval route for brand signage - legal authority? | Register entry, supporting drawing/report, approval note and updated risk item. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
19.073 | 19 | WP19 | Fuel Partner and Forecourt Coordination | Has the gate file tested whether TotalEnergies standards - technical feasibility creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
19.074 | 19 | WP19 | Fuel Partner and Forecourt Coordination | Are assumptions for forecourt layout - technical feasibility documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
19.075 | 19 | WP19 | Fuel Partner and Forecourt Coordination | Has the relevant authority, specialist or professional adviser reviewed tank farm - technical feasibility where required? | Authority response, compliance checklist, file note and management approval. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
19.076 | 19 | WP19 | Fuel Partner and Forecourt Coordination | Is the decision record for fuel logistics - technical feasibility aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
19.077 | 19 | WP19 | Fuel Partner and Forecourt Coordination | Have cost, programme and compliance implications of C-store integration - technical feasibility been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
19.078 | 19 | WP19 | Fuel Partner and Forecourt Coordination | Has the team obtained written confirmation or documented proof for brand signage - technical feasibility? | Current certificate/letter/report, version control and document-control entry. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
19.079 | 19 | WP19 | Fuel Partner and Forecourt Coordination | Does the evidence for TotalEnergies standards - financial viability support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
19.080 | 19 | WP19 | Fuel Partner and Forecourt Coordination | Have dependencies linked to forecourt layout - financial viability been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
19.081 | 19 | WP19 | Fuel Partner and Forecourt Coordination | Has the project team confirmed tank farm - financial viability in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
19.082 | 19 | WP19 | Fuel Partner and Forecourt Coordination | Is there a responsible owner, due date and approval route for fuel logistics - financial viability? | Register entry, supporting drawing/report, approval note and updated risk item. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
19.083 | 19 | WP19 | Fuel Partner and Forecourt Coordination | Has the gate file tested whether C-store integration - financial viability creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
19.084 | 19 | WP19 | Fuel Partner and Forecourt Coordination | Are assumptions for brand signage - financial viability documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
19.085 | 19 | WP19 | Fuel Partner and Forecourt Coordination | Has the relevant authority, specialist or professional adviser reviewed TotalEnergies standards - programme impact where required? | Authority response, compliance checklist, file note and management approval. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
19.086 | 19 | WP19 | Fuel Partner and Forecourt Coordination | Is the decision record for forecourt layout - programme impact aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
19.087 | 19 | WP19 | Fuel Partner and Forecourt Coordination | Have cost, programme and compliance implications of tank farm - programme impact been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
19.088 | 19 | WP19 | Fuel Partner and Forecourt Coordination | Has the team obtained written confirmation or documented proof for fuel logistics - programme impact? | Current certificate/letter/report, version control and document-control entry. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
19.089 | 19 | WP19 | Fuel Partner and Forecourt Coordination | Does the evidence for C-store integration - programme impact support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
19.090 | 19 | WP19 | Fuel Partner and Forecourt Coordination | Have dependencies linked to brand signage - programme impact been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
19.091 | 19 | WP19 | Fuel Partner and Forecourt Coordination | Has the project team confirmed TotalEnergies standards - risk mitigation in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
19.092 | 19 | WP19 | Fuel Partner and Forecourt Coordination | Is there a responsible owner, due date and approval route for forecourt layout - risk mitigation? | Register entry, supporting drawing/report, approval note and updated risk item. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
19.093 | 19 | WP19 | Fuel Partner and Forecourt Coordination | Has the gate file tested whether tank farm - risk mitigation creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
19.094 | 19 | WP19 | Fuel Partner and Forecourt Coordination | Are assumptions for fuel logistics - risk mitigation documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
19.095 | 19 | WP19 | Fuel Partner and Forecourt Coordination | Has the relevant authority, specialist or professional adviser reviewed C-store integration - risk mitigation where required? | Authority response, compliance checklist, file note and management approval. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
19.096 | 19 | WP19 | Fuel Partner and Forecourt Coordination | Is the decision record for brand signage - risk mitigation aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
19.097 | 19 | WP19 | Fuel Partner and Forecourt Coordination | Have cost, programme and compliance implications of TotalEnergies standards - stakeholder acceptance been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
19.098 | 19 | WP19 | Fuel Partner and Forecourt Coordination | Has the team obtained written confirmation or documented proof for forecourt layout - stakeholder acceptance? | Current certificate/letter/report, version control and document-control entry. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
19.099 | 19 | WP19 | Fuel Partner and Forecourt Coordination | Does the evidence for tank farm - stakeholder acceptance support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
19.100 | 19 | WP19 | Fuel Partner and Forecourt Coordination | Have dependencies linked to fuel logistics - stakeholder acceptance been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
20.001 | 20 | WP20 | Development Design | Has the project team confirmed architectural design - governance approval in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
20.002 | 20 | WP20 | Development Design | Is there a responsible owner, due date and approval route for civil design - governance approval? | Register entry, supporting drawing/report, approval note and updated risk item. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
20.003 | 20 | WP20 | Development Design | Has the gate file tested whether structural design - governance approval creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
20.004 | 20 | WP20 | Development Design | Are assumptions for MEP design - governance approval documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
20.005 | 20 | WP20 | Development Design | Has the relevant authority, specialist or professional adviser reviewed fire strategy - governance approval where required? | Authority response, compliance checklist, file note and management approval. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
20.006 | 20 | WP20 | Development Design | Is the decision record for landscaping - governance approval aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
20.007 | 20 | WP20 | Development Design | Have cost, programme and compliance implications of architectural design - legal authority been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
20.008 | 20 | WP20 | Development Design | Has the team obtained written confirmation or documented proof for civil design - legal authority? | Current certificate/letter/report, version control and document-control entry. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
20.009 | 20 | WP20 | Development Design | Does the evidence for structural design - legal authority support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
20.010 | 20 | WP20 | Development Design | Have dependencies linked to MEP design - legal authority been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
20.011 | 20 | WP20 | Development Design | Has the project team confirmed fire strategy - legal authority in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
20.012 | 20 | WP20 | Development Design | Is there a responsible owner, due date and approval route for landscaping - legal authority? | Register entry, supporting drawing/report, approval note and updated risk item. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
20.013 | 20 | WP20 | Development Design | Has the gate file tested whether architectural design - technical feasibility creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
20.014 | 20 | WP20 | Development Design | Are assumptions for civil design - technical feasibility documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
20.015 | 20 | WP20 | Development Design | Has the relevant authority, specialist or professional adviser reviewed structural design - technical feasibility where required? | Authority response, compliance checklist, file note and management approval. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
20.016 | 20 | WP20 | Development Design | Is the decision record for MEP design - technical feasibility aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
20.017 | 20 | WP20 | Development Design | Have cost, programme and compliance implications of fire strategy - technical feasibility been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
20.018 | 20 | WP20 | Development Design | Has the team obtained written confirmation or documented proof for landscaping - technical feasibility? | Current certificate/letter/report, version control and document-control entry. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
20.019 | 20 | WP20 | Development Design | Does the evidence for architectural design - financial viability support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
20.020 | 20 | WP20 | Development Design | Have dependencies linked to civil design - financial viability been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
20.021 | 20 | WP20 | Development Design | Has the project team confirmed structural design - financial viability in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
20.022 | 20 | WP20 | Development Design | Is there a responsible owner, due date and approval route for MEP design - financial viability? | Register entry, supporting drawing/report, approval note and updated risk item. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
20.023 | 20 | WP20 | Development Design | Has the gate file tested whether fire strategy - financial viability creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
20.024 | 20 | WP20 | Development Design | Are assumptions for landscaping - financial viability documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
20.025 | 20 | WP20 | Development Design | Has the relevant authority, specialist or professional adviser reviewed architectural design - programme impact where required? | Authority response, compliance checklist, file note and management approval. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
20.026 | 20 | WP20 | Development Design | Is the decision record for civil design - programme impact aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
20.027 | 20 | WP20 | Development Design | Have cost, programme and compliance implications of structural design - programme impact been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
20.028 | 20 | WP20 | Development Design | Has the team obtained written confirmation or documented proof for MEP design - programme impact? | Current certificate/letter/report, version control and document-control entry. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
20.029 | 20 | WP20 | Development Design | Does the evidence for fire strategy - programme impact support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
20.030 | 20 | WP20 | Development Design | Have dependencies linked to landscaping - programme impact been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
20.031 | 20 | WP20 | Development Design | Has the project team confirmed architectural design - risk mitigation in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
20.032 | 20 | WP20 | Development Design | Is there a responsible owner, due date and approval route for civil design - risk mitigation? | Register entry, supporting drawing/report, approval note and updated risk item. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
20.033 | 20 | WP20 | Development Design | Has the gate file tested whether structural design - risk mitigation creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
20.034 | 20 | WP20 | Development Design | Are assumptions for MEP design - risk mitigation documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
20.035 | 20 | WP20 | Development Design | Has the relevant authority, specialist or professional adviser reviewed fire strategy - risk mitigation where required? | Authority response, compliance checklist, file note and management approval. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
20.036 | 20 | WP20 | Development Design | Is the decision record for landscaping - risk mitigation aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
20.037 | 20 | WP20 | Development Design | Have cost, programme and compliance implications of architectural design - stakeholder acceptance been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
20.038 | 20 | WP20 | Development Design | Has the team obtained written confirmation or documented proof for civil design - stakeholder acceptance? | Current certificate/letter/report, version control and document-control entry. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
20.039 | 20 | WP20 | Development Design | Does the evidence for structural design - stakeholder acceptance support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
20.040 | 20 | WP20 | Development Design | Have dependencies linked to MEP design - stakeholder acceptance been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
20.041 | 20 | WP20 | Development Design | Has the project team confirmed fire strategy - stakeholder acceptance in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
20.042 | 20 | WP20 | Development Design | Is there a responsible owner, due date and approval route for landscaping - stakeholder acceptance? | Register entry, supporting drawing/report, approval note and updated risk item. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
20.043 | 20 | WP20 | Development Design | Has the gate file tested whether architectural design - document control creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
20.044 | 20 | WP20 | Development Design | Are assumptions for civil design - document control documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
20.045 | 20 | WP20 | Development Design | Has the relevant authority, specialist or professional adviser reviewed structural design - document control where required? | Authority response, compliance checklist, file note and management approval. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
20.046 | 20 | WP20 | Development Design | Is the decision record for MEP design - document control aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
20.047 | 20 | WP20 | Development Design | Have cost, programme and compliance implications of fire strategy - document control been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
20.048 | 20 | WP20 | Development Design | Has the team obtained written confirmation or documented proof for landscaping - document control? | Current certificate/letter/report, version control and document-control entry. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
20.049 | 20 | WP20 | Development Design | Does the evidence for architectural design - professional certification support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
20.050 | 20 | WP20 | Development Design | Have dependencies linked to civil design - professional certification been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
20.051 | 20 | WP20 | Development Design | Has the project team confirmed structural design - professional certification in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
20.052 | 20 | WP20 | Development Design | Is there a responsible owner, due date and approval route for MEP design - professional certification? | Register entry, supporting drawing/report, approval note and updated risk item. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
20.053 | 20 | WP20 | Development Design | Has the gate file tested whether fire strategy - professional certification creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
20.054 | 20 | WP20 | Development Design | Are assumptions for landscaping - professional certification documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
20.055 | 20 | WP20 | Development Design | Has the relevant authority, specialist or professional adviser reviewed architectural design - implementation readiness where required? | Authority response, compliance checklist, file note and management approval. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
20.056 | 20 | WP20 | Development Design | Is the decision record for civil design - implementation readiness aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
20.057 | 20 | WP20 | Development Design | Have cost, programme and compliance implications of structural design - implementation readiness been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
20.058 | 20 | WP20 | Development Design | Has the team obtained written confirmation or documented proof for MEP design - implementation readiness? | Current certificate/letter/report, version control and document-control entry. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
20.059 | 20 | WP20 | Development Design | Does the evidence for fire strategy - implementation readiness support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
20.060 | 20 | WP20 | Development Design | Have dependencies linked to landscaping - implementation readiness been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
20.061 | 20 | WP20 | Development Design | Has the project team confirmed architectural design - governance approval in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
20.062 | 20 | WP20 | Development Design | Is there a responsible owner, due date and approval route for civil design - governance approval? | Register entry, supporting drawing/report, approval note and updated risk item. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
20.063 | 20 | WP20 | Development Design | Has the gate file tested whether structural design - governance approval creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
20.064 | 20 | WP20 | Development Design | Are assumptions for MEP design - governance approval documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
20.065 | 20 | WP20 | Development Design | Has the relevant authority, specialist or professional adviser reviewed fire strategy - governance approval where required? | Authority response, compliance checklist, file note and management approval. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
20.066 | 20 | WP20 | Development Design | Is the decision record for landscaping - governance approval aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
20.067 | 20 | WP20 | Development Design | Have cost, programme and compliance implications of architectural design - legal authority been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
20.068 | 20 | WP20 | Development Design | Has the team obtained written confirmation or documented proof for civil design - legal authority? | Current certificate/letter/report, version control and document-control entry. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
20.069 | 20 | WP20 | Development Design | Does the evidence for structural design - legal authority support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
20.070 | 20 | WP20 | Development Design | Have dependencies linked to MEP design - legal authority been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
20.071 | 20 | WP20 | Development Design | Has the project team confirmed fire strategy - legal authority in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
20.072 | 20 | WP20 | Development Design | Is there a responsible owner, due date and approval route for landscaping - legal authority? | Register entry, supporting drawing/report, approval note and updated risk item. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
20.073 | 20 | WP20 | Development Design | Has the gate file tested whether architectural design - technical feasibility creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
20.074 | 20 | WP20 | Development Design | Are assumptions for civil design - technical feasibility documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
20.075 | 20 | WP20 | Development Design | Has the relevant authority, specialist or professional adviser reviewed structural design - technical feasibility where required? | Authority response, compliance checklist, file note and management approval. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
20.076 | 20 | WP20 | Development Design | Is the decision record for MEP design - technical feasibility aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
20.077 | 20 | WP20 | Development Design | Have cost, programme and compliance implications of fire strategy - technical feasibility been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
20.078 | 20 | WP20 | Development Design | Has the team obtained written confirmation or documented proof for landscaping - technical feasibility? | Current certificate/letter/report, version control and document-control entry. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
20.079 | 20 | WP20 | Development Design | Does the evidence for architectural design - financial viability support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
20.080 | 20 | WP20 | Development Design | Have dependencies linked to civil design - financial viability been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
20.081 | 20 | WP20 | Development Design | Has the project team confirmed structural design - financial viability in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
20.082 | 20 | WP20 | Development Design | Is there a responsible owner, due date and approval route for MEP design - financial viability? | Register entry, supporting drawing/report, approval note and updated risk item. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
20.083 | 20 | WP20 | Development Design | Has the gate file tested whether fire strategy - financial viability creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
20.084 | 20 | WP20 | Development Design | Are assumptions for landscaping - financial viability documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
20.085 | 20 | WP20 | Development Design | Has the relevant authority, specialist or professional adviser reviewed architectural design - programme impact where required? | Authority response, compliance checklist, file note and management approval. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
20.086 | 20 | WP20 | Development Design | Is the decision record for civil design - programme impact aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
20.087 | 20 | WP20 | Development Design | Have cost, programme and compliance implications of structural design - programme impact been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
20.088 | 20 | WP20 | Development Design | Has the team obtained written confirmation or documented proof for MEP design - programme impact? | Current certificate/letter/report, version control and document-control entry. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
20.089 | 20 | WP20 | Development Design | Does the evidence for fire strategy - programme impact support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
20.090 | 20 | WP20 | Development Design | Have dependencies linked to landscaping - programme impact been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
20.091 | 20 | WP20 | Development Design | Has the project team confirmed architectural design - risk mitigation in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
20.092 | 20 | WP20 | Development Design | Is there a responsible owner, due date and approval route for civil design - risk mitigation? | Register entry, supporting drawing/report, approval note and updated risk item. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
20.093 | 20 | WP20 | Development Design | Has the gate file tested whether structural design - risk mitigation creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
20.094 | 20 | WP20 | Development Design | Are assumptions for MEP design - risk mitigation documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
20.095 | 20 | WP20 | Development Design | Has the relevant authority, specialist or professional adviser reviewed fire strategy - risk mitigation where required? | Authority response, compliance checklist, file note and management approval. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
20.096 | 20 | WP20 | Development Design | Is the decision record for landscaping - risk mitigation aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
20.097 | 20 | WP20 | Development Design | Have cost, programme and compliance implications of architectural design - stakeholder acceptance been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
20.098 | 20 | WP20 | Development Design | Has the team obtained written confirmation or documented proof for civil design - stakeholder acceptance? | Current certificate/letter/report, version control and document-control entry. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
20.099 | 20 | WP20 | Development Design | Does the evidence for structural design - stakeholder acceptance support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
20.100 | 20 | WP20 | Development Design | Have dependencies linked to MEP design - stakeholder acceptance been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
21.001 | 21 | WP21 | Engineering Design and Technical Documentation | Has the project team confirmed bulk earthworks - governance approval in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
21.002 | 21 | WP21 | Engineering Design and Technical Documentation | Is there a responsible owner, due date and approval route for stormwater design - governance approval? | Register entry, supporting drawing/report, approval note and updated risk item. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
21.003 | 21 | WP21 | Engineering Design and Technical Documentation | Has the gate file tested whether road pavements - governance approval creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
21.004 | 21 | WP21 | Engineering Design and Technical Documentation | Are assumptions for water reticulation - governance approval documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
21.005 | 21 | WP21 | Engineering Design and Technical Documentation | Has the relevant authority, specialist or professional adviser reviewed sewer reticulation - governance approval where required? | Authority response, compliance checklist, file note and management approval. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
21.006 | 21 | WP21 | Engineering Design and Technical Documentation | Is the decision record for electrical reticulation - governance approval aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
21.007 | 21 | WP21 | Engineering Design and Technical Documentation | Have cost, programme and compliance implications of bulk earthworks - legal authority been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
21.008 | 21 | WP21 | Engineering Design and Technical Documentation | Has the team obtained written confirmation or documented proof for stormwater design - legal authority? | Current certificate/letter/report, version control and document-control entry. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
21.009 | 21 | WP21 | Engineering Design and Technical Documentation | Does the evidence for road pavements - legal authority support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
21.010 | 21 | WP21 | Engineering Design and Technical Documentation | Have dependencies linked to water reticulation - legal authority been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
21.011 | 21 | WP21 | Engineering Design and Technical Documentation | Has the project team confirmed sewer reticulation - legal authority in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
21.012 | 21 | WP21 | Engineering Design and Technical Documentation | Is there a responsible owner, due date and approval route for electrical reticulation - legal authority? | Register entry, supporting drawing/report, approval note and updated risk item. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
21.013 | 21 | WP21 | Engineering Design and Technical Documentation | Has the gate file tested whether bulk earthworks - technical feasibility creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
21.014 | 21 | WP21 | Engineering Design and Technical Documentation | Are assumptions for stormwater design - technical feasibility documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
21.015 | 21 | WP21 | Engineering Design and Technical Documentation | Has the relevant authority, specialist or professional adviser reviewed road pavements - technical feasibility where required? | Authority response, compliance checklist, file note and management approval. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
21.016 | 21 | WP21 | Engineering Design and Technical Documentation | Is the decision record for water reticulation - technical feasibility aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
21.017 | 21 | WP21 | Engineering Design and Technical Documentation | Have cost, programme and compliance implications of sewer reticulation - technical feasibility been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
21.018 | 21 | WP21 | Engineering Design and Technical Documentation | Has the team obtained written confirmation or documented proof for electrical reticulation - technical feasibility? | Current certificate/letter/report, version control and document-control entry. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
21.019 | 21 | WP21 | Engineering Design and Technical Documentation | Does the evidence for bulk earthworks - financial viability support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
21.020 | 21 | WP21 | Engineering Design and Technical Documentation | Have dependencies linked to stormwater design - financial viability been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
21.021 | 21 | WP21 | Engineering Design and Technical Documentation | Has the project team confirmed road pavements - financial viability in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
21.022 | 21 | WP21 | Engineering Design and Technical Documentation | Is there a responsible owner, due date and approval route for water reticulation - financial viability? | Register entry, supporting drawing/report, approval note and updated risk item. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
21.023 | 21 | WP21 | Engineering Design and Technical Documentation | Has the gate file tested whether sewer reticulation - financial viability creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
21.024 | 21 | WP21 | Engineering Design and Technical Documentation | Are assumptions for electrical reticulation - financial viability documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
21.025 | 21 | WP21 | Engineering Design and Technical Documentation | Has the relevant authority, specialist or professional adviser reviewed bulk earthworks - programme impact where required? | Authority response, compliance checklist, file note and management approval. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
21.026 | 21 | WP21 | Engineering Design and Technical Documentation | Is the decision record for stormwater design - programme impact aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
21.027 | 21 | WP21 | Engineering Design and Technical Documentation | Have cost, programme and compliance implications of road pavements - programme impact been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
21.028 | 21 | WP21 | Engineering Design and Technical Documentation | Has the team obtained written confirmation or documented proof for water reticulation - programme impact? | Current certificate/letter/report, version control and document-control entry. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
21.029 | 21 | WP21 | Engineering Design and Technical Documentation | Does the evidence for sewer reticulation - programme impact support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
21.030 | 21 | WP21 | Engineering Design and Technical Documentation | Have dependencies linked to electrical reticulation - programme impact been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
21.031 | 21 | WP21 | Engineering Design and Technical Documentation | Has the project team confirmed bulk earthworks - risk mitigation in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
21.032 | 21 | WP21 | Engineering Design and Technical Documentation | Is there a responsible owner, due date and approval route for stormwater design - risk mitigation? | Register entry, supporting drawing/report, approval note and updated risk item. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
21.033 | 21 | WP21 | Engineering Design and Technical Documentation | Has the gate file tested whether road pavements - risk mitigation creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
21.034 | 21 | WP21 | Engineering Design and Technical Documentation | Are assumptions for water reticulation - risk mitigation documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
21.035 | 21 | WP21 | Engineering Design and Technical Documentation | Has the relevant authority, specialist or professional adviser reviewed sewer reticulation - risk mitigation where required? | Authority response, compliance checklist, file note and management approval. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
21.036 | 21 | WP21 | Engineering Design and Technical Documentation | Is the decision record for electrical reticulation - risk mitigation aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
21.037 | 21 | WP21 | Engineering Design and Technical Documentation | Have cost, programme and compliance implications of bulk earthworks - stakeholder acceptance been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
21.038 | 21 | WP21 | Engineering Design and Technical Documentation | Has the team obtained written confirmation or documented proof for stormwater design - stakeholder acceptance? | Current certificate/letter/report, version control and document-control entry. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
21.039 | 21 | WP21 | Engineering Design and Technical Documentation | Does the evidence for road pavements - stakeholder acceptance support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
21.040 | 21 | WP21 | Engineering Design and Technical Documentation | Have dependencies linked to water reticulation - stakeholder acceptance been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
21.041 | 21 | WP21 | Engineering Design and Technical Documentation | Has the project team confirmed sewer reticulation - stakeholder acceptance in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
21.042 | 21 | WP21 | Engineering Design and Technical Documentation | Is there a responsible owner, due date and approval route for electrical reticulation - stakeholder acceptance? | Register entry, supporting drawing/report, approval note and updated risk item. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
21.043 | 21 | WP21 | Engineering Design and Technical Documentation | Has the gate file tested whether bulk earthworks - document control creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
21.044 | 21 | WP21 | Engineering Design and Technical Documentation | Are assumptions for stormwater design - document control documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
21.045 | 21 | WP21 | Engineering Design and Technical Documentation | Has the relevant authority, specialist or professional adviser reviewed road pavements - document control where required? | Authority response, compliance checklist, file note and management approval. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
21.046 | 21 | WP21 | Engineering Design and Technical Documentation | Is the decision record for water reticulation - document control aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
21.047 | 21 | WP21 | Engineering Design and Technical Documentation | Have cost, programme and compliance implications of sewer reticulation - document control been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
21.048 | 21 | WP21 | Engineering Design and Technical Documentation | Has the team obtained written confirmation or documented proof for electrical reticulation - document control? | Current certificate/letter/report, version control and document-control entry. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
21.049 | 21 | WP21 | Engineering Design and Technical Documentation | Does the evidence for bulk earthworks - professional certification support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
21.050 | 21 | WP21 | Engineering Design and Technical Documentation | Have dependencies linked to stormwater design - professional certification been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
21.051 | 21 | WP21 | Engineering Design and Technical Documentation | Has the project team confirmed road pavements - professional certification in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
21.052 | 21 | WP21 | Engineering Design and Technical Documentation | Is there a responsible owner, due date and approval route for water reticulation - professional certification? | Register entry, supporting drawing/report, approval note and updated risk item. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
21.053 | 21 | WP21 | Engineering Design and Technical Documentation | Has the gate file tested whether sewer reticulation - professional certification creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
21.054 | 21 | WP21 | Engineering Design and Technical Documentation | Are assumptions for electrical reticulation - professional certification documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
21.055 | 21 | WP21 | Engineering Design and Technical Documentation | Has the relevant authority, specialist or professional adviser reviewed bulk earthworks - implementation readiness where required? | Authority response, compliance checklist, file note and management approval. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
21.056 | 21 | WP21 | Engineering Design and Technical Documentation | Is the decision record for stormwater design - implementation readiness aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
21.057 | 21 | WP21 | Engineering Design and Technical Documentation | Have cost, programme and compliance implications of road pavements - implementation readiness been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
21.058 | 21 | WP21 | Engineering Design and Technical Documentation | Has the team obtained written confirmation or documented proof for water reticulation - implementation readiness? | Current certificate/letter/report, version control and document-control entry. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
21.059 | 21 | WP21 | Engineering Design and Technical Documentation | Does the evidence for sewer reticulation - implementation readiness support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
21.060 | 21 | WP21 | Engineering Design and Technical Documentation | Have dependencies linked to electrical reticulation - implementation readiness been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
21.061 | 21 | WP21 | Engineering Design and Technical Documentation | Has the project team confirmed bulk earthworks - governance approval in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
21.062 | 21 | WP21 | Engineering Design and Technical Documentation | Is there a responsible owner, due date and approval route for stormwater design - governance approval? | Register entry, supporting drawing/report, approval note and updated risk item. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
21.063 | 21 | WP21 | Engineering Design and Technical Documentation | Has the gate file tested whether road pavements - governance approval creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
21.064 | 21 | WP21 | Engineering Design and Technical Documentation | Are assumptions for water reticulation - governance approval documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
21.065 | 21 | WP21 | Engineering Design and Technical Documentation | Has the relevant authority, specialist or professional adviser reviewed sewer reticulation - governance approval where required? | Authority response, compliance checklist, file note and management approval. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
21.066 | 21 | WP21 | Engineering Design and Technical Documentation | Is the decision record for electrical reticulation - governance approval aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
21.067 | 21 | WP21 | Engineering Design and Technical Documentation | Have cost, programme and compliance implications of bulk earthworks - legal authority been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
21.068 | 21 | WP21 | Engineering Design and Technical Documentation | Has the team obtained written confirmation or documented proof for stormwater design - legal authority? | Current certificate/letter/report, version control and document-control entry. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
21.069 | 21 | WP21 | Engineering Design and Technical Documentation | Does the evidence for road pavements - legal authority support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
21.070 | 21 | WP21 | Engineering Design and Technical Documentation | Have dependencies linked to water reticulation - legal authority been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
21.071 | 21 | WP21 | Engineering Design and Technical Documentation | Has the project team confirmed sewer reticulation - legal authority in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
21.072 | 21 | WP21 | Engineering Design and Technical Documentation | Is there a responsible owner, due date and approval route for electrical reticulation - legal authority? | Register entry, supporting drawing/report, approval note and updated risk item. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
21.073 | 21 | WP21 | Engineering Design and Technical Documentation | Has the gate file tested whether bulk earthworks - technical feasibility creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
21.074 | 21 | WP21 | Engineering Design and Technical Documentation | Are assumptions for stormwater design - technical feasibility documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
21.075 | 21 | WP21 | Engineering Design and Technical Documentation | Has the relevant authority, specialist or professional adviser reviewed road pavements - technical feasibility where required? | Authority response, compliance checklist, file note and management approval. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
21.076 | 21 | WP21 | Engineering Design and Technical Documentation | Is the decision record for water reticulation - technical feasibility aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
21.077 | 21 | WP21 | Engineering Design and Technical Documentation | Have cost, programme and compliance implications of sewer reticulation - technical feasibility been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
21.078 | 21 | WP21 | Engineering Design and Technical Documentation | Has the team obtained written confirmation or documented proof for electrical reticulation - technical feasibility? | Current certificate/letter/report, version control and document-control entry. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
21.079 | 21 | WP21 | Engineering Design and Technical Documentation | Does the evidence for bulk earthworks - financial viability support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
21.080 | 21 | WP21 | Engineering Design and Technical Documentation | Have dependencies linked to stormwater design - financial viability been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
21.081 | 21 | WP21 | Engineering Design and Technical Documentation | Has the project team confirmed road pavements - financial viability in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
21.082 | 21 | WP21 | Engineering Design and Technical Documentation | Is there a responsible owner, due date and approval route for water reticulation - financial viability? | Register entry, supporting drawing/report, approval note and updated risk item. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
21.083 | 21 | WP21 | Engineering Design and Technical Documentation | Has the gate file tested whether sewer reticulation - financial viability creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
21.084 | 21 | WP21 | Engineering Design and Technical Documentation | Are assumptions for electrical reticulation - financial viability documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
21.085 | 21 | WP21 | Engineering Design and Technical Documentation | Has the relevant authority, specialist or professional adviser reviewed bulk earthworks - programme impact where required? | Authority response, compliance checklist, file note and management approval. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
21.086 | 21 | WP21 | Engineering Design and Technical Documentation | Is the decision record for stormwater design - programme impact aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
21.087 | 21 | WP21 | Engineering Design and Technical Documentation | Have cost, programme and compliance implications of road pavements - programme impact been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
21.088 | 21 | WP21 | Engineering Design and Technical Documentation | Has the team obtained written confirmation or documented proof for water reticulation - programme impact? | Current certificate/letter/report, version control and document-control entry. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
21.089 | 21 | WP21 | Engineering Design and Technical Documentation | Does the evidence for sewer reticulation - programme impact support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
21.090 | 21 | WP21 | Engineering Design and Technical Documentation | Have dependencies linked to electrical reticulation - programme impact been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
21.091 | 21 | WP21 | Engineering Design and Technical Documentation | Has the project team confirmed bulk earthworks - risk mitigation in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
21.092 | 21 | WP21 | Engineering Design and Technical Documentation | Is there a responsible owner, due date and approval route for stormwater design - risk mitigation? | Register entry, supporting drawing/report, approval note and updated risk item. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
21.093 | 21 | WP21 | Engineering Design and Technical Documentation | Has the gate file tested whether road pavements - risk mitigation creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
21.094 | 21 | WP21 | Engineering Design and Technical Documentation | Are assumptions for water reticulation - risk mitigation documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
21.095 | 21 | WP21 | Engineering Design and Technical Documentation | Has the relevant authority, specialist or professional adviser reviewed sewer reticulation - risk mitigation where required? | Authority response, compliance checklist, file note and management approval. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
21.096 | 21 | WP21 | Engineering Design and Technical Documentation | Is the decision record for electrical reticulation - risk mitigation aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
21.097 | 21 | WP21 | Engineering Design and Technical Documentation | Have cost, programme and compliance implications of bulk earthworks - stakeholder acceptance been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
21.098 | 21 | WP21 | Engineering Design and Technical Documentation | Has the team obtained written confirmation or documented proof for stormwater design - stakeholder acceptance? | Current certificate/letter/report, version control and document-control entry. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
21.099 | 21 | WP21 | Engineering Design and Technical Documentation | Does the evidence for road pavements - stakeholder acceptance support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
21.100 | 21 | WP21 | Engineering Design and Technical Documentation | Have dependencies linked to water reticulation - stakeholder acceptance been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
22.001 | 22 | WP22 | Cost Planning and Financial Modelling | Has the project team confirmed CAPEX estimate - governance approval in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | IFRS/IFRS for SMEs principles; lender due diligence checklist; signed financial model | Yes / No / N/A + Score 0–5 + Rating
22.002 | 22 | WP22 | Cost Planning and Financial Modelling | Is there a responsible owner, due date and approval route for professional fees - governance approval? | Register entry, supporting drawing/report, approval note and updated risk item. | CIDB/procurement best practice; cost plan; QS measurement and BOQ controls | Yes / No / N/A + Score 0–5 + Rating
22.003 | 22 | WP22 | Cost Planning and Financial Modelling | Has the gate file tested whether approval costs - governance approval creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | Treasury-style value-for-money principles; funding term sheet; drawdown controls | Yes / No / N/A + Score 0–5 + Rating
22.004 | 22 | WP22 | Cost Planning and Financial Modelling | Are assumptions for tenant fit-out allowances - governance approval documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | IFRS/IFRS for SMEs principles; lender due diligence checklist; signed financial model | Yes / No / N/A + Score 0–5 + Rating
22.005 | 22 | WP22 | Cost Planning and Financial Modelling | Has the relevant authority, specialist or professional adviser reviewed contingency - governance approval where required? | Authority response, compliance checklist, file note and management approval. | CIDB/procurement best practice; cost plan; QS measurement and BOQ controls | Yes / No / N/A + Score 0–5 + Rating
22.006 | 22 | WP22 | Cost Planning and Financial Modelling | Is the decision record for rental income - governance approval aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | Treasury-style value-for-money principles; funding term sheet; drawdown controls | Yes / No / N/A + Score 0–5 + Rating
22.007 | 22 | WP22 | Cost Planning and Financial Modelling | Have cost, programme and compliance implications of CAPEX estimate - legal authority been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | IFRS/IFRS for SMEs principles; lender due diligence checklist; signed financial model | Yes / No / N/A + Score 0–5 + Rating
22.008 | 22 | WP22 | Cost Planning and Financial Modelling | Has the team obtained written confirmation or documented proof for professional fees - legal authority? | Current certificate/letter/report, version control and document-control entry. | CIDB/procurement best practice; cost plan; QS measurement and BOQ controls | Yes / No / N/A + Score 0–5 + Rating
22.009 | 22 | WP22 | Cost Planning and Financial Modelling | Does the evidence for approval costs - legal authority support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | Treasury-style value-for-money principles; funding term sheet; drawdown controls | Yes / No / N/A + Score 0–5 + Rating
22.010 | 22 | WP22 | Cost Planning and Financial Modelling | Have dependencies linked to tenant fit-out allowances - legal authority been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | IFRS/IFRS for SMEs principles; lender due diligence checklist; signed financial model | Yes / No / N/A + Score 0–5 + Rating
22.011 | 22 | WP22 | Cost Planning and Financial Modelling | Has the project team confirmed contingency - legal authority in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | CIDB/procurement best practice; cost plan; QS measurement and BOQ controls | Yes / No / N/A + Score 0–5 + Rating
22.012 | 22 | WP22 | Cost Planning and Financial Modelling | Is there a responsible owner, due date and approval route for rental income - legal authority? | Register entry, supporting drawing/report, approval note and updated risk item. | Treasury-style value-for-money principles; funding term sheet; drawdown controls | Yes / No / N/A + Score 0–5 + Rating
22.013 | 22 | WP22 | Cost Planning and Financial Modelling | Has the gate file tested whether CAPEX estimate - technical feasibility creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | IFRS/IFRS for SMEs principles; lender due diligence checklist; signed financial model | Yes / No / N/A + Score 0–5 + Rating
22.014 | 22 | WP22 | Cost Planning and Financial Modelling | Are assumptions for professional fees - technical feasibility documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | CIDB/procurement best practice; cost plan; QS measurement and BOQ controls | Yes / No / N/A + Score 0–5 + Rating
22.015 | 22 | WP22 | Cost Planning and Financial Modelling | Has the relevant authority, specialist or professional adviser reviewed approval costs - technical feasibility where required? | Authority response, compliance checklist, file note and management approval. | Treasury-style value-for-money principles; funding term sheet; drawdown controls | Yes / No / N/A + Score 0–5 + Rating
22.016 | 22 | WP22 | Cost Planning and Financial Modelling | Is the decision record for tenant fit-out allowances - technical feasibility aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | IFRS/IFRS for SMEs principles; lender due diligence checklist; signed financial model | Yes / No / N/A + Score 0–5 + Rating
22.017 | 22 | WP22 | Cost Planning and Financial Modelling | Have cost, programme and compliance implications of contingency - technical feasibility been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | CIDB/procurement best practice; cost plan; QS measurement and BOQ controls | Yes / No / N/A + Score 0–5 + Rating
22.018 | 22 | WP22 | Cost Planning and Financial Modelling | Has the team obtained written confirmation or documented proof for rental income - technical feasibility? | Current certificate/letter/report, version control and document-control entry. | Treasury-style value-for-money principles; funding term sheet; drawdown controls | Yes / No / N/A + Score 0–5 + Rating
22.019 | 22 | WP22 | Cost Planning and Financial Modelling | Does the evidence for CAPEX estimate - financial viability support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | IFRS/IFRS for SMEs principles; lender due diligence checklist; signed financial model | Yes / No / N/A + Score 0–5 + Rating
22.020 | 22 | WP22 | Cost Planning and Financial Modelling | Have dependencies linked to professional fees - financial viability been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | CIDB/procurement best practice; cost plan; QS measurement and BOQ controls | Yes / No / N/A + Score 0–5 + Rating
22.021 | 22 | WP22 | Cost Planning and Financial Modelling | Has the project team confirmed approval costs - financial viability in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | Treasury-style value-for-money principles; funding term sheet; drawdown controls | Yes / No / N/A + Score 0–5 + Rating
22.022 | 22 | WP22 | Cost Planning and Financial Modelling | Is there a responsible owner, due date and approval route for tenant fit-out allowances - financial viability? | Register entry, supporting drawing/report, approval note and updated risk item. | IFRS/IFRS for SMEs principles; lender due diligence checklist; signed financial model | Yes / No / N/A + Score 0–5 + Rating
22.023 | 22 | WP22 | Cost Planning and Financial Modelling | Has the gate file tested whether contingency - financial viability creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | CIDB/procurement best practice; cost plan; QS measurement and BOQ controls | Yes / No / N/A + Score 0–5 + Rating
22.024 | 22 | WP22 | Cost Planning and Financial Modelling | Are assumptions for rental income - financial viability documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | Treasury-style value-for-money principles; funding term sheet; drawdown controls | Yes / No / N/A + Score 0–5 + Rating
22.025 | 22 | WP22 | Cost Planning and Financial Modelling | Has the relevant authority, specialist or professional adviser reviewed CAPEX estimate - programme impact where required? | Authority response, compliance checklist, file note and management approval. | IFRS/IFRS for SMEs principles; lender due diligence checklist; signed financial model | Yes / No / N/A + Score 0–5 + Rating
22.026 | 22 | WP22 | Cost Planning and Financial Modelling | Is the decision record for professional fees - programme impact aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | CIDB/procurement best practice; cost plan; QS measurement and BOQ controls | Yes / No / N/A + Score 0–5 + Rating
22.027 | 22 | WP22 | Cost Planning and Financial Modelling | Have cost, programme and compliance implications of approval costs - programme impact been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | Treasury-style value-for-money principles; funding term sheet; drawdown controls | Yes / No / N/A + Score 0–5 + Rating
22.028 | 22 | WP22 | Cost Planning and Financial Modelling | Has the team obtained written confirmation or documented proof for tenant fit-out allowances - programme impact? | Current certificate/letter/report, version control and document-control entry. | IFRS/IFRS for SMEs principles; lender due diligence checklist; signed financial model | Yes / No / N/A + Score 0–5 + Rating
22.029 | 22 | WP22 | Cost Planning and Financial Modelling | Does the evidence for contingency - programme impact support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | CIDB/procurement best practice; cost plan; QS measurement and BOQ controls | Yes / No / N/A + Score 0–5 + Rating
22.030 | 22 | WP22 | Cost Planning and Financial Modelling | Have dependencies linked to rental income - programme impact been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | Treasury-style value-for-money principles; funding term sheet; drawdown controls | Yes / No / N/A + Score 0–5 + Rating
22.031 | 22 | WP22 | Cost Planning and Financial Modelling | Has the project team confirmed CAPEX estimate - risk mitigation in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | IFRS/IFRS for SMEs principles; lender due diligence checklist; signed financial model | Yes / No / N/A + Score 0–5 + Rating
22.032 | 22 | WP22 | Cost Planning and Financial Modelling | Is there a responsible owner, due date and approval route for professional fees - risk mitigation? | Register entry, supporting drawing/report, approval note and updated risk item. | CIDB/procurement best practice; cost plan; QS measurement and BOQ controls | Yes / No / N/A + Score 0–5 + Rating
22.033 | 22 | WP22 | Cost Planning and Financial Modelling | Has the gate file tested whether approval costs - risk mitigation creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | Treasury-style value-for-money principles; funding term sheet; drawdown controls | Yes / No / N/A + Score 0–5 + Rating
22.034 | 22 | WP22 | Cost Planning and Financial Modelling | Are assumptions for tenant fit-out allowances - risk mitigation documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | IFRS/IFRS for SMEs principles; lender due diligence checklist; signed financial model | Yes / No / N/A + Score 0–5 + Rating
22.035 | 22 | WP22 | Cost Planning and Financial Modelling | Has the relevant authority, specialist or professional adviser reviewed contingency - risk mitigation where required? | Authority response, compliance checklist, file note and management approval. | CIDB/procurement best practice; cost plan; QS measurement and BOQ controls | Yes / No / N/A + Score 0–5 + Rating
22.036 | 22 | WP22 | Cost Planning and Financial Modelling | Is the decision record for rental income - risk mitigation aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | Treasury-style value-for-money principles; funding term sheet; drawdown controls | Yes / No / N/A + Score 0–5 + Rating
22.037 | 22 | WP22 | Cost Planning and Financial Modelling | Have cost, programme and compliance implications of CAPEX estimate - stakeholder acceptance been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | IFRS/IFRS for SMEs principles; lender due diligence checklist; signed financial model | Yes / No / N/A + Score 0–5 + Rating
22.038 | 22 | WP22 | Cost Planning and Financial Modelling | Has the team obtained written confirmation or documented proof for professional fees - stakeholder acceptance? | Current certificate/letter/report, version control and document-control entry. | CIDB/procurement best practice; cost plan; QS measurement and BOQ controls | Yes / No / N/A + Score 0–5 + Rating
22.039 | 22 | WP22 | Cost Planning and Financial Modelling | Does the evidence for approval costs - stakeholder acceptance support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | Treasury-style value-for-money principles; funding term sheet; drawdown controls | Yes / No / N/A + Score 0–5 + Rating
22.040 | 22 | WP22 | Cost Planning and Financial Modelling | Have dependencies linked to tenant fit-out allowances - stakeholder acceptance been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | IFRS/IFRS for SMEs principles; lender due diligence checklist; signed financial model | Yes / No / N/A + Score 0–5 + Rating
22.041 | 22 | WP22 | Cost Planning and Financial Modelling | Has the project team confirmed contingency - stakeholder acceptance in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | CIDB/procurement best practice; cost plan; QS measurement and BOQ controls | Yes / No / N/A + Score 0–5 + Rating
22.042 | 22 | WP22 | Cost Planning and Financial Modelling | Is there a responsible owner, due date and approval route for rental income - stakeholder acceptance? | Register entry, supporting drawing/report, approval note and updated risk item. | Treasury-style value-for-money principles; funding term sheet; drawdown controls | Yes / No / N/A + Score 0–5 + Rating
22.043 | 22 | WP22 | Cost Planning and Financial Modelling | Has the gate file tested whether CAPEX estimate - document control creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | IFRS/IFRS for SMEs principles; lender due diligence checklist; signed financial model | Yes / No / N/A + Score 0–5 + Rating
22.044 | 22 | WP22 | Cost Planning and Financial Modelling | Are assumptions for professional fees - document control documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | CIDB/procurement best practice; cost plan; QS measurement and BOQ controls | Yes / No / N/A + Score 0–5 + Rating
22.045 | 22 | WP22 | Cost Planning and Financial Modelling | Has the relevant authority, specialist or professional adviser reviewed approval costs - document control where required? | Authority response, compliance checklist, file note and management approval. | Treasury-style value-for-money principles; funding term sheet; drawdown controls | Yes / No / N/A + Score 0–5 + Rating
22.046 | 22 | WP22 | Cost Planning and Financial Modelling | Is the decision record for tenant fit-out allowances - document control aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | IFRS/IFRS for SMEs principles; lender due diligence checklist; signed financial model | Yes / No / N/A + Score 0–5 + Rating
22.047 | 22 | WP22 | Cost Planning and Financial Modelling | Have cost, programme and compliance implications of contingency - document control been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | CIDB/procurement best practice; cost plan; QS measurement and BOQ controls | Yes / No / N/A + Score 0–5 + Rating
22.048 | 22 | WP22 | Cost Planning and Financial Modelling | Has the team obtained written confirmation or documented proof for rental income - document control? | Current certificate/letter/report, version control and document-control entry. | Treasury-style value-for-money principles; funding term sheet; drawdown controls | Yes / No / N/A + Score 0–5 + Rating
22.049 | 22 | WP22 | Cost Planning and Financial Modelling | Does the evidence for CAPEX estimate - professional certification support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | IFRS/IFRS for SMEs principles; lender due diligence checklist; signed financial model | Yes / No / N/A + Score 0–5 + Rating
22.050 | 22 | WP22 | Cost Planning and Financial Modelling | Have dependencies linked to professional fees - professional certification been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | CIDB/procurement best practice; cost plan; QS measurement and BOQ controls | Yes / No / N/A + Score 0–5 + Rating
22.051 | 22 | WP22 | Cost Planning and Financial Modelling | Has the project team confirmed approval costs - professional certification in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | Treasury-style value-for-money principles; funding term sheet; drawdown controls | Yes / No / N/A + Score 0–5 + Rating
22.052 | 22 | WP22 | Cost Planning and Financial Modelling | Is there a responsible owner, due date and approval route for tenant fit-out allowances - professional certification? | Register entry, supporting drawing/report, approval note and updated risk item. | IFRS/IFRS for SMEs principles; lender due diligence checklist; signed financial model | Yes / No / N/A + Score 0–5 + Rating
22.053 | 22 | WP22 | Cost Planning and Financial Modelling | Has the gate file tested whether contingency - professional certification creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | CIDB/procurement best practice; cost plan; QS measurement and BOQ controls | Yes / No / N/A + Score 0–5 + Rating
22.054 | 22 | WP22 | Cost Planning and Financial Modelling | Are assumptions for rental income - professional certification documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | Treasury-style value-for-money principles; funding term sheet; drawdown controls | Yes / No / N/A + Score 0–5 + Rating
22.055 | 22 | WP22 | Cost Planning and Financial Modelling | Has the relevant authority, specialist or professional adviser reviewed CAPEX estimate - implementation readiness where required? | Authority response, compliance checklist, file note and management approval. | IFRS/IFRS for SMEs principles; lender due diligence checklist; signed financial model | Yes / No / N/A + Score 0–5 + Rating
22.056 | 22 | WP22 | Cost Planning and Financial Modelling | Is the decision record for professional fees - implementation readiness aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | CIDB/procurement best practice; cost plan; QS measurement and BOQ controls | Yes / No / N/A + Score 0–5 + Rating
22.057 | 22 | WP22 | Cost Planning and Financial Modelling | Have cost, programme and compliance implications of approval costs - implementation readiness been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | Treasury-style value-for-money principles; funding term sheet; drawdown controls | Yes / No / N/A + Score 0–5 + Rating
22.058 | 22 | WP22 | Cost Planning and Financial Modelling | Has the team obtained written confirmation or documented proof for tenant fit-out allowances - implementation readiness? | Current certificate/letter/report, version control and document-control entry. | IFRS/IFRS for SMEs principles; lender due diligence checklist; signed financial model | Yes / No / N/A + Score 0–5 + Rating
22.059 | 22 | WP22 | Cost Planning and Financial Modelling | Does the evidence for contingency - implementation readiness support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | CIDB/procurement best practice; cost plan; QS measurement and BOQ controls | Yes / No / N/A + Score 0–5 + Rating
22.060 | 22 | WP22 | Cost Planning and Financial Modelling | Have dependencies linked to rental income - implementation readiness been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | Treasury-style value-for-money principles; funding term sheet; drawdown controls | Yes / No / N/A + Score 0–5 + Rating
22.061 | 22 | WP22 | Cost Planning and Financial Modelling | Has the project team confirmed CAPEX estimate - governance approval in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | IFRS/IFRS for SMEs principles; lender due diligence checklist; signed financial model | Yes / No / N/A + Score 0–5 + Rating
22.062 | 22 | WP22 | Cost Planning and Financial Modelling | Is there a responsible owner, due date and approval route for professional fees - governance approval? | Register entry, supporting drawing/report, approval note and updated risk item. | CIDB/procurement best practice; cost plan; QS measurement and BOQ controls | Yes / No / N/A + Score 0–5 + Rating
22.063 | 22 | WP22 | Cost Planning and Financial Modelling | Has the gate file tested whether approval costs - governance approval creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | Treasury-style value-for-money principles; funding term sheet; drawdown controls | Yes / No / N/A + Score 0–5 + Rating
22.064 | 22 | WP22 | Cost Planning and Financial Modelling | Are assumptions for tenant fit-out allowances - governance approval documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | IFRS/IFRS for SMEs principles; lender due diligence checklist; signed financial model | Yes / No / N/A + Score 0–5 + Rating
22.065 | 22 | WP22 | Cost Planning and Financial Modelling | Has the relevant authority, specialist or professional adviser reviewed contingency - governance approval where required? | Authority response, compliance checklist, file note and management approval. | CIDB/procurement best practice; cost plan; QS measurement and BOQ controls | Yes / No / N/A + Score 0–5 + Rating
22.066 | 22 | WP22 | Cost Planning and Financial Modelling | Is the decision record for rental income - governance approval aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | Treasury-style value-for-money principles; funding term sheet; drawdown controls | Yes / No / N/A + Score 0–5 + Rating
22.067 | 22 | WP22 | Cost Planning and Financial Modelling | Have cost, programme and compliance implications of CAPEX estimate - legal authority been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | IFRS/IFRS for SMEs principles; lender due diligence checklist; signed financial model | Yes / No / N/A + Score 0–5 + Rating
22.068 | 22 | WP22 | Cost Planning and Financial Modelling | Has the team obtained written confirmation or documented proof for professional fees - legal authority? | Current certificate/letter/report, version control and document-control entry. | CIDB/procurement best practice; cost plan; QS measurement and BOQ controls | Yes / No / N/A + Score 0–5 + Rating
22.069 | 22 | WP22 | Cost Planning and Financial Modelling | Does the evidence for approval costs - legal authority support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | Treasury-style value-for-money principles; funding term sheet; drawdown controls | Yes / No / N/A + Score 0–5 + Rating
22.070 | 22 | WP22 | Cost Planning and Financial Modelling | Have dependencies linked to tenant fit-out allowances - legal authority been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | IFRS/IFRS for SMEs principles; lender due diligence checklist; signed financial model | Yes / No / N/A + Score 0–5 + Rating
22.071 | 22 | WP22 | Cost Planning and Financial Modelling | Has the project team confirmed contingency - legal authority in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | CIDB/procurement best practice; cost plan; QS measurement and BOQ controls | Yes / No / N/A + Score 0–5 + Rating
22.072 | 22 | WP22 | Cost Planning and Financial Modelling | Is there a responsible owner, due date and approval route for rental income - legal authority? | Register entry, supporting drawing/report, approval note and updated risk item. | Treasury-style value-for-money principles; funding term sheet; drawdown controls | Yes / No / N/A + Score 0–5 + Rating
22.073 | 22 | WP22 | Cost Planning and Financial Modelling | Has the gate file tested whether CAPEX estimate - technical feasibility creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | IFRS/IFRS for SMEs principles; lender due diligence checklist; signed financial model | Yes / No / N/A + Score 0–5 + Rating
22.074 | 22 | WP22 | Cost Planning and Financial Modelling | Are assumptions for professional fees - technical feasibility documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | CIDB/procurement best practice; cost plan; QS measurement and BOQ controls | Yes / No / N/A + Score 0–5 + Rating
22.075 | 22 | WP22 | Cost Planning and Financial Modelling | Has the relevant authority, specialist or professional adviser reviewed approval costs - technical feasibility where required? | Authority response, compliance checklist, file note and management approval. | Treasury-style value-for-money principles; funding term sheet; drawdown controls | Yes / No / N/A + Score 0–5 + Rating
22.076 | 22 | WP22 | Cost Planning and Financial Modelling | Is the decision record for tenant fit-out allowances - technical feasibility aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | IFRS/IFRS for SMEs principles; lender due diligence checklist; signed financial model | Yes / No / N/A + Score 0–5 + Rating
22.077 | 22 | WP22 | Cost Planning and Financial Modelling | Have cost, programme and compliance implications of contingency - technical feasibility been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | CIDB/procurement best practice; cost plan; QS measurement and BOQ controls | Yes / No / N/A + Score 0–5 + Rating
22.078 | 22 | WP22 | Cost Planning and Financial Modelling | Has the team obtained written confirmation or documented proof for rental income - technical feasibility? | Current certificate/letter/report, version control and document-control entry. | Treasury-style value-for-money principles; funding term sheet; drawdown controls | Yes / No / N/A + Score 0–5 + Rating
22.079 | 22 | WP22 | Cost Planning and Financial Modelling | Does the evidence for CAPEX estimate - financial viability support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | IFRS/IFRS for SMEs principles; lender due diligence checklist; signed financial model | Yes / No / N/A + Score 0–5 + Rating
22.080 | 22 | WP22 | Cost Planning and Financial Modelling | Have dependencies linked to professional fees - financial viability been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | CIDB/procurement best practice; cost plan; QS measurement and BOQ controls | Yes / No / N/A + Score 0–5 + Rating
22.081 | 22 | WP22 | Cost Planning and Financial Modelling | Has the project team confirmed approval costs - financial viability in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | Treasury-style value-for-money principles; funding term sheet; drawdown controls | Yes / No / N/A + Score 0–5 + Rating
22.082 | 22 | WP22 | Cost Planning and Financial Modelling | Is there a responsible owner, due date and approval route for tenant fit-out allowances - financial viability? | Register entry, supporting drawing/report, approval note and updated risk item. | IFRS/IFRS for SMEs principles; lender due diligence checklist; signed financial model | Yes / No / N/A + Score 0–5 + Rating
22.083 | 22 | WP22 | Cost Planning and Financial Modelling | Has the gate file tested whether contingency - financial viability creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | CIDB/procurement best practice; cost plan; QS measurement and BOQ controls | Yes / No / N/A + Score 0–5 + Rating
22.084 | 22 | WP22 | Cost Planning and Financial Modelling | Are assumptions for rental income - financial viability documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | Treasury-style value-for-money principles; funding term sheet; drawdown controls | Yes / No / N/A + Score 0–5 + Rating
22.085 | 22 | WP22 | Cost Planning and Financial Modelling | Has the relevant authority, specialist or professional adviser reviewed CAPEX estimate - programme impact where required? | Authority response, compliance checklist, file note and management approval. | IFRS/IFRS for SMEs principles; lender due diligence checklist; signed financial model | Yes / No / N/A + Score 0–5 + Rating
22.086 | 22 | WP22 | Cost Planning and Financial Modelling | Is the decision record for professional fees - programme impact aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | CIDB/procurement best practice; cost plan; QS measurement and BOQ controls | Yes / No / N/A + Score 0–5 + Rating
22.087 | 22 | WP22 | Cost Planning and Financial Modelling | Have cost, programme and compliance implications of approval costs - programme impact been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | Treasury-style value-for-money principles; funding term sheet; drawdown controls | Yes / No / N/A + Score 0–5 + Rating
22.088 | 22 | WP22 | Cost Planning and Financial Modelling | Has the team obtained written confirmation or documented proof for tenant fit-out allowances - programme impact? | Current certificate/letter/report, version control and document-control entry. | IFRS/IFRS for SMEs principles; lender due diligence checklist; signed financial model | Yes / No / N/A + Score 0–5 + Rating
22.089 | 22 | WP22 | Cost Planning and Financial Modelling | Does the evidence for contingency - programme impact support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | CIDB/procurement best practice; cost plan; QS measurement and BOQ controls | Yes / No / N/A + Score 0–5 + Rating
22.090 | 22 | WP22 | Cost Planning and Financial Modelling | Have dependencies linked to rental income - programme impact been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | Treasury-style value-for-money principles; funding term sheet; drawdown controls | Yes / No / N/A + Score 0–5 + Rating
22.091 | 22 | WP22 | Cost Planning and Financial Modelling | Has the project team confirmed CAPEX estimate - risk mitigation in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | IFRS/IFRS for SMEs principles; lender due diligence checklist; signed financial model | Yes / No / N/A + Score 0–5 + Rating
22.092 | 22 | WP22 | Cost Planning and Financial Modelling | Is there a responsible owner, due date and approval route for professional fees - risk mitigation? | Register entry, supporting drawing/report, approval note and updated risk item. | CIDB/procurement best practice; cost plan; QS measurement and BOQ controls | Yes / No / N/A + Score 0–5 + Rating
22.093 | 22 | WP22 | Cost Planning and Financial Modelling | Has the gate file tested whether approval costs - risk mitigation creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | Treasury-style value-for-money principles; funding term sheet; drawdown controls | Yes / No / N/A + Score 0–5 + Rating
22.094 | 22 | WP22 | Cost Planning and Financial Modelling | Are assumptions for tenant fit-out allowances - risk mitigation documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | IFRS/IFRS for SMEs principles; lender due diligence checklist; signed financial model | Yes / No / N/A + Score 0–5 + Rating
22.095 | 22 | WP22 | Cost Planning and Financial Modelling | Has the relevant authority, specialist or professional adviser reviewed contingency - risk mitigation where required? | Authority response, compliance checklist, file note and management approval. | CIDB/procurement best practice; cost plan; QS measurement and BOQ controls | Yes / No / N/A + Score 0–5 + Rating
22.096 | 22 | WP22 | Cost Planning and Financial Modelling | Is the decision record for rental income - risk mitigation aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | Treasury-style value-for-money principles; funding term sheet; drawdown controls | Yes / No / N/A + Score 0–5 + Rating
22.097 | 22 | WP22 | Cost Planning and Financial Modelling | Have cost, programme and compliance implications of CAPEX estimate - stakeholder acceptance been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | IFRS/IFRS for SMEs principles; lender due diligence checklist; signed financial model | Yes / No / N/A + Score 0–5 + Rating
22.098 | 22 | WP22 | Cost Planning and Financial Modelling | Has the team obtained written confirmation or documented proof for professional fees - stakeholder acceptance? | Current certificate/letter/report, version control and document-control entry. | CIDB/procurement best practice; cost plan; QS measurement and BOQ controls | Yes / No / N/A + Score 0–5 + Rating
22.099 | 22 | WP22 | Cost Planning and Financial Modelling | Does the evidence for approval costs - stakeholder acceptance support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | Treasury-style value-for-money principles; funding term sheet; drawdown controls | Yes / No / N/A + Score 0–5 + Rating
22.100 | 22 | WP22 | Cost Planning and Financial Modelling | Have dependencies linked to tenant fit-out allowances - stakeholder acceptance been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | IFRS/IFRS for SMEs principles; lender due diligence checklist; signed financial model | Yes / No / N/A + Score 0–5 + Rating
23.001 | 23 | WP23 | Capital Structuring and Funding Readiness | Has the project team confirmed equity contribution - governance approval in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | King IV governance practice; Companies Act 71 of 2008; project mandate file | Yes / No / N/A + Score 0–5 + Rating
23.002 | 23 | WP23 | Capital Structuring and Funding Readiness | Is there a responsible owner, due date and approval route for debt funding - governance approval? | Register entry, supporting drawing/report, approval note and updated risk item. | PMBOK stage-gate governance; board resolution; delegated authority matrix | Yes / No / N/A + Score 0–5 + Rating
23.003 | 23 | WP23 | Capital Structuring and Funding Readiness | Has the gate file tested whether drawdown plan - governance approval creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | ISO 31000 risk management; stakeholder decision register; project charter | Yes / No / N/A + Score 0–5 + Rating
23.004 | 23 | WP23 | Capital Structuring and Funding Readiness | Are assumptions for security package - governance approval documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | King IV governance practice; Companies Act 71 of 2008; project mandate file | Yes / No / N/A + Score 0–5 + Rating
23.005 | 23 | WP23 | Capital Structuring and Funding Readiness | Has the relevant authority, specialist or professional adviser reviewed funder due diligence - governance approval where required? | Authority response, compliance checklist, file note and management approval. | PMBOK stage-gate governance; board resolution; delegated authority matrix | Yes / No / N/A + Score 0–5 + Rating
23.006 | 23 | WP23 | Capital Structuring and Funding Readiness | Is the decision record for term sheet - governance approval aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | ISO 31000 risk management; stakeholder decision register; project charter | Yes / No / N/A + Score 0–5 + Rating
23.007 | 23 | WP23 | Capital Structuring and Funding Readiness | Have cost, programme and compliance implications of equity contribution - legal authority been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | King IV governance practice; Companies Act 71 of 2008; project mandate file | Yes / No / N/A + Score 0–5 + Rating
23.008 | 23 | WP23 | Capital Structuring and Funding Readiness | Has the team obtained written confirmation or documented proof for debt funding - legal authority? | Current certificate/letter/report, version control and document-control entry. | PMBOK stage-gate governance; board resolution; delegated authority matrix | Yes / No / N/A + Score 0–5 + Rating
23.009 | 23 | WP23 | Capital Structuring and Funding Readiness | Does the evidence for drawdown plan - legal authority support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | ISO 31000 risk management; stakeholder decision register; project charter | Yes / No / N/A + Score 0–5 + Rating
23.010 | 23 | WP23 | Capital Structuring and Funding Readiness | Have dependencies linked to security package - legal authority been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | King IV governance practice; Companies Act 71 of 2008; project mandate file | Yes / No / N/A + Score 0–5 + Rating
23.011 | 23 | WP23 | Capital Structuring and Funding Readiness | Has the project team confirmed funder due diligence - legal authority in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | PMBOK stage-gate governance; board resolution; delegated authority matrix | Yes / No / N/A + Score 0–5 + Rating
23.012 | 23 | WP23 | Capital Structuring and Funding Readiness | Is there a responsible owner, due date and approval route for term sheet - legal authority? | Register entry, supporting drawing/report, approval note and updated risk item. | ISO 31000 risk management; stakeholder decision register; project charter | Yes / No / N/A + Score 0–5 + Rating
23.013 | 23 | WP23 | Capital Structuring and Funding Readiness | Has the gate file tested whether equity contribution - technical feasibility creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | King IV governance practice; Companies Act 71 of 2008; project mandate file | Yes / No / N/A + Score 0–5 + Rating
23.014 | 23 | WP23 | Capital Structuring and Funding Readiness | Are assumptions for debt funding - technical feasibility documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | PMBOK stage-gate governance; board resolution; delegated authority matrix | Yes / No / N/A + Score 0–5 + Rating
23.015 | 23 | WP23 | Capital Structuring and Funding Readiness | Has the relevant authority, specialist or professional adviser reviewed drawdown plan - technical feasibility where required? | Authority response, compliance checklist, file note and management approval. | ISO 31000 risk management; stakeholder decision register; project charter | Yes / No / N/A + Score 0–5 + Rating
23.016 | 23 | WP23 | Capital Structuring and Funding Readiness | Is the decision record for security package - technical feasibility aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | King IV governance practice; Companies Act 71 of 2008; project mandate file | Yes / No / N/A + Score 0–5 + Rating
23.017 | 23 | WP23 | Capital Structuring and Funding Readiness | Have cost, programme and compliance implications of funder due diligence - technical feasibility been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | PMBOK stage-gate governance; board resolution; delegated authority matrix | Yes / No / N/A + Score 0–5 + Rating
23.018 | 23 | WP23 | Capital Structuring and Funding Readiness | Has the team obtained written confirmation or documented proof for term sheet - technical feasibility? | Current certificate/letter/report, version control and document-control entry. | ISO 31000 risk management; stakeholder decision register; project charter | Yes / No / N/A + Score 0–5 + Rating
23.019 | 23 | WP23 | Capital Structuring and Funding Readiness | Does the evidence for equity contribution - financial viability support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | King IV governance practice; Companies Act 71 of 2008; project mandate file | Yes / No / N/A + Score 0–5 + Rating
23.020 | 23 | WP23 | Capital Structuring and Funding Readiness | Have dependencies linked to debt funding - financial viability been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | PMBOK stage-gate governance; board resolution; delegated authority matrix | Yes / No / N/A + Score 0–5 + Rating
23.021 | 23 | WP23 | Capital Structuring and Funding Readiness | Has the project team confirmed drawdown plan - financial viability in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | ISO 31000 risk management; stakeholder decision register; project charter | Yes / No / N/A + Score 0–5 + Rating
23.022 | 23 | WP23 | Capital Structuring and Funding Readiness | Is there a responsible owner, due date and approval route for security package - financial viability? | Register entry, supporting drawing/report, approval note and updated risk item. | King IV governance practice; Companies Act 71 of 2008; project mandate file | Yes / No / N/A + Score 0–5 + Rating
23.023 | 23 | WP23 | Capital Structuring and Funding Readiness | Has the gate file tested whether funder due diligence - financial viability creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | PMBOK stage-gate governance; board resolution; delegated authority matrix | Yes / No / N/A + Score 0–5 + Rating
23.024 | 23 | WP23 | Capital Structuring and Funding Readiness | Are assumptions for term sheet - financial viability documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | ISO 31000 risk management; stakeholder decision register; project charter | Yes / No / N/A + Score 0–5 + Rating
23.025 | 23 | WP23 | Capital Structuring and Funding Readiness | Has the relevant authority, specialist or professional adviser reviewed equity contribution - programme impact where required? | Authority response, compliance checklist, file note and management approval. | King IV governance practice; Companies Act 71 of 2008; project mandate file | Yes / No / N/A + Score 0–5 + Rating
23.026 | 23 | WP23 | Capital Structuring and Funding Readiness | Is the decision record for debt funding - programme impact aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | PMBOK stage-gate governance; board resolution; delegated authority matrix | Yes / No / N/A + Score 0–5 + Rating
23.027 | 23 | WP23 | Capital Structuring and Funding Readiness | Have cost, programme and compliance implications of drawdown plan - programme impact been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | ISO 31000 risk management; stakeholder decision register; project charter | Yes / No / N/A + Score 0–5 + Rating
23.028 | 23 | WP23 | Capital Structuring and Funding Readiness | Has the team obtained written confirmation or documented proof for security package - programme impact? | Current certificate/letter/report, version control and document-control entry. | King IV governance practice; Companies Act 71 of 2008; project mandate file | Yes / No / N/A + Score 0–5 + Rating
23.029 | 23 | WP23 | Capital Structuring and Funding Readiness | Does the evidence for funder due diligence - programme impact support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | PMBOK stage-gate governance; board resolution; delegated authority matrix | Yes / No / N/A + Score 0–5 + Rating
23.030 | 23 | WP23 | Capital Structuring and Funding Readiness | Have dependencies linked to term sheet - programme impact been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | ISO 31000 risk management; stakeholder decision register; project charter | Yes / No / N/A + Score 0–5 + Rating
23.031 | 23 | WP23 | Capital Structuring and Funding Readiness | Has the project team confirmed equity contribution - risk mitigation in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | King IV governance practice; Companies Act 71 of 2008; project mandate file | Yes / No / N/A + Score 0–5 + Rating
23.032 | 23 | WP23 | Capital Structuring and Funding Readiness | Is there a responsible owner, due date and approval route for debt funding - risk mitigation? | Register entry, supporting drawing/report, approval note and updated risk item. | PMBOK stage-gate governance; board resolution; delegated authority matrix | Yes / No / N/A + Score 0–5 + Rating
23.033 | 23 | WP23 | Capital Structuring and Funding Readiness | Has the gate file tested whether drawdown plan - risk mitigation creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | ISO 31000 risk management; stakeholder decision register; project charter | Yes / No / N/A + Score 0–5 + Rating
23.034 | 23 | WP23 | Capital Structuring and Funding Readiness | Are assumptions for security package - risk mitigation documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | King IV governance practice; Companies Act 71 of 2008; project mandate file | Yes / No / N/A + Score 0–5 + Rating
23.035 | 23 | WP23 | Capital Structuring and Funding Readiness | Has the relevant authority, specialist or professional adviser reviewed funder due diligence - risk mitigation where required? | Authority response, compliance checklist, file note and management approval. | PMBOK stage-gate governance; board resolution; delegated authority matrix | Yes / No / N/A + Score 0–5 + Rating
23.036 | 23 | WP23 | Capital Structuring and Funding Readiness | Is the decision record for term sheet - risk mitigation aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | ISO 31000 risk management; stakeholder decision register; project charter | Yes / No / N/A + Score 0–5 + Rating
23.037 | 23 | WP23 | Capital Structuring and Funding Readiness | Have cost, programme and compliance implications of equity contribution - stakeholder acceptance been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | King IV governance practice; Companies Act 71 of 2008; project mandate file | Yes / No / N/A + Score 0–5 + Rating
23.038 | 23 | WP23 | Capital Structuring and Funding Readiness | Has the team obtained written confirmation or documented proof for debt funding - stakeholder acceptance? | Current certificate/letter/report, version control and document-control entry. | PMBOK stage-gate governance; board resolution; delegated authority matrix | Yes / No / N/A + Score 0–5 + Rating
23.039 | 23 | WP23 | Capital Structuring and Funding Readiness | Does the evidence for drawdown plan - stakeholder acceptance support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | ISO 31000 risk management; stakeholder decision register; project charter | Yes / No / N/A + Score 0–5 + Rating
23.040 | 23 | WP23 | Capital Structuring and Funding Readiness | Have dependencies linked to security package - stakeholder acceptance been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | King IV governance practice; Companies Act 71 of 2008; project mandate file | Yes / No / N/A + Score 0–5 + Rating
23.041 | 23 | WP23 | Capital Structuring and Funding Readiness | Has the project team confirmed funder due diligence - stakeholder acceptance in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | PMBOK stage-gate governance; board resolution; delegated authority matrix | Yes / No / N/A + Score 0–5 + Rating
23.042 | 23 | WP23 | Capital Structuring and Funding Readiness | Is there a responsible owner, due date and approval route for term sheet - stakeholder acceptance? | Register entry, supporting drawing/report, approval note and updated risk item. | ISO 31000 risk management; stakeholder decision register; project charter | Yes / No / N/A + Score 0–5 + Rating
23.043 | 23 | WP23 | Capital Structuring and Funding Readiness | Has the gate file tested whether equity contribution - document control creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | King IV governance practice; Companies Act 71 of 2008; project mandate file | Yes / No / N/A + Score 0–5 + Rating
23.044 | 23 | WP23 | Capital Structuring and Funding Readiness | Are assumptions for debt funding - document control documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | PMBOK stage-gate governance; board resolution; delegated authority matrix | Yes / No / N/A + Score 0–5 + Rating
23.045 | 23 | WP23 | Capital Structuring and Funding Readiness | Has the relevant authority, specialist or professional adviser reviewed drawdown plan - document control where required? | Authority response, compliance checklist, file note and management approval. | ISO 31000 risk management; stakeholder decision register; project charter | Yes / No / N/A + Score 0–5 + Rating
23.046 | 23 | WP23 | Capital Structuring and Funding Readiness | Is the decision record for security package - document control aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | King IV governance practice; Companies Act 71 of 2008; project mandate file | Yes / No / N/A + Score 0–5 + Rating
23.047 | 23 | WP23 | Capital Structuring and Funding Readiness | Have cost, programme and compliance implications of funder due diligence - document control been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | PMBOK stage-gate governance; board resolution; delegated authority matrix | Yes / No / N/A + Score 0–5 + Rating
23.048 | 23 | WP23 | Capital Structuring and Funding Readiness | Has the team obtained written confirmation or documented proof for term sheet - document control? | Current certificate/letter/report, version control and document-control entry. | ISO 31000 risk management; stakeholder decision register; project charter | Yes / No / N/A + Score 0–5 + Rating
23.049 | 23 | WP23 | Capital Structuring and Funding Readiness | Does the evidence for equity contribution - professional certification support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | King IV governance practice; Companies Act 71 of 2008; project mandate file | Yes / No / N/A + Score 0–5 + Rating
23.050 | 23 | WP23 | Capital Structuring and Funding Readiness | Have dependencies linked to debt funding - professional certification been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | PMBOK stage-gate governance; board resolution; delegated authority matrix | Yes / No / N/A + Score 0–5 + Rating
23.051 | 23 | WP23 | Capital Structuring and Funding Readiness | Has the project team confirmed drawdown plan - professional certification in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | ISO 31000 risk management; stakeholder decision register; project charter | Yes / No / N/A + Score 0–5 + Rating
23.052 | 23 | WP23 | Capital Structuring and Funding Readiness | Is there a responsible owner, due date and approval route for security package - professional certification? | Register entry, supporting drawing/report, approval note and updated risk item. | King IV governance practice; Companies Act 71 of 2008; project mandate file | Yes / No / N/A + Score 0–5 + Rating
23.053 | 23 | WP23 | Capital Structuring and Funding Readiness | Has the gate file tested whether funder due diligence - professional certification creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | PMBOK stage-gate governance; board resolution; delegated authority matrix | Yes / No / N/A + Score 0–5 + Rating
23.054 | 23 | WP23 | Capital Structuring and Funding Readiness | Are assumptions for term sheet - professional certification documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | ISO 31000 risk management; stakeholder decision register; project charter | Yes / No / N/A + Score 0–5 + Rating
23.055 | 23 | WP23 | Capital Structuring and Funding Readiness | Has the relevant authority, specialist or professional adviser reviewed equity contribution - implementation readiness where required? | Authority response, compliance checklist, file note and management approval. | King IV governance practice; Companies Act 71 of 2008; project mandate file | Yes / No / N/A + Score 0–5 + Rating
23.056 | 23 | WP23 | Capital Structuring and Funding Readiness | Is the decision record for debt funding - implementation readiness aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | PMBOK stage-gate governance; board resolution; delegated authority matrix | Yes / No / N/A + Score 0–5 + Rating
23.057 | 23 | WP23 | Capital Structuring and Funding Readiness | Have cost, programme and compliance implications of drawdown plan - implementation readiness been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | ISO 31000 risk management; stakeholder decision register; project charter | Yes / No / N/A + Score 0–5 + Rating
23.058 | 23 | WP23 | Capital Structuring and Funding Readiness | Has the team obtained written confirmation or documented proof for security package - implementation readiness? | Current certificate/letter/report, version control and document-control entry. | King IV governance practice; Companies Act 71 of 2008; project mandate file | Yes / No / N/A + Score 0–5 + Rating
23.059 | 23 | WP23 | Capital Structuring and Funding Readiness | Does the evidence for funder due diligence - implementation readiness support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | PMBOK stage-gate governance; board resolution; delegated authority matrix | Yes / No / N/A + Score 0–5 + Rating
23.060 | 23 | WP23 | Capital Structuring and Funding Readiness | Have dependencies linked to term sheet - implementation readiness been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | ISO 31000 risk management; stakeholder decision register; project charter | Yes / No / N/A + Score 0–5 + Rating
23.061 | 23 | WP23 | Capital Structuring and Funding Readiness | Has the project team confirmed equity contribution - governance approval in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | King IV governance practice; Companies Act 71 of 2008; project mandate file | Yes / No / N/A + Score 0–5 + Rating
23.062 | 23 | WP23 | Capital Structuring and Funding Readiness | Is there a responsible owner, due date and approval route for debt funding - governance approval? | Register entry, supporting drawing/report, approval note and updated risk item. | PMBOK stage-gate governance; board resolution; delegated authority matrix | Yes / No / N/A + Score 0–5 + Rating
23.063 | 23 | WP23 | Capital Structuring and Funding Readiness | Has the gate file tested whether drawdown plan - governance approval creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | ISO 31000 risk management; stakeholder decision register; project charter | Yes / No / N/A + Score 0–5 + Rating
23.064 | 23 | WP23 | Capital Structuring and Funding Readiness | Are assumptions for security package - governance approval documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | King IV governance practice; Companies Act 71 of 2008; project mandate file | Yes / No / N/A + Score 0–5 + Rating
23.065 | 23 | WP23 | Capital Structuring and Funding Readiness | Has the relevant authority, specialist or professional adviser reviewed funder due diligence - governance approval where required? | Authority response, compliance checklist, file note and management approval. | PMBOK stage-gate governance; board resolution; delegated authority matrix | Yes / No / N/A + Score 0–5 + Rating
23.066 | 23 | WP23 | Capital Structuring and Funding Readiness | Is the decision record for term sheet - governance approval aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | ISO 31000 risk management; stakeholder decision register; project charter | Yes / No / N/A + Score 0–5 + Rating
23.067 | 23 | WP23 | Capital Structuring and Funding Readiness | Have cost, programme and compliance implications of equity contribution - legal authority been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | King IV governance practice; Companies Act 71 of 2008; project mandate file | Yes / No / N/A + Score 0–5 + Rating
23.068 | 23 | WP23 | Capital Structuring and Funding Readiness | Has the team obtained written confirmation or documented proof for debt funding - legal authority? | Current certificate/letter/report, version control and document-control entry. | PMBOK stage-gate governance; board resolution; delegated authority matrix | Yes / No / N/A + Score 0–5 + Rating
23.069 | 23 | WP23 | Capital Structuring and Funding Readiness | Does the evidence for drawdown plan - legal authority support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | ISO 31000 risk management; stakeholder decision register; project charter | Yes / No / N/A + Score 0–5 + Rating
23.070 | 23 | WP23 | Capital Structuring and Funding Readiness | Have dependencies linked to security package - legal authority been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | King IV governance practice; Companies Act 71 of 2008; project mandate file | Yes / No / N/A + Score 0–5 + Rating
23.071 | 23 | WP23 | Capital Structuring and Funding Readiness | Has the project team confirmed funder due diligence - legal authority in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | PMBOK stage-gate governance; board resolution; delegated authority matrix | Yes / No / N/A + Score 0–5 + Rating
23.072 | 23 | WP23 | Capital Structuring and Funding Readiness | Is there a responsible owner, due date and approval route for term sheet - legal authority? | Register entry, supporting drawing/report, approval note and updated risk item. | ISO 31000 risk management; stakeholder decision register; project charter | Yes / No / N/A + Score 0–5 + Rating
23.073 | 23 | WP23 | Capital Structuring and Funding Readiness | Has the gate file tested whether equity contribution - technical feasibility creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | King IV governance practice; Companies Act 71 of 2008; project mandate file | Yes / No / N/A + Score 0–5 + Rating
23.074 | 23 | WP23 | Capital Structuring and Funding Readiness | Are assumptions for debt funding - technical feasibility documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | PMBOK stage-gate governance; board resolution; delegated authority matrix | Yes / No / N/A + Score 0–5 + Rating
23.075 | 23 | WP23 | Capital Structuring and Funding Readiness | Has the relevant authority, specialist or professional adviser reviewed drawdown plan - technical feasibility where required? | Authority response, compliance checklist, file note and management approval. | ISO 31000 risk management; stakeholder decision register; project charter | Yes / No / N/A + Score 0–5 + Rating
23.076 | 23 | WP23 | Capital Structuring and Funding Readiness | Is the decision record for security package - technical feasibility aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | King IV governance practice; Companies Act 71 of 2008; project mandate file | Yes / No / N/A + Score 0–5 + Rating
23.077 | 23 | WP23 | Capital Structuring and Funding Readiness | Have cost, programme and compliance implications of funder due diligence - technical feasibility been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | PMBOK stage-gate governance; board resolution; delegated authority matrix | Yes / No / N/A + Score 0–5 + Rating
23.078 | 23 | WP23 | Capital Structuring and Funding Readiness | Has the team obtained written confirmation or documented proof for term sheet - technical feasibility? | Current certificate/letter/report, version control and document-control entry. | ISO 31000 risk management; stakeholder decision register; project charter | Yes / No / N/A + Score 0–5 + Rating
23.079 | 23 | WP23 | Capital Structuring and Funding Readiness | Does the evidence for equity contribution - financial viability support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | King IV governance practice; Companies Act 71 of 2008; project mandate file | Yes / No / N/A + Score 0–5 + Rating
23.080 | 23 | WP23 | Capital Structuring and Funding Readiness | Have dependencies linked to debt funding - financial viability been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | PMBOK stage-gate governance; board resolution; delegated authority matrix | Yes / No / N/A + Score 0–5 + Rating
23.081 | 23 | WP23 | Capital Structuring and Funding Readiness | Has the project team confirmed drawdown plan - financial viability in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | ISO 31000 risk management; stakeholder decision register; project charter | Yes / No / N/A + Score 0–5 + Rating
23.082 | 23 | WP23 | Capital Structuring and Funding Readiness | Is there a responsible owner, due date and approval route for security package - financial viability? | Register entry, supporting drawing/report, approval note and updated risk item. | King IV governance practice; Companies Act 71 of 2008; project mandate file | Yes / No / N/A + Score 0–5 + Rating
23.083 | 23 | WP23 | Capital Structuring and Funding Readiness | Has the gate file tested whether funder due diligence - financial viability creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | PMBOK stage-gate governance; board resolution; delegated authority matrix | Yes / No / N/A + Score 0–5 + Rating
23.084 | 23 | WP23 | Capital Structuring and Funding Readiness | Are assumptions for term sheet - financial viability documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | ISO 31000 risk management; stakeholder decision register; project charter | Yes / No / N/A + Score 0–5 + Rating
23.085 | 23 | WP23 | Capital Structuring and Funding Readiness | Has the relevant authority, specialist or professional adviser reviewed equity contribution - programme impact where required? | Authority response, compliance checklist, file note and management approval. | King IV governance practice; Companies Act 71 of 2008; project mandate file | Yes / No / N/A + Score 0–5 + Rating
23.086 | 23 | WP23 | Capital Structuring and Funding Readiness | Is the decision record for debt funding - programme impact aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | PMBOK stage-gate governance; board resolution; delegated authority matrix | Yes / No / N/A + Score 0–5 + Rating
23.087 | 23 | WP23 | Capital Structuring and Funding Readiness | Have cost, programme and compliance implications of drawdown plan - programme impact been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | ISO 31000 risk management; stakeholder decision register; project charter | Yes / No / N/A + Score 0–5 + Rating
23.088 | 23 | WP23 | Capital Structuring and Funding Readiness | Has the team obtained written confirmation or documented proof for security package - programme impact? | Current certificate/letter/report, version control and document-control entry. | King IV governance practice; Companies Act 71 of 2008; project mandate file | Yes / No / N/A + Score 0–5 + Rating
23.089 | 23 | WP23 | Capital Structuring and Funding Readiness | Does the evidence for funder due diligence - programme impact support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | PMBOK stage-gate governance; board resolution; delegated authority matrix | Yes / No / N/A + Score 0–5 + Rating
23.090 | 23 | WP23 | Capital Structuring and Funding Readiness | Have dependencies linked to term sheet - programme impact been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | ISO 31000 risk management; stakeholder decision register; project charter | Yes / No / N/A + Score 0–5 + Rating
23.091 | 23 | WP23 | Capital Structuring and Funding Readiness | Has the project team confirmed equity contribution - risk mitigation in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | King IV governance practice; Companies Act 71 of 2008; project mandate file | Yes / No / N/A + Score 0–5 + Rating
23.092 | 23 | WP23 | Capital Structuring and Funding Readiness | Is there a responsible owner, due date and approval route for debt funding - risk mitigation? | Register entry, supporting drawing/report, approval note and updated risk item. | PMBOK stage-gate governance; board resolution; delegated authority matrix | Yes / No / N/A + Score 0–5 + Rating
23.093 | 23 | WP23 | Capital Structuring and Funding Readiness | Has the gate file tested whether drawdown plan - risk mitigation creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | ISO 31000 risk management; stakeholder decision register; project charter | Yes / No / N/A + Score 0–5 + Rating
23.094 | 23 | WP23 | Capital Structuring and Funding Readiness | Are assumptions for security package - risk mitigation documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | King IV governance practice; Companies Act 71 of 2008; project mandate file | Yes / No / N/A + Score 0–5 + Rating
23.095 | 23 | WP23 | Capital Structuring and Funding Readiness | Has the relevant authority, specialist or professional adviser reviewed funder due diligence - risk mitigation where required? | Authority response, compliance checklist, file note and management approval. | PMBOK stage-gate governance; board resolution; delegated authority matrix | Yes / No / N/A + Score 0–5 + Rating
23.096 | 23 | WP23 | Capital Structuring and Funding Readiness | Is the decision record for term sheet - risk mitigation aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | ISO 31000 risk management; stakeholder decision register; project charter | Yes / No / N/A + Score 0–5 + Rating
23.097 | 23 | WP23 | Capital Structuring and Funding Readiness | Have cost, programme and compliance implications of equity contribution - stakeholder acceptance been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | King IV governance practice; Companies Act 71 of 2008; project mandate file | Yes / No / N/A + Score 0–5 + Rating
23.098 | 23 | WP23 | Capital Structuring and Funding Readiness | Has the team obtained written confirmation or documented proof for debt funding - stakeholder acceptance? | Current certificate/letter/report, version control and document-control entry. | PMBOK stage-gate governance; board resolution; delegated authority matrix | Yes / No / N/A + Score 0–5 + Rating
23.099 | 23 | WP23 | Capital Structuring and Funding Readiness | Does the evidence for drawdown plan - stakeholder acceptance support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | ISO 31000 risk management; stakeholder decision register; project charter | Yes / No / N/A + Score 0–5 + Rating
23.100 | 23 | WP23 | Capital Structuring and Funding Readiness | Have dependencies linked to security package - stakeholder acceptance been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | King IV governance practice; Companies Act 71 of 2008; project mandate file | Yes / No / N/A + Score 0–5 + Rating
24.001 | 24 | WP24 | Procurement Strategy and Tender Documentation | Has the project team confirmed procurement route - governance approval in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | IFRS/IFRS for SMEs principles; lender due diligence checklist; signed financial model | Yes / No / N/A + Score 0–5 + Rating
24.002 | 24 | WP24 | Procurement Strategy and Tender Documentation | Is there a responsible owner, due date and approval route for tender pack - governance approval? | Register entry, supporting drawing/report, approval note and updated risk item. | CIDB/procurement best practice; cost plan; QS measurement and BOQ controls | Yes / No / N/A + Score 0–5 + Rating
24.003 | 24 | WP24 | Procurement Strategy and Tender Documentation | Has the gate file tested whether BOQ - governance approval creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | Treasury-style value-for-money principles; funding term sheet; drawdown controls | Yes / No / N/A + Score 0–5 + Rating
24.004 | 24 | WP24 | Procurement Strategy and Tender Documentation | Are assumptions for contract conditions - governance approval documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | IFRS/IFRS for SMEs principles; lender due diligence checklist; signed financial model | Yes / No / N/A + Score 0–5 + Rating
24.005 | 24 | WP24 | Procurement Strategy and Tender Documentation | Has the relevant authority, specialist or professional adviser reviewed bid evaluation - governance approval where required? | Authority response, compliance checklist, file note and management approval. | CIDB/procurement best practice; cost plan; QS measurement and BOQ controls | Yes / No / N/A + Score 0–5 + Rating
24.006 | 24 | WP24 | Procurement Strategy and Tender Documentation | Is the decision record for supplier strategy - governance approval aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | Treasury-style value-for-money principles; funding term sheet; drawdown controls | Yes / No / N/A + Score 0–5 + Rating
24.007 | 24 | WP24 | Procurement Strategy and Tender Documentation | Have cost, programme and compliance implications of procurement route - legal authority been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | IFRS/IFRS for SMEs principles; lender due diligence checklist; signed financial model | Yes / No / N/A + Score 0–5 + Rating
24.008 | 24 | WP24 | Procurement Strategy and Tender Documentation | Has the team obtained written confirmation or documented proof for tender pack - legal authority? | Current certificate/letter/report, version control and document-control entry. | CIDB/procurement best practice; cost plan; QS measurement and BOQ controls | Yes / No / N/A + Score 0–5 + Rating
24.009 | 24 | WP24 | Procurement Strategy and Tender Documentation | Does the evidence for BOQ - legal authority support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | Treasury-style value-for-money principles; funding term sheet; drawdown controls | Yes / No / N/A + Score 0–5 + Rating
24.010 | 24 | WP24 | Procurement Strategy and Tender Documentation | Have dependencies linked to contract conditions - legal authority been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | IFRS/IFRS for SMEs principles; lender due diligence checklist; signed financial model | Yes / No / N/A + Score 0–5 + Rating
24.011 | 24 | WP24 | Procurement Strategy and Tender Documentation | Has the project team confirmed bid evaluation - legal authority in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | CIDB/procurement best practice; cost plan; QS measurement and BOQ controls | Yes / No / N/A + Score 0–5 + Rating
24.012 | 24 | WP24 | Procurement Strategy and Tender Documentation | Is there a responsible owner, due date and approval route for supplier strategy - legal authority? | Register entry, supporting drawing/report, approval note and updated risk item. | Treasury-style value-for-money principles; funding term sheet; drawdown controls | Yes / No / N/A + Score 0–5 + Rating
24.013 | 24 | WP24 | Procurement Strategy and Tender Documentation | Has the gate file tested whether procurement route - technical feasibility creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | IFRS/IFRS for SMEs principles; lender due diligence checklist; signed financial model | Yes / No / N/A + Score 0–5 + Rating
24.014 | 24 | WP24 | Procurement Strategy and Tender Documentation | Are assumptions for tender pack - technical feasibility documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | CIDB/procurement best practice; cost plan; QS measurement and BOQ controls | Yes / No / N/A + Score 0–5 + Rating
24.015 | 24 | WP24 | Procurement Strategy and Tender Documentation | Has the relevant authority, specialist or professional adviser reviewed BOQ - technical feasibility where required? | Authority response, compliance checklist, file note and management approval. | Treasury-style value-for-money principles; funding term sheet; drawdown controls | Yes / No / N/A + Score 0–5 + Rating
24.016 | 24 | WP24 | Procurement Strategy and Tender Documentation | Is the decision record for contract conditions - technical feasibility aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | IFRS/IFRS for SMEs principles; lender due diligence checklist; signed financial model | Yes / No / N/A + Score 0–5 + Rating
24.017 | 24 | WP24 | Procurement Strategy and Tender Documentation | Have cost, programme and compliance implications of bid evaluation - technical feasibility been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | CIDB/procurement best practice; cost plan; QS measurement and BOQ controls | Yes / No / N/A + Score 0–5 + Rating
24.018 | 24 | WP24 | Procurement Strategy and Tender Documentation | Has the team obtained written confirmation or documented proof for supplier strategy - technical feasibility? | Current certificate/letter/report, version control and document-control entry. | Treasury-style value-for-money principles; funding term sheet; drawdown controls | Yes / No / N/A + Score 0–5 + Rating
24.019 | 24 | WP24 | Procurement Strategy and Tender Documentation | Does the evidence for procurement route - financial viability support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | IFRS/IFRS for SMEs principles; lender due diligence checklist; signed financial model | Yes / No / N/A + Score 0–5 + Rating
24.020 | 24 | WP24 | Procurement Strategy and Tender Documentation | Have dependencies linked to tender pack - financial viability been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | CIDB/procurement best practice; cost plan; QS measurement and BOQ controls | Yes / No / N/A + Score 0–5 + Rating
24.021 | 24 | WP24 | Procurement Strategy and Tender Documentation | Has the project team confirmed BOQ - financial viability in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | Treasury-style value-for-money principles; funding term sheet; drawdown controls | Yes / No / N/A + Score 0–5 + Rating
24.022 | 24 | WP24 | Procurement Strategy and Tender Documentation | Is there a responsible owner, due date and approval route for contract conditions - financial viability? | Register entry, supporting drawing/report, approval note and updated risk item. | IFRS/IFRS for SMEs principles; lender due diligence checklist; signed financial model | Yes / No / N/A + Score 0–5 + Rating
24.023 | 24 | WP24 | Procurement Strategy and Tender Documentation | Has the gate file tested whether bid evaluation - financial viability creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | CIDB/procurement best practice; cost plan; QS measurement and BOQ controls | Yes / No / N/A + Score 0–5 + Rating
24.024 | 24 | WP24 | Procurement Strategy and Tender Documentation | Are assumptions for supplier strategy - financial viability documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | Treasury-style value-for-money principles; funding term sheet; drawdown controls | Yes / No / N/A + Score 0–5 + Rating
24.025 | 24 | WP24 | Procurement Strategy and Tender Documentation | Has the relevant authority, specialist or professional adviser reviewed procurement route - programme impact where required? | Authority response, compliance checklist, file note and management approval. | IFRS/IFRS for SMEs principles; lender due diligence checklist; signed financial model | Yes / No / N/A + Score 0–5 + Rating
24.026 | 24 | WP24 | Procurement Strategy and Tender Documentation | Is the decision record for tender pack - programme impact aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | CIDB/procurement best practice; cost plan; QS measurement and BOQ controls | Yes / No / N/A + Score 0–5 + Rating
24.027 | 24 | WP24 | Procurement Strategy and Tender Documentation | Have cost, programme and compliance implications of BOQ - programme impact been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | Treasury-style value-for-money principles; funding term sheet; drawdown controls | Yes / No / N/A + Score 0–5 + Rating
24.028 | 24 | WP24 | Procurement Strategy and Tender Documentation | Has the team obtained written confirmation or documented proof for contract conditions - programme impact? | Current certificate/letter/report, version control and document-control entry. | IFRS/IFRS for SMEs principles; lender due diligence checklist; signed financial model | Yes / No / N/A + Score 0–5 + Rating
24.029 | 24 | WP24 | Procurement Strategy and Tender Documentation | Does the evidence for bid evaluation - programme impact support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | CIDB/procurement best practice; cost plan; QS measurement and BOQ controls | Yes / No / N/A + Score 0–5 + Rating
24.030 | 24 | WP24 | Procurement Strategy and Tender Documentation | Have dependencies linked to supplier strategy - programme impact been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | Treasury-style value-for-money principles; funding term sheet; drawdown controls | Yes / No / N/A + Score 0–5 + Rating
24.031 | 24 | WP24 | Procurement Strategy and Tender Documentation | Has the project team confirmed procurement route - risk mitigation in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | IFRS/IFRS for SMEs principles; lender due diligence checklist; signed financial model | Yes / No / N/A + Score 0–5 + Rating
24.032 | 24 | WP24 | Procurement Strategy and Tender Documentation | Is there a responsible owner, due date and approval route for tender pack - risk mitigation? | Register entry, supporting drawing/report, approval note and updated risk item. | CIDB/procurement best practice; cost plan; QS measurement and BOQ controls | Yes / No / N/A + Score 0–5 + Rating
24.033 | 24 | WP24 | Procurement Strategy and Tender Documentation | Has the gate file tested whether BOQ - risk mitigation creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | Treasury-style value-for-money principles; funding term sheet; drawdown controls | Yes / No / N/A + Score 0–5 + Rating
24.034 | 24 | WP24 | Procurement Strategy and Tender Documentation | Are assumptions for contract conditions - risk mitigation documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | IFRS/IFRS for SMEs principles; lender due diligence checklist; signed financial model | Yes / No / N/A + Score 0–5 + Rating
24.035 | 24 | WP24 | Procurement Strategy and Tender Documentation | Has the relevant authority, specialist or professional adviser reviewed bid evaluation - risk mitigation where required? | Authority response, compliance checklist, file note and management approval. | CIDB/procurement best practice; cost plan; QS measurement and BOQ controls | Yes / No / N/A + Score 0–5 + Rating
24.036 | 24 | WP24 | Procurement Strategy and Tender Documentation | Is the decision record for supplier strategy - risk mitigation aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | Treasury-style value-for-money principles; funding term sheet; drawdown controls | Yes / No / N/A + Score 0–5 + Rating
24.037 | 24 | WP24 | Procurement Strategy and Tender Documentation | Have cost, programme and compliance implications of procurement route - stakeholder acceptance been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | IFRS/IFRS for SMEs principles; lender due diligence checklist; signed financial model | Yes / No / N/A + Score 0–5 + Rating
24.038 | 24 | WP24 | Procurement Strategy and Tender Documentation | Has the team obtained written confirmation or documented proof for tender pack - stakeholder acceptance? | Current certificate/letter/report, version control and document-control entry. | CIDB/procurement best practice; cost plan; QS measurement and BOQ controls | Yes / No / N/A + Score 0–5 + Rating
24.039 | 24 | WP24 | Procurement Strategy and Tender Documentation | Does the evidence for BOQ - stakeholder acceptance support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | Treasury-style value-for-money principles; funding term sheet; drawdown controls | Yes / No / N/A + Score 0–5 + Rating
24.040 | 24 | WP24 | Procurement Strategy and Tender Documentation | Have dependencies linked to contract conditions - stakeholder acceptance been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | IFRS/IFRS for SMEs principles; lender due diligence checklist; signed financial model | Yes / No / N/A + Score 0–5 + Rating
24.041 | 24 | WP24 | Procurement Strategy and Tender Documentation | Has the project team confirmed bid evaluation - stakeholder acceptance in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | CIDB/procurement best practice; cost plan; QS measurement and BOQ controls | Yes / No / N/A + Score 0–5 + Rating
24.042 | 24 | WP24 | Procurement Strategy and Tender Documentation | Is there a responsible owner, due date and approval route for supplier strategy - stakeholder acceptance? | Register entry, supporting drawing/report, approval note and updated risk item. | Treasury-style value-for-money principles; funding term sheet; drawdown controls | Yes / No / N/A + Score 0–5 + Rating
24.043 | 24 | WP24 | Procurement Strategy and Tender Documentation | Has the gate file tested whether procurement route - document control creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | IFRS/IFRS for SMEs principles; lender due diligence checklist; signed financial model | Yes / No / N/A + Score 0–5 + Rating
24.044 | 24 | WP24 | Procurement Strategy and Tender Documentation | Are assumptions for tender pack - document control documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | CIDB/procurement best practice; cost plan; QS measurement and BOQ controls | Yes / No / N/A + Score 0–5 + Rating
24.045 | 24 | WP24 | Procurement Strategy and Tender Documentation | Has the relevant authority, specialist or professional adviser reviewed BOQ - document control where required? | Authority response, compliance checklist, file note and management approval. | Treasury-style value-for-money principles; funding term sheet; drawdown controls | Yes / No / N/A + Score 0–5 + Rating
24.046 | 24 | WP24 | Procurement Strategy and Tender Documentation | Is the decision record for contract conditions - document control aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | IFRS/IFRS for SMEs principles; lender due diligence checklist; signed financial model | Yes / No / N/A + Score 0–5 + Rating
24.047 | 24 | WP24 | Procurement Strategy and Tender Documentation | Have cost, programme and compliance implications of bid evaluation - document control been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | CIDB/procurement best practice; cost plan; QS measurement and BOQ controls | Yes / No / N/A + Score 0–5 + Rating
24.048 | 24 | WP24 | Procurement Strategy and Tender Documentation | Has the team obtained written confirmation or documented proof for supplier strategy - document control? | Current certificate/letter/report, version control and document-control entry. | Treasury-style value-for-money principles; funding term sheet; drawdown controls | Yes / No / N/A + Score 0–5 + Rating
24.049 | 24 | WP24 | Procurement Strategy and Tender Documentation | Does the evidence for procurement route - professional certification support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | IFRS/IFRS for SMEs principles; lender due diligence checklist; signed financial model | Yes / No / N/A + Score 0–5 + Rating
24.050 | 24 | WP24 | Procurement Strategy and Tender Documentation | Have dependencies linked to tender pack - professional certification been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | CIDB/procurement best practice; cost plan; QS measurement and BOQ controls | Yes / No / N/A + Score 0–5 + Rating
24.051 | 24 | WP24 | Procurement Strategy and Tender Documentation | Has the project team confirmed BOQ - professional certification in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | Treasury-style value-for-money principles; funding term sheet; drawdown controls | Yes / No / N/A + Score 0–5 + Rating
24.052 | 24 | WP24 | Procurement Strategy and Tender Documentation | Is there a responsible owner, due date and approval route for contract conditions - professional certification? | Register entry, supporting drawing/report, approval note and updated risk item. | IFRS/IFRS for SMEs principles; lender due diligence checklist; signed financial model | Yes / No / N/A + Score 0–5 + Rating
24.053 | 24 | WP24 | Procurement Strategy and Tender Documentation | Has the gate file tested whether bid evaluation - professional certification creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | CIDB/procurement best practice; cost plan; QS measurement and BOQ controls | Yes / No / N/A + Score 0–5 + Rating
24.054 | 24 | WP24 | Procurement Strategy and Tender Documentation | Are assumptions for supplier strategy - professional certification documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | Treasury-style value-for-money principles; funding term sheet; drawdown controls | Yes / No / N/A + Score 0–5 + Rating
24.055 | 24 | WP24 | Procurement Strategy and Tender Documentation | Has the relevant authority, specialist or professional adviser reviewed procurement route - implementation readiness where required? | Authority response, compliance checklist, file note and management approval. | IFRS/IFRS for SMEs principles; lender due diligence checklist; signed financial model | Yes / No / N/A + Score 0–5 + Rating
24.056 | 24 | WP24 | Procurement Strategy and Tender Documentation | Is the decision record for tender pack - implementation readiness aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | CIDB/procurement best practice; cost plan; QS measurement and BOQ controls | Yes / No / N/A + Score 0–5 + Rating
24.057 | 24 | WP24 | Procurement Strategy and Tender Documentation | Have cost, programme and compliance implications of BOQ - implementation readiness been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | Treasury-style value-for-money principles; funding term sheet; drawdown controls | Yes / No / N/A + Score 0–5 + Rating
24.058 | 24 | WP24 | Procurement Strategy and Tender Documentation | Has the team obtained written confirmation or documented proof for contract conditions - implementation readiness? | Current certificate/letter/report, version control and document-control entry. | IFRS/IFRS for SMEs principles; lender due diligence checklist; signed financial model | Yes / No / N/A + Score 0–5 + Rating
24.059 | 24 | WP24 | Procurement Strategy and Tender Documentation | Does the evidence for bid evaluation - implementation readiness support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | CIDB/procurement best practice; cost plan; QS measurement and BOQ controls | Yes / No / N/A + Score 0–5 + Rating
24.060 | 24 | WP24 | Procurement Strategy and Tender Documentation | Have dependencies linked to supplier strategy - implementation readiness been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | Treasury-style value-for-money principles; funding term sheet; drawdown controls | Yes / No / N/A + Score 0–5 + Rating
24.061 | 24 | WP24 | Procurement Strategy and Tender Documentation | Has the project team confirmed procurement route - governance approval in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | IFRS/IFRS for SMEs principles; lender due diligence checklist; signed financial model | Yes / No / N/A + Score 0–5 + Rating
24.062 | 24 | WP24 | Procurement Strategy and Tender Documentation | Is there a responsible owner, due date and approval route for tender pack - governance approval? | Register entry, supporting drawing/report, approval note and updated risk item. | CIDB/procurement best practice; cost plan; QS measurement and BOQ controls | Yes / No / N/A + Score 0–5 + Rating
24.063 | 24 | WP24 | Procurement Strategy and Tender Documentation | Has the gate file tested whether BOQ - governance approval creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | Treasury-style value-for-money principles; funding term sheet; drawdown controls | Yes / No / N/A + Score 0–5 + Rating
24.064 | 24 | WP24 | Procurement Strategy and Tender Documentation | Are assumptions for contract conditions - governance approval documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | IFRS/IFRS for SMEs principles; lender due diligence checklist; signed financial model | Yes / No / N/A + Score 0–5 + Rating
24.065 | 24 | WP24 | Procurement Strategy and Tender Documentation | Has the relevant authority, specialist or professional adviser reviewed bid evaluation - governance approval where required? | Authority response, compliance checklist, file note and management approval. | CIDB/procurement best practice; cost plan; QS measurement and BOQ controls | Yes / No / N/A + Score 0–5 + Rating
24.066 | 24 | WP24 | Procurement Strategy and Tender Documentation | Is the decision record for supplier strategy - governance approval aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | Treasury-style value-for-money principles; funding term sheet; drawdown controls | Yes / No / N/A + Score 0–5 + Rating
24.067 | 24 | WP24 | Procurement Strategy and Tender Documentation | Have cost, programme and compliance implications of procurement route - legal authority been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | IFRS/IFRS for SMEs principles; lender due diligence checklist; signed financial model | Yes / No / N/A + Score 0–5 + Rating
24.068 | 24 | WP24 | Procurement Strategy and Tender Documentation | Has the team obtained written confirmation or documented proof for tender pack - legal authority? | Current certificate/letter/report, version control and document-control entry. | CIDB/procurement best practice; cost plan; QS measurement and BOQ controls | Yes / No / N/A + Score 0–5 + Rating
24.069 | 24 | WP24 | Procurement Strategy and Tender Documentation | Does the evidence for BOQ - legal authority support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | Treasury-style value-for-money principles; funding term sheet; drawdown controls | Yes / No / N/A + Score 0–5 + Rating
24.070 | 24 | WP24 | Procurement Strategy and Tender Documentation | Have dependencies linked to contract conditions - legal authority been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | IFRS/IFRS for SMEs principles; lender due diligence checklist; signed financial model | Yes / No / N/A + Score 0–5 + Rating
24.071 | 24 | WP24 | Procurement Strategy and Tender Documentation | Has the project team confirmed bid evaluation - legal authority in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | CIDB/procurement best practice; cost plan; QS measurement and BOQ controls | Yes / No / N/A + Score 0–5 + Rating
24.072 | 24 | WP24 | Procurement Strategy and Tender Documentation | Is there a responsible owner, due date and approval route for supplier strategy - legal authority? | Register entry, supporting drawing/report, approval note and updated risk item. | Treasury-style value-for-money principles; funding term sheet; drawdown controls | Yes / No / N/A + Score 0–5 + Rating
24.073 | 24 | WP24 | Procurement Strategy and Tender Documentation | Has the gate file tested whether procurement route - technical feasibility creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | IFRS/IFRS for SMEs principles; lender due diligence checklist; signed financial model | Yes / No / N/A + Score 0–5 + Rating
24.074 | 24 | WP24 | Procurement Strategy and Tender Documentation | Are assumptions for tender pack - technical feasibility documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | CIDB/procurement best practice; cost plan; QS measurement and BOQ controls | Yes / No / N/A + Score 0–5 + Rating
24.075 | 24 | WP24 | Procurement Strategy and Tender Documentation | Has the relevant authority, specialist or professional adviser reviewed BOQ - technical feasibility where required? | Authority response, compliance checklist, file note and management approval. | Treasury-style value-for-money principles; funding term sheet; drawdown controls | Yes / No / N/A + Score 0–5 + Rating
24.076 | 24 | WP24 | Procurement Strategy and Tender Documentation | Is the decision record for contract conditions - technical feasibility aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | IFRS/IFRS for SMEs principles; lender due diligence checklist; signed financial model | Yes / No / N/A + Score 0–5 + Rating
24.077 | 24 | WP24 | Procurement Strategy and Tender Documentation | Have cost, programme and compliance implications of bid evaluation - technical feasibility been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | CIDB/procurement best practice; cost plan; QS measurement and BOQ controls | Yes / No / N/A + Score 0–5 + Rating
24.078 | 24 | WP24 | Procurement Strategy and Tender Documentation | Has the team obtained written confirmation or documented proof for supplier strategy - technical feasibility? | Current certificate/letter/report, version control and document-control entry. | Treasury-style value-for-money principles; funding term sheet; drawdown controls | Yes / No / N/A + Score 0–5 + Rating
24.079 | 24 | WP24 | Procurement Strategy and Tender Documentation | Does the evidence for procurement route - financial viability support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | IFRS/IFRS for SMEs principles; lender due diligence checklist; signed financial model | Yes / No / N/A + Score 0–5 + Rating
24.080 | 24 | WP24 | Procurement Strategy and Tender Documentation | Have dependencies linked to tender pack - financial viability been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | CIDB/procurement best practice; cost plan; QS measurement and BOQ controls | Yes / No / N/A + Score 0–5 + Rating
24.081 | 24 | WP24 | Procurement Strategy and Tender Documentation | Has the project team confirmed BOQ - financial viability in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | Treasury-style value-for-money principles; funding term sheet; drawdown controls | Yes / No / N/A + Score 0–5 + Rating
24.082 | 24 | WP24 | Procurement Strategy and Tender Documentation | Is there a responsible owner, due date and approval route for contract conditions - financial viability? | Register entry, supporting drawing/report, approval note and updated risk item. | IFRS/IFRS for SMEs principles; lender due diligence checklist; signed financial model | Yes / No / N/A + Score 0–5 + Rating
24.083 | 24 | WP24 | Procurement Strategy and Tender Documentation | Has the gate file tested whether bid evaluation - financial viability creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | CIDB/procurement best practice; cost plan; QS measurement and BOQ controls | Yes / No / N/A + Score 0–5 + Rating
24.084 | 24 | WP24 | Procurement Strategy and Tender Documentation | Are assumptions for supplier strategy - financial viability documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | Treasury-style value-for-money principles; funding term sheet; drawdown controls | Yes / No / N/A + Score 0–5 + Rating
24.085 | 24 | WP24 | Procurement Strategy and Tender Documentation | Has the relevant authority, specialist or professional adviser reviewed procurement route - programme impact where required? | Authority response, compliance checklist, file note and management approval. | IFRS/IFRS for SMEs principles; lender due diligence checklist; signed financial model | Yes / No / N/A + Score 0–5 + Rating
24.086 | 24 | WP24 | Procurement Strategy and Tender Documentation | Is the decision record for tender pack - programme impact aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | CIDB/procurement best practice; cost plan; QS measurement and BOQ controls | Yes / No / N/A + Score 0–5 + Rating
24.087 | 24 | WP24 | Procurement Strategy and Tender Documentation | Have cost, programme and compliance implications of BOQ - programme impact been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | Treasury-style value-for-money principles; funding term sheet; drawdown controls | Yes / No / N/A + Score 0–5 + Rating
24.088 | 24 | WP24 | Procurement Strategy and Tender Documentation | Has the team obtained written confirmation or documented proof for contract conditions - programme impact? | Current certificate/letter/report, version control and document-control entry. | IFRS/IFRS for SMEs principles; lender due diligence checklist; signed financial model | Yes / No / N/A + Score 0–5 + Rating
24.089 | 24 | WP24 | Procurement Strategy and Tender Documentation | Does the evidence for bid evaluation - programme impact support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | CIDB/procurement best practice; cost plan; QS measurement and BOQ controls | Yes / No / N/A + Score 0–5 + Rating
24.090 | 24 | WP24 | Procurement Strategy and Tender Documentation | Have dependencies linked to supplier strategy - programme impact been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | Treasury-style value-for-money principles; funding term sheet; drawdown controls | Yes / No / N/A + Score 0–5 + Rating
24.091 | 24 | WP24 | Procurement Strategy and Tender Documentation | Has the project team confirmed procurement route - risk mitigation in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | IFRS/IFRS for SMEs principles; lender due diligence checklist; signed financial model | Yes / No / N/A + Score 0–5 + Rating
24.092 | 24 | WP24 | Procurement Strategy and Tender Documentation | Is there a responsible owner, due date and approval route for tender pack - risk mitigation? | Register entry, supporting drawing/report, approval note and updated risk item. | CIDB/procurement best practice; cost plan; QS measurement and BOQ controls | Yes / No / N/A + Score 0–5 + Rating
24.093 | 24 | WP24 | Procurement Strategy and Tender Documentation | Has the gate file tested whether BOQ - risk mitigation creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | Treasury-style value-for-money principles; funding term sheet; drawdown controls | Yes / No / N/A + Score 0–5 + Rating
24.094 | 24 | WP24 | Procurement Strategy and Tender Documentation | Are assumptions for contract conditions - risk mitigation documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | IFRS/IFRS for SMEs principles; lender due diligence checklist; signed financial model | Yes / No / N/A + Score 0–5 + Rating
24.095 | 24 | WP24 | Procurement Strategy and Tender Documentation | Has the relevant authority, specialist or professional adviser reviewed bid evaluation - risk mitigation where required? | Authority response, compliance checklist, file note and management approval. | CIDB/procurement best practice; cost plan; QS measurement and BOQ controls | Yes / No / N/A + Score 0–5 + Rating
24.096 | 24 | WP24 | Procurement Strategy and Tender Documentation | Is the decision record for supplier strategy - risk mitigation aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | Treasury-style value-for-money principles; funding term sheet; drawdown controls | Yes / No / N/A + Score 0–5 + Rating
24.097 | 24 | WP24 | Procurement Strategy and Tender Documentation | Have cost, programme and compliance implications of procurement route - stakeholder acceptance been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | IFRS/IFRS for SMEs principles; lender due diligence checklist; signed financial model | Yes / No / N/A + Score 0–5 + Rating
24.098 | 24 | WP24 | Procurement Strategy and Tender Documentation | Has the team obtained written confirmation or documented proof for tender pack - stakeholder acceptance? | Current certificate/letter/report, version control and document-control entry. | CIDB/procurement best practice; cost plan; QS measurement and BOQ controls | Yes / No / N/A + Score 0–5 + Rating
24.099 | 24 | WP24 | Procurement Strategy and Tender Documentation | Does the evidence for BOQ - stakeholder acceptance support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | Treasury-style value-for-money principles; funding term sheet; drawdown controls | Yes / No / N/A + Score 0–5 + Rating
24.100 | 24 | WP24 | Procurement Strategy and Tender Documentation | Have dependencies linked to contract conditions - stakeholder acceptance been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | IFRS/IFRS for SMEs principles; lender due diligence checklist; signed financial model | Yes / No / N/A + Score 0–5 + Rating
25.001 | 25 | WP25 | Contractor Due Diligence and Appointment | Has the project team confirmed contractor capacity - governance approval in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | IFRS/IFRS for SMEs principles; lender due diligence checklist; signed financial model | Yes / No / N/A + Score 0–5 + Rating
25.002 | 25 | WP25 | Contractor Due Diligence and Appointment | Is there a responsible owner, due date and approval route for financial strength - governance approval? | Register entry, supporting drawing/report, approval note and updated risk item. | CIDB/procurement best practice; cost plan; QS measurement and BOQ controls | Yes / No / N/A + Score 0–5 + Rating
25.003 | 25 | WP25 | Contractor Due Diligence and Appointment | Has the gate file tested whether similar project experience - governance approval creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | Treasury-style value-for-money principles; funding term sheet; drawdown controls | Yes / No / N/A + Score 0–5 + Rating
25.004 | 25 | WP25 | Contractor Due Diligence and Appointment | Are assumptions for HSE record - governance approval documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | IFRS/IFRS for SMEs principles; lender due diligence checklist; signed financial model | Yes / No / N/A + Score 0–5 + Rating
25.005 | 25 | WP25 | Contractor Due Diligence and Appointment | Has the relevant authority, specialist or professional adviser reviewed quality systems - governance approval where required? | Authority response, compliance checklist, file note and management approval. | CIDB/procurement best practice; cost plan; QS measurement and BOQ controls | Yes / No / N/A + Score 0–5 + Rating
25.006 | 25 | WP25 | Contractor Due Diligence and Appointment | Is the decision record for programme credibility - governance approval aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | Treasury-style value-for-money principles; funding term sheet; drawdown controls | Yes / No / N/A + Score 0–5 + Rating
25.007 | 25 | WP25 | Contractor Due Diligence and Appointment | Have cost, programme and compliance implications of contractor capacity - legal authority been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | IFRS/IFRS for SMEs principles; lender due diligence checklist; signed financial model | Yes / No / N/A + Score 0–5 + Rating
25.008 | 25 | WP25 | Contractor Due Diligence and Appointment | Has the team obtained written confirmation or documented proof for financial strength - legal authority? | Current certificate/letter/report, version control and document-control entry. | CIDB/procurement best practice; cost plan; QS measurement and BOQ controls | Yes / No / N/A + Score 0–5 + Rating
25.009 | 25 | WP25 | Contractor Due Diligence and Appointment | Does the evidence for similar project experience - legal authority support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | Treasury-style value-for-money principles; funding term sheet; drawdown controls | Yes / No / N/A + Score 0–5 + Rating
25.010 | 25 | WP25 | Contractor Due Diligence and Appointment | Have dependencies linked to HSE record - legal authority been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | IFRS/IFRS for SMEs principles; lender due diligence checklist; signed financial model | Yes / No / N/A + Score 0–5 + Rating
25.011 | 25 | WP25 | Contractor Due Diligence and Appointment | Has the project team confirmed quality systems - legal authority in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | CIDB/procurement best practice; cost plan; QS measurement and BOQ controls | Yes / No / N/A + Score 0–5 + Rating
25.012 | 25 | WP25 | Contractor Due Diligence and Appointment | Is there a responsible owner, due date and approval route for programme credibility - legal authority? | Register entry, supporting drawing/report, approval note and updated risk item. | Treasury-style value-for-money principles; funding term sheet; drawdown controls | Yes / No / N/A + Score 0–5 + Rating
25.013 | 25 | WP25 | Contractor Due Diligence and Appointment | Has the gate file tested whether contractor capacity - technical feasibility creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | IFRS/IFRS for SMEs principles; lender due diligence checklist; signed financial model | Yes / No / N/A + Score 0–5 + Rating
25.014 | 25 | WP25 | Contractor Due Diligence and Appointment | Are assumptions for financial strength - technical feasibility documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | CIDB/procurement best practice; cost plan; QS measurement and BOQ controls | Yes / No / N/A + Score 0–5 + Rating
25.015 | 25 | WP25 | Contractor Due Diligence and Appointment | Has the relevant authority, specialist or professional adviser reviewed similar project experience - technical feasibility where required? | Authority response, compliance checklist, file note and management approval. | Treasury-style value-for-money principles; funding term sheet; drawdown controls | Yes / No / N/A + Score 0–5 + Rating
25.016 | 25 | WP25 | Contractor Due Diligence and Appointment | Is the decision record for HSE record - technical feasibility aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | IFRS/IFRS for SMEs principles; lender due diligence checklist; signed financial model | Yes / No / N/A + Score 0–5 + Rating
25.017 | 25 | WP25 | Contractor Due Diligence and Appointment | Have cost, programme and compliance implications of quality systems - technical feasibility been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | CIDB/procurement best practice; cost plan; QS measurement and BOQ controls | Yes / No / N/A + Score 0–5 + Rating
25.018 | 25 | WP25 | Contractor Due Diligence and Appointment | Has the team obtained written confirmation or documented proof for programme credibility - technical feasibility? | Current certificate/letter/report, version control and document-control entry. | Treasury-style value-for-money principles; funding term sheet; drawdown controls | Yes / No / N/A + Score 0–5 + Rating
25.019 | 25 | WP25 | Contractor Due Diligence and Appointment | Does the evidence for contractor capacity - financial viability support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | IFRS/IFRS for SMEs principles; lender due diligence checklist; signed financial model | Yes / No / N/A + Score 0–5 + Rating
25.020 | 25 | WP25 | Contractor Due Diligence and Appointment | Have dependencies linked to financial strength - financial viability been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | CIDB/procurement best practice; cost plan; QS measurement and BOQ controls | Yes / No / N/A + Score 0–5 + Rating
25.021 | 25 | WP25 | Contractor Due Diligence and Appointment | Has the project team confirmed similar project experience - financial viability in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | Treasury-style value-for-money principles; funding term sheet; drawdown controls | Yes / No / N/A + Score 0–5 + Rating
25.022 | 25 | WP25 | Contractor Due Diligence and Appointment | Is there a responsible owner, due date and approval route for HSE record - financial viability? | Register entry, supporting drawing/report, approval note and updated risk item. | IFRS/IFRS for SMEs principles; lender due diligence checklist; signed financial model | Yes / No / N/A + Score 0–5 + Rating
25.023 | 25 | WP25 | Contractor Due Diligence and Appointment | Has the gate file tested whether quality systems - financial viability creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | CIDB/procurement best practice; cost plan; QS measurement and BOQ controls | Yes / No / N/A + Score 0–5 + Rating
25.024 | 25 | WP25 | Contractor Due Diligence and Appointment | Are assumptions for programme credibility - financial viability documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | Treasury-style value-for-money principles; funding term sheet; drawdown controls | Yes / No / N/A + Score 0–5 + Rating
25.025 | 25 | WP25 | Contractor Due Diligence and Appointment | Has the relevant authority, specialist or professional adviser reviewed contractor capacity - programme impact where required? | Authority response, compliance checklist, file note and management approval. | IFRS/IFRS for SMEs principles; lender due diligence checklist; signed financial model | Yes / No / N/A + Score 0–5 + Rating
25.026 | 25 | WP25 | Contractor Due Diligence and Appointment | Is the decision record for financial strength - programme impact aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | CIDB/procurement best practice; cost plan; QS measurement and BOQ controls | Yes / No / N/A + Score 0–5 + Rating
25.027 | 25 | WP25 | Contractor Due Diligence and Appointment | Have cost, programme and compliance implications of similar project experience - programme impact been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | Treasury-style value-for-money principles; funding term sheet; drawdown controls | Yes / No / N/A + Score 0–5 + Rating
25.028 | 25 | WP25 | Contractor Due Diligence and Appointment | Has the team obtained written confirmation or documented proof for HSE record - programme impact? | Current certificate/letter/report, version control and document-control entry. | IFRS/IFRS for SMEs principles; lender due diligence checklist; signed financial model | Yes / No / N/A + Score 0–5 + Rating
25.029 | 25 | WP25 | Contractor Due Diligence and Appointment | Does the evidence for quality systems - programme impact support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | CIDB/procurement best practice; cost plan; QS measurement and BOQ controls | Yes / No / N/A + Score 0–5 + Rating
25.030 | 25 | WP25 | Contractor Due Diligence and Appointment | Have dependencies linked to programme credibility - programme impact been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | Treasury-style value-for-money principles; funding term sheet; drawdown controls | Yes / No / N/A + Score 0–5 + Rating
25.031 | 25 | WP25 | Contractor Due Diligence and Appointment | Has the project team confirmed contractor capacity - risk mitigation in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | IFRS/IFRS for SMEs principles; lender due diligence checklist; signed financial model | Yes / No / N/A + Score 0–5 + Rating
25.032 | 25 | WP25 | Contractor Due Diligence and Appointment | Is there a responsible owner, due date and approval route for financial strength - risk mitigation? | Register entry, supporting drawing/report, approval note and updated risk item. | CIDB/procurement best practice; cost plan; QS measurement and BOQ controls | Yes / No / N/A + Score 0–5 + Rating
25.033 | 25 | WP25 | Contractor Due Diligence and Appointment | Has the gate file tested whether similar project experience - risk mitigation creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | Treasury-style value-for-money principles; funding term sheet; drawdown controls | Yes / No / N/A + Score 0–5 + Rating
25.034 | 25 | WP25 | Contractor Due Diligence and Appointment | Are assumptions for HSE record - risk mitigation documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | IFRS/IFRS for SMEs principles; lender due diligence checklist; signed financial model | Yes / No / N/A + Score 0–5 + Rating
25.035 | 25 | WP25 | Contractor Due Diligence and Appointment | Has the relevant authority, specialist or professional adviser reviewed quality systems - risk mitigation where required? | Authority response, compliance checklist, file note and management approval. | CIDB/procurement best practice; cost plan; QS measurement and BOQ controls | Yes / No / N/A + Score 0–5 + Rating
25.036 | 25 | WP25 | Contractor Due Diligence and Appointment | Is the decision record for programme credibility - risk mitigation aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | Treasury-style value-for-money principles; funding term sheet; drawdown controls | Yes / No / N/A + Score 0–5 + Rating
25.037 | 25 | WP25 | Contractor Due Diligence and Appointment | Have cost, programme and compliance implications of contractor capacity - stakeholder acceptance been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | IFRS/IFRS for SMEs principles; lender due diligence checklist; signed financial model | Yes / No / N/A + Score 0–5 + Rating
25.038 | 25 | WP25 | Contractor Due Diligence and Appointment | Has the team obtained written confirmation or documented proof for financial strength - stakeholder acceptance? | Current certificate/letter/report, version control and document-control entry. | CIDB/procurement best practice; cost plan; QS measurement and BOQ controls | Yes / No / N/A + Score 0–5 + Rating
25.039 | 25 | WP25 | Contractor Due Diligence and Appointment | Does the evidence for similar project experience - stakeholder acceptance support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | Treasury-style value-for-money principles; funding term sheet; drawdown controls | Yes / No / N/A + Score 0–5 + Rating
25.040 | 25 | WP25 | Contractor Due Diligence and Appointment | Have dependencies linked to HSE record - stakeholder acceptance been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | IFRS/IFRS for SMEs principles; lender due diligence checklist; signed financial model | Yes / No / N/A + Score 0–5 + Rating
25.041 | 25 | WP25 | Contractor Due Diligence and Appointment | Has the project team confirmed quality systems - stakeholder acceptance in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | CIDB/procurement best practice; cost plan; QS measurement and BOQ controls | Yes / No / N/A + Score 0–5 + Rating
25.042 | 25 | WP25 | Contractor Due Diligence and Appointment | Is there a responsible owner, due date and approval route for programme credibility - stakeholder acceptance? | Register entry, supporting drawing/report, approval note and updated risk item. | Treasury-style value-for-money principles; funding term sheet; drawdown controls | Yes / No / N/A + Score 0–5 + Rating
25.043 | 25 | WP25 | Contractor Due Diligence and Appointment | Has the gate file tested whether contractor capacity - document control creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | IFRS/IFRS for SMEs principles; lender due diligence checklist; signed financial model | Yes / No / N/A + Score 0–5 + Rating
25.044 | 25 | WP25 | Contractor Due Diligence and Appointment | Are assumptions for financial strength - document control documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | CIDB/procurement best practice; cost plan; QS measurement and BOQ controls | Yes / No / N/A + Score 0–5 + Rating
25.045 | 25 | WP25 | Contractor Due Diligence and Appointment | Has the relevant authority, specialist or professional adviser reviewed similar project experience - document control where required? | Authority response, compliance checklist, file note and management approval. | Treasury-style value-for-money principles; funding term sheet; drawdown controls | Yes / No / N/A + Score 0–5 + Rating
25.046 | 25 | WP25 | Contractor Due Diligence and Appointment | Is the decision record for HSE record - document control aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | IFRS/IFRS for SMEs principles; lender due diligence checklist; signed financial model | Yes / No / N/A + Score 0–5 + Rating
25.047 | 25 | WP25 | Contractor Due Diligence and Appointment | Have cost, programme and compliance implications of quality systems - document control been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | CIDB/procurement best practice; cost plan; QS measurement and BOQ controls | Yes / No / N/A + Score 0–5 + Rating
25.048 | 25 | WP25 | Contractor Due Diligence and Appointment | Has the team obtained written confirmation or documented proof for programme credibility - document control? | Current certificate/letter/report, version control and document-control entry. | Treasury-style value-for-money principles; funding term sheet; drawdown controls | Yes / No / N/A + Score 0–5 + Rating
25.049 | 25 | WP25 | Contractor Due Diligence and Appointment | Does the evidence for contractor capacity - professional certification support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | IFRS/IFRS for SMEs principles; lender due diligence checklist; signed financial model | Yes / No / N/A + Score 0–5 + Rating
25.050 | 25 | WP25 | Contractor Due Diligence and Appointment | Have dependencies linked to financial strength - professional certification been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | CIDB/procurement best practice; cost plan; QS measurement and BOQ controls | Yes / No / N/A + Score 0–5 + Rating
25.051 | 25 | WP25 | Contractor Due Diligence and Appointment | Has the project team confirmed similar project experience - professional certification in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | Treasury-style value-for-money principles; funding term sheet; drawdown controls | Yes / No / N/A + Score 0–5 + Rating
25.052 | 25 | WP25 | Contractor Due Diligence and Appointment | Is there a responsible owner, due date and approval route for HSE record - professional certification? | Register entry, supporting drawing/report, approval note and updated risk item. | IFRS/IFRS for SMEs principles; lender due diligence checklist; signed financial model | Yes / No / N/A + Score 0–5 + Rating
25.053 | 25 | WP25 | Contractor Due Diligence and Appointment | Has the gate file tested whether quality systems - professional certification creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | CIDB/procurement best practice; cost plan; QS measurement and BOQ controls | Yes / No / N/A + Score 0–5 + Rating
25.054 | 25 | WP25 | Contractor Due Diligence and Appointment | Are assumptions for programme credibility - professional certification documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | Treasury-style value-for-money principles; funding term sheet; drawdown controls | Yes / No / N/A + Score 0–5 + Rating
25.055 | 25 | WP25 | Contractor Due Diligence and Appointment | Has the relevant authority, specialist or professional adviser reviewed contractor capacity - implementation readiness where required? | Authority response, compliance checklist, file note and management approval. | IFRS/IFRS for SMEs principles; lender due diligence checklist; signed financial model | Yes / No / N/A + Score 0–5 + Rating
25.056 | 25 | WP25 | Contractor Due Diligence and Appointment | Is the decision record for financial strength - implementation readiness aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | CIDB/procurement best practice; cost plan; QS measurement and BOQ controls | Yes / No / N/A + Score 0–5 + Rating
25.057 | 25 | WP25 | Contractor Due Diligence and Appointment | Have cost, programme and compliance implications of similar project experience - implementation readiness been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | Treasury-style value-for-money principles; funding term sheet; drawdown controls | Yes / No / N/A + Score 0–5 + Rating
25.058 | 25 | WP25 | Contractor Due Diligence and Appointment | Has the team obtained written confirmation or documented proof for HSE record - implementation readiness? | Current certificate/letter/report, version control and document-control entry. | IFRS/IFRS for SMEs principles; lender due diligence checklist; signed financial model | Yes / No / N/A + Score 0–5 + Rating
25.059 | 25 | WP25 | Contractor Due Diligence and Appointment | Does the evidence for quality systems - implementation readiness support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | CIDB/procurement best practice; cost plan; QS measurement and BOQ controls | Yes / No / N/A + Score 0–5 + Rating
25.060 | 25 | WP25 | Contractor Due Diligence and Appointment | Have dependencies linked to programme credibility - implementation readiness been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | Treasury-style value-for-money principles; funding term sheet; drawdown controls | Yes / No / N/A + Score 0–5 + Rating
25.061 | 25 | WP25 | Contractor Due Diligence and Appointment | Has the project team confirmed contractor capacity - governance approval in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | IFRS/IFRS for SMEs principles; lender due diligence checklist; signed financial model | Yes / No / N/A + Score 0–5 + Rating
25.062 | 25 | WP25 | Contractor Due Diligence and Appointment | Is there a responsible owner, due date and approval route for financial strength - governance approval? | Register entry, supporting drawing/report, approval note and updated risk item. | CIDB/procurement best practice; cost plan; QS measurement and BOQ controls | Yes / No / N/A + Score 0–5 + Rating
25.063 | 25 | WP25 | Contractor Due Diligence and Appointment | Has the gate file tested whether similar project experience - governance approval creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | Treasury-style value-for-money principles; funding term sheet; drawdown controls | Yes / No / N/A + Score 0–5 + Rating
25.064 | 25 | WP25 | Contractor Due Diligence and Appointment | Are assumptions for HSE record - governance approval documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | IFRS/IFRS for SMEs principles; lender due diligence checklist; signed financial model | Yes / No / N/A + Score 0–5 + Rating
25.065 | 25 | WP25 | Contractor Due Diligence and Appointment | Has the relevant authority, specialist or professional adviser reviewed quality systems - governance approval where required? | Authority response, compliance checklist, file note and management approval. | CIDB/procurement best practice; cost plan; QS measurement and BOQ controls | Yes / No / N/A + Score 0–5 + Rating
25.066 | 25 | WP25 | Contractor Due Diligence and Appointment | Is the decision record for programme credibility - governance approval aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | Treasury-style value-for-money principles; funding term sheet; drawdown controls | Yes / No / N/A + Score 0–5 + Rating
25.067 | 25 | WP25 | Contractor Due Diligence and Appointment | Have cost, programme and compliance implications of contractor capacity - legal authority been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | IFRS/IFRS for SMEs principles; lender due diligence checklist; signed financial model | Yes / No / N/A + Score 0–5 + Rating
25.068 | 25 | WP25 | Contractor Due Diligence and Appointment | Has the team obtained written confirmation or documented proof for financial strength - legal authority? | Current certificate/letter/report, version control and document-control entry. | CIDB/procurement best practice; cost plan; QS measurement and BOQ controls | Yes / No / N/A + Score 0–5 + Rating
25.069 | 25 | WP25 | Contractor Due Diligence and Appointment | Does the evidence for similar project experience - legal authority support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | Treasury-style value-for-money principles; funding term sheet; drawdown controls | Yes / No / N/A + Score 0–5 + Rating
25.070 | 25 | WP25 | Contractor Due Diligence and Appointment | Have dependencies linked to HSE record - legal authority been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | IFRS/IFRS for SMEs principles; lender due diligence checklist; signed financial model | Yes / No / N/A + Score 0–5 + Rating
25.071 | 25 | WP25 | Contractor Due Diligence and Appointment | Has the project team confirmed quality systems - legal authority in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | CIDB/procurement best practice; cost plan; QS measurement and BOQ controls | Yes / No / N/A + Score 0–5 + Rating
25.072 | 25 | WP25 | Contractor Due Diligence and Appointment | Is there a responsible owner, due date and approval route for programme credibility - legal authority? | Register entry, supporting drawing/report, approval note and updated risk item. | Treasury-style value-for-money principles; funding term sheet; drawdown controls | Yes / No / N/A + Score 0–5 + Rating
25.073 | 25 | WP25 | Contractor Due Diligence and Appointment | Has the gate file tested whether contractor capacity - technical feasibility creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | IFRS/IFRS for SMEs principles; lender due diligence checklist; signed financial model | Yes / No / N/A + Score 0–5 + Rating
25.074 | 25 | WP25 | Contractor Due Diligence and Appointment | Are assumptions for financial strength - technical feasibility documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | CIDB/procurement best practice; cost plan; QS measurement and BOQ controls | Yes / No / N/A + Score 0–5 + Rating
25.075 | 25 | WP25 | Contractor Due Diligence and Appointment | Has the relevant authority, specialist or professional adviser reviewed similar project experience - technical feasibility where required? | Authority response, compliance checklist, file note and management approval. | Treasury-style value-for-money principles; funding term sheet; drawdown controls | Yes / No / N/A + Score 0–5 + Rating
25.076 | 25 | WP25 | Contractor Due Diligence and Appointment | Is the decision record for HSE record - technical feasibility aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | IFRS/IFRS for SMEs principles; lender due diligence checklist; signed financial model | Yes / No / N/A + Score 0–5 + Rating
25.077 | 25 | WP25 | Contractor Due Diligence and Appointment | Have cost, programme and compliance implications of quality systems - technical feasibility been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | CIDB/procurement best practice; cost plan; QS measurement and BOQ controls | Yes / No / N/A + Score 0–5 + Rating
25.078 | 25 | WP25 | Contractor Due Diligence and Appointment | Has the team obtained written confirmation or documented proof for programme credibility - technical feasibility? | Current certificate/letter/report, version control and document-control entry. | Treasury-style value-for-money principles; funding term sheet; drawdown controls | Yes / No / N/A + Score 0–5 + Rating
25.079 | 25 | WP25 | Contractor Due Diligence and Appointment | Does the evidence for contractor capacity - financial viability support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | IFRS/IFRS for SMEs principles; lender due diligence checklist; signed financial model | Yes / No / N/A + Score 0–5 + Rating
25.080 | 25 | WP25 | Contractor Due Diligence and Appointment | Have dependencies linked to financial strength - financial viability been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | CIDB/procurement best practice; cost plan; QS measurement and BOQ controls | Yes / No / N/A + Score 0–5 + Rating
25.081 | 25 | WP25 | Contractor Due Diligence and Appointment | Has the project team confirmed similar project experience - financial viability in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | Treasury-style value-for-money principles; funding term sheet; drawdown controls | Yes / No / N/A + Score 0–5 + Rating
25.082 | 25 | WP25 | Contractor Due Diligence and Appointment | Is there a responsible owner, due date and approval route for HSE record - financial viability? | Register entry, supporting drawing/report, approval note and updated risk item. | IFRS/IFRS for SMEs principles; lender due diligence checklist; signed financial model | Yes / No / N/A + Score 0–5 + Rating
25.083 | 25 | WP25 | Contractor Due Diligence and Appointment | Has the gate file tested whether quality systems - financial viability creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | CIDB/procurement best practice; cost plan; QS measurement and BOQ controls | Yes / No / N/A + Score 0–5 + Rating
25.084 | 25 | WP25 | Contractor Due Diligence and Appointment | Are assumptions for programme credibility - financial viability documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | Treasury-style value-for-money principles; funding term sheet; drawdown controls | Yes / No / N/A + Score 0–5 + Rating
25.085 | 25 | WP25 | Contractor Due Diligence and Appointment | Has the relevant authority, specialist or professional adviser reviewed contractor capacity - programme impact where required? | Authority response, compliance checklist, file note and management approval. | IFRS/IFRS for SMEs principles; lender due diligence checklist; signed financial model | Yes / No / N/A + Score 0–5 + Rating
25.086 | 25 | WP25 | Contractor Due Diligence and Appointment | Is the decision record for financial strength - programme impact aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | CIDB/procurement best practice; cost plan; QS measurement and BOQ controls | Yes / No / N/A + Score 0–5 + Rating
25.087 | 25 | WP25 | Contractor Due Diligence and Appointment | Have cost, programme and compliance implications of similar project experience - programme impact been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | Treasury-style value-for-money principles; funding term sheet; drawdown controls | Yes / No / N/A + Score 0–5 + Rating
25.088 | 25 | WP25 | Contractor Due Diligence and Appointment | Has the team obtained written confirmation or documented proof for HSE record - programme impact? | Current certificate/letter/report, version control and document-control entry. | IFRS/IFRS for SMEs principles; lender due diligence checklist; signed financial model | Yes / No / N/A + Score 0–5 + Rating
25.089 | 25 | WP25 | Contractor Due Diligence and Appointment | Does the evidence for quality systems - programme impact support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | CIDB/procurement best practice; cost plan; QS measurement and BOQ controls | Yes / No / N/A + Score 0–5 + Rating
25.090 | 25 | WP25 | Contractor Due Diligence and Appointment | Have dependencies linked to programme credibility - programme impact been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | Treasury-style value-for-money principles; funding term sheet; drawdown controls | Yes / No / N/A + Score 0–5 + Rating
25.091 | 25 | WP25 | Contractor Due Diligence and Appointment | Has the project team confirmed contractor capacity - risk mitigation in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | IFRS/IFRS for SMEs principles; lender due diligence checklist; signed financial model | Yes / No / N/A + Score 0–5 + Rating
25.092 | 25 | WP25 | Contractor Due Diligence and Appointment | Is there a responsible owner, due date and approval route for financial strength - risk mitigation? | Register entry, supporting drawing/report, approval note and updated risk item. | CIDB/procurement best practice; cost plan; QS measurement and BOQ controls | Yes / No / N/A + Score 0–5 + Rating
25.093 | 25 | WP25 | Contractor Due Diligence and Appointment | Has the gate file tested whether similar project experience - risk mitigation creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | Treasury-style value-for-money principles; funding term sheet; drawdown controls | Yes / No / N/A + Score 0–5 + Rating
25.094 | 25 | WP25 | Contractor Due Diligence and Appointment | Are assumptions for HSE record - risk mitigation documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | IFRS/IFRS for SMEs principles; lender due diligence checklist; signed financial model | Yes / No / N/A + Score 0–5 + Rating
25.095 | 25 | WP25 | Contractor Due Diligence and Appointment | Has the relevant authority, specialist or professional adviser reviewed quality systems - risk mitigation where required? | Authority response, compliance checklist, file note and management approval. | CIDB/procurement best practice; cost plan; QS measurement and BOQ controls | Yes / No / N/A + Score 0–5 + Rating
25.096 | 25 | WP25 | Contractor Due Diligence and Appointment | Is the decision record for programme credibility - risk mitigation aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | Treasury-style value-for-money principles; funding term sheet; drawdown controls | Yes / No / N/A + Score 0–5 + Rating
25.097 | 25 | WP25 | Contractor Due Diligence and Appointment | Have cost, programme and compliance implications of contractor capacity - stakeholder acceptance been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | IFRS/IFRS for SMEs principles; lender due diligence checklist; signed financial model | Yes / No / N/A + Score 0–5 + Rating
25.098 | 25 | WP25 | Contractor Due Diligence and Appointment | Has the team obtained written confirmation or documented proof for financial strength - stakeholder acceptance? | Current certificate/letter/report, version control and document-control entry. | CIDB/procurement best practice; cost plan; QS measurement and BOQ controls | Yes / No / N/A + Score 0–5 + Rating
25.099 | 25 | WP25 | Contractor Due Diligence and Appointment | Does the evidence for similar project experience - stakeholder acceptance support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | Treasury-style value-for-money principles; funding term sheet; drawdown controls | Yes / No / N/A + Score 0–5 + Rating
25.100 | 25 | WP25 | Contractor Due Diligence and Appointment | Have dependencies linked to HSE record - stakeholder acceptance been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | IFRS/IFRS for SMEs principles; lender due diligence checklist; signed financial model | Yes / No / N/A + Score 0–5 + Rating
26.001 | 26 | WP26 | Regulatory Permitting and Building Plan Approval | Has the project team confirmed building plans - governance approval in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
26.002 | 26 | WP26 | Regulatory Permitting and Building Plan Approval | Is there a responsible owner, due date and approval route for fire approval - governance approval? | Register entry, supporting drawing/report, approval note and updated risk item. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
26.003 | 26 | WP26 | Regulatory Permitting and Building Plan Approval | Has the gate file tested whether health approval - governance approval creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
26.004 | 26 | WP26 | Regulatory Permitting and Building Plan Approval | Are assumptions for road access approval - governance approval documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
26.005 | 26 | WP26 | Regulatory Permitting and Building Plan Approval | Has the relevant authority, specialist or professional adviser reviewed water connection - governance approval where required? | Authority response, compliance checklist, file note and management approval. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
26.006 | 26 | WP26 | Regulatory Permitting and Building Plan Approval | Is the decision record for sewer connection - governance approval aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
26.007 | 26 | WP26 | Regulatory Permitting and Building Plan Approval | Have cost, programme and compliance implications of building plans - legal authority been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
26.008 | 26 | WP26 | Regulatory Permitting and Building Plan Approval | Has the team obtained written confirmation or documented proof for fire approval - legal authority? | Current certificate/letter/report, version control and document-control entry. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
26.009 | 26 | WP26 | Regulatory Permitting and Building Plan Approval | Does the evidence for health approval - legal authority support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
26.010 | 26 | WP26 | Regulatory Permitting and Building Plan Approval | Have dependencies linked to road access approval - legal authority been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
26.011 | 26 | WP26 | Regulatory Permitting and Building Plan Approval | Has the project team confirmed water connection - legal authority in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
26.012 | 26 | WP26 | Regulatory Permitting and Building Plan Approval | Is there a responsible owner, due date and approval route for sewer connection - legal authority? | Register entry, supporting drawing/report, approval note and updated risk item. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
26.013 | 26 | WP26 | Regulatory Permitting and Building Plan Approval | Has the gate file tested whether building plans - technical feasibility creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
26.014 | 26 | WP26 | Regulatory Permitting and Building Plan Approval | Are assumptions for fire approval - technical feasibility documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
26.015 | 26 | WP26 | Regulatory Permitting and Building Plan Approval | Has the relevant authority, specialist or professional adviser reviewed health approval - technical feasibility where required? | Authority response, compliance checklist, file note and management approval. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
26.016 | 26 | WP26 | Regulatory Permitting and Building Plan Approval | Is the decision record for road access approval - technical feasibility aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
26.017 | 26 | WP26 | Regulatory Permitting and Building Plan Approval | Have cost, programme and compliance implications of water connection - technical feasibility been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
26.018 | 26 | WP26 | Regulatory Permitting and Building Plan Approval | Has the team obtained written confirmation or documented proof for sewer connection - technical feasibility? | Current certificate/letter/report, version control and document-control entry. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
26.019 | 26 | WP26 | Regulatory Permitting and Building Plan Approval | Does the evidence for building plans - financial viability support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
26.020 | 26 | WP26 | Regulatory Permitting and Building Plan Approval | Have dependencies linked to fire approval - financial viability been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
26.021 | 26 | WP26 | Regulatory Permitting and Building Plan Approval | Has the project team confirmed health approval - financial viability in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
26.022 | 26 | WP26 | Regulatory Permitting and Building Plan Approval | Is there a responsible owner, due date and approval route for road access approval - financial viability? | Register entry, supporting drawing/report, approval note and updated risk item. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
26.023 | 26 | WP26 | Regulatory Permitting and Building Plan Approval | Has the gate file tested whether water connection - financial viability creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
26.024 | 26 | WP26 | Regulatory Permitting and Building Plan Approval | Are assumptions for sewer connection - financial viability documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
26.025 | 26 | WP26 | Regulatory Permitting and Building Plan Approval | Has the relevant authority, specialist or professional adviser reviewed building plans - programme impact where required? | Authority response, compliance checklist, file note and management approval. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
26.026 | 26 | WP26 | Regulatory Permitting and Building Plan Approval | Is the decision record for fire approval - programme impact aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
26.027 | 26 | WP26 | Regulatory Permitting and Building Plan Approval | Have cost, programme and compliance implications of health approval - programme impact been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
26.028 | 26 | WP26 | Regulatory Permitting and Building Plan Approval | Has the team obtained written confirmation or documented proof for road access approval - programme impact? | Current certificate/letter/report, version control and document-control entry. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
26.029 | 26 | WP26 | Regulatory Permitting and Building Plan Approval | Does the evidence for water connection - programme impact support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
26.030 | 26 | WP26 | Regulatory Permitting and Building Plan Approval | Have dependencies linked to sewer connection - programme impact been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
26.031 | 26 | WP26 | Regulatory Permitting and Building Plan Approval | Has the project team confirmed building plans - risk mitigation in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
26.032 | 26 | WP26 | Regulatory Permitting and Building Plan Approval | Is there a responsible owner, due date and approval route for fire approval - risk mitigation? | Register entry, supporting drawing/report, approval note and updated risk item. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
26.033 | 26 | WP26 | Regulatory Permitting and Building Plan Approval | Has the gate file tested whether health approval - risk mitigation creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
26.034 | 26 | WP26 | Regulatory Permitting and Building Plan Approval | Are assumptions for road access approval - risk mitigation documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
26.035 | 26 | WP26 | Regulatory Permitting and Building Plan Approval | Has the relevant authority, specialist or professional adviser reviewed water connection - risk mitigation where required? | Authority response, compliance checklist, file note and management approval. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
26.036 | 26 | WP26 | Regulatory Permitting and Building Plan Approval | Is the decision record for sewer connection - risk mitigation aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
26.037 | 26 | WP26 | Regulatory Permitting and Building Plan Approval | Have cost, programme and compliance implications of building plans - stakeholder acceptance been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
26.038 | 26 | WP26 | Regulatory Permitting and Building Plan Approval | Has the team obtained written confirmation or documented proof for fire approval - stakeholder acceptance? | Current certificate/letter/report, version control and document-control entry. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
26.039 | 26 | WP26 | Regulatory Permitting and Building Plan Approval | Does the evidence for health approval - stakeholder acceptance support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
26.040 | 26 | WP26 | Regulatory Permitting and Building Plan Approval | Have dependencies linked to road access approval - stakeholder acceptance been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
26.041 | 26 | WP26 | Regulatory Permitting and Building Plan Approval | Has the project team confirmed water connection - stakeholder acceptance in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
26.042 | 26 | WP26 | Regulatory Permitting and Building Plan Approval | Is there a responsible owner, due date and approval route for sewer connection - stakeholder acceptance? | Register entry, supporting drawing/report, approval note and updated risk item. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
26.043 | 26 | WP26 | Regulatory Permitting and Building Plan Approval | Has the gate file tested whether building plans - document control creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
26.044 | 26 | WP26 | Regulatory Permitting and Building Plan Approval | Are assumptions for fire approval - document control documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
26.045 | 26 | WP26 | Regulatory Permitting and Building Plan Approval | Has the relevant authority, specialist or professional adviser reviewed health approval - document control where required? | Authority response, compliance checklist, file note and management approval. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
26.046 | 26 | WP26 | Regulatory Permitting and Building Plan Approval | Is the decision record for road access approval - document control aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
26.047 | 26 | WP26 | Regulatory Permitting and Building Plan Approval | Have cost, programme and compliance implications of water connection - document control been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
26.048 | 26 | WP26 | Regulatory Permitting and Building Plan Approval | Has the team obtained written confirmation or documented proof for sewer connection - document control? | Current certificate/letter/report, version control and document-control entry. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
26.049 | 26 | WP26 | Regulatory Permitting and Building Plan Approval | Does the evidence for building plans - professional certification support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
26.050 | 26 | WP26 | Regulatory Permitting and Building Plan Approval | Have dependencies linked to fire approval - professional certification been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
26.051 | 26 | WP26 | Regulatory Permitting and Building Plan Approval | Has the project team confirmed health approval - professional certification in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
26.052 | 26 | WP26 | Regulatory Permitting and Building Plan Approval | Is there a responsible owner, due date and approval route for road access approval - professional certification? | Register entry, supporting drawing/report, approval note and updated risk item. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
26.053 | 26 | WP26 | Regulatory Permitting and Building Plan Approval | Has the gate file tested whether water connection - professional certification creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
26.054 | 26 | WP26 | Regulatory Permitting and Building Plan Approval | Are assumptions for sewer connection - professional certification documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
26.055 | 26 | WP26 | Regulatory Permitting and Building Plan Approval | Has the relevant authority, specialist or professional adviser reviewed building plans - implementation readiness where required? | Authority response, compliance checklist, file note and management approval. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
26.056 | 26 | WP26 | Regulatory Permitting and Building Plan Approval | Is the decision record for fire approval - implementation readiness aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
26.057 | 26 | WP26 | Regulatory Permitting and Building Plan Approval | Have cost, programme and compliance implications of health approval - implementation readiness been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
26.058 | 26 | WP26 | Regulatory Permitting and Building Plan Approval | Has the team obtained written confirmation or documented proof for road access approval - implementation readiness? | Current certificate/letter/report, version control and document-control entry. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
26.059 | 26 | WP26 | Regulatory Permitting and Building Plan Approval | Does the evidence for water connection - implementation readiness support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
26.060 | 26 | WP26 | Regulatory Permitting and Building Plan Approval | Have dependencies linked to sewer connection - implementation readiness been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
26.061 | 26 | WP26 | Regulatory Permitting and Building Plan Approval | Has the project team confirmed building plans - governance approval in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
26.062 | 26 | WP26 | Regulatory Permitting and Building Plan Approval | Is there a responsible owner, due date and approval route for fire approval - governance approval? | Register entry, supporting drawing/report, approval note and updated risk item. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
26.063 | 26 | WP26 | Regulatory Permitting and Building Plan Approval | Has the gate file tested whether health approval - governance approval creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
26.064 | 26 | WP26 | Regulatory Permitting and Building Plan Approval | Are assumptions for road access approval - governance approval documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
26.065 | 26 | WP26 | Regulatory Permitting and Building Plan Approval | Has the relevant authority, specialist or professional adviser reviewed water connection - governance approval where required? | Authority response, compliance checklist, file note and management approval. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
26.066 | 26 | WP26 | Regulatory Permitting and Building Plan Approval | Is the decision record for sewer connection - governance approval aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
26.067 | 26 | WP26 | Regulatory Permitting and Building Plan Approval | Have cost, programme and compliance implications of building plans - legal authority been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
26.068 | 26 | WP26 | Regulatory Permitting and Building Plan Approval | Has the team obtained written confirmation or documented proof for fire approval - legal authority? | Current certificate/letter/report, version control and document-control entry. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
26.069 | 26 | WP26 | Regulatory Permitting and Building Plan Approval | Does the evidence for health approval - legal authority support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
26.070 | 26 | WP26 | Regulatory Permitting and Building Plan Approval | Have dependencies linked to road access approval - legal authority been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
26.071 | 26 | WP26 | Regulatory Permitting and Building Plan Approval | Has the project team confirmed water connection - legal authority in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
26.072 | 26 | WP26 | Regulatory Permitting and Building Plan Approval | Is there a responsible owner, due date and approval route for sewer connection - legal authority? | Register entry, supporting drawing/report, approval note and updated risk item. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
26.073 | 26 | WP26 | Regulatory Permitting and Building Plan Approval | Has the gate file tested whether building plans - technical feasibility creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
26.074 | 26 | WP26 | Regulatory Permitting and Building Plan Approval | Are assumptions for fire approval - technical feasibility documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
26.075 | 26 | WP26 | Regulatory Permitting and Building Plan Approval | Has the relevant authority, specialist or professional adviser reviewed health approval - technical feasibility where required? | Authority response, compliance checklist, file note and management approval. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
26.076 | 26 | WP26 | Regulatory Permitting and Building Plan Approval | Is the decision record for road access approval - technical feasibility aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
26.077 | 26 | WP26 | Regulatory Permitting and Building Plan Approval | Have cost, programme and compliance implications of water connection - technical feasibility been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
26.078 | 26 | WP26 | Regulatory Permitting and Building Plan Approval | Has the team obtained written confirmation or documented proof for sewer connection - technical feasibility? | Current certificate/letter/report, version control and document-control entry. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
26.079 | 26 | WP26 | Regulatory Permitting and Building Plan Approval | Does the evidence for building plans - financial viability support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
26.080 | 26 | WP26 | Regulatory Permitting and Building Plan Approval | Have dependencies linked to fire approval - financial viability been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
26.081 | 26 | WP26 | Regulatory Permitting and Building Plan Approval | Has the project team confirmed health approval - financial viability in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
26.082 | 26 | WP26 | Regulatory Permitting and Building Plan Approval | Is there a responsible owner, due date and approval route for road access approval - financial viability? | Register entry, supporting drawing/report, approval note and updated risk item. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
26.083 | 26 | WP26 | Regulatory Permitting and Building Plan Approval | Has the gate file tested whether water connection - financial viability creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
26.084 | 26 | WP26 | Regulatory Permitting and Building Plan Approval | Are assumptions for sewer connection - financial viability documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
26.085 | 26 | WP26 | Regulatory Permitting and Building Plan Approval | Has the relevant authority, specialist or professional adviser reviewed building plans - programme impact where required? | Authority response, compliance checklist, file note and management approval. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
26.086 | 26 | WP26 | Regulatory Permitting and Building Plan Approval | Is the decision record for fire approval - programme impact aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
26.087 | 26 | WP26 | Regulatory Permitting and Building Plan Approval | Have cost, programme and compliance implications of health approval - programme impact been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
26.088 | 26 | WP26 | Regulatory Permitting and Building Plan Approval | Has the team obtained written confirmation or documented proof for road access approval - programme impact? | Current certificate/letter/report, version control and document-control entry. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
26.089 | 26 | WP26 | Regulatory Permitting and Building Plan Approval | Does the evidence for water connection - programme impact support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
26.090 | 26 | WP26 | Regulatory Permitting and Building Plan Approval | Have dependencies linked to sewer connection - programme impact been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
26.091 | 26 | WP26 | Regulatory Permitting and Building Plan Approval | Has the project team confirmed building plans - risk mitigation in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
26.092 | 26 | WP26 | Regulatory Permitting and Building Plan Approval | Is there a responsible owner, due date and approval route for fire approval - risk mitigation? | Register entry, supporting drawing/report, approval note and updated risk item. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
26.093 | 26 | WP26 | Regulatory Permitting and Building Plan Approval | Has the gate file tested whether health approval - risk mitigation creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
26.094 | 26 | WP26 | Regulatory Permitting and Building Plan Approval | Are assumptions for road access approval - risk mitigation documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
26.095 | 26 | WP26 | Regulatory Permitting and Building Plan Approval | Has the relevant authority, specialist or professional adviser reviewed water connection - risk mitigation where required? | Authority response, compliance checklist, file note and management approval. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
26.096 | 26 | WP26 | Regulatory Permitting and Building Plan Approval | Is the decision record for sewer connection - risk mitigation aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
26.097 | 26 | WP26 | Regulatory Permitting and Building Plan Approval | Have cost, programme and compliance implications of building plans - stakeholder acceptance been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
26.098 | 26 | WP26 | Regulatory Permitting and Building Plan Approval | Has the team obtained written confirmation or documented proof for fire approval - stakeholder acceptance? | Current certificate/letter/report, version control and document-control entry. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
26.099 | 26 | WP26 | Regulatory Permitting and Building Plan Approval | Does the evidence for health approval - stakeholder acceptance support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
26.100 | 26 | WP26 | Regulatory Permitting and Building Plan Approval | Have dependencies linked to road access approval - stakeholder acceptance been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
27.001 | 27 | WP27 | Construction Mobilisation | Has the project team confirmed site handover - governance approval in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | OHS Act 85 of 1993; Construction Regulations, 2014; HSE file | Yes / No / N/A + Score 0–5 + Rating
27.002 | 27 | WP27 | Construction Mobilisation | Is there a responsible owner, due date and approval route for site camp - governance approval? | Register entry, supporting drawing/report, approval note and updated risk item. | JBCC/NEC/FIDIC contract conditions; QA/QC inspection and test plans | Yes / No / N/A + Score 0–5 + Rating
27.003 | 27 | WP27 | Construction Mobilisation | Has the gate file tested whether survey setting out - governance approval creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | NEMA EMPr; municipal inspections; material approvals and payment certification | Yes / No / N/A + Score 0–5 + Rating
27.004 | 27 | WP27 | Construction Mobilisation | Are assumptions for HSE file - governance approval documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | OHS Act 85 of 1993; Construction Regulations, 2014; HSE file | Yes / No / N/A + Score 0–5 + Rating
27.005 | 27 | WP27 | Construction Mobilisation | Has the relevant authority, specialist or professional adviser reviewed environmental controls - governance approval where required? | Authority response, compliance checklist, file note and management approval. | JBCC/NEC/FIDIC contract conditions; QA/QC inspection and test plans | Yes / No / N/A + Score 0–5 + Rating
27.006 | 27 | WP27 | Construction Mobilisation | Is the decision record for baseline programme - governance approval aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | NEMA EMPr; municipal inspections; material approvals and payment certification | Yes / No / N/A + Score 0–5 + Rating
27.007 | 27 | WP27 | Construction Mobilisation | Have cost, programme and compliance implications of site handover - legal authority been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | OHS Act 85 of 1993; Construction Regulations, 2014; HSE file | Yes / No / N/A + Score 0–5 + Rating
27.008 | 27 | WP27 | Construction Mobilisation | Has the team obtained written confirmation or documented proof for site camp - legal authority? | Current certificate/letter/report, version control and document-control entry. | JBCC/NEC/FIDIC contract conditions; QA/QC inspection and test plans | Yes / No / N/A + Score 0–5 + Rating
27.009 | 27 | WP27 | Construction Mobilisation | Does the evidence for survey setting out - legal authority support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | NEMA EMPr; municipal inspections; material approvals and payment certification | Yes / No / N/A + Score 0–5 + Rating
27.010 | 27 | WP27 | Construction Mobilisation | Have dependencies linked to HSE file - legal authority been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | OHS Act 85 of 1993; Construction Regulations, 2014; HSE file | Yes / No / N/A + Score 0–5 + Rating
27.011 | 27 | WP27 | Construction Mobilisation | Has the project team confirmed environmental controls - legal authority in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | JBCC/NEC/FIDIC contract conditions; QA/QC inspection and test plans | Yes / No / N/A + Score 0–5 + Rating
27.012 | 27 | WP27 | Construction Mobilisation | Is there a responsible owner, due date and approval route for baseline programme - legal authority? | Register entry, supporting drawing/report, approval note and updated risk item. | NEMA EMPr; municipal inspections; material approvals and payment certification | Yes / No / N/A + Score 0–5 + Rating
27.013 | 27 | WP27 | Construction Mobilisation | Has the gate file tested whether site handover - technical feasibility creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | OHS Act 85 of 1993; Construction Regulations, 2014; HSE file | Yes / No / N/A + Score 0–5 + Rating
27.014 | 27 | WP27 | Construction Mobilisation | Are assumptions for site camp - technical feasibility documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | JBCC/NEC/FIDIC contract conditions; QA/QC inspection and test plans | Yes / No / N/A + Score 0–5 + Rating
27.015 | 27 | WP27 | Construction Mobilisation | Has the relevant authority, specialist or professional adviser reviewed survey setting out - technical feasibility where required? | Authority response, compliance checklist, file note and management approval. | NEMA EMPr; municipal inspections; material approvals and payment certification | Yes / No / N/A + Score 0–5 + Rating
27.016 | 27 | WP27 | Construction Mobilisation | Is the decision record for HSE file - technical feasibility aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | OHS Act 85 of 1993; Construction Regulations, 2014; HSE file | Yes / No / N/A + Score 0–5 + Rating
27.017 | 27 | WP27 | Construction Mobilisation | Have cost, programme and compliance implications of environmental controls - technical feasibility been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | JBCC/NEC/FIDIC contract conditions; QA/QC inspection and test plans | Yes / No / N/A + Score 0–5 + Rating
27.018 | 27 | WP27 | Construction Mobilisation | Has the team obtained written confirmation or documented proof for baseline programme - technical feasibility? | Current certificate/letter/report, version control and document-control entry. | NEMA EMPr; municipal inspections; material approvals and payment certification | Yes / No / N/A + Score 0–5 + Rating
27.019 | 27 | WP27 | Construction Mobilisation | Does the evidence for site handover - financial viability support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | OHS Act 85 of 1993; Construction Regulations, 2014; HSE file | Yes / No / N/A + Score 0–5 + Rating
27.020 | 27 | WP27 | Construction Mobilisation | Have dependencies linked to site camp - financial viability been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | JBCC/NEC/FIDIC contract conditions; QA/QC inspection and test plans | Yes / No / N/A + Score 0–5 + Rating
27.021 | 27 | WP27 | Construction Mobilisation | Has the project team confirmed survey setting out - financial viability in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | NEMA EMPr; municipal inspections; material approvals and payment certification | Yes / No / N/A + Score 0–5 + Rating
27.022 | 27 | WP27 | Construction Mobilisation | Is there a responsible owner, due date and approval route for HSE file - financial viability? | Register entry, supporting drawing/report, approval note and updated risk item. | OHS Act 85 of 1993; Construction Regulations, 2014; HSE file | Yes / No / N/A + Score 0–5 + Rating
27.023 | 27 | WP27 | Construction Mobilisation | Has the gate file tested whether environmental controls - financial viability creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | JBCC/NEC/FIDIC contract conditions; QA/QC inspection and test plans | Yes / No / N/A + Score 0–5 + Rating
27.024 | 27 | WP27 | Construction Mobilisation | Are assumptions for baseline programme - financial viability documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | NEMA EMPr; municipal inspections; material approvals and payment certification | Yes / No / N/A + Score 0–5 + Rating
27.025 | 27 | WP27 | Construction Mobilisation | Has the relevant authority, specialist or professional adviser reviewed site handover - programme impact where required? | Authority response, compliance checklist, file note and management approval. | OHS Act 85 of 1993; Construction Regulations, 2014; HSE file | Yes / No / N/A + Score 0–5 + Rating
27.026 | 27 | WP27 | Construction Mobilisation | Is the decision record for site camp - programme impact aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | JBCC/NEC/FIDIC contract conditions; QA/QC inspection and test plans | Yes / No / N/A + Score 0–5 + Rating
27.027 | 27 | WP27 | Construction Mobilisation | Have cost, programme and compliance implications of survey setting out - programme impact been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | NEMA EMPr; municipal inspections; material approvals and payment certification | Yes / No / N/A + Score 0–5 + Rating
27.028 | 27 | WP27 | Construction Mobilisation | Has the team obtained written confirmation or documented proof for HSE file - programme impact? | Current certificate/letter/report, version control and document-control entry. | OHS Act 85 of 1993; Construction Regulations, 2014; HSE file | Yes / No / N/A + Score 0–5 + Rating
27.029 | 27 | WP27 | Construction Mobilisation | Does the evidence for environmental controls - programme impact support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | JBCC/NEC/FIDIC contract conditions; QA/QC inspection and test plans | Yes / No / N/A + Score 0–5 + Rating
27.030 | 27 | WP27 | Construction Mobilisation | Have dependencies linked to baseline programme - programme impact been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | NEMA EMPr; municipal inspections; material approvals and payment certification | Yes / No / N/A + Score 0–5 + Rating
27.031 | 27 | WP27 | Construction Mobilisation | Has the project team confirmed site handover - risk mitigation in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | OHS Act 85 of 1993; Construction Regulations, 2014; HSE file | Yes / No / N/A + Score 0–5 + Rating
27.032 | 27 | WP27 | Construction Mobilisation | Is there a responsible owner, due date and approval route for site camp - risk mitigation? | Register entry, supporting drawing/report, approval note and updated risk item. | JBCC/NEC/FIDIC contract conditions; QA/QC inspection and test plans | Yes / No / N/A + Score 0–5 + Rating
27.033 | 27 | WP27 | Construction Mobilisation | Has the gate file tested whether survey setting out - risk mitigation creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | NEMA EMPr; municipal inspections; material approvals and payment certification | Yes / No / N/A + Score 0–5 + Rating
27.034 | 27 | WP27 | Construction Mobilisation | Are assumptions for HSE file - risk mitigation documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | OHS Act 85 of 1993; Construction Regulations, 2014; HSE file | Yes / No / N/A + Score 0–5 + Rating
27.035 | 27 | WP27 | Construction Mobilisation | Has the relevant authority, specialist or professional adviser reviewed environmental controls - risk mitigation where required? | Authority response, compliance checklist, file note and management approval. | JBCC/NEC/FIDIC contract conditions; QA/QC inspection and test plans | Yes / No / N/A + Score 0–5 + Rating
27.036 | 27 | WP27 | Construction Mobilisation | Is the decision record for baseline programme - risk mitigation aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | NEMA EMPr; municipal inspections; material approvals and payment certification | Yes / No / N/A + Score 0–5 + Rating
27.037 | 27 | WP27 | Construction Mobilisation | Have cost, programme and compliance implications of site handover - stakeholder acceptance been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | OHS Act 85 of 1993; Construction Regulations, 2014; HSE file | Yes / No / N/A + Score 0–5 + Rating
27.038 | 27 | WP27 | Construction Mobilisation | Has the team obtained written confirmation or documented proof for site camp - stakeholder acceptance? | Current certificate/letter/report, version control and document-control entry. | JBCC/NEC/FIDIC contract conditions; QA/QC inspection and test plans | Yes / No / N/A + Score 0–5 + Rating
27.039 | 27 | WP27 | Construction Mobilisation | Does the evidence for survey setting out - stakeholder acceptance support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | NEMA EMPr; municipal inspections; material approvals and payment certification | Yes / No / N/A + Score 0–5 + Rating
27.040 | 27 | WP27 | Construction Mobilisation | Have dependencies linked to HSE file - stakeholder acceptance been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | OHS Act 85 of 1993; Construction Regulations, 2014; HSE file | Yes / No / N/A + Score 0–5 + Rating
27.041 | 27 | WP27 | Construction Mobilisation | Has the project team confirmed environmental controls - stakeholder acceptance in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | JBCC/NEC/FIDIC contract conditions; QA/QC inspection and test plans | Yes / No / N/A + Score 0–5 + Rating
27.042 | 27 | WP27 | Construction Mobilisation | Is there a responsible owner, due date and approval route for baseline programme - stakeholder acceptance? | Register entry, supporting drawing/report, approval note and updated risk item. | NEMA EMPr; municipal inspections; material approvals and payment certification | Yes / No / N/A + Score 0–5 + Rating
27.043 | 27 | WP27 | Construction Mobilisation | Has the gate file tested whether site handover - document control creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | OHS Act 85 of 1993; Construction Regulations, 2014; HSE file | Yes / No / N/A + Score 0–5 + Rating
27.044 | 27 | WP27 | Construction Mobilisation | Are assumptions for site camp - document control documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | JBCC/NEC/FIDIC contract conditions; QA/QC inspection and test plans | Yes / No / N/A + Score 0–5 + Rating
27.045 | 27 | WP27 | Construction Mobilisation | Has the relevant authority, specialist or professional adviser reviewed survey setting out - document control where required? | Authority response, compliance checklist, file note and management approval. | NEMA EMPr; municipal inspections; material approvals and payment certification | Yes / No / N/A + Score 0–5 + Rating
27.046 | 27 | WP27 | Construction Mobilisation | Is the decision record for HSE file - document control aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | OHS Act 85 of 1993; Construction Regulations, 2014; HSE file | Yes / No / N/A + Score 0–5 + Rating
27.047 | 27 | WP27 | Construction Mobilisation | Have cost, programme and compliance implications of environmental controls - document control been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | JBCC/NEC/FIDIC contract conditions; QA/QC inspection and test plans | Yes / No / N/A + Score 0–5 + Rating
27.048 | 27 | WP27 | Construction Mobilisation | Has the team obtained written confirmation or documented proof for baseline programme - document control? | Current certificate/letter/report, version control and document-control entry. | NEMA EMPr; municipal inspections; material approvals and payment certification | Yes / No / N/A + Score 0–5 + Rating
27.049 | 27 | WP27 | Construction Mobilisation | Does the evidence for site handover - professional certification support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | OHS Act 85 of 1993; Construction Regulations, 2014; HSE file | Yes / No / N/A + Score 0–5 + Rating
27.050 | 27 | WP27 | Construction Mobilisation | Have dependencies linked to site camp - professional certification been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | JBCC/NEC/FIDIC contract conditions; QA/QC inspection and test plans | Yes / No / N/A + Score 0–5 + Rating
27.051 | 27 | WP27 | Construction Mobilisation | Has the project team confirmed survey setting out - professional certification in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | NEMA EMPr; municipal inspections; material approvals and payment certification | Yes / No / N/A + Score 0–5 + Rating
27.052 | 27 | WP27 | Construction Mobilisation | Is there a responsible owner, due date and approval route for HSE file - professional certification? | Register entry, supporting drawing/report, approval note and updated risk item. | OHS Act 85 of 1993; Construction Regulations, 2014; HSE file | Yes / No / N/A + Score 0–5 + Rating
27.053 | 27 | WP27 | Construction Mobilisation | Has the gate file tested whether environmental controls - professional certification creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | JBCC/NEC/FIDIC contract conditions; QA/QC inspection and test plans | Yes / No / N/A + Score 0–5 + Rating
27.054 | 27 | WP27 | Construction Mobilisation | Are assumptions for baseline programme - professional certification documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | NEMA EMPr; municipal inspections; material approvals and payment certification | Yes / No / N/A + Score 0–5 + Rating
27.055 | 27 | WP27 | Construction Mobilisation | Has the relevant authority, specialist or professional adviser reviewed site handover - implementation readiness where required? | Authority response, compliance checklist, file note and management approval. | OHS Act 85 of 1993; Construction Regulations, 2014; HSE file | Yes / No / N/A + Score 0–5 + Rating
27.056 | 27 | WP27 | Construction Mobilisation | Is the decision record for site camp - implementation readiness aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | JBCC/NEC/FIDIC contract conditions; QA/QC inspection and test plans | Yes / No / N/A + Score 0–5 + Rating
27.057 | 27 | WP27 | Construction Mobilisation | Have cost, programme and compliance implications of survey setting out - implementation readiness been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | NEMA EMPr; municipal inspections; material approvals and payment certification | Yes / No / N/A + Score 0–5 + Rating
27.058 | 27 | WP27 | Construction Mobilisation | Has the team obtained written confirmation or documented proof for HSE file - implementation readiness? | Current certificate/letter/report, version control and document-control entry. | OHS Act 85 of 1993; Construction Regulations, 2014; HSE file | Yes / No / N/A + Score 0–5 + Rating
27.059 | 27 | WP27 | Construction Mobilisation | Does the evidence for environmental controls - implementation readiness support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | JBCC/NEC/FIDIC contract conditions; QA/QC inspection and test plans | Yes / No / N/A + Score 0–5 + Rating
27.060 | 27 | WP27 | Construction Mobilisation | Have dependencies linked to baseline programme - implementation readiness been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | NEMA EMPr; municipal inspections; material approvals and payment certification | Yes / No / N/A + Score 0–5 + Rating
27.061 | 27 | WP27 | Construction Mobilisation | Has the project team confirmed site handover - governance approval in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | OHS Act 85 of 1993; Construction Regulations, 2014; HSE file | Yes / No / N/A + Score 0–5 + Rating
27.062 | 27 | WP27 | Construction Mobilisation | Is there a responsible owner, due date and approval route for site camp - governance approval? | Register entry, supporting drawing/report, approval note and updated risk item. | JBCC/NEC/FIDIC contract conditions; QA/QC inspection and test plans | Yes / No / N/A + Score 0–5 + Rating
27.063 | 27 | WP27 | Construction Mobilisation | Has the gate file tested whether survey setting out - governance approval creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | NEMA EMPr; municipal inspections; material approvals and payment certification | Yes / No / N/A + Score 0–5 + Rating
27.064 | 27 | WP27 | Construction Mobilisation | Are assumptions for HSE file - governance approval documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | OHS Act 85 of 1993; Construction Regulations, 2014; HSE file | Yes / No / N/A + Score 0–5 + Rating
27.065 | 27 | WP27 | Construction Mobilisation | Has the relevant authority, specialist or professional adviser reviewed environmental controls - governance approval where required? | Authority response, compliance checklist, file note and management approval. | JBCC/NEC/FIDIC contract conditions; QA/QC inspection and test plans | Yes / No / N/A + Score 0–5 + Rating
27.066 | 27 | WP27 | Construction Mobilisation | Is the decision record for baseline programme - governance approval aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | NEMA EMPr; municipal inspections; material approvals and payment certification | Yes / No / N/A + Score 0–5 + Rating
27.067 | 27 | WP27 | Construction Mobilisation | Have cost, programme and compliance implications of site handover - legal authority been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | OHS Act 85 of 1993; Construction Regulations, 2014; HSE file | Yes / No / N/A + Score 0–5 + Rating
27.068 | 27 | WP27 | Construction Mobilisation | Has the team obtained written confirmation or documented proof for site camp - legal authority? | Current certificate/letter/report, version control and document-control entry. | JBCC/NEC/FIDIC contract conditions; QA/QC inspection and test plans | Yes / No / N/A + Score 0–5 + Rating
27.069 | 27 | WP27 | Construction Mobilisation | Does the evidence for survey setting out - legal authority support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | NEMA EMPr; municipal inspections; material approvals and payment certification | Yes / No / N/A + Score 0–5 + Rating
27.070 | 27 | WP27 | Construction Mobilisation | Have dependencies linked to HSE file - legal authority been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | OHS Act 85 of 1993; Construction Regulations, 2014; HSE file | Yes / No / N/A + Score 0–5 + Rating
27.071 | 27 | WP27 | Construction Mobilisation | Has the project team confirmed environmental controls - legal authority in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | JBCC/NEC/FIDIC contract conditions; QA/QC inspection and test plans | Yes / No / N/A + Score 0–5 + Rating
27.072 | 27 | WP27 | Construction Mobilisation | Is there a responsible owner, due date and approval route for baseline programme - legal authority? | Register entry, supporting drawing/report, approval note and updated risk item. | NEMA EMPr; municipal inspections; material approvals and payment certification | Yes / No / N/A + Score 0–5 + Rating
27.073 | 27 | WP27 | Construction Mobilisation | Has the gate file tested whether site handover - technical feasibility creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | OHS Act 85 of 1993; Construction Regulations, 2014; HSE file | Yes / No / N/A + Score 0–5 + Rating
27.074 | 27 | WP27 | Construction Mobilisation | Are assumptions for site camp - technical feasibility documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | JBCC/NEC/FIDIC contract conditions; QA/QC inspection and test plans | Yes / No / N/A + Score 0–5 + Rating
27.075 | 27 | WP27 | Construction Mobilisation | Has the relevant authority, specialist or professional adviser reviewed survey setting out - technical feasibility where required? | Authority response, compliance checklist, file note and management approval. | NEMA EMPr; municipal inspections; material approvals and payment certification | Yes / No / N/A + Score 0–5 + Rating
27.076 | 27 | WP27 | Construction Mobilisation | Is the decision record for HSE file - technical feasibility aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | OHS Act 85 of 1993; Construction Regulations, 2014; HSE file | Yes / No / N/A + Score 0–5 + Rating
27.077 | 27 | WP27 | Construction Mobilisation | Have cost, programme and compliance implications of environmental controls - technical feasibility been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | JBCC/NEC/FIDIC contract conditions; QA/QC inspection and test plans | Yes / No / N/A + Score 0–5 + Rating
27.078 | 27 | WP27 | Construction Mobilisation | Has the team obtained written confirmation or documented proof for baseline programme - technical feasibility? | Current certificate/letter/report, version control and document-control entry. | NEMA EMPr; municipal inspections; material approvals and payment certification | Yes / No / N/A + Score 0–5 + Rating
27.079 | 27 | WP27 | Construction Mobilisation | Does the evidence for site handover - financial viability support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | OHS Act 85 of 1993; Construction Regulations, 2014; HSE file | Yes / No / N/A + Score 0–5 + Rating
27.080 | 27 | WP27 | Construction Mobilisation | Have dependencies linked to site camp - financial viability been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | JBCC/NEC/FIDIC contract conditions; QA/QC inspection and test plans | Yes / No / N/A + Score 0–5 + Rating
27.081 | 27 | WP27 | Construction Mobilisation | Has the project team confirmed survey setting out - financial viability in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | NEMA EMPr; municipal inspections; material approvals and payment certification | Yes / No / N/A + Score 0–5 + Rating
27.082 | 27 | WP27 | Construction Mobilisation | Is there a responsible owner, due date and approval route for HSE file - financial viability? | Register entry, supporting drawing/report, approval note and updated risk item. | OHS Act 85 of 1993; Construction Regulations, 2014; HSE file | Yes / No / N/A + Score 0–5 + Rating
27.083 | 27 | WP27 | Construction Mobilisation | Has the gate file tested whether environmental controls - financial viability creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | JBCC/NEC/FIDIC contract conditions; QA/QC inspection and test plans | Yes / No / N/A + Score 0–5 + Rating
27.084 | 27 | WP27 | Construction Mobilisation | Are assumptions for baseline programme - financial viability documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | NEMA EMPr; municipal inspections; material approvals and payment certification | Yes / No / N/A + Score 0–5 + Rating
27.085 | 27 | WP27 | Construction Mobilisation | Has the relevant authority, specialist or professional adviser reviewed site handover - programme impact where required? | Authority response, compliance checklist, file note and management approval. | OHS Act 85 of 1993; Construction Regulations, 2014; HSE file | Yes / No / N/A + Score 0–5 + Rating
27.086 | 27 | WP27 | Construction Mobilisation | Is the decision record for site camp - programme impact aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | JBCC/NEC/FIDIC contract conditions; QA/QC inspection and test plans | Yes / No / N/A + Score 0–5 + Rating
27.087 | 27 | WP27 | Construction Mobilisation | Have cost, programme and compliance implications of survey setting out - programme impact been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | NEMA EMPr; municipal inspections; material approvals and payment certification | Yes / No / N/A + Score 0–5 + Rating
27.088 | 27 | WP27 | Construction Mobilisation | Has the team obtained written confirmation or documented proof for HSE file - programme impact? | Current certificate/letter/report, version control and document-control entry. | OHS Act 85 of 1993; Construction Regulations, 2014; HSE file | Yes / No / N/A + Score 0–5 + Rating
27.089 | 27 | WP27 | Construction Mobilisation | Does the evidence for environmental controls - programme impact support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | JBCC/NEC/FIDIC contract conditions; QA/QC inspection and test plans | Yes / No / N/A + Score 0–5 + Rating
27.090 | 27 | WP27 | Construction Mobilisation | Have dependencies linked to baseline programme - programme impact been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | NEMA EMPr; municipal inspections; material approvals and payment certification | Yes / No / N/A + Score 0–5 + Rating
27.091 | 27 | WP27 | Construction Mobilisation | Has the project team confirmed site handover - risk mitigation in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | OHS Act 85 of 1993; Construction Regulations, 2014; HSE file | Yes / No / N/A + Score 0–5 + Rating
27.092 | 27 | WP27 | Construction Mobilisation | Is there a responsible owner, due date and approval route for site camp - risk mitigation? | Register entry, supporting drawing/report, approval note and updated risk item. | JBCC/NEC/FIDIC contract conditions; QA/QC inspection and test plans | Yes / No / N/A + Score 0–5 + Rating
27.093 | 27 | WP27 | Construction Mobilisation | Has the gate file tested whether survey setting out - risk mitigation creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | NEMA EMPr; municipal inspections; material approvals and payment certification | Yes / No / N/A + Score 0–5 + Rating
27.094 | 27 | WP27 | Construction Mobilisation | Are assumptions for HSE file - risk mitigation documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | OHS Act 85 of 1993; Construction Regulations, 2014; HSE file | Yes / No / N/A + Score 0–5 + Rating
27.095 | 27 | WP27 | Construction Mobilisation | Has the relevant authority, specialist or professional adviser reviewed environmental controls - risk mitigation where required? | Authority response, compliance checklist, file note and management approval. | JBCC/NEC/FIDIC contract conditions; QA/QC inspection and test plans | Yes / No / N/A + Score 0–5 + Rating
27.096 | 27 | WP27 | Construction Mobilisation | Is the decision record for baseline programme - risk mitigation aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | NEMA EMPr; municipal inspections; material approvals and payment certification | Yes / No / N/A + Score 0–5 + Rating
27.097 | 27 | WP27 | Construction Mobilisation | Have cost, programme and compliance implications of site handover - stakeholder acceptance been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | OHS Act 85 of 1993; Construction Regulations, 2014; HSE file | Yes / No / N/A + Score 0–5 + Rating
27.098 | 27 | WP27 | Construction Mobilisation | Has the team obtained written confirmation or documented proof for site camp - stakeholder acceptance? | Current certificate/letter/report, version control and document-control entry. | JBCC/NEC/FIDIC contract conditions; QA/QC inspection and test plans | Yes / No / N/A + Score 0–5 + Rating
27.099 | 27 | WP27 | Construction Mobilisation | Does the evidence for survey setting out - stakeholder acceptance support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | NEMA EMPr; municipal inspections; material approvals and payment certification | Yes / No / N/A + Score 0–5 + Rating
27.100 | 27 | WP27 | Construction Mobilisation | Have dependencies linked to HSE file - stakeholder acceptance been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | OHS Act 85 of 1993; Construction Regulations, 2014; HSE file | Yes / No / N/A + Score 0–5 + Rating
28.001 | 28 | WP28 | Civil Works, Earthworks and Access Construction | Has the project team confirmed clearing and grubbing - governance approval in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | OHS Act 85 of 1993; Construction Regulations, 2014; HSE file | Yes / No / N/A + Score 0–5 + Rating
28.002 | 28 | WP28 | Civil Works, Earthworks and Access Construction | Is there a responsible owner, due date and approval route for bulk earthworks - governance approval? | Register entry, supporting drawing/report, approval note and updated risk item. | JBCC/NEC/FIDIC contract conditions; QA/QC inspection and test plans | Yes / No / N/A + Score 0–5 + Rating
28.003 | 28 | WP28 | Civil Works, Earthworks and Access Construction | Has the gate file tested whether platforms - governance approval creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | NEMA EMPr; municipal inspections; material approvals and payment certification | Yes / No / N/A + Score 0–5 + Rating
28.004 | 28 | WP28 | Civil Works, Earthworks and Access Construction | Are assumptions for R567 entrance works - governance approval documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | OHS Act 85 of 1993; Construction Regulations, 2014; HSE file | Yes / No / N/A + Score 0–5 + Rating
28.005 | 28 | WP28 | Civil Works, Earthworks and Access Construction | Has the relevant authority, specialist or professional adviser reviewed stormwater structures - governance approval where required? | Authority response, compliance checklist, file note and management approval. | JBCC/NEC/FIDIC contract conditions; QA/QC inspection and test plans | Yes / No / N/A + Score 0–5 + Rating
28.006 | 28 | WP28 | Civil Works, Earthworks and Access Construction | Is the decision record for internal roads - governance approval aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | NEMA EMPr; municipal inspections; material approvals and payment certification | Yes / No / N/A + Score 0–5 + Rating
28.007 | 28 | WP28 | Civil Works, Earthworks and Access Construction | Have cost, programme and compliance implications of clearing and grubbing - legal authority been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | OHS Act 85 of 1993; Construction Regulations, 2014; HSE file | Yes / No / N/A + Score 0–5 + Rating
28.008 | 28 | WP28 | Civil Works, Earthworks and Access Construction | Has the team obtained written confirmation or documented proof for bulk earthworks - legal authority? | Current certificate/letter/report, version control and document-control entry. | JBCC/NEC/FIDIC contract conditions; QA/QC inspection and test plans | Yes / No / N/A + Score 0–5 + Rating
28.009 | 28 | WP28 | Civil Works, Earthworks and Access Construction | Does the evidence for platforms - legal authority support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | NEMA EMPr; municipal inspections; material approvals and payment certification | Yes / No / N/A + Score 0–5 + Rating
28.010 | 28 | WP28 | Civil Works, Earthworks and Access Construction | Have dependencies linked to R567 entrance works - legal authority been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | OHS Act 85 of 1993; Construction Regulations, 2014; HSE file | Yes / No / N/A + Score 0–5 + Rating
28.011 | 28 | WP28 | Civil Works, Earthworks and Access Construction | Has the project team confirmed stormwater structures - legal authority in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | JBCC/NEC/FIDIC contract conditions; QA/QC inspection and test plans | Yes / No / N/A + Score 0–5 + Rating
28.012 | 28 | WP28 | Civil Works, Earthworks and Access Construction | Is there a responsible owner, due date and approval route for internal roads - legal authority? | Register entry, supporting drawing/report, approval note and updated risk item. | NEMA EMPr; municipal inspections; material approvals and payment certification | Yes / No / N/A + Score 0–5 + Rating
28.013 | 28 | WP28 | Civil Works, Earthworks and Access Construction | Has the gate file tested whether clearing and grubbing - technical feasibility creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | OHS Act 85 of 1993; Construction Regulations, 2014; HSE file | Yes / No / N/A + Score 0–5 + Rating
28.014 | 28 | WP28 | Civil Works, Earthworks and Access Construction | Are assumptions for bulk earthworks - technical feasibility documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | JBCC/NEC/FIDIC contract conditions; QA/QC inspection and test plans | Yes / No / N/A + Score 0–5 + Rating
28.015 | 28 | WP28 | Civil Works, Earthworks and Access Construction | Has the relevant authority, specialist or professional adviser reviewed platforms - technical feasibility where required? | Authority response, compliance checklist, file note and management approval. | NEMA EMPr; municipal inspections; material approvals and payment certification | Yes / No / N/A + Score 0–5 + Rating
28.016 | 28 | WP28 | Civil Works, Earthworks and Access Construction | Is the decision record for R567 entrance works - technical feasibility aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | OHS Act 85 of 1993; Construction Regulations, 2014; HSE file | Yes / No / N/A + Score 0–5 + Rating
28.017 | 28 | WP28 | Civil Works, Earthworks and Access Construction | Have cost, programme and compliance implications of stormwater structures - technical feasibility been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | JBCC/NEC/FIDIC contract conditions; QA/QC inspection and test plans | Yes / No / N/A + Score 0–5 + Rating
28.018 | 28 | WP28 | Civil Works, Earthworks and Access Construction | Has the team obtained written confirmation or documented proof for internal roads - technical feasibility? | Current certificate/letter/report, version control and document-control entry. | NEMA EMPr; municipal inspections; material approvals and payment certification | Yes / No / N/A + Score 0–5 + Rating
28.019 | 28 | WP28 | Civil Works, Earthworks and Access Construction | Does the evidence for clearing and grubbing - financial viability support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | OHS Act 85 of 1993; Construction Regulations, 2014; HSE file | Yes / No / N/A + Score 0–5 + Rating
28.020 | 28 | WP28 | Civil Works, Earthworks and Access Construction | Have dependencies linked to bulk earthworks - financial viability been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | JBCC/NEC/FIDIC contract conditions; QA/QC inspection and test plans | Yes / No / N/A + Score 0–5 + Rating
28.021 | 28 | WP28 | Civil Works, Earthworks and Access Construction | Has the project team confirmed platforms - financial viability in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | NEMA EMPr; municipal inspections; material approvals and payment certification | Yes / No / N/A + Score 0–5 + Rating
28.022 | 28 | WP28 | Civil Works, Earthworks and Access Construction | Is there a responsible owner, due date and approval route for R567 entrance works - financial viability? | Register entry, supporting drawing/report, approval note and updated risk item. | OHS Act 85 of 1993; Construction Regulations, 2014; HSE file | Yes / No / N/A + Score 0–5 + Rating
28.023 | 28 | WP28 | Civil Works, Earthworks and Access Construction | Has the gate file tested whether stormwater structures - financial viability creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | JBCC/NEC/FIDIC contract conditions; QA/QC inspection and test plans | Yes / No / N/A + Score 0–5 + Rating
28.024 | 28 | WP28 | Civil Works, Earthworks and Access Construction | Are assumptions for internal roads - financial viability documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | NEMA EMPr; municipal inspections; material approvals and payment certification | Yes / No / N/A + Score 0–5 + Rating
28.025 | 28 | WP28 | Civil Works, Earthworks and Access Construction | Has the relevant authority, specialist or professional adviser reviewed clearing and grubbing - programme impact where required? | Authority response, compliance checklist, file note and management approval. | OHS Act 85 of 1993; Construction Regulations, 2014; HSE file | Yes / No / N/A + Score 0–5 + Rating
28.026 | 28 | WP28 | Civil Works, Earthworks and Access Construction | Is the decision record for bulk earthworks - programme impact aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | JBCC/NEC/FIDIC contract conditions; QA/QC inspection and test plans | Yes / No / N/A + Score 0–5 + Rating
28.027 | 28 | WP28 | Civil Works, Earthworks and Access Construction | Have cost, programme and compliance implications of platforms - programme impact been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | NEMA EMPr; municipal inspections; material approvals and payment certification | Yes / No / N/A + Score 0–5 + Rating
28.028 | 28 | WP28 | Civil Works, Earthworks and Access Construction | Has the team obtained written confirmation or documented proof for R567 entrance works - programme impact? | Current certificate/letter/report, version control and document-control entry. | OHS Act 85 of 1993; Construction Regulations, 2014; HSE file | Yes / No / N/A + Score 0–5 + Rating
28.029 | 28 | WP28 | Civil Works, Earthworks and Access Construction | Does the evidence for stormwater structures - programme impact support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | JBCC/NEC/FIDIC contract conditions; QA/QC inspection and test plans | Yes / No / N/A + Score 0–5 + Rating
28.030 | 28 | WP28 | Civil Works, Earthworks and Access Construction | Have dependencies linked to internal roads - programme impact been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | NEMA EMPr; municipal inspections; material approvals and payment certification | Yes / No / N/A + Score 0–5 + Rating
28.031 | 28 | WP28 | Civil Works, Earthworks and Access Construction | Has the project team confirmed clearing and grubbing - risk mitigation in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | OHS Act 85 of 1993; Construction Regulations, 2014; HSE file | Yes / No / N/A + Score 0–5 + Rating
28.032 | 28 | WP28 | Civil Works, Earthworks and Access Construction | Is there a responsible owner, due date and approval route for bulk earthworks - risk mitigation? | Register entry, supporting drawing/report, approval note and updated risk item. | JBCC/NEC/FIDIC contract conditions; QA/QC inspection and test plans | Yes / No / N/A + Score 0–5 + Rating
28.033 | 28 | WP28 | Civil Works, Earthworks and Access Construction | Has the gate file tested whether platforms - risk mitigation creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | NEMA EMPr; municipal inspections; material approvals and payment certification | Yes / No / N/A + Score 0–5 + Rating
28.034 | 28 | WP28 | Civil Works, Earthworks and Access Construction | Are assumptions for R567 entrance works - risk mitigation documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | OHS Act 85 of 1993; Construction Regulations, 2014; HSE file | Yes / No / N/A + Score 0–5 + Rating
28.035 | 28 | WP28 | Civil Works, Earthworks and Access Construction | Has the relevant authority, specialist or professional adviser reviewed stormwater structures - risk mitigation where required? | Authority response, compliance checklist, file note and management approval. | JBCC/NEC/FIDIC contract conditions; QA/QC inspection and test plans | Yes / No / N/A + Score 0–5 + Rating
28.036 | 28 | WP28 | Civil Works, Earthworks and Access Construction | Is the decision record for internal roads - risk mitigation aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | NEMA EMPr; municipal inspections; material approvals and payment certification | Yes / No / N/A + Score 0–5 + Rating
28.037 | 28 | WP28 | Civil Works, Earthworks and Access Construction | Have cost, programme and compliance implications of clearing and grubbing - stakeholder acceptance been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | OHS Act 85 of 1993; Construction Regulations, 2014; HSE file | Yes / No / N/A + Score 0–5 + Rating
28.038 | 28 | WP28 | Civil Works, Earthworks and Access Construction | Has the team obtained written confirmation or documented proof for bulk earthworks - stakeholder acceptance? | Current certificate/letter/report, version control and document-control entry. | JBCC/NEC/FIDIC contract conditions; QA/QC inspection and test plans | Yes / No / N/A + Score 0–5 + Rating
28.039 | 28 | WP28 | Civil Works, Earthworks and Access Construction | Does the evidence for platforms - stakeholder acceptance support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | NEMA EMPr; municipal inspections; material approvals and payment certification | Yes / No / N/A + Score 0–5 + Rating
28.040 | 28 | WP28 | Civil Works, Earthworks and Access Construction | Have dependencies linked to R567 entrance works - stakeholder acceptance been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | OHS Act 85 of 1993; Construction Regulations, 2014; HSE file | Yes / No / N/A + Score 0–5 + Rating
28.041 | 28 | WP28 | Civil Works, Earthworks and Access Construction | Has the project team confirmed stormwater structures - stakeholder acceptance in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | JBCC/NEC/FIDIC contract conditions; QA/QC inspection and test plans | Yes / No / N/A + Score 0–5 + Rating
28.042 | 28 | WP28 | Civil Works, Earthworks and Access Construction | Is there a responsible owner, due date and approval route for internal roads - stakeholder acceptance? | Register entry, supporting drawing/report, approval note and updated risk item. | NEMA EMPr; municipal inspections; material approvals and payment certification | Yes / No / N/A + Score 0–5 + Rating
28.043 | 28 | WP28 | Civil Works, Earthworks and Access Construction | Has the gate file tested whether clearing and grubbing - document control creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | OHS Act 85 of 1993; Construction Regulations, 2014; HSE file | Yes / No / N/A + Score 0–5 + Rating
28.044 | 28 | WP28 | Civil Works, Earthworks and Access Construction | Are assumptions for bulk earthworks - document control documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | JBCC/NEC/FIDIC contract conditions; QA/QC inspection and test plans | Yes / No / N/A + Score 0–5 + Rating
28.045 | 28 | WP28 | Civil Works, Earthworks and Access Construction | Has the relevant authority, specialist or professional adviser reviewed platforms - document control where required? | Authority response, compliance checklist, file note and management approval. | NEMA EMPr; municipal inspections; material approvals and payment certification | Yes / No / N/A + Score 0–5 + Rating
28.046 | 28 | WP28 | Civil Works, Earthworks and Access Construction | Is the decision record for R567 entrance works - document control aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | OHS Act 85 of 1993; Construction Regulations, 2014; HSE file | Yes / No / N/A + Score 0–5 + Rating
28.047 | 28 | WP28 | Civil Works, Earthworks and Access Construction | Have cost, programme and compliance implications of stormwater structures - document control been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | JBCC/NEC/FIDIC contract conditions; QA/QC inspection and test plans | Yes / No / N/A + Score 0–5 + Rating
28.048 | 28 | WP28 | Civil Works, Earthworks and Access Construction | Has the team obtained written confirmation or documented proof for internal roads - document control? | Current certificate/letter/report, version control and document-control entry. | NEMA EMPr; municipal inspections; material approvals and payment certification | Yes / No / N/A + Score 0–5 + Rating
28.049 | 28 | WP28 | Civil Works, Earthworks and Access Construction | Does the evidence for clearing and grubbing - professional certification support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | OHS Act 85 of 1993; Construction Regulations, 2014; HSE file | Yes / No / N/A + Score 0–5 + Rating
28.050 | 28 | WP28 | Civil Works, Earthworks and Access Construction | Have dependencies linked to bulk earthworks - professional certification been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | JBCC/NEC/FIDIC contract conditions; QA/QC inspection and test plans | Yes / No / N/A + Score 0–5 + Rating
28.051 | 28 | WP28 | Civil Works, Earthworks and Access Construction | Has the project team confirmed platforms - professional certification in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | NEMA EMPr; municipal inspections; material approvals and payment certification | Yes / No / N/A + Score 0–5 + Rating
28.052 | 28 | WP28 | Civil Works, Earthworks and Access Construction | Is there a responsible owner, due date and approval route for R567 entrance works - professional certification? | Register entry, supporting drawing/report, approval note and updated risk item. | OHS Act 85 of 1993; Construction Regulations, 2014; HSE file | Yes / No / N/A + Score 0–5 + Rating
28.053 | 28 | WP28 | Civil Works, Earthworks and Access Construction | Has the gate file tested whether stormwater structures - professional certification creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | JBCC/NEC/FIDIC contract conditions; QA/QC inspection and test plans | Yes / No / N/A + Score 0–5 + Rating
28.054 | 28 | WP28 | Civil Works, Earthworks and Access Construction | Are assumptions for internal roads - professional certification documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | NEMA EMPr; municipal inspections; material approvals and payment certification | Yes / No / N/A + Score 0–5 + Rating
28.055 | 28 | WP28 | Civil Works, Earthworks and Access Construction | Has the relevant authority, specialist or professional adviser reviewed clearing and grubbing - implementation readiness where required? | Authority response, compliance checklist, file note and management approval. | OHS Act 85 of 1993; Construction Regulations, 2014; HSE file | Yes / No / N/A + Score 0–5 + Rating
28.056 | 28 | WP28 | Civil Works, Earthworks and Access Construction | Is the decision record for bulk earthworks - implementation readiness aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | JBCC/NEC/FIDIC contract conditions; QA/QC inspection and test plans | Yes / No / N/A + Score 0–5 + Rating
28.057 | 28 | WP28 | Civil Works, Earthworks and Access Construction | Have cost, programme and compliance implications of platforms - implementation readiness been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | NEMA EMPr; municipal inspections; material approvals and payment certification | Yes / No / N/A + Score 0–5 + Rating
28.058 | 28 | WP28 | Civil Works, Earthworks and Access Construction | Has the team obtained written confirmation or documented proof for R567 entrance works - implementation readiness? | Current certificate/letter/report, version control and document-control entry. | OHS Act 85 of 1993; Construction Regulations, 2014; HSE file | Yes / No / N/A + Score 0–5 + Rating
28.059 | 28 | WP28 | Civil Works, Earthworks and Access Construction | Does the evidence for stormwater structures - implementation readiness support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | JBCC/NEC/FIDIC contract conditions; QA/QC inspection and test plans | Yes / No / N/A + Score 0–5 + Rating
28.060 | 28 | WP28 | Civil Works, Earthworks and Access Construction | Have dependencies linked to internal roads - implementation readiness been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | NEMA EMPr; municipal inspections; material approvals and payment certification | Yes / No / N/A + Score 0–5 + Rating
28.061 | 28 | WP28 | Civil Works, Earthworks and Access Construction | Has the project team confirmed clearing and grubbing - governance approval in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | OHS Act 85 of 1993; Construction Regulations, 2014; HSE file | Yes / No / N/A + Score 0–5 + Rating
28.062 | 28 | WP28 | Civil Works, Earthworks and Access Construction | Is there a responsible owner, due date and approval route for bulk earthworks - governance approval? | Register entry, supporting drawing/report, approval note and updated risk item. | JBCC/NEC/FIDIC contract conditions; QA/QC inspection and test plans | Yes / No / N/A + Score 0–5 + Rating
28.063 | 28 | WP28 | Civil Works, Earthworks and Access Construction | Has the gate file tested whether platforms - governance approval creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | NEMA EMPr; municipal inspections; material approvals and payment certification | Yes / No / N/A + Score 0–5 + Rating
28.064 | 28 | WP28 | Civil Works, Earthworks and Access Construction | Are assumptions for R567 entrance works - governance approval documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | OHS Act 85 of 1993; Construction Regulations, 2014; HSE file | Yes / No / N/A + Score 0–5 + Rating
28.065 | 28 | WP28 | Civil Works, Earthworks and Access Construction | Has the relevant authority, specialist or professional adviser reviewed stormwater structures - governance approval where required? | Authority response, compliance checklist, file note and management approval. | JBCC/NEC/FIDIC contract conditions; QA/QC inspection and test plans | Yes / No / N/A + Score 0–5 + Rating
28.066 | 28 | WP28 | Civil Works, Earthworks and Access Construction | Is the decision record for internal roads - governance approval aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | NEMA EMPr; municipal inspections; material approvals and payment certification | Yes / No / N/A + Score 0–5 + Rating
28.067 | 28 | WP28 | Civil Works, Earthworks and Access Construction | Have cost, programme and compliance implications of clearing and grubbing - legal authority been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | OHS Act 85 of 1993; Construction Regulations, 2014; HSE file | Yes / No / N/A + Score 0–5 + Rating
28.068 | 28 | WP28 | Civil Works, Earthworks and Access Construction | Has the team obtained written confirmation or documented proof for bulk earthworks - legal authority? | Current certificate/letter/report, version control and document-control entry. | JBCC/NEC/FIDIC contract conditions; QA/QC inspection and test plans | Yes / No / N/A + Score 0–5 + Rating
28.069 | 28 | WP28 | Civil Works, Earthworks and Access Construction | Does the evidence for platforms - legal authority support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | NEMA EMPr; municipal inspections; material approvals and payment certification | Yes / No / N/A + Score 0–5 + Rating
28.070 | 28 | WP28 | Civil Works, Earthworks and Access Construction | Have dependencies linked to R567 entrance works - legal authority been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | OHS Act 85 of 1993; Construction Regulations, 2014; HSE file | Yes / No / N/A + Score 0–5 + Rating
28.071 | 28 | WP28 | Civil Works, Earthworks and Access Construction | Has the project team confirmed stormwater structures - legal authority in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | JBCC/NEC/FIDIC contract conditions; QA/QC inspection and test plans | Yes / No / N/A + Score 0–5 + Rating
28.072 | 28 | WP28 | Civil Works, Earthworks and Access Construction | Is there a responsible owner, due date and approval route for internal roads - legal authority? | Register entry, supporting drawing/report, approval note and updated risk item. | NEMA EMPr; municipal inspections; material approvals and payment certification | Yes / No / N/A + Score 0–5 + Rating
28.073 | 28 | WP28 | Civil Works, Earthworks and Access Construction | Has the gate file tested whether clearing and grubbing - technical feasibility creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | OHS Act 85 of 1993; Construction Regulations, 2014; HSE file | Yes / No / N/A + Score 0–5 + Rating
28.074 | 28 | WP28 | Civil Works, Earthworks and Access Construction | Are assumptions for bulk earthworks - technical feasibility documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | JBCC/NEC/FIDIC contract conditions; QA/QC inspection and test plans | Yes / No / N/A + Score 0–5 + Rating
28.075 | 28 | WP28 | Civil Works, Earthworks and Access Construction | Has the relevant authority, specialist or professional adviser reviewed platforms - technical feasibility where required? | Authority response, compliance checklist, file note and management approval. | NEMA EMPr; municipal inspections; material approvals and payment certification | Yes / No / N/A + Score 0–5 + Rating
28.076 | 28 | WP28 | Civil Works, Earthworks and Access Construction | Is the decision record for R567 entrance works - technical feasibility aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | OHS Act 85 of 1993; Construction Regulations, 2014; HSE file | Yes / No / N/A + Score 0–5 + Rating
28.077 | 28 | WP28 | Civil Works, Earthworks and Access Construction | Have cost, programme and compliance implications of stormwater structures - technical feasibility been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | JBCC/NEC/FIDIC contract conditions; QA/QC inspection and test plans | Yes / No / N/A + Score 0–5 + Rating
28.078 | 28 | WP28 | Civil Works, Earthworks and Access Construction | Has the team obtained written confirmation or documented proof for internal roads - technical feasibility? | Current certificate/letter/report, version control and document-control entry. | NEMA EMPr; municipal inspections; material approvals and payment certification | Yes / No / N/A + Score 0–5 + Rating
28.079 | 28 | WP28 | Civil Works, Earthworks and Access Construction | Does the evidence for clearing and grubbing - financial viability support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | OHS Act 85 of 1993; Construction Regulations, 2014; HSE file | Yes / No / N/A + Score 0–5 + Rating
28.080 | 28 | WP28 | Civil Works, Earthworks and Access Construction | Have dependencies linked to bulk earthworks - financial viability been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | JBCC/NEC/FIDIC contract conditions; QA/QC inspection and test plans | Yes / No / N/A + Score 0–5 + Rating
28.081 | 28 | WP28 | Civil Works, Earthworks and Access Construction | Has the project team confirmed platforms - financial viability in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | NEMA EMPr; municipal inspections; material approvals and payment certification | Yes / No / N/A + Score 0–5 + Rating
28.082 | 28 | WP28 | Civil Works, Earthworks and Access Construction | Is there a responsible owner, due date and approval route for R567 entrance works - financial viability? | Register entry, supporting drawing/report, approval note and updated risk item. | OHS Act 85 of 1993; Construction Regulations, 2014; HSE file | Yes / No / N/A + Score 0–5 + Rating
28.083 | 28 | WP28 | Civil Works, Earthworks and Access Construction | Has the gate file tested whether stormwater structures - financial viability creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | JBCC/NEC/FIDIC contract conditions; QA/QC inspection and test plans | Yes / No / N/A + Score 0–5 + Rating
28.084 | 28 | WP28 | Civil Works, Earthworks and Access Construction | Are assumptions for internal roads - financial viability documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | NEMA EMPr; municipal inspections; material approvals and payment certification | Yes / No / N/A + Score 0–5 + Rating
28.085 | 28 | WP28 | Civil Works, Earthworks and Access Construction | Has the relevant authority, specialist or professional adviser reviewed clearing and grubbing - programme impact where required? | Authority response, compliance checklist, file note and management approval. | OHS Act 85 of 1993; Construction Regulations, 2014; HSE file | Yes / No / N/A + Score 0–5 + Rating
28.086 | 28 | WP28 | Civil Works, Earthworks and Access Construction | Is the decision record for bulk earthworks - programme impact aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | JBCC/NEC/FIDIC contract conditions; QA/QC inspection and test plans | Yes / No / N/A + Score 0–5 + Rating
28.087 | 28 | WP28 | Civil Works, Earthworks and Access Construction | Have cost, programme and compliance implications of platforms - programme impact been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | NEMA EMPr; municipal inspections; material approvals and payment certification | Yes / No / N/A + Score 0–5 + Rating
28.088 | 28 | WP28 | Civil Works, Earthworks and Access Construction | Has the team obtained written confirmation or documented proof for R567 entrance works - programme impact? | Current certificate/letter/report, version control and document-control entry. | OHS Act 85 of 1993; Construction Regulations, 2014; HSE file | Yes / No / N/A + Score 0–5 + Rating
28.089 | 28 | WP28 | Civil Works, Earthworks and Access Construction | Does the evidence for stormwater structures - programme impact support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | JBCC/NEC/FIDIC contract conditions; QA/QC inspection and test plans | Yes / No / N/A + Score 0–5 + Rating
28.090 | 28 | WP28 | Civil Works, Earthworks and Access Construction | Have dependencies linked to internal roads - programme impact been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | NEMA EMPr; municipal inspections; material approvals and payment certification | Yes / No / N/A + Score 0–5 + Rating
28.091 | 28 | WP28 | Civil Works, Earthworks and Access Construction | Has the project team confirmed clearing and grubbing - risk mitigation in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | OHS Act 85 of 1993; Construction Regulations, 2014; HSE file | Yes / No / N/A + Score 0–5 + Rating
28.092 | 28 | WP28 | Civil Works, Earthworks and Access Construction | Is there a responsible owner, due date and approval route for bulk earthworks - risk mitigation? | Register entry, supporting drawing/report, approval note and updated risk item. | JBCC/NEC/FIDIC contract conditions; QA/QC inspection and test plans | Yes / No / N/A + Score 0–5 + Rating
28.093 | 28 | WP28 | Civil Works, Earthworks and Access Construction | Has the gate file tested whether platforms - risk mitigation creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | NEMA EMPr; municipal inspections; material approvals and payment certification | Yes / No / N/A + Score 0–5 + Rating
28.094 | 28 | WP28 | Civil Works, Earthworks and Access Construction | Are assumptions for R567 entrance works - risk mitigation documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | OHS Act 85 of 1993; Construction Regulations, 2014; HSE file | Yes / No / N/A + Score 0–5 + Rating
28.095 | 28 | WP28 | Civil Works, Earthworks and Access Construction | Has the relevant authority, specialist or professional adviser reviewed stormwater structures - risk mitigation where required? | Authority response, compliance checklist, file note and management approval. | JBCC/NEC/FIDIC contract conditions; QA/QC inspection and test plans | Yes / No / N/A + Score 0–5 + Rating
28.096 | 28 | WP28 | Civil Works, Earthworks and Access Construction | Is the decision record for internal roads - risk mitigation aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | NEMA EMPr; municipal inspections; material approvals and payment certification | Yes / No / N/A + Score 0–5 + Rating
28.097 | 28 | WP28 | Civil Works, Earthworks and Access Construction | Have cost, programme and compliance implications of clearing and grubbing - stakeholder acceptance been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | OHS Act 85 of 1993; Construction Regulations, 2014; HSE file | Yes / No / N/A + Score 0–5 + Rating
28.098 | 28 | WP28 | Civil Works, Earthworks and Access Construction | Has the team obtained written confirmation or documented proof for bulk earthworks - stakeholder acceptance? | Current certificate/letter/report, version control and document-control entry. | JBCC/NEC/FIDIC contract conditions; QA/QC inspection and test plans | Yes / No / N/A + Score 0–5 + Rating
28.099 | 28 | WP28 | Civil Works, Earthworks and Access Construction | Does the evidence for platforms - stakeholder acceptance support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | NEMA EMPr; municipal inspections; material approvals and payment certification | Yes / No / N/A + Score 0–5 + Rating
28.100 | 28 | WP28 | Civil Works, Earthworks and Access Construction | Have dependencies linked to R567 entrance works - stakeholder acceptance been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | OHS Act 85 of 1993; Construction Regulations, 2014; HSE file | Yes / No / N/A + Score 0–5 + Rating
29.001 | 29 | WP29 | Building Shells and Services Installation | Has the project team confirmed Boxer shell - governance approval in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | OHS Act 85 of 1993; Construction Regulations, 2014; HSE file | Yes / No / N/A + Score 0–5 + Rating
29.002 | 29 | WP29 | Building Shells and Services Installation | Is there a responsible owner, due date and approval route for line-shop shells - governance approval? | Register entry, supporting drawing/report, approval note and updated risk item. | JBCC/NEC/FIDIC contract conditions; QA/QC inspection and test plans | Yes / No / N/A + Score 0–5 + Rating
29.003 | 29 | WP29 | Building Shells and Services Installation | Has the gate file tested whether QSR shells - governance approval creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | NEMA EMPr; municipal inspections; material approvals and payment certification | Yes / No / N/A + Score 0–5 + Rating
29.004 | 29 | WP29 | Building Shells and Services Installation | Are assumptions for roofing - governance approval documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | OHS Act 85 of 1993; Construction Regulations, 2014; HSE file | Yes / No / N/A + Score 0–5 + Rating
29.005 | 29 | WP29 | Building Shells and Services Installation | Has the relevant authority, specialist or professional adviser reviewed shopfronts - governance approval where required? | Authority response, compliance checklist, file note and management approval. | JBCC/NEC/FIDIC contract conditions; QA/QC inspection and test plans | Yes / No / N/A + Score 0–5 + Rating
29.006 | 29 | WP29 | Building Shells and Services Installation | Is the decision record for water services - governance approval aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | NEMA EMPr; municipal inspections; material approvals and payment certification | Yes / No / N/A + Score 0–5 + Rating
29.007 | 29 | WP29 | Building Shells and Services Installation | Have cost, programme and compliance implications of Boxer shell - legal authority been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | OHS Act 85 of 1993; Construction Regulations, 2014; HSE file | Yes / No / N/A + Score 0–5 + Rating
29.008 | 29 | WP29 | Building Shells and Services Installation | Has the team obtained written confirmation or documented proof for line-shop shells - legal authority? | Current certificate/letter/report, version control and document-control entry. | JBCC/NEC/FIDIC contract conditions; QA/QC inspection and test plans | Yes / No / N/A + Score 0–5 + Rating
29.009 | 29 | WP29 | Building Shells and Services Installation | Does the evidence for QSR shells - legal authority support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | NEMA EMPr; municipal inspections; material approvals and payment certification | Yes / No / N/A + Score 0–5 + Rating
29.010 | 29 | WP29 | Building Shells and Services Installation | Have dependencies linked to roofing - legal authority been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | OHS Act 85 of 1993; Construction Regulations, 2014; HSE file | Yes / No / N/A + Score 0–5 + Rating
29.011 | 29 | WP29 | Building Shells and Services Installation | Has the project team confirmed shopfronts - legal authority in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | JBCC/NEC/FIDIC contract conditions; QA/QC inspection and test plans | Yes / No / N/A + Score 0–5 + Rating
29.012 | 29 | WP29 | Building Shells and Services Installation | Is there a responsible owner, due date and approval route for water services - legal authority? | Register entry, supporting drawing/report, approval note and updated risk item. | NEMA EMPr; municipal inspections; material approvals and payment certification | Yes / No / N/A + Score 0–5 + Rating
29.013 | 29 | WP29 | Building Shells and Services Installation | Has the gate file tested whether Boxer shell - technical feasibility creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | OHS Act 85 of 1993; Construction Regulations, 2014; HSE file | Yes / No / N/A + Score 0–5 + Rating
29.014 | 29 | WP29 | Building Shells and Services Installation | Are assumptions for line-shop shells - technical feasibility documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | JBCC/NEC/FIDIC contract conditions; QA/QC inspection and test plans | Yes / No / N/A + Score 0–5 + Rating
29.015 | 29 | WP29 | Building Shells and Services Installation | Has the relevant authority, specialist or professional adviser reviewed QSR shells - technical feasibility where required? | Authority response, compliance checklist, file note and management approval. | NEMA EMPr; municipal inspections; material approvals and payment certification | Yes / No / N/A + Score 0–5 + Rating
29.016 | 29 | WP29 | Building Shells and Services Installation | Is the decision record for roofing - technical feasibility aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | OHS Act 85 of 1993; Construction Regulations, 2014; HSE file | Yes / No / N/A + Score 0–5 + Rating
29.017 | 29 | WP29 | Building Shells and Services Installation | Have cost, programme and compliance implications of shopfronts - technical feasibility been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | JBCC/NEC/FIDIC contract conditions; QA/QC inspection and test plans | Yes / No / N/A + Score 0–5 + Rating
29.018 | 29 | WP29 | Building Shells and Services Installation | Has the team obtained written confirmation or documented proof for water services - technical feasibility? | Current certificate/letter/report, version control and document-control entry. | NEMA EMPr; municipal inspections; material approvals and payment certification | Yes / No / N/A + Score 0–5 + Rating
29.019 | 29 | WP29 | Building Shells and Services Installation | Does the evidence for Boxer shell - financial viability support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | OHS Act 85 of 1993; Construction Regulations, 2014; HSE file | Yes / No / N/A + Score 0–5 + Rating
29.020 | 29 | WP29 | Building Shells and Services Installation | Have dependencies linked to line-shop shells - financial viability been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | JBCC/NEC/FIDIC contract conditions; QA/QC inspection and test plans | Yes / No / N/A + Score 0–5 + Rating
29.021 | 29 | WP29 | Building Shells and Services Installation | Has the project team confirmed QSR shells - financial viability in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | NEMA EMPr; municipal inspections; material approvals and payment certification | Yes / No / N/A + Score 0–5 + Rating
29.022 | 29 | WP29 | Building Shells and Services Installation | Is there a responsible owner, due date and approval route for roofing - financial viability? | Register entry, supporting drawing/report, approval note and updated risk item. | OHS Act 85 of 1993; Construction Regulations, 2014; HSE file | Yes / No / N/A + Score 0–5 + Rating
29.023 | 29 | WP29 | Building Shells and Services Installation | Has the gate file tested whether shopfronts - financial viability creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | JBCC/NEC/FIDIC contract conditions; QA/QC inspection and test plans | Yes / No / N/A + Score 0–5 + Rating
29.024 | 29 | WP29 | Building Shells and Services Installation | Are assumptions for water services - financial viability documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | NEMA EMPr; municipal inspections; material approvals and payment certification | Yes / No / N/A + Score 0–5 + Rating
29.025 | 29 | WP29 | Building Shells and Services Installation | Has the relevant authority, specialist or professional adviser reviewed Boxer shell - programme impact where required? | Authority response, compliance checklist, file note and management approval. | OHS Act 85 of 1993; Construction Regulations, 2014; HSE file | Yes / No / N/A + Score 0–5 + Rating
29.026 | 29 | WP29 | Building Shells and Services Installation | Is the decision record for line-shop shells - programme impact aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | JBCC/NEC/FIDIC contract conditions; QA/QC inspection and test plans | Yes / No / N/A + Score 0–5 + Rating
29.027 | 29 | WP29 | Building Shells and Services Installation | Have cost, programme and compliance implications of QSR shells - programme impact been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | NEMA EMPr; municipal inspections; material approvals and payment certification | Yes / No / N/A + Score 0–5 + Rating
29.028 | 29 | WP29 | Building Shells and Services Installation | Has the team obtained written confirmation or documented proof for roofing - programme impact? | Current certificate/letter/report, version control and document-control entry. | OHS Act 85 of 1993; Construction Regulations, 2014; HSE file | Yes / No / N/A + Score 0–5 + Rating
29.029 | 29 | WP29 | Building Shells and Services Installation | Does the evidence for shopfronts - programme impact support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | JBCC/NEC/FIDIC contract conditions; QA/QC inspection and test plans | Yes / No / N/A + Score 0–5 + Rating
29.030 | 29 | WP29 | Building Shells and Services Installation | Have dependencies linked to water services - programme impact been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | NEMA EMPr; municipal inspections; material approvals and payment certification | Yes / No / N/A + Score 0–5 + Rating
29.031 | 29 | WP29 | Building Shells and Services Installation | Has the project team confirmed Boxer shell - risk mitigation in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | OHS Act 85 of 1993; Construction Regulations, 2014; HSE file | Yes / No / N/A + Score 0–5 + Rating
29.032 | 29 | WP29 | Building Shells and Services Installation | Is there a responsible owner, due date and approval route for line-shop shells - risk mitigation? | Register entry, supporting drawing/report, approval note and updated risk item. | JBCC/NEC/FIDIC contract conditions; QA/QC inspection and test plans | Yes / No / N/A + Score 0–5 + Rating
29.033 | 29 | WP29 | Building Shells and Services Installation | Has the gate file tested whether QSR shells - risk mitigation creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | NEMA EMPr; municipal inspections; material approvals and payment certification | Yes / No / N/A + Score 0–5 + Rating
29.034 | 29 | WP29 | Building Shells and Services Installation | Are assumptions for roofing - risk mitigation documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | OHS Act 85 of 1993; Construction Regulations, 2014; HSE file | Yes / No / N/A + Score 0–5 + Rating
29.035 | 29 | WP29 | Building Shells and Services Installation | Has the relevant authority, specialist or professional adviser reviewed shopfronts - risk mitigation where required? | Authority response, compliance checklist, file note and management approval. | JBCC/NEC/FIDIC contract conditions; QA/QC inspection and test plans | Yes / No / N/A + Score 0–5 + Rating
29.036 | 29 | WP29 | Building Shells and Services Installation | Is the decision record for water services - risk mitigation aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | NEMA EMPr; municipal inspections; material approvals and payment certification | Yes / No / N/A + Score 0–5 + Rating
29.037 | 29 | WP29 | Building Shells and Services Installation | Have cost, programme and compliance implications of Boxer shell - stakeholder acceptance been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | OHS Act 85 of 1993; Construction Regulations, 2014; HSE file | Yes / No / N/A + Score 0–5 + Rating
29.038 | 29 | WP29 | Building Shells and Services Installation | Has the team obtained written confirmation or documented proof for line-shop shells - stakeholder acceptance? | Current certificate/letter/report, version control and document-control entry. | JBCC/NEC/FIDIC contract conditions; QA/QC inspection and test plans | Yes / No / N/A + Score 0–5 + Rating
29.039 | 29 | WP29 | Building Shells and Services Installation | Does the evidence for QSR shells - stakeholder acceptance support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | NEMA EMPr; municipal inspections; material approvals and payment certification | Yes / No / N/A + Score 0–5 + Rating
29.040 | 29 | WP29 | Building Shells and Services Installation | Have dependencies linked to roofing - stakeholder acceptance been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | OHS Act 85 of 1993; Construction Regulations, 2014; HSE file | Yes / No / N/A + Score 0–5 + Rating
29.041 | 29 | WP29 | Building Shells and Services Installation | Has the project team confirmed shopfronts - stakeholder acceptance in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | JBCC/NEC/FIDIC contract conditions; QA/QC inspection and test plans | Yes / No / N/A + Score 0–5 + Rating
29.042 | 29 | WP29 | Building Shells and Services Installation | Is there a responsible owner, due date and approval route for water services - stakeholder acceptance? | Register entry, supporting drawing/report, approval note and updated risk item. | NEMA EMPr; municipal inspections; material approvals and payment certification | Yes / No / N/A + Score 0–5 + Rating
29.043 | 29 | WP29 | Building Shells and Services Installation | Has the gate file tested whether Boxer shell - document control creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | OHS Act 85 of 1993; Construction Regulations, 2014; HSE file | Yes / No / N/A + Score 0–5 + Rating
29.044 | 29 | WP29 | Building Shells and Services Installation | Are assumptions for line-shop shells - document control documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | JBCC/NEC/FIDIC contract conditions; QA/QC inspection and test plans | Yes / No / N/A + Score 0–5 + Rating
29.045 | 29 | WP29 | Building Shells and Services Installation | Has the relevant authority, specialist or professional adviser reviewed QSR shells - document control where required? | Authority response, compliance checklist, file note and management approval. | NEMA EMPr; municipal inspections; material approvals and payment certification | Yes / No / N/A + Score 0–5 + Rating
29.046 | 29 | WP29 | Building Shells and Services Installation | Is the decision record for roofing - document control aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | OHS Act 85 of 1993; Construction Regulations, 2014; HSE file | Yes / No / N/A + Score 0–5 + Rating
29.047 | 29 | WP29 | Building Shells and Services Installation | Have cost, programme and compliance implications of shopfronts - document control been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | JBCC/NEC/FIDIC contract conditions; QA/QC inspection and test plans | Yes / No / N/A + Score 0–5 + Rating
29.048 | 29 | WP29 | Building Shells and Services Installation | Has the team obtained written confirmation or documented proof for water services - document control? | Current certificate/letter/report, version control and document-control entry. | NEMA EMPr; municipal inspections; material approvals and payment certification | Yes / No / N/A + Score 0–5 + Rating
29.049 | 29 | WP29 | Building Shells and Services Installation | Does the evidence for Boxer shell - professional certification support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | OHS Act 85 of 1993; Construction Regulations, 2014; HSE file | Yes / No / N/A + Score 0–5 + Rating
29.050 | 29 | WP29 | Building Shells and Services Installation | Have dependencies linked to line-shop shells - professional certification been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | JBCC/NEC/FIDIC contract conditions; QA/QC inspection and test plans | Yes / No / N/A + Score 0–5 + Rating
29.051 | 29 | WP29 | Building Shells and Services Installation | Has the project team confirmed QSR shells - professional certification in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | NEMA EMPr; municipal inspections; material approvals and payment certification | Yes / No / N/A + Score 0–5 + Rating
29.052 | 29 | WP29 | Building Shells and Services Installation | Is there a responsible owner, due date and approval route for roofing - professional certification? | Register entry, supporting drawing/report, approval note and updated risk item. | OHS Act 85 of 1993; Construction Regulations, 2014; HSE file | Yes / No / N/A + Score 0–5 + Rating
29.053 | 29 | WP29 | Building Shells and Services Installation | Has the gate file tested whether shopfronts - professional certification creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | JBCC/NEC/FIDIC contract conditions; QA/QC inspection and test plans | Yes / No / N/A + Score 0–5 + Rating
29.054 | 29 | WP29 | Building Shells and Services Installation | Are assumptions for water services - professional certification documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | NEMA EMPr; municipal inspections; material approvals and payment certification | Yes / No / N/A + Score 0–5 + Rating
29.055 | 29 | WP29 | Building Shells and Services Installation | Has the relevant authority, specialist or professional adviser reviewed Boxer shell - implementation readiness where required? | Authority response, compliance checklist, file note and management approval. | OHS Act 85 of 1993; Construction Regulations, 2014; HSE file | Yes / No / N/A + Score 0–5 + Rating
29.056 | 29 | WP29 | Building Shells and Services Installation | Is the decision record for line-shop shells - implementation readiness aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | JBCC/NEC/FIDIC contract conditions; QA/QC inspection and test plans | Yes / No / N/A + Score 0–5 + Rating
29.057 | 29 | WP29 | Building Shells and Services Installation | Have cost, programme and compliance implications of QSR shells - implementation readiness been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | NEMA EMPr; municipal inspections; material approvals and payment certification | Yes / No / N/A + Score 0–5 + Rating
29.058 | 29 | WP29 | Building Shells and Services Installation | Has the team obtained written confirmation or documented proof for roofing - implementation readiness? | Current certificate/letter/report, version control and document-control entry. | OHS Act 85 of 1993; Construction Regulations, 2014; HSE file | Yes / No / N/A + Score 0–5 + Rating
29.059 | 29 | WP29 | Building Shells and Services Installation | Does the evidence for shopfronts - implementation readiness support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | JBCC/NEC/FIDIC contract conditions; QA/QC inspection and test plans | Yes / No / N/A + Score 0–5 + Rating
29.060 | 29 | WP29 | Building Shells and Services Installation | Have dependencies linked to water services - implementation readiness been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | NEMA EMPr; municipal inspections; material approvals and payment certification | Yes / No / N/A + Score 0–5 + Rating
29.061 | 29 | WP29 | Building Shells and Services Installation | Has the project team confirmed Boxer shell - governance approval in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | OHS Act 85 of 1993; Construction Regulations, 2014; HSE file | Yes / No / N/A + Score 0–5 + Rating
29.062 | 29 | WP29 | Building Shells and Services Installation | Is there a responsible owner, due date and approval route for line-shop shells - governance approval? | Register entry, supporting drawing/report, approval note and updated risk item. | JBCC/NEC/FIDIC contract conditions; QA/QC inspection and test plans | Yes / No / N/A + Score 0–5 + Rating
29.063 | 29 | WP29 | Building Shells and Services Installation | Has the gate file tested whether QSR shells - governance approval creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | NEMA EMPr; municipal inspections; material approvals and payment certification | Yes / No / N/A + Score 0–5 + Rating
29.064 | 29 | WP29 | Building Shells and Services Installation | Are assumptions for roofing - governance approval documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | OHS Act 85 of 1993; Construction Regulations, 2014; HSE file | Yes / No / N/A + Score 0–5 + Rating
29.065 | 29 | WP29 | Building Shells and Services Installation | Has the relevant authority, specialist or professional adviser reviewed shopfronts - governance approval where required? | Authority response, compliance checklist, file note and management approval. | JBCC/NEC/FIDIC contract conditions; QA/QC inspection and test plans | Yes / No / N/A + Score 0–5 + Rating
29.066 | 29 | WP29 | Building Shells and Services Installation | Is the decision record for water services - governance approval aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | NEMA EMPr; municipal inspections; material approvals and payment certification | Yes / No / N/A + Score 0–5 + Rating
29.067 | 29 | WP29 | Building Shells and Services Installation | Have cost, programme and compliance implications of Boxer shell - legal authority been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | OHS Act 85 of 1993; Construction Regulations, 2014; HSE file | Yes / No / N/A + Score 0–5 + Rating
29.068 | 29 | WP29 | Building Shells and Services Installation | Has the team obtained written confirmation or documented proof for line-shop shells - legal authority? | Current certificate/letter/report, version control and document-control entry. | JBCC/NEC/FIDIC contract conditions; QA/QC inspection and test plans | Yes / No / N/A + Score 0–5 + Rating
29.069 | 29 | WP29 | Building Shells and Services Installation | Does the evidence for QSR shells - legal authority support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | NEMA EMPr; municipal inspections; material approvals and payment certification | Yes / No / N/A + Score 0–5 + Rating
29.070 | 29 | WP29 | Building Shells and Services Installation | Have dependencies linked to roofing - legal authority been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | OHS Act 85 of 1993; Construction Regulations, 2014; HSE file | Yes / No / N/A + Score 0–5 + Rating
29.071 | 29 | WP29 | Building Shells and Services Installation | Has the project team confirmed shopfronts - legal authority in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | JBCC/NEC/FIDIC contract conditions; QA/QC inspection and test plans | Yes / No / N/A + Score 0–5 + Rating
29.072 | 29 | WP29 | Building Shells and Services Installation | Is there a responsible owner, due date and approval route for water services - legal authority? | Register entry, supporting drawing/report, approval note and updated risk item. | NEMA EMPr; municipal inspections; material approvals and payment certification | Yes / No / N/A + Score 0–5 + Rating
29.073 | 29 | WP29 | Building Shells and Services Installation | Has the gate file tested whether Boxer shell - technical feasibility creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | OHS Act 85 of 1993; Construction Regulations, 2014; HSE file | Yes / No / N/A + Score 0–5 + Rating
29.074 | 29 | WP29 | Building Shells and Services Installation | Are assumptions for line-shop shells - technical feasibility documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | JBCC/NEC/FIDIC contract conditions; QA/QC inspection and test plans | Yes / No / N/A + Score 0–5 + Rating
29.075 | 29 | WP29 | Building Shells and Services Installation | Has the relevant authority, specialist or professional adviser reviewed QSR shells - technical feasibility where required? | Authority response, compliance checklist, file note and management approval. | NEMA EMPr; municipal inspections; material approvals and payment certification | Yes / No / N/A + Score 0–5 + Rating
29.076 | 29 | WP29 | Building Shells and Services Installation | Is the decision record for roofing - technical feasibility aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | OHS Act 85 of 1993; Construction Regulations, 2014; HSE file | Yes / No / N/A + Score 0–5 + Rating
29.077 | 29 | WP29 | Building Shells and Services Installation | Have cost, programme and compliance implications of shopfronts - technical feasibility been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | JBCC/NEC/FIDIC contract conditions; QA/QC inspection and test plans | Yes / No / N/A + Score 0–5 + Rating
29.078 | 29 | WP29 | Building Shells and Services Installation | Has the team obtained written confirmation or documented proof for water services - technical feasibility? | Current certificate/letter/report, version control and document-control entry. | NEMA EMPr; municipal inspections; material approvals and payment certification | Yes / No / N/A + Score 0–5 + Rating
29.079 | 29 | WP29 | Building Shells and Services Installation | Does the evidence for Boxer shell - financial viability support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | OHS Act 85 of 1993; Construction Regulations, 2014; HSE file | Yes / No / N/A + Score 0–5 + Rating
29.080 | 29 | WP29 | Building Shells and Services Installation | Have dependencies linked to line-shop shells - financial viability been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | JBCC/NEC/FIDIC contract conditions; QA/QC inspection and test plans | Yes / No / N/A + Score 0–5 + Rating
29.081 | 29 | WP29 | Building Shells and Services Installation | Has the project team confirmed QSR shells - financial viability in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | NEMA EMPr; municipal inspections; material approvals and payment certification | Yes / No / N/A + Score 0–5 + Rating
29.082 | 29 | WP29 | Building Shells and Services Installation | Is there a responsible owner, due date and approval route for roofing - financial viability? | Register entry, supporting drawing/report, approval note and updated risk item. | OHS Act 85 of 1993; Construction Regulations, 2014; HSE file | Yes / No / N/A + Score 0–5 + Rating
29.083 | 29 | WP29 | Building Shells and Services Installation | Has the gate file tested whether shopfronts - financial viability creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | JBCC/NEC/FIDIC contract conditions; QA/QC inspection and test plans | Yes / No / N/A + Score 0–5 + Rating
29.084 | 29 | WP29 | Building Shells and Services Installation | Are assumptions for water services - financial viability documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | NEMA EMPr; municipal inspections; material approvals and payment certification | Yes / No / N/A + Score 0–5 + Rating
29.085 | 29 | WP29 | Building Shells and Services Installation | Has the relevant authority, specialist or professional adviser reviewed Boxer shell - programme impact where required? | Authority response, compliance checklist, file note and management approval. | OHS Act 85 of 1993; Construction Regulations, 2014; HSE file | Yes / No / N/A + Score 0–5 + Rating
29.086 | 29 | WP29 | Building Shells and Services Installation | Is the decision record for line-shop shells - programme impact aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | JBCC/NEC/FIDIC contract conditions; QA/QC inspection and test plans | Yes / No / N/A + Score 0–5 + Rating
29.087 | 29 | WP29 | Building Shells and Services Installation | Have cost, programme and compliance implications of QSR shells - programme impact been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | NEMA EMPr; municipal inspections; material approvals and payment certification | Yes / No / N/A + Score 0–5 + Rating
29.088 | 29 | WP29 | Building Shells and Services Installation | Has the team obtained written confirmation or documented proof for roofing - programme impact? | Current certificate/letter/report, version control and document-control entry. | OHS Act 85 of 1993; Construction Regulations, 2014; HSE file | Yes / No / N/A + Score 0–5 + Rating
29.089 | 29 | WP29 | Building Shells and Services Installation | Does the evidence for shopfronts - programme impact support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | JBCC/NEC/FIDIC contract conditions; QA/QC inspection and test plans | Yes / No / N/A + Score 0–5 + Rating
29.090 | 29 | WP29 | Building Shells and Services Installation | Have dependencies linked to water services - programme impact been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | NEMA EMPr; municipal inspections; material approvals and payment certification | Yes / No / N/A + Score 0–5 + Rating
29.091 | 29 | WP29 | Building Shells and Services Installation | Has the project team confirmed Boxer shell - risk mitigation in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | OHS Act 85 of 1993; Construction Regulations, 2014; HSE file | Yes / No / N/A + Score 0–5 + Rating
29.092 | 29 | WP29 | Building Shells and Services Installation | Is there a responsible owner, due date and approval route for line-shop shells - risk mitigation? | Register entry, supporting drawing/report, approval note and updated risk item. | JBCC/NEC/FIDIC contract conditions; QA/QC inspection and test plans | Yes / No / N/A + Score 0–5 + Rating
29.093 | 29 | WP29 | Building Shells and Services Installation | Has the gate file tested whether QSR shells - risk mitigation creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | NEMA EMPr; municipal inspections; material approvals and payment certification | Yes / No / N/A + Score 0–5 + Rating
29.094 | 29 | WP29 | Building Shells and Services Installation | Are assumptions for roofing - risk mitigation documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | OHS Act 85 of 1993; Construction Regulations, 2014; HSE file | Yes / No / N/A + Score 0–5 + Rating
29.095 | 29 | WP29 | Building Shells and Services Installation | Has the relevant authority, specialist or professional adviser reviewed shopfronts - risk mitigation where required? | Authority response, compliance checklist, file note and management approval. | JBCC/NEC/FIDIC contract conditions; QA/QC inspection and test plans | Yes / No / N/A + Score 0–5 + Rating
29.096 | 29 | WP29 | Building Shells and Services Installation | Is the decision record for water services - risk mitigation aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | NEMA EMPr; municipal inspections; material approvals and payment certification | Yes / No / N/A + Score 0–5 + Rating
29.097 | 29 | WP29 | Building Shells and Services Installation | Have cost, programme and compliance implications of Boxer shell - stakeholder acceptance been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | OHS Act 85 of 1993; Construction Regulations, 2014; HSE file | Yes / No / N/A + Score 0–5 + Rating
29.098 | 29 | WP29 | Building Shells and Services Installation | Has the team obtained written confirmation or documented proof for line-shop shells - stakeholder acceptance? | Current certificate/letter/report, version control and document-control entry. | JBCC/NEC/FIDIC contract conditions; QA/QC inspection and test plans | Yes / No / N/A + Score 0–5 + Rating
29.099 | 29 | WP29 | Building Shells and Services Installation | Does the evidence for QSR shells - stakeholder acceptance support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | NEMA EMPr; municipal inspections; material approvals and payment certification | Yes / No / N/A + Score 0–5 + Rating
29.100 | 29 | WP29 | Building Shells and Services Installation | Have dependencies linked to roofing - stakeholder acceptance been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | OHS Act 85 of 1993; Construction Regulations, 2014; HSE file | Yes / No / N/A + Score 0–5 + Rating
30.001 | 30 | WP30 | Tenant Fit-Out Coordination | Has the project team confirmed Boxer fit-out - governance approval in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
30.002 | 30 | WP30 | Tenant Fit-Out Coordination | Is there a responsible owner, due date and approval route for line-shop fit-out - governance approval? | Register entry, supporting drawing/report, approval note and updated risk item. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
30.003 | 30 | WP30 | Tenant Fit-Out Coordination | Has the gate file tested whether fast-food fit-out - governance approval creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
30.004 | 30 | WP30 | Tenant Fit-Out Coordination | Are assumptions for handover dates - governance approval documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
30.005 | 30 | WP30 | Tenant Fit-Out Coordination | Has the relevant authority, specialist or professional adviser reviewed fit-out rules - governance approval where required? | Authority response, compliance checklist, file note and management approval. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
30.006 | 30 | WP30 | Tenant Fit-Out Coordination | Is the decision record for tenant utilities - governance approval aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
30.007 | 30 | WP30 | Tenant Fit-Out Coordination | Have cost, programme and compliance implications of Boxer fit-out - legal authority been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
30.008 | 30 | WP30 | Tenant Fit-Out Coordination | Has the team obtained written confirmation or documented proof for line-shop fit-out - legal authority? | Current certificate/letter/report, version control and document-control entry. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
30.009 | 30 | WP30 | Tenant Fit-Out Coordination | Does the evidence for fast-food fit-out - legal authority support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
30.010 | 30 | WP30 | Tenant Fit-Out Coordination | Have dependencies linked to handover dates - legal authority been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
30.011 | 30 | WP30 | Tenant Fit-Out Coordination | Has the project team confirmed fit-out rules - legal authority in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
30.012 | 30 | WP30 | Tenant Fit-Out Coordination | Is there a responsible owner, due date and approval route for tenant utilities - legal authority? | Register entry, supporting drawing/report, approval note and updated risk item. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
30.013 | 30 | WP30 | Tenant Fit-Out Coordination | Has the gate file tested whether Boxer fit-out - technical feasibility creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
30.014 | 30 | WP30 | Tenant Fit-Out Coordination | Are assumptions for line-shop fit-out - technical feasibility documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
30.015 | 30 | WP30 | Tenant Fit-Out Coordination | Has the relevant authority, specialist or professional adviser reviewed fast-food fit-out - technical feasibility where required? | Authority response, compliance checklist, file note and management approval. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
30.016 | 30 | WP30 | Tenant Fit-Out Coordination | Is the decision record for handover dates - technical feasibility aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
30.017 | 30 | WP30 | Tenant Fit-Out Coordination | Have cost, programme and compliance implications of fit-out rules - technical feasibility been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
30.018 | 30 | WP30 | Tenant Fit-Out Coordination | Has the team obtained written confirmation or documented proof for tenant utilities - technical feasibility? | Current certificate/letter/report, version control and document-control entry. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
30.019 | 30 | WP30 | Tenant Fit-Out Coordination | Does the evidence for Boxer fit-out - financial viability support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
30.020 | 30 | WP30 | Tenant Fit-Out Coordination | Have dependencies linked to line-shop fit-out - financial viability been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
30.021 | 30 | WP30 | Tenant Fit-Out Coordination | Has the project team confirmed fast-food fit-out - financial viability in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
30.022 | 30 | WP30 | Tenant Fit-Out Coordination | Is there a responsible owner, due date and approval route for handover dates - financial viability? | Register entry, supporting drawing/report, approval note and updated risk item. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
30.023 | 30 | WP30 | Tenant Fit-Out Coordination | Has the gate file tested whether fit-out rules - financial viability creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
30.024 | 30 | WP30 | Tenant Fit-Out Coordination | Are assumptions for tenant utilities - financial viability documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
30.025 | 30 | WP30 | Tenant Fit-Out Coordination | Has the relevant authority, specialist or professional adviser reviewed Boxer fit-out - programme impact where required? | Authority response, compliance checklist, file note and management approval. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
30.026 | 30 | WP30 | Tenant Fit-Out Coordination | Is the decision record for line-shop fit-out - programme impact aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
30.027 | 30 | WP30 | Tenant Fit-Out Coordination | Have cost, programme and compliance implications of fast-food fit-out - programme impact been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
30.028 | 30 | WP30 | Tenant Fit-Out Coordination | Has the team obtained written confirmation or documented proof for handover dates - programme impact? | Current certificate/letter/report, version control and document-control entry. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
30.029 | 30 | WP30 | Tenant Fit-Out Coordination | Does the evidence for fit-out rules - programme impact support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
30.030 | 30 | WP30 | Tenant Fit-Out Coordination | Have dependencies linked to tenant utilities - programme impact been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
30.031 | 30 | WP30 | Tenant Fit-Out Coordination | Has the project team confirmed Boxer fit-out - risk mitigation in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
30.032 | 30 | WP30 | Tenant Fit-Out Coordination | Is there a responsible owner, due date and approval route for line-shop fit-out - risk mitigation? | Register entry, supporting drawing/report, approval note and updated risk item. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
30.033 | 30 | WP30 | Tenant Fit-Out Coordination | Has the gate file tested whether fast-food fit-out - risk mitigation creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
30.034 | 30 | WP30 | Tenant Fit-Out Coordination | Are assumptions for handover dates - risk mitigation documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
30.035 | 30 | WP30 | Tenant Fit-Out Coordination | Has the relevant authority, specialist or professional adviser reviewed fit-out rules - risk mitigation where required? | Authority response, compliance checklist, file note and management approval. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
30.036 | 30 | WP30 | Tenant Fit-Out Coordination | Is the decision record for tenant utilities - risk mitigation aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
30.037 | 30 | WP30 | Tenant Fit-Out Coordination | Have cost, programme and compliance implications of Boxer fit-out - stakeholder acceptance been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
30.038 | 30 | WP30 | Tenant Fit-Out Coordination | Has the team obtained written confirmation or documented proof for line-shop fit-out - stakeholder acceptance? | Current certificate/letter/report, version control and document-control entry. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
30.039 | 30 | WP30 | Tenant Fit-Out Coordination | Does the evidence for fast-food fit-out - stakeholder acceptance support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
30.040 | 30 | WP30 | Tenant Fit-Out Coordination | Have dependencies linked to handover dates - stakeholder acceptance been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
30.041 | 30 | WP30 | Tenant Fit-Out Coordination | Has the project team confirmed fit-out rules - stakeholder acceptance in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
30.042 | 30 | WP30 | Tenant Fit-Out Coordination | Is there a responsible owner, due date and approval route for tenant utilities - stakeholder acceptance? | Register entry, supporting drawing/report, approval note and updated risk item. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
30.043 | 30 | WP30 | Tenant Fit-Out Coordination | Has the gate file tested whether Boxer fit-out - document control creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
30.044 | 30 | WP30 | Tenant Fit-Out Coordination | Are assumptions for line-shop fit-out - document control documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
30.045 | 30 | WP30 | Tenant Fit-Out Coordination | Has the relevant authority, specialist or professional adviser reviewed fast-food fit-out - document control where required? | Authority response, compliance checklist, file note and management approval. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
30.046 | 30 | WP30 | Tenant Fit-Out Coordination | Is the decision record for handover dates - document control aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
30.047 | 30 | WP30 | Tenant Fit-Out Coordination | Have cost, programme and compliance implications of fit-out rules - document control been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
30.048 | 30 | WP30 | Tenant Fit-Out Coordination | Has the team obtained written confirmation or documented proof for tenant utilities - document control? | Current certificate/letter/report, version control and document-control entry. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
30.049 | 30 | WP30 | Tenant Fit-Out Coordination | Does the evidence for Boxer fit-out - professional certification support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
30.050 | 30 | WP30 | Tenant Fit-Out Coordination | Have dependencies linked to line-shop fit-out - professional certification been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
30.051 | 30 | WP30 | Tenant Fit-Out Coordination | Has the project team confirmed fast-food fit-out - professional certification in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
30.052 | 30 | WP30 | Tenant Fit-Out Coordination | Is there a responsible owner, due date and approval route for handover dates - professional certification? | Register entry, supporting drawing/report, approval note and updated risk item. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
30.053 | 30 | WP30 | Tenant Fit-Out Coordination | Has the gate file tested whether fit-out rules - professional certification creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
30.054 | 30 | WP30 | Tenant Fit-Out Coordination | Are assumptions for tenant utilities - professional certification documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
30.055 | 30 | WP30 | Tenant Fit-Out Coordination | Has the relevant authority, specialist or professional adviser reviewed Boxer fit-out - implementation readiness where required? | Authority response, compliance checklist, file note and management approval. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
30.056 | 30 | WP30 | Tenant Fit-Out Coordination | Is the decision record for line-shop fit-out - implementation readiness aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
30.057 | 30 | WP30 | Tenant Fit-Out Coordination | Have cost, programme and compliance implications of fast-food fit-out - implementation readiness been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
30.058 | 30 | WP30 | Tenant Fit-Out Coordination | Has the team obtained written confirmation or documented proof for handover dates - implementation readiness? | Current certificate/letter/report, version control and document-control entry. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
30.059 | 30 | WP30 | Tenant Fit-Out Coordination | Does the evidence for fit-out rules - implementation readiness support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
30.060 | 30 | WP30 | Tenant Fit-Out Coordination | Have dependencies linked to tenant utilities - implementation readiness been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
30.061 | 30 | WP30 | Tenant Fit-Out Coordination | Has the project team confirmed Boxer fit-out - governance approval in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
30.062 | 30 | WP30 | Tenant Fit-Out Coordination | Is there a responsible owner, due date and approval route for line-shop fit-out - governance approval? | Register entry, supporting drawing/report, approval note and updated risk item. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
30.063 | 30 | WP30 | Tenant Fit-Out Coordination | Has the gate file tested whether fast-food fit-out - governance approval creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
30.064 | 30 | WP30 | Tenant Fit-Out Coordination | Are assumptions for handover dates - governance approval documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
30.065 | 30 | WP30 | Tenant Fit-Out Coordination | Has the relevant authority, specialist or professional adviser reviewed fit-out rules - governance approval where required? | Authority response, compliance checklist, file note and management approval. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
30.066 | 30 | WP30 | Tenant Fit-Out Coordination | Is the decision record for tenant utilities - governance approval aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
30.067 | 30 | WP30 | Tenant Fit-Out Coordination | Have cost, programme and compliance implications of Boxer fit-out - legal authority been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
30.068 | 30 | WP30 | Tenant Fit-Out Coordination | Has the team obtained written confirmation or documented proof for line-shop fit-out - legal authority? | Current certificate/letter/report, version control and document-control entry. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
30.069 | 30 | WP30 | Tenant Fit-Out Coordination | Does the evidence for fast-food fit-out - legal authority support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
30.070 | 30 | WP30 | Tenant Fit-Out Coordination | Have dependencies linked to handover dates - legal authority been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
30.071 | 30 | WP30 | Tenant Fit-Out Coordination | Has the project team confirmed fit-out rules - legal authority in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
30.072 | 30 | WP30 | Tenant Fit-Out Coordination | Is there a responsible owner, due date and approval route for tenant utilities - legal authority? | Register entry, supporting drawing/report, approval note and updated risk item. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
30.073 | 30 | WP30 | Tenant Fit-Out Coordination | Has the gate file tested whether Boxer fit-out - technical feasibility creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
30.074 | 30 | WP30 | Tenant Fit-Out Coordination | Are assumptions for line-shop fit-out - technical feasibility documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
30.075 | 30 | WP30 | Tenant Fit-Out Coordination | Has the relevant authority, specialist or professional adviser reviewed fast-food fit-out - technical feasibility where required? | Authority response, compliance checklist, file note and management approval. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
30.076 | 30 | WP30 | Tenant Fit-Out Coordination | Is the decision record for handover dates - technical feasibility aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
30.077 | 30 | WP30 | Tenant Fit-Out Coordination | Have cost, programme and compliance implications of fit-out rules - technical feasibility been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
30.078 | 30 | WP30 | Tenant Fit-Out Coordination | Has the team obtained written confirmation or documented proof for tenant utilities - technical feasibility? | Current certificate/letter/report, version control and document-control entry. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
30.079 | 30 | WP30 | Tenant Fit-Out Coordination | Does the evidence for Boxer fit-out - financial viability support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
30.080 | 30 | WP30 | Tenant Fit-Out Coordination | Have dependencies linked to line-shop fit-out - financial viability been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
30.081 | 30 | WP30 | Tenant Fit-Out Coordination | Has the project team confirmed fast-food fit-out - financial viability in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
30.082 | 30 | WP30 | Tenant Fit-Out Coordination | Is there a responsible owner, due date and approval route for handover dates - financial viability? | Register entry, supporting drawing/report, approval note and updated risk item. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
30.083 | 30 | WP30 | Tenant Fit-Out Coordination | Has the gate file tested whether fit-out rules - financial viability creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
30.084 | 30 | WP30 | Tenant Fit-Out Coordination | Are assumptions for tenant utilities - financial viability documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
30.085 | 30 | WP30 | Tenant Fit-Out Coordination | Has the relevant authority, specialist or professional adviser reviewed Boxer fit-out - programme impact where required? | Authority response, compliance checklist, file note and management approval. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
30.086 | 30 | WP30 | Tenant Fit-Out Coordination | Is the decision record for line-shop fit-out - programme impact aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
30.087 | 30 | WP30 | Tenant Fit-Out Coordination | Have cost, programme and compliance implications of fast-food fit-out - programme impact been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
30.088 | 30 | WP30 | Tenant Fit-Out Coordination | Has the team obtained written confirmation or documented proof for handover dates - programme impact? | Current certificate/letter/report, version control and document-control entry. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
30.089 | 30 | WP30 | Tenant Fit-Out Coordination | Does the evidence for fit-out rules - programme impact support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
30.090 | 30 | WP30 | Tenant Fit-Out Coordination | Have dependencies linked to tenant utilities - programme impact been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
30.091 | 30 | WP30 | Tenant Fit-Out Coordination | Has the project team confirmed Boxer fit-out - risk mitigation in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
30.092 | 30 | WP30 | Tenant Fit-Out Coordination | Is there a responsible owner, due date and approval route for line-shop fit-out - risk mitigation? | Register entry, supporting drawing/report, approval note and updated risk item. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
30.093 | 30 | WP30 | Tenant Fit-Out Coordination | Has the gate file tested whether fast-food fit-out - risk mitigation creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
30.094 | 30 | WP30 | Tenant Fit-Out Coordination | Are assumptions for handover dates - risk mitigation documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
30.095 | 30 | WP30 | Tenant Fit-Out Coordination | Has the relevant authority, specialist or professional adviser reviewed fit-out rules - risk mitigation where required? | Authority response, compliance checklist, file note and management approval. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
30.096 | 30 | WP30 | Tenant Fit-Out Coordination | Is the decision record for tenant utilities - risk mitigation aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
30.097 | 30 | WP30 | Tenant Fit-Out Coordination | Have cost, programme and compliance implications of Boxer fit-out - stakeholder acceptance been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
30.098 | 30 | WP30 | Tenant Fit-Out Coordination | Has the team obtained written confirmation or documented proof for line-shop fit-out - stakeholder acceptance? | Current certificate/letter/report, version control and document-control entry. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
30.099 | 30 | WP30 | Tenant Fit-Out Coordination | Does the evidence for fast-food fit-out - stakeholder acceptance support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
30.100 | 30 | WP30 | Tenant Fit-Out Coordination | Have dependencies linked to handover dates - stakeholder acceptance been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
31.001 | 31 | WP31 | Quality Assurance, HSE and Compliance Control | Has the project team confirmed quality inspections - governance approval in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | OHS Act 85 of 1993; Construction Regulations, 2014; HSE file | Yes / No / N/A + Score 0–5 + Rating
31.002 | 31 | WP31 | Quality Assurance, HSE and Compliance Control | Is there a responsible owner, due date and approval route for HSE audits - governance approval? | Register entry, supporting drawing/report, approval note and updated risk item. | JBCC/NEC/FIDIC contract conditions; QA/QC inspection and test plans | Yes / No / N/A + Score 0–5 + Rating
31.003 | 31 | WP31 | Quality Assurance, HSE and Compliance Control | Has the gate file tested whether environmental monitoring - governance approval creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | NEMA EMPr; municipal inspections; material approvals and payment certification | Yes / No / N/A + Score 0–5 + Rating
31.004 | 31 | WP31 | Quality Assurance, HSE and Compliance Control | Are assumptions for material approvals - governance approval documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | OHS Act 85 of 1993; Construction Regulations, 2014; HSE file | Yes / No / N/A + Score 0–5 + Rating
31.005 | 31 | WP31 | Quality Assurance, HSE and Compliance Control | Has the relevant authority, specialist or professional adviser reviewed variation control - governance approval where required? | Authority response, compliance checklist, file note and management approval. | JBCC/NEC/FIDIC contract conditions; QA/QC inspection and test plans | Yes / No / N/A + Score 0–5 + Rating
31.006 | 31 | WP31 | Quality Assurance, HSE and Compliance Control | Is the decision record for payment certification - governance approval aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | NEMA EMPr; municipal inspections; material approvals and payment certification | Yes / No / N/A + Score 0–5 + Rating
31.007 | 31 | WP31 | Quality Assurance, HSE and Compliance Control | Have cost, programme and compliance implications of quality inspections - legal authority been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | OHS Act 85 of 1993; Construction Regulations, 2014; HSE file | Yes / No / N/A + Score 0–5 + Rating
31.008 | 31 | WP31 | Quality Assurance, HSE and Compliance Control | Has the team obtained written confirmation or documented proof for HSE audits - legal authority? | Current certificate/letter/report, version control and document-control entry. | JBCC/NEC/FIDIC contract conditions; QA/QC inspection and test plans | Yes / No / N/A + Score 0–5 + Rating
31.009 | 31 | WP31 | Quality Assurance, HSE and Compliance Control | Does the evidence for environmental monitoring - legal authority support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | NEMA EMPr; municipal inspections; material approvals and payment certification | Yes / No / N/A + Score 0–5 + Rating
31.010 | 31 | WP31 | Quality Assurance, HSE and Compliance Control | Have dependencies linked to material approvals - legal authority been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | OHS Act 85 of 1993; Construction Regulations, 2014; HSE file | Yes / No / N/A + Score 0–5 + Rating
31.011 | 31 | WP31 | Quality Assurance, HSE and Compliance Control | Has the project team confirmed variation control - legal authority in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | JBCC/NEC/FIDIC contract conditions; QA/QC inspection and test plans | Yes / No / N/A + Score 0–5 + Rating
31.012 | 31 | WP31 | Quality Assurance, HSE and Compliance Control | Is there a responsible owner, due date and approval route for payment certification - legal authority? | Register entry, supporting drawing/report, approval note and updated risk item. | NEMA EMPr; municipal inspections; material approvals and payment certification | Yes / No / N/A + Score 0–5 + Rating
31.013 | 31 | WP31 | Quality Assurance, HSE and Compliance Control | Has the gate file tested whether quality inspections - technical feasibility creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | OHS Act 85 of 1993; Construction Regulations, 2014; HSE file | Yes / No / N/A + Score 0–5 + Rating
31.014 | 31 | WP31 | Quality Assurance, HSE and Compliance Control | Are assumptions for HSE audits - technical feasibility documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | JBCC/NEC/FIDIC contract conditions; QA/QC inspection and test plans | Yes / No / N/A + Score 0–5 + Rating
31.015 | 31 | WP31 | Quality Assurance, HSE and Compliance Control | Has the relevant authority, specialist or professional adviser reviewed environmental monitoring - technical feasibility where required? | Authority response, compliance checklist, file note and management approval. | NEMA EMPr; municipal inspections; material approvals and payment certification | Yes / No / N/A + Score 0–5 + Rating
31.016 | 31 | WP31 | Quality Assurance, HSE and Compliance Control | Is the decision record for material approvals - technical feasibility aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | OHS Act 85 of 1993; Construction Regulations, 2014; HSE file | Yes / No / N/A + Score 0–5 + Rating
31.017 | 31 | WP31 | Quality Assurance, HSE and Compliance Control | Have cost, programme and compliance implications of variation control - technical feasibility been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | JBCC/NEC/FIDIC contract conditions; QA/QC inspection and test plans | Yes / No / N/A + Score 0–5 + Rating
31.018 | 31 | WP31 | Quality Assurance, HSE and Compliance Control | Has the team obtained written confirmation or documented proof for payment certification - technical feasibility? | Current certificate/letter/report, version control and document-control entry. | NEMA EMPr; municipal inspections; material approvals and payment certification | Yes / No / N/A + Score 0–5 + Rating
31.019 | 31 | WP31 | Quality Assurance, HSE and Compliance Control | Does the evidence for quality inspections - financial viability support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | OHS Act 85 of 1993; Construction Regulations, 2014; HSE file | Yes / No / N/A + Score 0–5 + Rating
31.020 | 31 | WP31 | Quality Assurance, HSE and Compliance Control | Have dependencies linked to HSE audits - financial viability been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | JBCC/NEC/FIDIC contract conditions; QA/QC inspection and test plans | Yes / No / N/A + Score 0–5 + Rating
31.021 | 31 | WP31 | Quality Assurance, HSE and Compliance Control | Has the project team confirmed environmental monitoring - financial viability in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | NEMA EMPr; municipal inspections; material approvals and payment certification | Yes / No / N/A + Score 0–5 + Rating
31.022 | 31 | WP31 | Quality Assurance, HSE and Compliance Control | Is there a responsible owner, due date and approval route for material approvals - financial viability? | Register entry, supporting drawing/report, approval note and updated risk item. | OHS Act 85 of 1993; Construction Regulations, 2014; HSE file | Yes / No / N/A + Score 0–5 + Rating
31.023 | 31 | WP31 | Quality Assurance, HSE and Compliance Control | Has the gate file tested whether variation control - financial viability creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | JBCC/NEC/FIDIC contract conditions; QA/QC inspection and test plans | Yes / No / N/A + Score 0–5 + Rating
31.024 | 31 | WP31 | Quality Assurance, HSE and Compliance Control | Are assumptions for payment certification - financial viability documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | NEMA EMPr; municipal inspections; material approvals and payment certification | Yes / No / N/A + Score 0–5 + Rating
31.025 | 31 | WP31 | Quality Assurance, HSE and Compliance Control | Has the relevant authority, specialist or professional adviser reviewed quality inspections - programme impact where required? | Authority response, compliance checklist, file note and management approval. | OHS Act 85 of 1993; Construction Regulations, 2014; HSE file | Yes / No / N/A + Score 0–5 + Rating
31.026 | 31 | WP31 | Quality Assurance, HSE and Compliance Control | Is the decision record for HSE audits - programme impact aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | JBCC/NEC/FIDIC contract conditions; QA/QC inspection and test plans | Yes / No / N/A + Score 0–5 + Rating
31.027 | 31 | WP31 | Quality Assurance, HSE and Compliance Control | Have cost, programme and compliance implications of environmental monitoring - programme impact been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | NEMA EMPr; municipal inspections; material approvals and payment certification | Yes / No / N/A + Score 0–5 + Rating
31.028 | 31 | WP31 | Quality Assurance, HSE and Compliance Control | Has the team obtained written confirmation or documented proof for material approvals - programme impact? | Current certificate/letter/report, version control and document-control entry. | OHS Act 85 of 1993; Construction Regulations, 2014; HSE file | Yes / No / N/A + Score 0–5 + Rating
31.029 | 31 | WP31 | Quality Assurance, HSE and Compliance Control | Does the evidence for variation control - programme impact support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | JBCC/NEC/FIDIC contract conditions; QA/QC inspection and test plans | Yes / No / N/A + Score 0–5 + Rating
31.030 | 31 | WP31 | Quality Assurance, HSE and Compliance Control | Have dependencies linked to payment certification - programme impact been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | NEMA EMPr; municipal inspections; material approvals and payment certification | Yes / No / N/A + Score 0–5 + Rating
31.031 | 31 | WP31 | Quality Assurance, HSE and Compliance Control | Has the project team confirmed quality inspections - risk mitigation in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | OHS Act 85 of 1993; Construction Regulations, 2014; HSE file | Yes / No / N/A + Score 0–5 + Rating
31.032 | 31 | WP31 | Quality Assurance, HSE and Compliance Control | Is there a responsible owner, due date and approval route for HSE audits - risk mitigation? | Register entry, supporting drawing/report, approval note and updated risk item. | JBCC/NEC/FIDIC contract conditions; QA/QC inspection and test plans | Yes / No / N/A + Score 0–5 + Rating
31.033 | 31 | WP31 | Quality Assurance, HSE and Compliance Control | Has the gate file tested whether environmental monitoring - risk mitigation creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | NEMA EMPr; municipal inspections; material approvals and payment certification | Yes / No / N/A + Score 0–5 + Rating
31.034 | 31 | WP31 | Quality Assurance, HSE and Compliance Control | Are assumptions for material approvals - risk mitigation documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | OHS Act 85 of 1993; Construction Regulations, 2014; HSE file | Yes / No / N/A + Score 0–5 + Rating
31.035 | 31 | WP31 | Quality Assurance, HSE and Compliance Control | Has the relevant authority, specialist or professional adviser reviewed variation control - risk mitigation where required? | Authority response, compliance checklist, file note and management approval. | JBCC/NEC/FIDIC contract conditions; QA/QC inspection and test plans | Yes / No / N/A + Score 0–5 + Rating
31.036 | 31 | WP31 | Quality Assurance, HSE and Compliance Control | Is the decision record for payment certification - risk mitigation aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | NEMA EMPr; municipal inspections; material approvals and payment certification | Yes / No / N/A + Score 0–5 + Rating
31.037 | 31 | WP31 | Quality Assurance, HSE and Compliance Control | Have cost, programme and compliance implications of quality inspections - stakeholder acceptance been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | OHS Act 85 of 1993; Construction Regulations, 2014; HSE file | Yes / No / N/A + Score 0–5 + Rating
31.038 | 31 | WP31 | Quality Assurance, HSE and Compliance Control | Has the team obtained written confirmation or documented proof for HSE audits - stakeholder acceptance? | Current certificate/letter/report, version control and document-control entry. | JBCC/NEC/FIDIC contract conditions; QA/QC inspection and test plans | Yes / No / N/A + Score 0–5 + Rating
31.039 | 31 | WP31 | Quality Assurance, HSE and Compliance Control | Does the evidence for environmental monitoring - stakeholder acceptance support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | NEMA EMPr; municipal inspections; material approvals and payment certification | Yes / No / N/A + Score 0–5 + Rating
31.040 | 31 | WP31 | Quality Assurance, HSE and Compliance Control | Have dependencies linked to material approvals - stakeholder acceptance been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | OHS Act 85 of 1993; Construction Regulations, 2014; HSE file | Yes / No / N/A + Score 0–5 + Rating
31.041 | 31 | WP31 | Quality Assurance, HSE and Compliance Control | Has the project team confirmed variation control - stakeholder acceptance in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | JBCC/NEC/FIDIC contract conditions; QA/QC inspection and test plans | Yes / No / N/A + Score 0–5 + Rating
31.042 | 31 | WP31 | Quality Assurance, HSE and Compliance Control | Is there a responsible owner, due date and approval route for payment certification - stakeholder acceptance? | Register entry, supporting drawing/report, approval note and updated risk item. | NEMA EMPr; municipal inspections; material approvals and payment certification | Yes / No / N/A + Score 0–5 + Rating
31.043 | 31 | WP31 | Quality Assurance, HSE and Compliance Control | Has the gate file tested whether quality inspections - document control creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | OHS Act 85 of 1993; Construction Regulations, 2014; HSE file | Yes / No / N/A + Score 0–5 + Rating
31.044 | 31 | WP31 | Quality Assurance, HSE and Compliance Control | Are assumptions for HSE audits - document control documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | JBCC/NEC/FIDIC contract conditions; QA/QC inspection and test plans | Yes / No / N/A + Score 0–5 + Rating
31.045 | 31 | WP31 | Quality Assurance, HSE and Compliance Control | Has the relevant authority, specialist or professional adviser reviewed environmental monitoring - document control where required? | Authority response, compliance checklist, file note and management approval. | NEMA EMPr; municipal inspections; material approvals and payment certification | Yes / No / N/A + Score 0–5 + Rating
31.046 | 31 | WP31 | Quality Assurance, HSE and Compliance Control | Is the decision record for material approvals - document control aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | OHS Act 85 of 1993; Construction Regulations, 2014; HSE file | Yes / No / N/A + Score 0–5 + Rating
31.047 | 31 | WP31 | Quality Assurance, HSE and Compliance Control | Have cost, programme and compliance implications of variation control - document control been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | JBCC/NEC/FIDIC contract conditions; QA/QC inspection and test plans | Yes / No / N/A + Score 0–5 + Rating
31.048 | 31 | WP31 | Quality Assurance, HSE and Compliance Control | Has the team obtained written confirmation or documented proof for payment certification - document control? | Current certificate/letter/report, version control and document-control entry. | NEMA EMPr; municipal inspections; material approvals and payment certification | Yes / No / N/A + Score 0–5 + Rating
31.049 | 31 | WP31 | Quality Assurance, HSE and Compliance Control | Does the evidence for quality inspections - professional certification support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | OHS Act 85 of 1993; Construction Regulations, 2014; HSE file | Yes / No / N/A + Score 0–5 + Rating
31.050 | 31 | WP31 | Quality Assurance, HSE and Compliance Control | Have dependencies linked to HSE audits - professional certification been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | JBCC/NEC/FIDIC contract conditions; QA/QC inspection and test plans | Yes / No / N/A + Score 0–5 + Rating
31.051 | 31 | WP31 | Quality Assurance, HSE and Compliance Control | Has the project team confirmed environmental monitoring - professional certification in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | NEMA EMPr; municipal inspections; material approvals and payment certification | Yes / No / N/A + Score 0–5 + Rating
31.052 | 31 | WP31 | Quality Assurance, HSE and Compliance Control | Is there a responsible owner, due date and approval route for material approvals - professional certification? | Register entry, supporting drawing/report, approval note and updated risk item. | OHS Act 85 of 1993; Construction Regulations, 2014; HSE file | Yes / No / N/A + Score 0–5 + Rating
31.053 | 31 | WP31 | Quality Assurance, HSE and Compliance Control | Has the gate file tested whether variation control - professional certification creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | JBCC/NEC/FIDIC contract conditions; QA/QC inspection and test plans | Yes / No / N/A + Score 0–5 + Rating
31.054 | 31 | WP31 | Quality Assurance, HSE and Compliance Control | Are assumptions for payment certification - professional certification documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | NEMA EMPr; municipal inspections; material approvals and payment certification | Yes / No / N/A + Score 0–5 + Rating
31.055 | 31 | WP31 | Quality Assurance, HSE and Compliance Control | Has the relevant authority, specialist or professional adviser reviewed quality inspections - implementation readiness where required? | Authority response, compliance checklist, file note and management approval. | OHS Act 85 of 1993; Construction Regulations, 2014; HSE file | Yes / No / N/A + Score 0–5 + Rating
31.056 | 31 | WP31 | Quality Assurance, HSE and Compliance Control | Is the decision record for HSE audits - implementation readiness aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | JBCC/NEC/FIDIC contract conditions; QA/QC inspection and test plans | Yes / No / N/A + Score 0–5 + Rating
31.057 | 31 | WP31 | Quality Assurance, HSE and Compliance Control | Have cost, programme and compliance implications of environmental monitoring - implementation readiness been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | NEMA EMPr; municipal inspections; material approvals and payment certification | Yes / No / N/A + Score 0–5 + Rating
31.058 | 31 | WP31 | Quality Assurance, HSE and Compliance Control | Has the team obtained written confirmation or documented proof for material approvals - implementation readiness? | Current certificate/letter/report, version control and document-control entry. | OHS Act 85 of 1993; Construction Regulations, 2014; HSE file | Yes / No / N/A + Score 0–5 + Rating
31.059 | 31 | WP31 | Quality Assurance, HSE and Compliance Control | Does the evidence for variation control - implementation readiness support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | JBCC/NEC/FIDIC contract conditions; QA/QC inspection and test plans | Yes / No / N/A + Score 0–5 + Rating
31.060 | 31 | WP31 | Quality Assurance, HSE and Compliance Control | Have dependencies linked to payment certification - implementation readiness been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | NEMA EMPr; municipal inspections; material approvals and payment certification | Yes / No / N/A + Score 0–5 + Rating
31.061 | 31 | WP31 | Quality Assurance, HSE and Compliance Control | Has the project team confirmed quality inspections - governance approval in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | OHS Act 85 of 1993; Construction Regulations, 2014; HSE file | Yes / No / N/A + Score 0–5 + Rating
31.062 | 31 | WP31 | Quality Assurance, HSE and Compliance Control | Is there a responsible owner, due date and approval route for HSE audits - governance approval? | Register entry, supporting drawing/report, approval note and updated risk item. | JBCC/NEC/FIDIC contract conditions; QA/QC inspection and test plans | Yes / No / N/A + Score 0–5 + Rating
31.063 | 31 | WP31 | Quality Assurance, HSE and Compliance Control | Has the gate file tested whether environmental monitoring - governance approval creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | NEMA EMPr; municipal inspections; material approvals and payment certification | Yes / No / N/A + Score 0–5 + Rating
31.064 | 31 | WP31 | Quality Assurance, HSE and Compliance Control | Are assumptions for material approvals - governance approval documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | OHS Act 85 of 1993; Construction Regulations, 2014; HSE file | Yes / No / N/A + Score 0–5 + Rating
31.065 | 31 | WP31 | Quality Assurance, HSE and Compliance Control | Has the relevant authority, specialist or professional adviser reviewed variation control - governance approval where required? | Authority response, compliance checklist, file note and management approval. | JBCC/NEC/FIDIC contract conditions; QA/QC inspection and test plans | Yes / No / N/A + Score 0–5 + Rating
31.066 | 31 | WP31 | Quality Assurance, HSE and Compliance Control | Is the decision record for payment certification - governance approval aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | NEMA EMPr; municipal inspections; material approvals and payment certification | Yes / No / N/A + Score 0–5 + Rating
31.067 | 31 | WP31 | Quality Assurance, HSE and Compliance Control | Have cost, programme and compliance implications of quality inspections - legal authority been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | OHS Act 85 of 1993; Construction Regulations, 2014; HSE file | Yes / No / N/A + Score 0–5 + Rating
31.068 | 31 | WP31 | Quality Assurance, HSE and Compliance Control | Has the team obtained written confirmation or documented proof for HSE audits - legal authority? | Current certificate/letter/report, version control and document-control entry. | JBCC/NEC/FIDIC contract conditions; QA/QC inspection and test plans | Yes / No / N/A + Score 0–5 + Rating
31.069 | 31 | WP31 | Quality Assurance, HSE and Compliance Control | Does the evidence for environmental monitoring - legal authority support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | NEMA EMPr; municipal inspections; material approvals and payment certification | Yes / No / N/A + Score 0–5 + Rating
31.070 | 31 | WP31 | Quality Assurance, HSE and Compliance Control | Have dependencies linked to material approvals - legal authority been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | OHS Act 85 of 1993; Construction Regulations, 2014; HSE file | Yes / No / N/A + Score 0–5 + Rating
31.071 | 31 | WP31 | Quality Assurance, HSE and Compliance Control | Has the project team confirmed variation control - legal authority in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | JBCC/NEC/FIDIC contract conditions; QA/QC inspection and test plans | Yes / No / N/A + Score 0–5 + Rating
31.072 | 31 | WP31 | Quality Assurance, HSE and Compliance Control | Is there a responsible owner, due date and approval route for payment certification - legal authority? | Register entry, supporting drawing/report, approval note and updated risk item. | NEMA EMPr; municipal inspections; material approvals and payment certification | Yes / No / N/A + Score 0–5 + Rating
31.073 | 31 | WP31 | Quality Assurance, HSE and Compliance Control | Has the gate file tested whether quality inspections - technical feasibility creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | OHS Act 85 of 1993; Construction Regulations, 2014; HSE file | Yes / No / N/A + Score 0–5 + Rating
31.074 | 31 | WP31 | Quality Assurance, HSE and Compliance Control | Are assumptions for HSE audits - technical feasibility documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | JBCC/NEC/FIDIC contract conditions; QA/QC inspection and test plans | Yes / No / N/A + Score 0–5 + Rating
31.075 | 31 | WP31 | Quality Assurance, HSE and Compliance Control | Has the relevant authority, specialist or professional adviser reviewed environmental monitoring - technical feasibility where required? | Authority response, compliance checklist, file note and management approval. | NEMA EMPr; municipal inspections; material approvals and payment certification | Yes / No / N/A + Score 0–5 + Rating
31.076 | 31 | WP31 | Quality Assurance, HSE and Compliance Control | Is the decision record for material approvals - technical feasibility aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | OHS Act 85 of 1993; Construction Regulations, 2014; HSE file | Yes / No / N/A + Score 0–5 + Rating
31.077 | 31 | WP31 | Quality Assurance, HSE and Compliance Control | Have cost, programme and compliance implications of variation control - technical feasibility been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | JBCC/NEC/FIDIC contract conditions; QA/QC inspection and test plans | Yes / No / N/A + Score 0–5 + Rating
31.078 | 31 | WP31 | Quality Assurance, HSE and Compliance Control | Has the team obtained written confirmation or documented proof for payment certification - technical feasibility? | Current certificate/letter/report, version control and document-control entry. | NEMA EMPr; municipal inspections; material approvals and payment certification | Yes / No / N/A + Score 0–5 + Rating
31.079 | 31 | WP31 | Quality Assurance, HSE and Compliance Control | Does the evidence for quality inspections - financial viability support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | OHS Act 85 of 1993; Construction Regulations, 2014; HSE file | Yes / No / N/A + Score 0–5 + Rating
31.080 | 31 | WP31 | Quality Assurance, HSE and Compliance Control | Have dependencies linked to HSE audits - financial viability been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | JBCC/NEC/FIDIC contract conditions; QA/QC inspection and test plans | Yes / No / N/A + Score 0–5 + Rating
31.081 | 31 | WP31 | Quality Assurance, HSE and Compliance Control | Has the project team confirmed environmental monitoring - financial viability in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | NEMA EMPr; municipal inspections; material approvals and payment certification | Yes / No / N/A + Score 0–5 + Rating
31.082 | 31 | WP31 | Quality Assurance, HSE and Compliance Control | Is there a responsible owner, due date and approval route for material approvals - financial viability? | Register entry, supporting drawing/report, approval note and updated risk item. | OHS Act 85 of 1993; Construction Regulations, 2014; HSE file | Yes / No / N/A + Score 0–5 + Rating
31.083 | 31 | WP31 | Quality Assurance, HSE and Compliance Control | Has the gate file tested whether variation control - financial viability creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | JBCC/NEC/FIDIC contract conditions; QA/QC inspection and test plans | Yes / No / N/A + Score 0–5 + Rating
31.084 | 31 | WP31 | Quality Assurance, HSE and Compliance Control | Are assumptions for payment certification - financial viability documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | NEMA EMPr; municipal inspections; material approvals and payment certification | Yes / No / N/A + Score 0–5 + Rating
31.085 | 31 | WP31 | Quality Assurance, HSE and Compliance Control | Has the relevant authority, specialist or professional adviser reviewed quality inspections - programme impact where required? | Authority response, compliance checklist, file note and management approval. | OHS Act 85 of 1993; Construction Regulations, 2014; HSE file | Yes / No / N/A + Score 0–5 + Rating
31.086 | 31 | WP31 | Quality Assurance, HSE and Compliance Control | Is the decision record for HSE audits - programme impact aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | JBCC/NEC/FIDIC contract conditions; QA/QC inspection and test plans | Yes / No / N/A + Score 0–5 + Rating
31.087 | 31 | WP31 | Quality Assurance, HSE and Compliance Control | Have cost, programme and compliance implications of environmental monitoring - programme impact been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | NEMA EMPr; municipal inspections; material approvals and payment certification | Yes / No / N/A + Score 0–5 + Rating
31.088 | 31 | WP31 | Quality Assurance, HSE and Compliance Control | Has the team obtained written confirmation or documented proof for material approvals - programme impact? | Current certificate/letter/report, version control and document-control entry. | OHS Act 85 of 1993; Construction Regulations, 2014; HSE file | Yes / No / N/A + Score 0–5 + Rating
31.089 | 31 | WP31 | Quality Assurance, HSE and Compliance Control | Does the evidence for variation control - programme impact support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | JBCC/NEC/FIDIC contract conditions; QA/QC inspection and test plans | Yes / No / N/A + Score 0–5 + Rating
31.090 | 31 | WP31 | Quality Assurance, HSE and Compliance Control | Have dependencies linked to payment certification - programme impact been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | NEMA EMPr; municipal inspections; material approvals and payment certification | Yes / No / N/A + Score 0–5 + Rating
31.091 | 31 | WP31 | Quality Assurance, HSE and Compliance Control | Has the project team confirmed quality inspections - risk mitigation in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | OHS Act 85 of 1993; Construction Regulations, 2014; HSE file | Yes / No / N/A + Score 0–5 + Rating
31.092 | 31 | WP31 | Quality Assurance, HSE and Compliance Control | Is there a responsible owner, due date and approval route for HSE audits - risk mitigation? | Register entry, supporting drawing/report, approval note and updated risk item. | JBCC/NEC/FIDIC contract conditions; QA/QC inspection and test plans | Yes / No / N/A + Score 0–5 + Rating
31.093 | 31 | WP31 | Quality Assurance, HSE and Compliance Control | Has the gate file tested whether environmental monitoring - risk mitigation creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | NEMA EMPr; municipal inspections; material approvals and payment certification | Yes / No / N/A + Score 0–5 + Rating
31.094 | 31 | WP31 | Quality Assurance, HSE and Compliance Control | Are assumptions for material approvals - risk mitigation documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | OHS Act 85 of 1993; Construction Regulations, 2014; HSE file | Yes / No / N/A + Score 0–5 + Rating
31.095 | 31 | WP31 | Quality Assurance, HSE and Compliance Control | Has the relevant authority, specialist or professional adviser reviewed variation control - risk mitigation where required? | Authority response, compliance checklist, file note and management approval. | JBCC/NEC/FIDIC contract conditions; QA/QC inspection and test plans | Yes / No / N/A + Score 0–5 + Rating
31.096 | 31 | WP31 | Quality Assurance, HSE and Compliance Control | Is the decision record for payment certification - risk mitigation aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | NEMA EMPr; municipal inspections; material approvals and payment certification | Yes / No / N/A + Score 0–5 + Rating
31.097 | 31 | WP31 | Quality Assurance, HSE and Compliance Control | Have cost, programme and compliance implications of quality inspections - stakeholder acceptance been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | OHS Act 85 of 1993; Construction Regulations, 2014; HSE file | Yes / No / N/A + Score 0–5 + Rating
31.098 | 31 | WP31 | Quality Assurance, HSE and Compliance Control | Has the team obtained written confirmation or documented proof for HSE audits - stakeholder acceptance? | Current certificate/letter/report, version control and document-control entry. | JBCC/NEC/FIDIC contract conditions; QA/QC inspection and test plans | Yes / No / N/A + Score 0–5 + Rating
31.099 | 31 | WP31 | Quality Assurance, HSE and Compliance Control | Does the evidence for environmental monitoring - stakeholder acceptance support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | NEMA EMPr; municipal inspections; material approvals and payment certification | Yes / No / N/A + Score 0–5 + Rating
31.100 | 31 | WP31 | Quality Assurance, HSE and Compliance Control | Have dependencies linked to material approvals - stakeholder acceptance been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | OHS Act 85 of 1993; Construction Regulations, 2014; HSE file | Yes / No / N/A + Score 0–5 + Rating
32.001 | 32 | WP32 | Commissioning and Testing | Has the project team confirmed electrical testing - governance approval in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
32.002 | 32 | WP32 | Commissioning and Testing | Is there a responsible owner, due date and approval route for water pressure testing - governance approval? | Register entry, supporting drawing/report, approval note and updated risk item. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
32.003 | 32 | WP32 | Commissioning and Testing | Has the gate file tested whether fire system testing - governance approval creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
32.004 | 32 | WP32 | Commissioning and Testing | Are assumptions for stormwater checks - governance approval documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
32.005 | 32 | WP32 | Commissioning and Testing | Has the relevant authority, specialist or professional adviser reviewed HVAC testing - governance approval where required? | Authority response, compliance checklist, file note and management approval. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
32.006 | 32 | WP32 | Commissioning and Testing | Is the decision record for ICT testing - governance approval aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
32.007 | 32 | WP32 | Commissioning and Testing | Have cost, programme and compliance implications of electrical testing - legal authority been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
32.008 | 32 | WP32 | Commissioning and Testing | Has the team obtained written confirmation or documented proof for water pressure testing - legal authority? | Current certificate/letter/report, version control and document-control entry. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
32.009 | 32 | WP32 | Commissioning and Testing | Does the evidence for fire system testing - legal authority support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
32.010 | 32 | WP32 | Commissioning and Testing | Have dependencies linked to stormwater checks - legal authority been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
32.011 | 32 | WP32 | Commissioning and Testing | Has the project team confirmed HVAC testing - legal authority in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
32.012 | 32 | WP32 | Commissioning and Testing | Is there a responsible owner, due date and approval route for ICT testing - legal authority? | Register entry, supporting drawing/report, approval note and updated risk item. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
32.013 | 32 | WP32 | Commissioning and Testing | Has the gate file tested whether electrical testing - technical feasibility creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
32.014 | 32 | WP32 | Commissioning and Testing | Are assumptions for water pressure testing - technical feasibility documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
32.015 | 32 | WP32 | Commissioning and Testing | Has the relevant authority, specialist or professional adviser reviewed fire system testing - technical feasibility where required? | Authority response, compliance checklist, file note and management approval. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
32.016 | 32 | WP32 | Commissioning and Testing | Is the decision record for stormwater checks - technical feasibility aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
32.017 | 32 | WP32 | Commissioning and Testing | Have cost, programme and compliance implications of HVAC testing - technical feasibility been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
32.018 | 32 | WP32 | Commissioning and Testing | Has the team obtained written confirmation or documented proof for ICT testing - technical feasibility? | Current certificate/letter/report, version control and document-control entry. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
32.019 | 32 | WP32 | Commissioning and Testing | Does the evidence for electrical testing - financial viability support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
32.020 | 32 | WP32 | Commissioning and Testing | Have dependencies linked to water pressure testing - financial viability been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
32.021 | 32 | WP32 | Commissioning and Testing | Has the project team confirmed fire system testing - financial viability in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
32.022 | 32 | WP32 | Commissioning and Testing | Is there a responsible owner, due date and approval route for stormwater checks - financial viability? | Register entry, supporting drawing/report, approval note and updated risk item. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
32.023 | 32 | WP32 | Commissioning and Testing | Has the gate file tested whether HVAC testing - financial viability creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
32.024 | 32 | WP32 | Commissioning and Testing | Are assumptions for ICT testing - financial viability documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
32.025 | 32 | WP32 | Commissioning and Testing | Has the relevant authority, specialist or professional adviser reviewed electrical testing - programme impact where required? | Authority response, compliance checklist, file note and management approval. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
32.026 | 32 | WP32 | Commissioning and Testing | Is the decision record for water pressure testing - programme impact aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
32.027 | 32 | WP32 | Commissioning and Testing | Have cost, programme and compliance implications of fire system testing - programme impact been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
32.028 | 32 | WP32 | Commissioning and Testing | Has the team obtained written confirmation or documented proof for stormwater checks - programme impact? | Current certificate/letter/report, version control and document-control entry. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
32.029 | 32 | WP32 | Commissioning and Testing | Does the evidence for HVAC testing - programme impact support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
32.030 | 32 | WP32 | Commissioning and Testing | Have dependencies linked to ICT testing - programme impact been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
32.031 | 32 | WP32 | Commissioning and Testing | Has the project team confirmed electrical testing - risk mitigation in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
32.032 | 32 | WP32 | Commissioning and Testing | Is there a responsible owner, due date and approval route for water pressure testing - risk mitigation? | Register entry, supporting drawing/report, approval note and updated risk item. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
32.033 | 32 | WP32 | Commissioning and Testing | Has the gate file tested whether fire system testing - risk mitigation creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
32.034 | 32 | WP32 | Commissioning and Testing | Are assumptions for stormwater checks - risk mitigation documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
32.035 | 32 | WP32 | Commissioning and Testing | Has the relevant authority, specialist or professional adviser reviewed HVAC testing - risk mitigation where required? | Authority response, compliance checklist, file note and management approval. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
32.036 | 32 | WP32 | Commissioning and Testing | Is the decision record for ICT testing - risk mitigation aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
32.037 | 32 | WP32 | Commissioning and Testing | Have cost, programme and compliance implications of electrical testing - stakeholder acceptance been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
32.038 | 32 | WP32 | Commissioning and Testing | Has the team obtained written confirmation or documented proof for water pressure testing - stakeholder acceptance? | Current certificate/letter/report, version control and document-control entry. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
32.039 | 32 | WP32 | Commissioning and Testing | Does the evidence for fire system testing - stakeholder acceptance support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
32.040 | 32 | WP32 | Commissioning and Testing | Have dependencies linked to stormwater checks - stakeholder acceptance been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
32.041 | 32 | WP32 | Commissioning and Testing | Has the project team confirmed HVAC testing - stakeholder acceptance in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
32.042 | 32 | WP32 | Commissioning and Testing | Is there a responsible owner, due date and approval route for ICT testing - stakeholder acceptance? | Register entry, supporting drawing/report, approval note and updated risk item. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
32.043 | 32 | WP32 | Commissioning and Testing | Has the gate file tested whether electrical testing - document control creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
32.044 | 32 | WP32 | Commissioning and Testing | Are assumptions for water pressure testing - document control documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
32.045 | 32 | WP32 | Commissioning and Testing | Has the relevant authority, specialist or professional adviser reviewed fire system testing - document control where required? | Authority response, compliance checklist, file note and management approval. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
32.046 | 32 | WP32 | Commissioning and Testing | Is the decision record for stormwater checks - document control aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
32.047 | 32 | WP32 | Commissioning and Testing | Have cost, programme and compliance implications of HVAC testing - document control been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
32.048 | 32 | WP32 | Commissioning and Testing | Has the team obtained written confirmation or documented proof for ICT testing - document control? | Current certificate/letter/report, version control and document-control entry. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
32.049 | 32 | WP32 | Commissioning and Testing | Does the evidence for electrical testing - professional certification support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
32.050 | 32 | WP32 | Commissioning and Testing | Have dependencies linked to water pressure testing - professional certification been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
32.051 | 32 | WP32 | Commissioning and Testing | Has the project team confirmed fire system testing - professional certification in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
32.052 | 32 | WP32 | Commissioning and Testing | Is there a responsible owner, due date and approval route for stormwater checks - professional certification? | Register entry, supporting drawing/report, approval note and updated risk item. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
32.053 | 32 | WP32 | Commissioning and Testing | Has the gate file tested whether HVAC testing - professional certification creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
32.054 | 32 | WP32 | Commissioning and Testing | Are assumptions for ICT testing - professional certification documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
32.055 | 32 | WP32 | Commissioning and Testing | Has the relevant authority, specialist or professional adviser reviewed electrical testing - implementation readiness where required? | Authority response, compliance checklist, file note and management approval. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
32.056 | 32 | WP32 | Commissioning and Testing | Is the decision record for water pressure testing - implementation readiness aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
32.057 | 32 | WP32 | Commissioning and Testing | Have cost, programme and compliance implications of fire system testing - implementation readiness been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
32.058 | 32 | WP32 | Commissioning and Testing | Has the team obtained written confirmation or documented proof for stormwater checks - implementation readiness? | Current certificate/letter/report, version control and document-control entry. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
32.059 | 32 | WP32 | Commissioning and Testing | Does the evidence for HVAC testing - implementation readiness support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
32.060 | 32 | WP32 | Commissioning and Testing | Have dependencies linked to ICT testing - implementation readiness been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
32.061 | 32 | WP32 | Commissioning and Testing | Has the project team confirmed electrical testing - governance approval in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
32.062 | 32 | WP32 | Commissioning and Testing | Is there a responsible owner, due date and approval route for water pressure testing - governance approval? | Register entry, supporting drawing/report, approval note and updated risk item. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
32.063 | 32 | WP32 | Commissioning and Testing | Has the gate file tested whether fire system testing - governance approval creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
32.064 | 32 | WP32 | Commissioning and Testing | Are assumptions for stormwater checks - governance approval documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
32.065 | 32 | WP32 | Commissioning and Testing | Has the relevant authority, specialist or professional adviser reviewed HVAC testing - governance approval where required? | Authority response, compliance checklist, file note and management approval. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
32.066 | 32 | WP32 | Commissioning and Testing | Is the decision record for ICT testing - governance approval aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
32.067 | 32 | WP32 | Commissioning and Testing | Have cost, programme and compliance implications of electrical testing - legal authority been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
32.068 | 32 | WP32 | Commissioning and Testing | Has the team obtained written confirmation or documented proof for water pressure testing - legal authority? | Current certificate/letter/report, version control and document-control entry. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
32.069 | 32 | WP32 | Commissioning and Testing | Does the evidence for fire system testing - legal authority support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
32.070 | 32 | WP32 | Commissioning and Testing | Have dependencies linked to stormwater checks - legal authority been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
32.071 | 32 | WP32 | Commissioning and Testing | Has the project team confirmed HVAC testing - legal authority in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
32.072 | 32 | WP32 | Commissioning and Testing | Is there a responsible owner, due date and approval route for ICT testing - legal authority? | Register entry, supporting drawing/report, approval note and updated risk item. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
32.073 | 32 | WP32 | Commissioning and Testing | Has the gate file tested whether electrical testing - technical feasibility creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
32.074 | 32 | WP32 | Commissioning and Testing | Are assumptions for water pressure testing - technical feasibility documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
32.075 | 32 | WP32 | Commissioning and Testing | Has the relevant authority, specialist or professional adviser reviewed fire system testing - technical feasibility where required? | Authority response, compliance checklist, file note and management approval. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
32.076 | 32 | WP32 | Commissioning and Testing | Is the decision record for stormwater checks - technical feasibility aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
32.077 | 32 | WP32 | Commissioning and Testing | Have cost, programme and compliance implications of HVAC testing - technical feasibility been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
32.078 | 32 | WP32 | Commissioning and Testing | Has the team obtained written confirmation or documented proof for ICT testing - technical feasibility? | Current certificate/letter/report, version control and document-control entry. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
32.079 | 32 | WP32 | Commissioning and Testing | Does the evidence for electrical testing - financial viability support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
32.080 | 32 | WP32 | Commissioning and Testing | Have dependencies linked to water pressure testing - financial viability been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
32.081 | 32 | WP32 | Commissioning and Testing | Has the project team confirmed fire system testing - financial viability in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
32.082 | 32 | WP32 | Commissioning and Testing | Is there a responsible owner, due date and approval route for stormwater checks - financial viability? | Register entry, supporting drawing/report, approval note and updated risk item. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
32.083 | 32 | WP32 | Commissioning and Testing | Has the gate file tested whether HVAC testing - financial viability creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
32.084 | 32 | WP32 | Commissioning and Testing | Are assumptions for ICT testing - financial viability documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
32.085 | 32 | WP32 | Commissioning and Testing | Has the relevant authority, specialist or professional adviser reviewed electrical testing - programme impact where required? | Authority response, compliance checklist, file note and management approval. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
32.086 | 32 | WP32 | Commissioning and Testing | Is the decision record for water pressure testing - programme impact aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
32.087 | 32 | WP32 | Commissioning and Testing | Have cost, programme and compliance implications of fire system testing - programme impact been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
32.088 | 32 | WP32 | Commissioning and Testing | Has the team obtained written confirmation or documented proof for stormwater checks - programme impact? | Current certificate/letter/report, version control and document-control entry. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
32.089 | 32 | WP32 | Commissioning and Testing | Does the evidence for HVAC testing - programme impact support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
32.090 | 32 | WP32 | Commissioning and Testing | Have dependencies linked to ICT testing - programme impact been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
32.091 | 32 | WP32 | Commissioning and Testing | Has the project team confirmed electrical testing - risk mitigation in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
32.092 | 32 | WP32 | Commissioning and Testing | Is there a responsible owner, due date and approval route for water pressure testing - risk mitigation? | Register entry, supporting drawing/report, approval note and updated risk item. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
32.093 | 32 | WP32 | Commissioning and Testing | Has the gate file tested whether fire system testing - risk mitigation creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
32.094 | 32 | WP32 | Commissioning and Testing | Are assumptions for stormwater checks - risk mitigation documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
32.095 | 32 | WP32 | Commissioning and Testing | Has the relevant authority, specialist or professional adviser reviewed HVAC testing - risk mitigation where required? | Authority response, compliance checklist, file note and management approval. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
32.096 | 32 | WP32 | Commissioning and Testing | Is the decision record for ICT testing - risk mitigation aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
32.097 | 32 | WP32 | Commissioning and Testing | Have cost, programme and compliance implications of electrical testing - stakeholder acceptance been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
32.098 | 32 | WP32 | Commissioning and Testing | Has the team obtained written confirmation or documented proof for water pressure testing - stakeholder acceptance? | Current certificate/letter/report, version control and document-control entry. | SANS 10252 water; SANS 10400 fire, access and drainage; professional design certificates | Yes / No / N/A + Score 0–5 + Rating
32.099 | 32 | WP32 | Commissioning and Testing | Does the evidence for fire system testing - stakeholder acceptance support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | SANS/municipal engineering standards; approved SDP; rational fire design | Yes / No / N/A + Score 0–5 + Rating
32.100 | 32 | WP32 | Commissioning and Testing | Have dependencies linked to stormwater checks - stakeholder acceptance been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | Yes / No / N/A + Score 0–5 + Rating
33.001 | 33 | WP33 | Handover to Operators and Tenants | Has the project team confirmed handover manuals - governance approval in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
33.002 | 33 | WP33 | Handover to Operators and Tenants | Is there a responsible owner, due date and approval route for as-built drawings - governance approval? | Register entry, supporting drawing/report, approval note and updated risk item. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
33.003 | 33 | WP33 | Handover to Operators and Tenants | Has the gate file tested whether warranty register - governance approval creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
33.004 | 33 | WP33 | Handover to Operators and Tenants | Are assumptions for tenant certificates - governance approval documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
33.005 | 33 | WP33 | Handover to Operators and Tenants | Has the relevant authority, specialist or professional adviser reviewed maintenance plans - governance approval where required? | Authority response, compliance checklist, file note and management approval. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
33.006 | 33 | WP33 | Handover to Operators and Tenants | Is the decision record for operator training - governance approval aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
33.007 | 33 | WP33 | Handover to Operators and Tenants | Have cost, programme and compliance implications of handover manuals - legal authority been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
33.008 | 33 | WP33 | Handover to Operators and Tenants | Has the team obtained written confirmation or documented proof for as-built drawings - legal authority? | Current certificate/letter/report, version control and document-control entry. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
33.009 | 33 | WP33 | Handover to Operators and Tenants | Does the evidence for warranty register - legal authority support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
33.010 | 33 | WP33 | Handover to Operators and Tenants | Have dependencies linked to tenant certificates - legal authority been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
33.011 | 33 | WP33 | Handover to Operators and Tenants | Has the project team confirmed maintenance plans - legal authority in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
33.012 | 33 | WP33 | Handover to Operators and Tenants | Is there a responsible owner, due date and approval route for operator training - legal authority? | Register entry, supporting drawing/report, approval note and updated risk item. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
33.013 | 33 | WP33 | Handover to Operators and Tenants | Has the gate file tested whether handover manuals - technical feasibility creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
33.014 | 33 | WP33 | Handover to Operators and Tenants | Are assumptions for as-built drawings - technical feasibility documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
33.015 | 33 | WP33 | Handover to Operators and Tenants | Has the relevant authority, specialist or professional adviser reviewed warranty register - technical feasibility where required? | Authority response, compliance checklist, file note and management approval. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
33.016 | 33 | WP33 | Handover to Operators and Tenants | Is the decision record for tenant certificates - technical feasibility aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
33.017 | 33 | WP33 | Handover to Operators and Tenants | Have cost, programme and compliance implications of maintenance plans - technical feasibility been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
33.018 | 33 | WP33 | Handover to Operators and Tenants | Has the team obtained written confirmation or documented proof for operator training - technical feasibility? | Current certificate/letter/report, version control and document-control entry. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
33.019 | 33 | WP33 | Handover to Operators and Tenants | Does the evidence for handover manuals - financial viability support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
33.020 | 33 | WP33 | Handover to Operators and Tenants | Have dependencies linked to as-built drawings - financial viability been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
33.021 | 33 | WP33 | Handover to Operators and Tenants | Has the project team confirmed warranty register - financial viability in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
33.022 | 33 | WP33 | Handover to Operators and Tenants | Is there a responsible owner, due date and approval route for tenant certificates - financial viability? | Register entry, supporting drawing/report, approval note and updated risk item. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
33.023 | 33 | WP33 | Handover to Operators and Tenants | Has the gate file tested whether maintenance plans - financial viability creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
33.024 | 33 | WP33 | Handover to Operators and Tenants | Are assumptions for operator training - financial viability documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
33.025 | 33 | WP33 | Handover to Operators and Tenants | Has the relevant authority, specialist or professional adviser reviewed handover manuals - programme impact where required? | Authority response, compliance checklist, file note and management approval. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
33.026 | 33 | WP33 | Handover to Operators and Tenants | Is the decision record for as-built drawings - programme impact aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
33.027 | 33 | WP33 | Handover to Operators and Tenants | Have cost, programme and compliance implications of warranty register - programme impact been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
33.028 | 33 | WP33 | Handover to Operators and Tenants | Has the team obtained written confirmation or documented proof for tenant certificates - programme impact? | Current certificate/letter/report, version control and document-control entry. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
33.029 | 33 | WP33 | Handover to Operators and Tenants | Does the evidence for maintenance plans - programme impact support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
33.030 | 33 | WP33 | Handover to Operators and Tenants | Have dependencies linked to operator training - programme impact been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
33.031 | 33 | WP33 | Handover to Operators and Tenants | Has the project team confirmed handover manuals - risk mitigation in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
33.032 | 33 | WP33 | Handover to Operators and Tenants | Is there a responsible owner, due date and approval route for as-built drawings - risk mitigation? | Register entry, supporting drawing/report, approval note and updated risk item. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
33.033 | 33 | WP33 | Handover to Operators and Tenants | Has the gate file tested whether warranty register - risk mitigation creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
33.034 | 33 | WP33 | Handover to Operators and Tenants | Are assumptions for tenant certificates - risk mitigation documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
33.035 | 33 | WP33 | Handover to Operators and Tenants | Has the relevant authority, specialist or professional adviser reviewed maintenance plans - risk mitigation where required? | Authority response, compliance checklist, file note and management approval. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
33.036 | 33 | WP33 | Handover to Operators and Tenants | Is the decision record for operator training - risk mitigation aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
33.037 | 33 | WP33 | Handover to Operators and Tenants | Have cost, programme and compliance implications of handover manuals - stakeholder acceptance been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
33.038 | 33 | WP33 | Handover to Operators and Tenants | Has the team obtained written confirmation or documented proof for as-built drawings - stakeholder acceptance? | Current certificate/letter/report, version control and document-control entry. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
33.039 | 33 | WP33 | Handover to Operators and Tenants | Does the evidence for warranty register - stakeholder acceptance support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
33.040 | 33 | WP33 | Handover to Operators and Tenants | Have dependencies linked to tenant certificates - stakeholder acceptance been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
33.041 | 33 | WP33 | Handover to Operators and Tenants | Has the project team confirmed maintenance plans - stakeholder acceptance in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
33.042 | 33 | WP33 | Handover to Operators and Tenants | Is there a responsible owner, due date and approval route for operator training - stakeholder acceptance? | Register entry, supporting drawing/report, approval note and updated risk item. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
33.043 | 33 | WP33 | Handover to Operators and Tenants | Has the gate file tested whether handover manuals - document control creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
33.044 | 33 | WP33 | Handover to Operators and Tenants | Are assumptions for as-built drawings - document control documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
33.045 | 33 | WP33 | Handover to Operators and Tenants | Has the relevant authority, specialist or professional adviser reviewed warranty register - document control where required? | Authority response, compliance checklist, file note and management approval. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
33.046 | 33 | WP33 | Handover to Operators and Tenants | Is the decision record for tenant certificates - document control aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
33.047 | 33 | WP33 | Handover to Operators and Tenants | Have cost, programme and compliance implications of maintenance plans - document control been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
33.048 | 33 | WP33 | Handover to Operators and Tenants | Has the team obtained written confirmation or documented proof for operator training - document control? | Current certificate/letter/report, version control and document-control entry. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
33.049 | 33 | WP33 | Handover to Operators and Tenants | Does the evidence for handover manuals - professional certification support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
33.050 | 33 | WP33 | Handover to Operators and Tenants | Have dependencies linked to as-built drawings - professional certification been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
33.051 | 33 | WP33 | Handover to Operators and Tenants | Has the project team confirmed warranty register - professional certification in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
33.052 | 33 | WP33 | Handover to Operators and Tenants | Is there a responsible owner, due date and approval route for tenant certificates - professional certification? | Register entry, supporting drawing/report, approval note and updated risk item. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
33.053 | 33 | WP33 | Handover to Operators and Tenants | Has the gate file tested whether maintenance plans - professional certification creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
33.054 | 33 | WP33 | Handover to Operators and Tenants | Are assumptions for operator training - professional certification documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
33.055 | 33 | WP33 | Handover to Operators and Tenants | Has the relevant authority, specialist or professional adviser reviewed handover manuals - implementation readiness where required? | Authority response, compliance checklist, file note and management approval. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
33.056 | 33 | WP33 | Handover to Operators and Tenants | Is the decision record for as-built drawings - implementation readiness aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
33.057 | 33 | WP33 | Handover to Operators and Tenants | Have cost, programme and compliance implications of warranty register - implementation readiness been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
33.058 | 33 | WP33 | Handover to Operators and Tenants | Has the team obtained written confirmation or documented proof for tenant certificates - implementation readiness? | Current certificate/letter/report, version control and document-control entry. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
33.059 | 33 | WP33 | Handover to Operators and Tenants | Does the evidence for maintenance plans - implementation readiness support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
33.060 | 33 | WP33 | Handover to Operators and Tenants | Have dependencies linked to operator training - implementation readiness been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
33.061 | 33 | WP33 | Handover to Operators and Tenants | Has the project team confirmed handover manuals - governance approval in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
33.062 | 33 | WP33 | Handover to Operators and Tenants | Is there a responsible owner, due date and approval route for as-built drawings - governance approval? | Register entry, supporting drawing/report, approval note and updated risk item. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
33.063 | 33 | WP33 | Handover to Operators and Tenants | Has the gate file tested whether warranty register - governance approval creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
33.064 | 33 | WP33 | Handover to Operators and Tenants | Are assumptions for tenant certificates - governance approval documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
33.065 | 33 | WP33 | Handover to Operators and Tenants | Has the relevant authority, specialist or professional adviser reviewed maintenance plans - governance approval where required? | Authority response, compliance checklist, file note and management approval. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
33.066 | 33 | WP33 | Handover to Operators and Tenants | Is the decision record for operator training - governance approval aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
33.067 | 33 | WP33 | Handover to Operators and Tenants | Have cost, programme and compliance implications of handover manuals - legal authority been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
33.068 | 33 | WP33 | Handover to Operators and Tenants | Has the team obtained written confirmation or documented proof for as-built drawings - legal authority? | Current certificate/letter/report, version control and document-control entry. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
33.069 | 33 | WP33 | Handover to Operators and Tenants | Does the evidence for warranty register - legal authority support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
33.070 | 33 | WP33 | Handover to Operators and Tenants | Have dependencies linked to tenant certificates - legal authority been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
33.071 | 33 | WP33 | Handover to Operators and Tenants | Has the project team confirmed maintenance plans - legal authority in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
33.072 | 33 | WP33 | Handover to Operators and Tenants | Is there a responsible owner, due date and approval route for operator training - legal authority? | Register entry, supporting drawing/report, approval note and updated risk item. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
33.073 | 33 | WP33 | Handover to Operators and Tenants | Has the gate file tested whether handover manuals - technical feasibility creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
33.074 | 33 | WP33 | Handover to Operators and Tenants | Are assumptions for as-built drawings - technical feasibility documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
33.075 | 33 | WP33 | Handover to Operators and Tenants | Has the relevant authority, specialist or professional adviser reviewed warranty register - technical feasibility where required? | Authority response, compliance checklist, file note and management approval. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
33.076 | 33 | WP33 | Handover to Operators and Tenants | Is the decision record for tenant certificates - technical feasibility aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
33.077 | 33 | WP33 | Handover to Operators and Tenants | Have cost, programme and compliance implications of maintenance plans - technical feasibility been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
33.078 | 33 | WP33 | Handover to Operators and Tenants | Has the team obtained written confirmation or documented proof for operator training - technical feasibility? | Current certificate/letter/report, version control and document-control entry. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
33.079 | 33 | WP33 | Handover to Operators and Tenants | Does the evidence for handover manuals - financial viability support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
33.080 | 33 | WP33 | Handover to Operators and Tenants | Have dependencies linked to as-built drawings - financial viability been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
33.081 | 33 | WP33 | Handover to Operators and Tenants | Has the project team confirmed warranty register - financial viability in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
33.082 | 33 | WP33 | Handover to Operators and Tenants | Is there a responsible owner, due date and approval route for tenant certificates - financial viability? | Register entry, supporting drawing/report, approval note and updated risk item. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
33.083 | 33 | WP33 | Handover to Operators and Tenants | Has the gate file tested whether maintenance plans - financial viability creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
33.084 | 33 | WP33 | Handover to Operators and Tenants | Are assumptions for operator training - financial viability documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
33.085 | 33 | WP33 | Handover to Operators and Tenants | Has the relevant authority, specialist or professional adviser reviewed handover manuals - programme impact where required? | Authority response, compliance checklist, file note and management approval. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
33.086 | 33 | WP33 | Handover to Operators and Tenants | Is the decision record for as-built drawings - programme impact aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
33.087 | 33 | WP33 | Handover to Operators and Tenants | Have cost, programme and compliance implications of warranty register - programme impact been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
33.088 | 33 | WP33 | Handover to Operators and Tenants | Has the team obtained written confirmation or documented proof for tenant certificates - programme impact? | Current certificate/letter/report, version control and document-control entry. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
33.089 | 33 | WP33 | Handover to Operators and Tenants | Does the evidence for maintenance plans - programme impact support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
33.090 | 33 | WP33 | Handover to Operators and Tenants | Have dependencies linked to operator training - programme impact been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
33.091 | 33 | WP33 | Handover to Operators and Tenants | Has the project team confirmed handover manuals - risk mitigation in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
33.092 | 33 | WP33 | Handover to Operators and Tenants | Is there a responsible owner, due date and approval route for as-built drawings - risk mitigation? | Register entry, supporting drawing/report, approval note and updated risk item. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
33.093 | 33 | WP33 | Handover to Operators and Tenants | Has the gate file tested whether warranty register - risk mitigation creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
33.094 | 33 | WP33 | Handover to Operators and Tenants | Are assumptions for tenant certificates - risk mitigation documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
33.095 | 33 | WP33 | Handover to Operators and Tenants | Has the relevant authority, specialist or professional adviser reviewed maintenance plans - risk mitigation where required? | Authority response, compliance checklist, file note and management approval. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
33.096 | 33 | WP33 | Handover to Operators and Tenants | Is the decision record for operator training - risk mitigation aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
33.097 | 33 | WP33 | Handover to Operators and Tenants | Have cost, programme and compliance implications of handover manuals - stakeholder acceptance been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
33.098 | 33 | WP33 | Handover to Operators and Tenants | Has the team obtained written confirmation or documented proof for as-built drawings - stakeholder acceptance? | Current certificate/letter/report, version control and document-control entry. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
33.099 | 33 | WP33 | Handover to Operators and Tenants | Does the evidence for warranty register - stakeholder acceptance support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
33.100 | 33 | WP33 | Handover to Operators and Tenants | Have dependencies linked to tenant certificates - stakeholder acceptance been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
34.001 | 34 | WP34 | Operational Ramp-Up | Has the project team confirmed soft opening - governance approval in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
34.002 | 34 | WP34 | Operational Ramp-Up | Is there a responsible owner, due date and approval route for Boxer opening - governance approval? | Register entry, supporting drawing/report, approval note and updated risk item. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
34.003 | 34 | WP34 | Operational Ramp-Up | Has the gate file tested whether tenant trading readiness - governance approval creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
34.004 | 34 | WP34 | Operational Ramp-Up | Are assumptions for traffic management - governance approval documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
34.005 | 34 | WP34 | Operational Ramp-Up | Has the relevant authority, specialist or professional adviser reviewed customer service - governance approval where required? | Authority response, compliance checklist, file note and management approval. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
34.006 | 34 | WP34 | Operational Ramp-Up | Is the decision record for operations dashboard - governance approval aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
34.007 | 34 | WP34 | Operational Ramp-Up | Have cost, programme and compliance implications of soft opening - legal authority been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
34.008 | 34 | WP34 | Operational Ramp-Up | Has the team obtained written confirmation or documented proof for Boxer opening - legal authority? | Current certificate/letter/report, version control and document-control entry. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
34.009 | 34 | WP34 | Operational Ramp-Up | Does the evidence for tenant trading readiness - legal authority support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
34.010 | 34 | WP34 | Operational Ramp-Up | Have dependencies linked to traffic management - legal authority been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
34.011 | 34 | WP34 | Operational Ramp-Up | Has the project team confirmed customer service - legal authority in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
34.012 | 34 | WP34 | Operational Ramp-Up | Is there a responsible owner, due date and approval route for operations dashboard - legal authority? | Register entry, supporting drawing/report, approval note and updated risk item. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
34.013 | 34 | WP34 | Operational Ramp-Up | Has the gate file tested whether soft opening - technical feasibility creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
34.014 | 34 | WP34 | Operational Ramp-Up | Are assumptions for Boxer opening - technical feasibility documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
34.015 | 34 | WP34 | Operational Ramp-Up | Has the relevant authority, specialist or professional adviser reviewed tenant trading readiness - technical feasibility where required? | Authority response, compliance checklist, file note and management approval. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
34.016 | 34 | WP34 | Operational Ramp-Up | Is the decision record for traffic management - technical feasibility aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
34.017 | 34 | WP34 | Operational Ramp-Up | Have cost, programme and compliance implications of customer service - technical feasibility been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
34.018 | 34 | WP34 | Operational Ramp-Up | Has the team obtained written confirmation or documented proof for operations dashboard - technical feasibility? | Current certificate/letter/report, version control and document-control entry. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
34.019 | 34 | WP34 | Operational Ramp-Up | Does the evidence for soft opening - financial viability support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
34.020 | 34 | WP34 | Operational Ramp-Up | Have dependencies linked to Boxer opening - financial viability been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
34.021 | 34 | WP34 | Operational Ramp-Up | Has the project team confirmed tenant trading readiness - financial viability in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
34.022 | 34 | WP34 | Operational Ramp-Up | Is there a responsible owner, due date and approval route for traffic management - financial viability? | Register entry, supporting drawing/report, approval note and updated risk item. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
34.023 | 34 | WP34 | Operational Ramp-Up | Has the gate file tested whether customer service - financial viability creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
34.024 | 34 | WP34 | Operational Ramp-Up | Are assumptions for operations dashboard - financial viability documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
34.025 | 34 | WP34 | Operational Ramp-Up | Has the relevant authority, specialist or professional adviser reviewed soft opening - programme impact where required? | Authority response, compliance checklist, file note and management approval. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
34.026 | 34 | WP34 | Operational Ramp-Up | Is the decision record for Boxer opening - programme impact aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
34.027 | 34 | WP34 | Operational Ramp-Up | Have cost, programme and compliance implications of tenant trading readiness - programme impact been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
34.028 | 34 | WP34 | Operational Ramp-Up | Has the team obtained written confirmation or documented proof for traffic management - programme impact? | Current certificate/letter/report, version control and document-control entry. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
34.029 | 34 | WP34 | Operational Ramp-Up | Does the evidence for customer service - programme impact support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
34.030 | 34 | WP34 | Operational Ramp-Up | Have dependencies linked to operations dashboard - programme impact been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
34.031 | 34 | WP34 | Operational Ramp-Up | Has the project team confirmed soft opening - risk mitigation in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
34.032 | 34 | WP34 | Operational Ramp-Up | Is there a responsible owner, due date and approval route for Boxer opening - risk mitigation? | Register entry, supporting drawing/report, approval note and updated risk item. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
34.033 | 34 | WP34 | Operational Ramp-Up | Has the gate file tested whether tenant trading readiness - risk mitigation creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
34.034 | 34 | WP34 | Operational Ramp-Up | Are assumptions for traffic management - risk mitigation documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
34.035 | 34 | WP34 | Operational Ramp-Up | Has the relevant authority, specialist or professional adviser reviewed customer service - risk mitigation where required? | Authority response, compliance checklist, file note and management approval. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
34.036 | 34 | WP34 | Operational Ramp-Up | Is the decision record for operations dashboard - risk mitigation aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
34.037 | 34 | WP34 | Operational Ramp-Up | Have cost, programme and compliance implications of soft opening - stakeholder acceptance been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
34.038 | 34 | WP34 | Operational Ramp-Up | Has the team obtained written confirmation or documented proof for Boxer opening - stakeholder acceptance? | Current certificate/letter/report, version control and document-control entry. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
34.039 | 34 | WP34 | Operational Ramp-Up | Does the evidence for tenant trading readiness - stakeholder acceptance support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
34.040 | 34 | WP34 | Operational Ramp-Up | Have dependencies linked to traffic management - stakeholder acceptance been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
34.041 | 34 | WP34 | Operational Ramp-Up | Has the project team confirmed customer service - stakeholder acceptance in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
34.042 | 34 | WP34 | Operational Ramp-Up | Is there a responsible owner, due date and approval route for operations dashboard - stakeholder acceptance? | Register entry, supporting drawing/report, approval note and updated risk item. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
34.043 | 34 | WP34 | Operational Ramp-Up | Has the gate file tested whether soft opening - document control creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
34.044 | 34 | WP34 | Operational Ramp-Up | Are assumptions for Boxer opening - document control documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
34.045 | 34 | WP34 | Operational Ramp-Up | Has the relevant authority, specialist or professional adviser reviewed tenant trading readiness - document control where required? | Authority response, compliance checklist, file note and management approval. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
34.046 | 34 | WP34 | Operational Ramp-Up | Is the decision record for traffic management - document control aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
34.047 | 34 | WP34 | Operational Ramp-Up | Have cost, programme and compliance implications of customer service - document control been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
34.048 | 34 | WP34 | Operational Ramp-Up | Has the team obtained written confirmation or documented proof for operations dashboard - document control? | Current certificate/letter/report, version control and document-control entry. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
34.049 | 34 | WP34 | Operational Ramp-Up | Does the evidence for soft opening - professional certification support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
34.050 | 34 | WP34 | Operational Ramp-Up | Have dependencies linked to Boxer opening - professional certification been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
34.051 | 34 | WP34 | Operational Ramp-Up | Has the project team confirmed tenant trading readiness - professional certification in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
34.052 | 34 | WP34 | Operational Ramp-Up | Is there a responsible owner, due date and approval route for traffic management - professional certification? | Register entry, supporting drawing/report, approval note and updated risk item. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
34.053 | 34 | WP34 | Operational Ramp-Up | Has the gate file tested whether customer service - professional certification creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
34.054 | 34 | WP34 | Operational Ramp-Up | Are assumptions for operations dashboard - professional certification documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
34.055 | 34 | WP34 | Operational Ramp-Up | Has the relevant authority, specialist or professional adviser reviewed soft opening - implementation readiness where required? | Authority response, compliance checklist, file note and management approval. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
34.056 | 34 | WP34 | Operational Ramp-Up | Is the decision record for Boxer opening - implementation readiness aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
34.057 | 34 | WP34 | Operational Ramp-Up | Have cost, programme and compliance implications of tenant trading readiness - implementation readiness been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
34.058 | 34 | WP34 | Operational Ramp-Up | Has the team obtained written confirmation or documented proof for traffic management - implementation readiness? | Current certificate/letter/report, version control and document-control entry. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
34.059 | 34 | WP34 | Operational Ramp-Up | Does the evidence for customer service - implementation readiness support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
34.060 | 34 | WP34 | Operational Ramp-Up | Have dependencies linked to operations dashboard - implementation readiness been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
34.061 | 34 | WP34 | Operational Ramp-Up | Has the project team confirmed soft opening - governance approval in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
34.062 | 34 | WP34 | Operational Ramp-Up | Is there a responsible owner, due date and approval route for Boxer opening - governance approval? | Register entry, supporting drawing/report, approval note and updated risk item. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
34.063 | 34 | WP34 | Operational Ramp-Up | Has the gate file tested whether tenant trading readiness - governance approval creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
34.064 | 34 | WP34 | Operational Ramp-Up | Are assumptions for traffic management - governance approval documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
34.065 | 34 | WP34 | Operational Ramp-Up | Has the relevant authority, specialist or professional adviser reviewed customer service - governance approval where required? | Authority response, compliance checklist, file note and management approval. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
34.066 | 34 | WP34 | Operational Ramp-Up | Is the decision record for operations dashboard - governance approval aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
34.067 | 34 | WP34 | Operational Ramp-Up | Have cost, programme and compliance implications of soft opening - legal authority been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
34.068 | 34 | WP34 | Operational Ramp-Up | Has the team obtained written confirmation or documented proof for Boxer opening - legal authority? | Current certificate/letter/report, version control and document-control entry. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
34.069 | 34 | WP34 | Operational Ramp-Up | Does the evidence for tenant trading readiness - legal authority support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
34.070 | 34 | WP34 | Operational Ramp-Up | Have dependencies linked to traffic management - legal authority been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
34.071 | 34 | WP34 | Operational Ramp-Up | Has the project team confirmed customer service - legal authority in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
34.072 | 34 | WP34 | Operational Ramp-Up | Is there a responsible owner, due date and approval route for operations dashboard - legal authority? | Register entry, supporting drawing/report, approval note and updated risk item. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
34.073 | 34 | WP34 | Operational Ramp-Up | Has the gate file tested whether soft opening - technical feasibility creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
34.074 | 34 | WP34 | Operational Ramp-Up | Are assumptions for Boxer opening - technical feasibility documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
34.075 | 34 | WP34 | Operational Ramp-Up | Has the relevant authority, specialist or professional adviser reviewed tenant trading readiness - technical feasibility where required? | Authority response, compliance checklist, file note and management approval. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
34.076 | 34 | WP34 | Operational Ramp-Up | Is the decision record for traffic management - technical feasibility aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
34.077 | 34 | WP34 | Operational Ramp-Up | Have cost, programme and compliance implications of customer service - technical feasibility been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
34.078 | 34 | WP34 | Operational Ramp-Up | Has the team obtained written confirmation or documented proof for operations dashboard - technical feasibility? | Current certificate/letter/report, version control and document-control entry. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
34.079 | 34 | WP34 | Operational Ramp-Up | Does the evidence for soft opening - financial viability support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
34.080 | 34 | WP34 | Operational Ramp-Up | Have dependencies linked to Boxer opening - financial viability been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
34.081 | 34 | WP34 | Operational Ramp-Up | Has the project team confirmed tenant trading readiness - financial viability in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
34.082 | 34 | WP34 | Operational Ramp-Up | Is there a responsible owner, due date and approval route for traffic management - financial viability? | Register entry, supporting drawing/report, approval note and updated risk item. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
34.083 | 34 | WP34 | Operational Ramp-Up | Has the gate file tested whether customer service - financial viability creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
34.084 | 34 | WP34 | Operational Ramp-Up | Are assumptions for operations dashboard - financial viability documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
34.085 | 34 | WP34 | Operational Ramp-Up | Has the relevant authority, specialist or professional adviser reviewed soft opening - programme impact where required? | Authority response, compliance checklist, file note and management approval. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
34.086 | 34 | WP34 | Operational Ramp-Up | Is the decision record for Boxer opening - programme impact aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
34.087 | 34 | WP34 | Operational Ramp-Up | Have cost, programme and compliance implications of tenant trading readiness - programme impact been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
34.088 | 34 | WP34 | Operational Ramp-Up | Has the team obtained written confirmation or documented proof for traffic management - programme impact? | Current certificate/letter/report, version control and document-control entry. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
34.089 | 34 | WP34 | Operational Ramp-Up | Does the evidence for customer service - programme impact support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
34.090 | 34 | WP34 | Operational Ramp-Up | Have dependencies linked to operations dashboard - programme impact been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
34.091 | 34 | WP34 | Operational Ramp-Up | Has the project team confirmed soft opening - risk mitigation in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
34.092 | 34 | WP34 | Operational Ramp-Up | Is there a responsible owner, due date and approval route for Boxer opening - risk mitigation? | Register entry, supporting drawing/report, approval note and updated risk item. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
34.093 | 34 | WP34 | Operational Ramp-Up | Has the gate file tested whether tenant trading readiness - risk mitigation creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
34.094 | 34 | WP34 | Operational Ramp-Up | Are assumptions for traffic management - risk mitigation documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
34.095 | 34 | WP34 | Operational Ramp-Up | Has the relevant authority, specialist or professional adviser reviewed customer service - risk mitigation where required? | Authority response, compliance checklist, file note and management approval. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
34.096 | 34 | WP34 | Operational Ramp-Up | Is the decision record for operations dashboard - risk mitigation aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
34.097 | 34 | WP34 | Operational Ramp-Up | Have cost, programme and compliance implications of soft opening - stakeholder acceptance been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
34.098 | 34 | WP34 | Operational Ramp-Up | Has the team obtained written confirmation or documented proof for Boxer opening - stakeholder acceptance? | Current certificate/letter/report, version control and document-control entry. | Tenant design and fit-out manual; anchor specifications; trading-readiness checklist | Yes / No / N/A + Score 0–5 + Rating
34.099 | 34 | WP34 | Operational Ramp-Up | Does the evidence for tenant trading readiness - stakeholder acceptance support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | CPA/POPIA where applicable; tenant compliance file; rental assumptions | Yes / No / N/A + Score 0–5 + Rating
34.100 | 34 | WP34 | Operational Ramp-Up | Have dependencies linked to traffic management - stakeholder acceptance been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | Yes / No / N/A + Score 0–5 + Rating
35.001 | 35 | WP35 | Operations Management | Has the project team confirmed property management - governance approval in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | SANS 10400 occupancy and fire safety; municipal health and fire requirements | Yes / No / N/A + Score 0–5 + Rating
35.002 | 35 | WP35 | Operations Management | Is there a responsible owner, due date and approval route for lease administration - governance approval? | Register entry, supporting drawing/report, approval note and updated risk item. | ISO 55000 asset management principles; maintenance plan; OHS operational file | Yes / No / N/A + Score 0–5 + Rating
35.003 | 35 | WP35 | Operations Management | Has the gate file tested whether tenant relations - governance approval creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | Lease administration best practice; service-level agreements; security and cleaning SOPs | Yes / No / N/A + Score 0–5 + Rating
35.004 | 35 | WP35 | Operations Management | Are assumptions for security operations - governance approval documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | SANS 10400 occupancy and fire safety; municipal health and fire requirements | Yes / No / N/A + Score 0–5 + Rating
35.005 | 35 | WP35 | Operations Management | Has the relevant authority, specialist or professional adviser reviewed cleaning operations - governance approval where required? | Authority response, compliance checklist, file note and management approval. | ISO 55000 asset management principles; maintenance plan; OHS operational file | Yes / No / N/A + Score 0–5 + Rating
35.006 | 35 | WP35 | Operations Management | Is the decision record for parking control - governance approval aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | Lease administration best practice; service-level agreements; security and cleaning SOPs | Yes / No / N/A + Score 0–5 + Rating
35.007 | 35 | WP35 | Operations Management | Have cost, programme and compliance implications of property management - legal authority been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | SANS 10400 occupancy and fire safety; municipal health and fire requirements | Yes / No / N/A + Score 0–5 + Rating
35.008 | 35 | WP35 | Operations Management | Has the team obtained written confirmation or documented proof for lease administration - legal authority? | Current certificate/letter/report, version control and document-control entry. | ISO 55000 asset management principles; maintenance plan; OHS operational file | Yes / No / N/A + Score 0–5 + Rating
35.009 | 35 | WP35 | Operations Management | Does the evidence for tenant relations - legal authority support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | Lease administration best practice; service-level agreements; security and cleaning SOPs | Yes / No / N/A + Score 0–5 + Rating
35.010 | 35 | WP35 | Operations Management | Have dependencies linked to security operations - legal authority been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | SANS 10400 occupancy and fire safety; municipal health and fire requirements | Yes / No / N/A + Score 0–5 + Rating
35.011 | 35 | WP35 | Operations Management | Has the project team confirmed cleaning operations - legal authority in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | ISO 55000 asset management principles; maintenance plan; OHS operational file | Yes / No / N/A + Score 0–5 + Rating
35.012 | 35 | WP35 | Operations Management | Is there a responsible owner, due date and approval route for parking control - legal authority? | Register entry, supporting drawing/report, approval note and updated risk item. | Lease administration best practice; service-level agreements; security and cleaning SOPs | Yes / No / N/A + Score 0–5 + Rating
35.013 | 35 | WP35 | Operations Management | Has the gate file tested whether property management - technical feasibility creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | SANS 10400 occupancy and fire safety; municipal health and fire requirements | Yes / No / N/A + Score 0–5 + Rating
35.014 | 35 | WP35 | Operations Management | Are assumptions for lease administration - technical feasibility documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | ISO 55000 asset management principles; maintenance plan; OHS operational file | Yes / No / N/A + Score 0–5 + Rating
35.015 | 35 | WP35 | Operations Management | Has the relevant authority, specialist or professional adviser reviewed tenant relations - technical feasibility where required? | Authority response, compliance checklist, file note and management approval. | Lease administration best practice; service-level agreements; security and cleaning SOPs | Yes / No / N/A + Score 0–5 + Rating
35.016 | 35 | WP35 | Operations Management | Is the decision record for security operations - technical feasibility aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | SANS 10400 occupancy and fire safety; municipal health and fire requirements | Yes / No / N/A + Score 0–5 + Rating
35.017 | 35 | WP35 | Operations Management | Have cost, programme and compliance implications of cleaning operations - technical feasibility been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | ISO 55000 asset management principles; maintenance plan; OHS operational file | Yes / No / N/A + Score 0–5 + Rating
35.018 | 35 | WP35 | Operations Management | Has the team obtained written confirmation or documented proof for parking control - technical feasibility? | Current certificate/letter/report, version control and document-control entry. | Lease administration best practice; service-level agreements; security and cleaning SOPs | Yes / No / N/A + Score 0–5 + Rating
35.019 | 35 | WP35 | Operations Management | Does the evidence for property management - financial viability support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | SANS 10400 occupancy and fire safety; municipal health and fire requirements | Yes / No / N/A + Score 0–5 + Rating
35.020 | 35 | WP35 | Operations Management | Have dependencies linked to lease administration - financial viability been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | ISO 55000 asset management principles; maintenance plan; OHS operational file | Yes / No / N/A + Score 0–5 + Rating
35.021 | 35 | WP35 | Operations Management | Has the project team confirmed tenant relations - financial viability in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | Lease administration best practice; service-level agreements; security and cleaning SOPs | Yes / No / N/A + Score 0–5 + Rating
35.022 | 35 | WP35 | Operations Management | Is there a responsible owner, due date and approval route for security operations - financial viability? | Register entry, supporting drawing/report, approval note and updated risk item. | SANS 10400 occupancy and fire safety; municipal health and fire requirements | Yes / No / N/A + Score 0–5 + Rating
35.023 | 35 | WP35 | Operations Management | Has the gate file tested whether cleaning operations - financial viability creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | ISO 55000 asset management principles; maintenance plan; OHS operational file | Yes / No / N/A + Score 0–5 + Rating
35.024 | 35 | WP35 | Operations Management | Are assumptions for parking control - financial viability documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | Lease administration best practice; service-level agreements; security and cleaning SOPs | Yes / No / N/A + Score 0–5 + Rating
35.025 | 35 | WP35 | Operations Management | Has the relevant authority, specialist or professional adviser reviewed property management - programme impact where required? | Authority response, compliance checklist, file note and management approval. | SANS 10400 occupancy and fire safety; municipal health and fire requirements | Yes / No / N/A + Score 0–5 + Rating
35.026 | 35 | WP35 | Operations Management | Is the decision record for lease administration - programme impact aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | ISO 55000 asset management principles; maintenance plan; OHS operational file | Yes / No / N/A + Score 0–5 + Rating
35.027 | 35 | WP35 | Operations Management | Have cost, programme and compliance implications of tenant relations - programme impact been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | Lease administration best practice; service-level agreements; security and cleaning SOPs | Yes / No / N/A + Score 0–5 + Rating
35.028 | 35 | WP35 | Operations Management | Has the team obtained written confirmation or documented proof for security operations - programme impact? | Current certificate/letter/report, version control and document-control entry. | SANS 10400 occupancy and fire safety; municipal health and fire requirements | Yes / No / N/A + Score 0–5 + Rating
35.029 | 35 | WP35 | Operations Management | Does the evidence for cleaning operations - programme impact support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | ISO 55000 asset management principles; maintenance plan; OHS operational file | Yes / No / N/A + Score 0–5 + Rating
35.030 | 35 | WP35 | Operations Management | Have dependencies linked to parking control - programme impact been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | Lease administration best practice; service-level agreements; security and cleaning SOPs | Yes / No / N/A + Score 0–5 + Rating
35.031 | 35 | WP35 | Operations Management | Has the project team confirmed property management - risk mitigation in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | SANS 10400 occupancy and fire safety; municipal health and fire requirements | Yes / No / N/A + Score 0–5 + Rating
35.032 | 35 | WP35 | Operations Management | Is there a responsible owner, due date and approval route for lease administration - risk mitigation? | Register entry, supporting drawing/report, approval note and updated risk item. | ISO 55000 asset management principles; maintenance plan; OHS operational file | Yes / No / N/A + Score 0–5 + Rating
35.033 | 35 | WP35 | Operations Management | Has the gate file tested whether tenant relations - risk mitigation creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | Lease administration best practice; service-level agreements; security and cleaning SOPs | Yes / No / N/A + Score 0–5 + Rating
35.034 | 35 | WP35 | Operations Management | Are assumptions for security operations - risk mitigation documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | SANS 10400 occupancy and fire safety; municipal health and fire requirements | Yes / No / N/A + Score 0–5 + Rating
35.035 | 35 | WP35 | Operations Management | Has the relevant authority, specialist or professional adviser reviewed cleaning operations - risk mitigation where required? | Authority response, compliance checklist, file note and management approval. | ISO 55000 asset management principles; maintenance plan; OHS operational file | Yes / No / N/A + Score 0–5 + Rating
35.036 | 35 | WP35 | Operations Management | Is the decision record for parking control - risk mitigation aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | Lease administration best practice; service-level agreements; security and cleaning SOPs | Yes / No / N/A + Score 0–5 + Rating
35.037 | 35 | WP35 | Operations Management | Have cost, programme and compliance implications of property management - stakeholder acceptance been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | SANS 10400 occupancy and fire safety; municipal health and fire requirements | Yes / No / N/A + Score 0–5 + Rating
35.038 | 35 | WP35 | Operations Management | Has the team obtained written confirmation or documented proof for lease administration - stakeholder acceptance? | Current certificate/letter/report, version control and document-control entry. | ISO 55000 asset management principles; maintenance plan; OHS operational file | Yes / No / N/A + Score 0–5 + Rating
35.039 | 35 | WP35 | Operations Management | Does the evidence for tenant relations - stakeholder acceptance support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | Lease administration best practice; service-level agreements; security and cleaning SOPs | Yes / No / N/A + Score 0–5 + Rating
35.040 | 35 | WP35 | Operations Management | Have dependencies linked to security operations - stakeholder acceptance been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | SANS 10400 occupancy and fire safety; municipal health and fire requirements | Yes / No / N/A + Score 0–5 + Rating
35.041 | 35 | WP35 | Operations Management | Has the project team confirmed cleaning operations - stakeholder acceptance in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | ISO 55000 asset management principles; maintenance plan; OHS operational file | Yes / No / N/A + Score 0–5 + Rating
35.042 | 35 | WP35 | Operations Management | Is there a responsible owner, due date and approval route for parking control - stakeholder acceptance? | Register entry, supporting drawing/report, approval note and updated risk item. | Lease administration best practice; service-level agreements; security and cleaning SOPs | Yes / No / N/A + Score 0–5 + Rating
35.043 | 35 | WP35 | Operations Management | Has the gate file tested whether property management - document control creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | SANS 10400 occupancy and fire safety; municipal health and fire requirements | Yes / No / N/A + Score 0–5 + Rating
35.044 | 35 | WP35 | Operations Management | Are assumptions for lease administration - document control documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | ISO 55000 asset management principles; maintenance plan; OHS operational file | Yes / No / N/A + Score 0–5 + Rating
35.045 | 35 | WP35 | Operations Management | Has the relevant authority, specialist or professional adviser reviewed tenant relations - document control where required? | Authority response, compliance checklist, file note and management approval. | Lease administration best practice; service-level agreements; security and cleaning SOPs | Yes / No / N/A + Score 0–5 + Rating
35.046 | 35 | WP35 | Operations Management | Is the decision record for security operations - document control aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | SANS 10400 occupancy and fire safety; municipal health and fire requirements | Yes / No / N/A + Score 0–5 + Rating
35.047 | 35 | WP35 | Operations Management | Have cost, programme and compliance implications of cleaning operations - document control been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | ISO 55000 asset management principles; maintenance plan; OHS operational file | Yes / No / N/A + Score 0–5 + Rating
35.048 | 35 | WP35 | Operations Management | Has the team obtained written confirmation or documented proof for parking control - document control? | Current certificate/letter/report, version control and document-control entry. | Lease administration best practice; service-level agreements; security and cleaning SOPs | Yes / No / N/A + Score 0–5 + Rating
35.049 | 35 | WP35 | Operations Management | Does the evidence for property management - professional certification support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | SANS 10400 occupancy and fire safety; municipal health and fire requirements | Yes / No / N/A + Score 0–5 + Rating
35.050 | 35 | WP35 | Operations Management | Have dependencies linked to lease administration - professional certification been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | ISO 55000 asset management principles; maintenance plan; OHS operational file | Yes / No / N/A + Score 0–5 + Rating
35.051 | 35 | WP35 | Operations Management | Has the project team confirmed tenant relations - professional certification in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | Lease administration best practice; service-level agreements; security and cleaning SOPs | Yes / No / N/A + Score 0–5 + Rating
35.052 | 35 | WP35 | Operations Management | Is there a responsible owner, due date and approval route for security operations - professional certification? | Register entry, supporting drawing/report, approval note and updated risk item. | SANS 10400 occupancy and fire safety; municipal health and fire requirements | Yes / No / N/A + Score 0–5 + Rating
35.053 | 35 | WP35 | Operations Management | Has the gate file tested whether cleaning operations - professional certification creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | ISO 55000 asset management principles; maintenance plan; OHS operational file | Yes / No / N/A + Score 0–5 + Rating
35.054 | 35 | WP35 | Operations Management | Are assumptions for parking control - professional certification documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | Lease administration best practice; service-level agreements; security and cleaning SOPs | Yes / No / N/A + Score 0–5 + Rating
35.055 | 35 | WP35 | Operations Management | Has the relevant authority, specialist or professional adviser reviewed property management - implementation readiness where required? | Authority response, compliance checklist, file note and management approval. | SANS 10400 occupancy and fire safety; municipal health and fire requirements | Yes / No / N/A + Score 0–5 + Rating
35.056 | 35 | WP35 | Operations Management | Is the decision record for lease administration - implementation readiness aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | ISO 55000 asset management principles; maintenance plan; OHS operational file | Yes / No / N/A + Score 0–5 + Rating
35.057 | 35 | WP35 | Operations Management | Have cost, programme and compliance implications of tenant relations - implementation readiness been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | Lease administration best practice; service-level agreements; security and cleaning SOPs | Yes / No / N/A + Score 0–5 + Rating
35.058 | 35 | WP35 | Operations Management | Has the team obtained written confirmation or documented proof for security operations - implementation readiness? | Current certificate/letter/report, version control and document-control entry. | SANS 10400 occupancy and fire safety; municipal health and fire requirements | Yes / No / N/A + Score 0–5 + Rating
35.059 | 35 | WP35 | Operations Management | Does the evidence for cleaning operations - implementation readiness support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | ISO 55000 asset management principles; maintenance plan; OHS operational file | Yes / No / N/A + Score 0–5 + Rating
35.060 | 35 | WP35 | Operations Management | Have dependencies linked to parking control - implementation readiness been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | Lease administration best practice; service-level agreements; security and cleaning SOPs | Yes / No / N/A + Score 0–5 + Rating
35.061 | 35 | WP35 | Operations Management | Has the project team confirmed property management - governance approval in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | SANS 10400 occupancy and fire safety; municipal health and fire requirements | Yes / No / N/A + Score 0–5 + Rating
35.062 | 35 | WP35 | Operations Management | Is there a responsible owner, due date and approval route for lease administration - governance approval? | Register entry, supporting drawing/report, approval note and updated risk item. | ISO 55000 asset management principles; maintenance plan; OHS operational file | Yes / No / N/A + Score 0–5 + Rating
35.063 | 35 | WP35 | Operations Management | Has the gate file tested whether tenant relations - governance approval creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | Lease administration best practice; service-level agreements; security and cleaning SOPs | Yes / No / N/A + Score 0–5 + Rating
35.064 | 35 | WP35 | Operations Management | Are assumptions for security operations - governance approval documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | SANS 10400 occupancy and fire safety; municipal health and fire requirements | Yes / No / N/A + Score 0–5 + Rating
35.065 | 35 | WP35 | Operations Management | Has the relevant authority, specialist or professional adviser reviewed cleaning operations - governance approval where required? | Authority response, compliance checklist, file note and management approval. | ISO 55000 asset management principles; maintenance plan; OHS operational file | Yes / No / N/A + Score 0–5 + Rating
35.066 | 35 | WP35 | Operations Management | Is the decision record for parking control - governance approval aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | Lease administration best practice; service-level agreements; security and cleaning SOPs | Yes / No / N/A + Score 0–5 + Rating
35.067 | 35 | WP35 | Operations Management | Have cost, programme and compliance implications of property management - legal authority been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | SANS 10400 occupancy and fire safety; municipal health and fire requirements | Yes / No / N/A + Score 0–5 + Rating
35.068 | 35 | WP35 | Operations Management | Has the team obtained written confirmation or documented proof for lease administration - legal authority? | Current certificate/letter/report, version control and document-control entry. | ISO 55000 asset management principles; maintenance plan; OHS operational file | Yes / No / N/A + Score 0–5 + Rating
35.069 | 35 | WP35 | Operations Management | Does the evidence for tenant relations - legal authority support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | Lease administration best practice; service-level agreements; security and cleaning SOPs | Yes / No / N/A + Score 0–5 + Rating
35.070 | 35 | WP35 | Operations Management | Have dependencies linked to security operations - legal authority been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | SANS 10400 occupancy and fire safety; municipal health and fire requirements | Yes / No / N/A + Score 0–5 + Rating
35.071 | 35 | WP35 | Operations Management | Has the project team confirmed cleaning operations - legal authority in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | ISO 55000 asset management principles; maintenance plan; OHS operational file | Yes / No / N/A + Score 0–5 + Rating
35.072 | 35 | WP35 | Operations Management | Is there a responsible owner, due date and approval route for parking control - legal authority? | Register entry, supporting drawing/report, approval note and updated risk item. | Lease administration best practice; service-level agreements; security and cleaning SOPs | Yes / No / N/A + Score 0–5 + Rating
35.073 | 35 | WP35 | Operations Management | Has the gate file tested whether property management - technical feasibility creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | SANS 10400 occupancy and fire safety; municipal health and fire requirements | Yes / No / N/A + Score 0–5 + Rating
35.074 | 35 | WP35 | Operations Management | Are assumptions for lease administration - technical feasibility documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | ISO 55000 asset management principles; maintenance plan; OHS operational file | Yes / No / N/A + Score 0–5 + Rating
35.075 | 35 | WP35 | Operations Management | Has the relevant authority, specialist or professional adviser reviewed tenant relations - technical feasibility where required? | Authority response, compliance checklist, file note and management approval. | Lease administration best practice; service-level agreements; security and cleaning SOPs | Yes / No / N/A + Score 0–5 + Rating
35.076 | 35 | WP35 | Operations Management | Is the decision record for security operations - technical feasibility aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | SANS 10400 occupancy and fire safety; municipal health and fire requirements | Yes / No / N/A + Score 0–5 + Rating
35.077 | 35 | WP35 | Operations Management | Have cost, programme and compliance implications of cleaning operations - technical feasibility been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | ISO 55000 asset management principles; maintenance plan; OHS operational file | Yes / No / N/A + Score 0–5 + Rating
35.078 | 35 | WP35 | Operations Management | Has the team obtained written confirmation or documented proof for parking control - technical feasibility? | Current certificate/letter/report, version control and document-control entry. | Lease administration best practice; service-level agreements; security and cleaning SOPs | Yes / No / N/A + Score 0–5 + Rating
35.079 | 35 | WP35 | Operations Management | Does the evidence for property management - financial viability support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | SANS 10400 occupancy and fire safety; municipal health and fire requirements | Yes / No / N/A + Score 0–5 + Rating
35.080 | 35 | WP35 | Operations Management | Have dependencies linked to lease administration - financial viability been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | ISO 55000 asset management principles; maintenance plan; OHS operational file | Yes / No / N/A + Score 0–5 + Rating
35.081 | 35 | WP35 | Operations Management | Has the project team confirmed tenant relations - financial viability in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | Lease administration best practice; service-level agreements; security and cleaning SOPs | Yes / No / N/A + Score 0–5 + Rating
35.082 | 35 | WP35 | Operations Management | Is there a responsible owner, due date and approval route for security operations - financial viability? | Register entry, supporting drawing/report, approval note and updated risk item. | SANS 10400 occupancy and fire safety; municipal health and fire requirements | Yes / No / N/A + Score 0–5 + Rating
35.083 | 35 | WP35 | Operations Management | Has the gate file tested whether cleaning operations - financial viability creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | ISO 55000 asset management principles; maintenance plan; OHS operational file | Yes / No / N/A + Score 0–5 + Rating
35.084 | 35 | WP35 | Operations Management | Are assumptions for parking control - financial viability documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | Lease administration best practice; service-level agreements; security and cleaning SOPs | Yes / No / N/A + Score 0–5 + Rating
35.085 | 35 | WP35 | Operations Management | Has the relevant authority, specialist or professional adviser reviewed property management - programme impact where required? | Authority response, compliance checklist, file note and management approval. | SANS 10400 occupancy and fire safety; municipal health and fire requirements | Yes / No / N/A + Score 0–5 + Rating
35.086 | 35 | WP35 | Operations Management | Is the decision record for lease administration - programme impact aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | ISO 55000 asset management principles; maintenance plan; OHS operational file | Yes / No / N/A + Score 0–5 + Rating
35.087 | 35 | WP35 | Operations Management | Have cost, programme and compliance implications of tenant relations - programme impact been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | Lease administration best practice; service-level agreements; security and cleaning SOPs | Yes / No / N/A + Score 0–5 + Rating
35.088 | 35 | WP35 | Operations Management | Has the team obtained written confirmation or documented proof for security operations - programme impact? | Current certificate/letter/report, version control and document-control entry. | SANS 10400 occupancy and fire safety; municipal health and fire requirements | Yes / No / N/A + Score 0–5 + Rating
35.089 | 35 | WP35 | Operations Management | Does the evidence for cleaning operations - programme impact support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | ISO 55000 asset management principles; maintenance plan; OHS operational file | Yes / No / N/A + Score 0–5 + Rating
35.090 | 35 | WP35 | Operations Management | Have dependencies linked to parking control - programme impact been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | Lease administration best practice; service-level agreements; security and cleaning SOPs | Yes / No / N/A + Score 0–5 + Rating
35.091 | 35 | WP35 | Operations Management | Has the project team confirmed property management - risk mitigation in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | SANS 10400 occupancy and fire safety; municipal health and fire requirements | Yes / No / N/A + Score 0–5 + Rating
35.092 | 35 | WP35 | Operations Management | Is there a responsible owner, due date and approval route for lease administration - risk mitigation? | Register entry, supporting drawing/report, approval note and updated risk item. | ISO 55000 asset management principles; maintenance plan; OHS operational file | Yes / No / N/A + Score 0–5 + Rating
35.093 | 35 | WP35 | Operations Management | Has the gate file tested whether tenant relations - risk mitigation creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | Lease administration best practice; service-level agreements; security and cleaning SOPs | Yes / No / N/A + Score 0–5 + Rating
35.094 | 35 | WP35 | Operations Management | Are assumptions for security operations - risk mitigation documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | SANS 10400 occupancy and fire safety; municipal health and fire requirements | Yes / No / N/A + Score 0–5 + Rating
35.095 | 35 | WP35 | Operations Management | Has the relevant authority, specialist or professional adviser reviewed cleaning operations - risk mitigation where required? | Authority response, compliance checklist, file note and management approval. | ISO 55000 asset management principles; maintenance plan; OHS operational file | Yes / No / N/A + Score 0–5 + Rating
35.096 | 35 | WP35 | Operations Management | Is the decision record for parking control - risk mitigation aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | Lease administration best practice; service-level agreements; security and cleaning SOPs | Yes / No / N/A + Score 0–5 + Rating
35.097 | 35 | WP35 | Operations Management | Have cost, programme and compliance implications of property management - stakeholder acceptance been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | SANS 10400 occupancy and fire safety; municipal health and fire requirements | Yes / No / N/A + Score 0–5 + Rating
35.098 | 35 | WP35 | Operations Management | Has the team obtained written confirmation or documented proof for lease administration - stakeholder acceptance? | Current certificate/letter/report, version control and document-control entry. | ISO 55000 asset management principles; maintenance plan; OHS operational file | Yes / No / N/A + Score 0–5 + Rating
35.099 | 35 | WP35 | Operations Management | Does the evidence for tenant relations - stakeholder acceptance support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | Lease administration best practice; service-level agreements; security and cleaning SOPs | Yes / No / N/A + Score 0–5 + Rating
35.100 | 35 | WP35 | Operations Management | Have dependencies linked to security operations - stakeholder acceptance been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | SANS 10400 occupancy and fire safety; municipal health and fire requirements | Yes / No / N/A + Score 0–5 + Rating
36.001 | 36 | WP36 | Maintenance Management | Has the project team confirmed preventive maintenance - governance approval in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | SANS 10400 occupancy and fire safety; municipal health and fire requirements | Yes / No / N/A + Score 0–5 + Rating
36.002 | 36 | WP36 | Maintenance Management | Is there a responsible owner, due date and approval route for reactive maintenance - governance approval? | Register entry, supporting drawing/report, approval note and updated risk item. | ISO 55000 asset management principles; maintenance plan; OHS operational file | Yes / No / N/A + Score 0–5 + Rating
36.003 | 36 | WP36 | Maintenance Management | Has the gate file tested whether roof and gutters - governance approval creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | Lease administration best practice; service-level agreements; security and cleaning SOPs | Yes / No / N/A + Score 0–5 + Rating
36.004 | 36 | WP36 | Maintenance Management | Are assumptions for electrical systems - governance approval documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | SANS 10400 occupancy and fire safety; municipal health and fire requirements | Yes / No / N/A + Score 0–5 + Rating
36.005 | 36 | WP36 | Maintenance Management | Has the relevant authority, specialist or professional adviser reviewed plumbing systems - governance approval where required? | Authority response, compliance checklist, file note and management approval. | ISO 55000 asset management principles; maintenance plan; OHS operational file | Yes / No / N/A + Score 0–5 + Rating
36.006 | 36 | WP36 | Maintenance Management | Is the decision record for fire equipment - governance approval aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | Lease administration best practice; service-level agreements; security and cleaning SOPs | Yes / No / N/A + Score 0–5 + Rating
36.007 | 36 | WP36 | Maintenance Management | Have cost, programme and compliance implications of preventive maintenance - legal authority been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | SANS 10400 occupancy and fire safety; municipal health and fire requirements | Yes / No / N/A + Score 0–5 + Rating
36.008 | 36 | WP36 | Maintenance Management | Has the team obtained written confirmation or documented proof for reactive maintenance - legal authority? | Current certificate/letter/report, version control and document-control entry. | ISO 55000 asset management principles; maintenance plan; OHS operational file | Yes / No / N/A + Score 0–5 + Rating
36.009 | 36 | WP36 | Maintenance Management | Does the evidence for roof and gutters - legal authority support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | Lease administration best practice; service-level agreements; security and cleaning SOPs | Yes / No / N/A + Score 0–5 + Rating
36.010 | 36 | WP36 | Maintenance Management | Have dependencies linked to electrical systems - legal authority been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | SANS 10400 occupancy and fire safety; municipal health and fire requirements | Yes / No / N/A + Score 0–5 + Rating
36.011 | 36 | WP36 | Maintenance Management | Has the project team confirmed plumbing systems - legal authority in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | ISO 55000 asset management principles; maintenance plan; OHS operational file | Yes / No / N/A + Score 0–5 + Rating
36.012 | 36 | WP36 | Maintenance Management | Is there a responsible owner, due date and approval route for fire equipment - legal authority? | Register entry, supporting drawing/report, approval note and updated risk item. | Lease administration best practice; service-level agreements; security and cleaning SOPs | Yes / No / N/A + Score 0–5 + Rating
36.013 | 36 | WP36 | Maintenance Management | Has the gate file tested whether preventive maintenance - technical feasibility creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | SANS 10400 occupancy and fire safety; municipal health and fire requirements | Yes / No / N/A + Score 0–5 + Rating
36.014 | 36 | WP36 | Maintenance Management | Are assumptions for reactive maintenance - technical feasibility documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | ISO 55000 asset management principles; maintenance plan; OHS operational file | Yes / No / N/A + Score 0–5 + Rating
36.015 | 36 | WP36 | Maintenance Management | Has the relevant authority, specialist or professional adviser reviewed roof and gutters - technical feasibility where required? | Authority response, compliance checklist, file note and management approval. | Lease administration best practice; service-level agreements; security and cleaning SOPs | Yes / No / N/A + Score 0–5 + Rating
36.016 | 36 | WP36 | Maintenance Management | Is the decision record for electrical systems - technical feasibility aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | SANS 10400 occupancy and fire safety; municipal health and fire requirements | Yes / No / N/A + Score 0–5 + Rating
36.017 | 36 | WP36 | Maintenance Management | Have cost, programme and compliance implications of plumbing systems - technical feasibility been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | ISO 55000 asset management principles; maintenance plan; OHS operational file | Yes / No / N/A + Score 0–5 + Rating
36.018 | 36 | WP36 | Maintenance Management | Has the team obtained written confirmation or documented proof for fire equipment - technical feasibility? | Current certificate/letter/report, version control and document-control entry. | Lease administration best practice; service-level agreements; security and cleaning SOPs | Yes / No / N/A + Score 0–5 + Rating
36.019 | 36 | WP36 | Maintenance Management | Does the evidence for preventive maintenance - financial viability support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | SANS 10400 occupancy and fire safety; municipal health and fire requirements | Yes / No / N/A + Score 0–5 + Rating
36.020 | 36 | WP36 | Maintenance Management | Have dependencies linked to reactive maintenance - financial viability been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | ISO 55000 asset management principles; maintenance plan; OHS operational file | Yes / No / N/A + Score 0–5 + Rating
36.021 | 36 | WP36 | Maintenance Management | Has the project team confirmed roof and gutters - financial viability in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | Lease administration best practice; service-level agreements; security and cleaning SOPs | Yes / No / N/A + Score 0–5 + Rating
36.022 | 36 | WP36 | Maintenance Management | Is there a responsible owner, due date and approval route for electrical systems - financial viability? | Register entry, supporting drawing/report, approval note and updated risk item. | SANS 10400 occupancy and fire safety; municipal health and fire requirements | Yes / No / N/A + Score 0–5 + Rating
36.023 | 36 | WP36 | Maintenance Management | Has the gate file tested whether plumbing systems - financial viability creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | ISO 55000 asset management principles; maintenance plan; OHS operational file | Yes / No / N/A + Score 0–5 + Rating
36.024 | 36 | WP36 | Maintenance Management | Are assumptions for fire equipment - financial viability documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | Lease administration best practice; service-level agreements; security and cleaning SOPs | Yes / No / N/A + Score 0–5 + Rating
36.025 | 36 | WP36 | Maintenance Management | Has the relevant authority, specialist or professional adviser reviewed preventive maintenance - programme impact where required? | Authority response, compliance checklist, file note and management approval. | SANS 10400 occupancy and fire safety; municipal health and fire requirements | Yes / No / N/A + Score 0–5 + Rating
36.026 | 36 | WP36 | Maintenance Management | Is the decision record for reactive maintenance - programme impact aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | ISO 55000 asset management principles; maintenance plan; OHS operational file | Yes / No / N/A + Score 0–5 + Rating
36.027 | 36 | WP36 | Maintenance Management | Have cost, programme and compliance implications of roof and gutters - programme impact been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | Lease administration best practice; service-level agreements; security and cleaning SOPs | Yes / No / N/A + Score 0–5 + Rating
36.028 | 36 | WP36 | Maintenance Management | Has the team obtained written confirmation or documented proof for electrical systems - programme impact? | Current certificate/letter/report, version control and document-control entry. | SANS 10400 occupancy and fire safety; municipal health and fire requirements | Yes / No / N/A + Score 0–5 + Rating
36.029 | 36 | WP36 | Maintenance Management | Does the evidence for plumbing systems - programme impact support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | ISO 55000 asset management principles; maintenance plan; OHS operational file | Yes / No / N/A + Score 0–5 + Rating
36.030 | 36 | WP36 | Maintenance Management | Have dependencies linked to fire equipment - programme impact been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | Lease administration best practice; service-level agreements; security and cleaning SOPs | Yes / No / N/A + Score 0–5 + Rating
36.031 | 36 | WP36 | Maintenance Management | Has the project team confirmed preventive maintenance - risk mitigation in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | SANS 10400 occupancy and fire safety; municipal health and fire requirements | Yes / No / N/A + Score 0–5 + Rating
36.032 | 36 | WP36 | Maintenance Management | Is there a responsible owner, due date and approval route for reactive maintenance - risk mitigation? | Register entry, supporting drawing/report, approval note and updated risk item. | ISO 55000 asset management principles; maintenance plan; OHS operational file | Yes / No / N/A + Score 0–5 + Rating
36.033 | 36 | WP36 | Maintenance Management | Has the gate file tested whether roof and gutters - risk mitigation creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | Lease administration best practice; service-level agreements; security and cleaning SOPs | Yes / No / N/A + Score 0–5 + Rating
36.034 | 36 | WP36 | Maintenance Management | Are assumptions for electrical systems - risk mitigation documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | SANS 10400 occupancy and fire safety; municipal health and fire requirements | Yes / No / N/A + Score 0–5 + Rating
36.035 | 36 | WP36 | Maintenance Management | Has the relevant authority, specialist or professional adviser reviewed plumbing systems - risk mitigation where required? | Authority response, compliance checklist, file note and management approval. | ISO 55000 asset management principles; maintenance plan; OHS operational file | Yes / No / N/A + Score 0–5 + Rating
36.036 | 36 | WP36 | Maintenance Management | Is the decision record for fire equipment - risk mitigation aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | Lease administration best practice; service-level agreements; security and cleaning SOPs | Yes / No / N/A + Score 0–5 + Rating
36.037 | 36 | WP36 | Maintenance Management | Have cost, programme and compliance implications of preventive maintenance - stakeholder acceptance been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | SANS 10400 occupancy and fire safety; municipal health and fire requirements | Yes / No / N/A + Score 0–5 + Rating
36.038 | 36 | WP36 | Maintenance Management | Has the team obtained written confirmation or documented proof for reactive maintenance - stakeholder acceptance? | Current certificate/letter/report, version control and document-control entry. | ISO 55000 asset management principles; maintenance plan; OHS operational file | Yes / No / N/A + Score 0–5 + Rating
36.039 | 36 | WP36 | Maintenance Management | Does the evidence for roof and gutters - stakeholder acceptance support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | Lease administration best practice; service-level agreements; security and cleaning SOPs | Yes / No / N/A + Score 0–5 + Rating
36.040 | 36 | WP36 | Maintenance Management | Have dependencies linked to electrical systems - stakeholder acceptance been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | SANS 10400 occupancy and fire safety; municipal health and fire requirements | Yes / No / N/A + Score 0–5 + Rating
36.041 | 36 | WP36 | Maintenance Management | Has the project team confirmed plumbing systems - stakeholder acceptance in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | ISO 55000 asset management principles; maintenance plan; OHS operational file | Yes / No / N/A + Score 0–5 + Rating
36.042 | 36 | WP36 | Maintenance Management | Is there a responsible owner, due date and approval route for fire equipment - stakeholder acceptance? | Register entry, supporting drawing/report, approval note and updated risk item. | Lease administration best practice; service-level agreements; security and cleaning SOPs | Yes / No / N/A + Score 0–5 + Rating
36.043 | 36 | WP36 | Maintenance Management | Has the gate file tested whether preventive maintenance - document control creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | SANS 10400 occupancy and fire safety; municipal health and fire requirements | Yes / No / N/A + Score 0–5 + Rating
36.044 | 36 | WP36 | Maintenance Management | Are assumptions for reactive maintenance - document control documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | ISO 55000 asset management principles; maintenance plan; OHS operational file | Yes / No / N/A + Score 0–5 + Rating
36.045 | 36 | WP36 | Maintenance Management | Has the relevant authority, specialist or professional adviser reviewed roof and gutters - document control where required? | Authority response, compliance checklist, file note and management approval. | Lease administration best practice; service-level agreements; security and cleaning SOPs | Yes / No / N/A + Score 0–5 + Rating
36.046 | 36 | WP36 | Maintenance Management | Is the decision record for electrical systems - document control aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | SANS 10400 occupancy and fire safety; municipal health and fire requirements | Yes / No / N/A + Score 0–5 + Rating
36.047 | 36 | WP36 | Maintenance Management | Have cost, programme and compliance implications of plumbing systems - document control been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | ISO 55000 asset management principles; maintenance plan; OHS operational file | Yes / No / N/A + Score 0–5 + Rating
36.048 | 36 | WP36 | Maintenance Management | Has the team obtained written confirmation or documented proof for fire equipment - document control? | Current certificate/letter/report, version control and document-control entry. | Lease administration best practice; service-level agreements; security and cleaning SOPs | Yes / No / N/A + Score 0–5 + Rating
36.049 | 36 | WP36 | Maintenance Management | Does the evidence for preventive maintenance - professional certification support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | SANS 10400 occupancy and fire safety; municipal health and fire requirements | Yes / No / N/A + Score 0–5 + Rating
36.050 | 36 | WP36 | Maintenance Management | Have dependencies linked to reactive maintenance - professional certification been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | ISO 55000 asset management principles; maintenance plan; OHS operational file | Yes / No / N/A + Score 0–5 + Rating
36.051 | 36 | WP36 | Maintenance Management | Has the project team confirmed roof and gutters - professional certification in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | Lease administration best practice; service-level agreements; security and cleaning SOPs | Yes / No / N/A + Score 0–5 + Rating
36.052 | 36 | WP36 | Maintenance Management | Is there a responsible owner, due date and approval route for electrical systems - professional certification? | Register entry, supporting drawing/report, approval note and updated risk item. | SANS 10400 occupancy and fire safety; municipal health and fire requirements | Yes / No / N/A + Score 0–5 + Rating
36.053 | 36 | WP36 | Maintenance Management | Has the gate file tested whether plumbing systems - professional certification creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | ISO 55000 asset management principles; maintenance plan; OHS operational file | Yes / No / N/A + Score 0–5 + Rating
36.054 | 36 | WP36 | Maintenance Management | Are assumptions for fire equipment - professional certification documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | Lease administration best practice; service-level agreements; security and cleaning SOPs | Yes / No / N/A + Score 0–5 + Rating
36.055 | 36 | WP36 | Maintenance Management | Has the relevant authority, specialist or professional adviser reviewed preventive maintenance - implementation readiness where required? | Authority response, compliance checklist, file note and management approval. | SANS 10400 occupancy and fire safety; municipal health and fire requirements | Yes / No / N/A + Score 0–5 + Rating
36.056 | 36 | WP36 | Maintenance Management | Is the decision record for reactive maintenance - implementation readiness aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | ISO 55000 asset management principles; maintenance plan; OHS operational file | Yes / No / N/A + Score 0–5 + Rating
36.057 | 36 | WP36 | Maintenance Management | Have cost, programme and compliance implications of roof and gutters - implementation readiness been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | Lease administration best practice; service-level agreements; security and cleaning SOPs | Yes / No / N/A + Score 0–5 + Rating
36.058 | 36 | WP36 | Maintenance Management | Has the team obtained written confirmation or documented proof for electrical systems - implementation readiness? | Current certificate/letter/report, version control and document-control entry. | SANS 10400 occupancy and fire safety; municipal health and fire requirements | Yes / No / N/A + Score 0–5 + Rating
36.059 | 36 | WP36 | Maintenance Management | Does the evidence for plumbing systems - implementation readiness support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | ISO 55000 asset management principles; maintenance plan; OHS operational file | Yes / No / N/A + Score 0–5 + Rating
36.060 | 36 | WP36 | Maintenance Management | Have dependencies linked to fire equipment - implementation readiness been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | Lease administration best practice; service-level agreements; security and cleaning SOPs | Yes / No / N/A + Score 0–5 + Rating
36.061 | 36 | WP36 | Maintenance Management | Has the project team confirmed preventive maintenance - governance approval in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | SANS 10400 occupancy and fire safety; municipal health and fire requirements | Yes / No / N/A + Score 0–5 + Rating
36.062 | 36 | WP36 | Maintenance Management | Is there a responsible owner, due date and approval route for reactive maintenance - governance approval? | Register entry, supporting drawing/report, approval note and updated risk item. | ISO 55000 asset management principles; maintenance plan; OHS operational file | Yes / No / N/A + Score 0–5 + Rating
36.063 | 36 | WP36 | Maintenance Management | Has the gate file tested whether roof and gutters - governance approval creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | Lease administration best practice; service-level agreements; security and cleaning SOPs | Yes / No / N/A + Score 0–5 + Rating
36.064 | 36 | WP36 | Maintenance Management | Are assumptions for electrical systems - governance approval documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | SANS 10400 occupancy and fire safety; municipal health and fire requirements | Yes / No / N/A + Score 0–5 + Rating
36.065 | 36 | WP36 | Maintenance Management | Has the relevant authority, specialist or professional adviser reviewed plumbing systems - governance approval where required? | Authority response, compliance checklist, file note and management approval. | ISO 55000 asset management principles; maintenance plan; OHS operational file | Yes / No / N/A + Score 0–5 + Rating
36.066 | 36 | WP36 | Maintenance Management | Is the decision record for fire equipment - governance approval aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | Lease administration best practice; service-level agreements; security and cleaning SOPs | Yes / No / N/A + Score 0–5 + Rating
36.067 | 36 | WP36 | Maintenance Management | Have cost, programme and compliance implications of preventive maintenance - legal authority been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | SANS 10400 occupancy and fire safety; municipal health and fire requirements | Yes / No / N/A + Score 0–5 + Rating
36.068 | 36 | WP36 | Maintenance Management | Has the team obtained written confirmation or documented proof for reactive maintenance - legal authority? | Current certificate/letter/report, version control and document-control entry. | ISO 55000 asset management principles; maintenance plan; OHS operational file | Yes / No / N/A + Score 0–5 + Rating
36.069 | 36 | WP36 | Maintenance Management | Does the evidence for roof and gutters - legal authority support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | Lease administration best practice; service-level agreements; security and cleaning SOPs | Yes / No / N/A + Score 0–5 + Rating
36.070 | 36 | WP36 | Maintenance Management | Have dependencies linked to electrical systems - legal authority been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | SANS 10400 occupancy and fire safety; municipal health and fire requirements | Yes / No / N/A + Score 0–5 + Rating
36.071 | 36 | WP36 | Maintenance Management | Has the project team confirmed plumbing systems - legal authority in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | ISO 55000 asset management principles; maintenance plan; OHS operational file | Yes / No / N/A + Score 0–5 + Rating
36.072 | 36 | WP36 | Maintenance Management | Is there a responsible owner, due date and approval route for fire equipment - legal authority? | Register entry, supporting drawing/report, approval note and updated risk item. | Lease administration best practice; service-level agreements; security and cleaning SOPs | Yes / No / N/A + Score 0–5 + Rating
36.073 | 36 | WP36 | Maintenance Management | Has the gate file tested whether preventive maintenance - technical feasibility creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | SANS 10400 occupancy and fire safety; municipal health and fire requirements | Yes / No / N/A + Score 0–5 + Rating
36.074 | 36 | WP36 | Maintenance Management | Are assumptions for reactive maintenance - technical feasibility documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | ISO 55000 asset management principles; maintenance plan; OHS operational file | Yes / No / N/A + Score 0–5 + Rating
36.075 | 36 | WP36 | Maintenance Management | Has the relevant authority, specialist or professional adviser reviewed roof and gutters - technical feasibility where required? | Authority response, compliance checklist, file note and management approval. | Lease administration best practice; service-level agreements; security and cleaning SOPs | Yes / No / N/A + Score 0–5 + Rating
36.076 | 36 | WP36 | Maintenance Management | Is the decision record for electrical systems - technical feasibility aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | SANS 10400 occupancy and fire safety; municipal health and fire requirements | Yes / No / N/A + Score 0–5 + Rating
36.077 | 36 | WP36 | Maintenance Management | Have cost, programme and compliance implications of plumbing systems - technical feasibility been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | ISO 55000 asset management principles; maintenance plan; OHS operational file | Yes / No / N/A + Score 0–5 + Rating
36.078 | 36 | WP36 | Maintenance Management | Has the team obtained written confirmation or documented proof for fire equipment - technical feasibility? | Current certificate/letter/report, version control and document-control entry. | Lease administration best practice; service-level agreements; security and cleaning SOPs | Yes / No / N/A + Score 0–5 + Rating
36.079 | 36 | WP36 | Maintenance Management | Does the evidence for preventive maintenance - financial viability support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | SANS 10400 occupancy and fire safety; municipal health and fire requirements | Yes / No / N/A + Score 0–5 + Rating
36.080 | 36 | WP36 | Maintenance Management | Have dependencies linked to reactive maintenance - financial viability been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | ISO 55000 asset management principles; maintenance plan; OHS operational file | Yes / No / N/A + Score 0–5 + Rating
36.081 | 36 | WP36 | Maintenance Management | Has the project team confirmed roof and gutters - financial viability in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | Lease administration best practice; service-level agreements; security and cleaning SOPs | Yes / No / N/A + Score 0–5 + Rating
36.082 | 36 | WP36 | Maintenance Management | Is there a responsible owner, due date and approval route for electrical systems - financial viability? | Register entry, supporting drawing/report, approval note and updated risk item. | SANS 10400 occupancy and fire safety; municipal health and fire requirements | Yes / No / N/A + Score 0–5 + Rating
36.083 | 36 | WP36 | Maintenance Management | Has the gate file tested whether plumbing systems - financial viability creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | ISO 55000 asset management principles; maintenance plan; OHS operational file | Yes / No / N/A + Score 0–5 + Rating
36.084 | 36 | WP36 | Maintenance Management | Are assumptions for fire equipment - financial viability documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | Lease administration best practice; service-level agreements; security and cleaning SOPs | Yes / No / N/A + Score 0–5 + Rating
36.085 | 36 | WP36 | Maintenance Management | Has the relevant authority, specialist or professional adviser reviewed preventive maintenance - programme impact where required? | Authority response, compliance checklist, file note and management approval. | SANS 10400 occupancy and fire safety; municipal health and fire requirements | Yes / No / N/A + Score 0–5 + Rating
36.086 | 36 | WP36 | Maintenance Management | Is the decision record for reactive maintenance - programme impact aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | ISO 55000 asset management principles; maintenance plan; OHS operational file | Yes / No / N/A + Score 0–5 + Rating
36.087 | 36 | WP36 | Maintenance Management | Have cost, programme and compliance implications of roof and gutters - programme impact been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | Lease administration best practice; service-level agreements; security and cleaning SOPs | Yes / No / N/A + Score 0–5 + Rating
36.088 | 36 | WP36 | Maintenance Management | Has the team obtained written confirmation or documented proof for electrical systems - programme impact? | Current certificate/letter/report, version control and document-control entry. | SANS 10400 occupancy and fire safety; municipal health and fire requirements | Yes / No / N/A + Score 0–5 + Rating
36.089 | 36 | WP36 | Maintenance Management | Does the evidence for plumbing systems - programme impact support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | ISO 55000 asset management principles; maintenance plan; OHS operational file | Yes / No / N/A + Score 0–5 + Rating
36.090 | 36 | WP36 | Maintenance Management | Have dependencies linked to fire equipment - programme impact been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | Lease administration best practice; service-level agreements; security and cleaning SOPs | Yes / No / N/A + Score 0–5 + Rating
36.091 | 36 | WP36 | Maintenance Management | Has the project team confirmed preventive maintenance - risk mitigation in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | SANS 10400 occupancy and fire safety; municipal health and fire requirements | Yes / No / N/A + Score 0–5 + Rating
36.092 | 36 | WP36 | Maintenance Management | Is there a responsible owner, due date and approval route for reactive maintenance - risk mitigation? | Register entry, supporting drawing/report, approval note and updated risk item. | ISO 55000 asset management principles; maintenance plan; OHS operational file | Yes / No / N/A + Score 0–5 + Rating
36.093 | 36 | WP36 | Maintenance Management | Has the gate file tested whether roof and gutters - risk mitigation creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | Lease administration best practice; service-level agreements; security and cleaning SOPs | Yes / No / N/A + Score 0–5 + Rating
36.094 | 36 | WP36 | Maintenance Management | Are assumptions for electrical systems - risk mitigation documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | SANS 10400 occupancy and fire safety; municipal health and fire requirements | Yes / No / N/A + Score 0–5 + Rating
36.095 | 36 | WP36 | Maintenance Management | Has the relevant authority, specialist or professional adviser reviewed plumbing systems - risk mitigation where required? | Authority response, compliance checklist, file note and management approval. | ISO 55000 asset management principles; maintenance plan; OHS operational file | Yes / No / N/A + Score 0–5 + Rating
36.096 | 36 | WP36 | Maintenance Management | Is the decision record for fire equipment - risk mitigation aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | Lease administration best practice; service-level agreements; security and cleaning SOPs | Yes / No / N/A + Score 0–5 + Rating
36.097 | 36 | WP36 | Maintenance Management | Have cost, programme and compliance implications of preventive maintenance - stakeholder acceptance been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | SANS 10400 occupancy and fire safety; municipal health and fire requirements | Yes / No / N/A + Score 0–5 + Rating
36.098 | 36 | WP36 | Maintenance Management | Has the team obtained written confirmation or documented proof for reactive maintenance - stakeholder acceptance? | Current certificate/letter/report, version control and document-control entry. | ISO 55000 asset management principles; maintenance plan; OHS operational file | Yes / No / N/A + Score 0–5 + Rating
36.099 | 36 | WP36 | Maintenance Management | Does the evidence for roof and gutters - stakeholder acceptance support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | Lease administration best practice; service-level agreements; security and cleaning SOPs | Yes / No / N/A + Score 0–5 + Rating
36.100 | 36 | WP36 | Maintenance Management | Have dependencies linked to electrical systems - stakeholder acceptance been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | SANS 10400 occupancy and fire safety; municipal health and fire requirements | Yes / No / N/A + Score 0–5 + Rating
37.001 | 37 | WP37 | Sustainable Impact, Performance Monitoring and Future Expansion | Has the project team confirmed ESG reporting - governance approval in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | ESG reporting practice; local economic development commitments; utility performance data | Yes / No / N/A + Score 0–5 + Rating
37.002 | 37 | WP37 | Sustainable Impact, Performance Monitoring and Future Expansion | Is there a responsible owner, due date and approval route for job creation - governance approval? | Register entry, supporting drawing/report, approval note and updated risk item. | ISO 14001 environmental management principles; water and energy monitoring | Yes / No / N/A + Score 0–5 + Rating
37.003 | 37 | WP37 | Sustainable Impact, Performance Monitoring and Future Expansion | Has the gate file tested whether local procurement - governance approval creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | Socio-economic impact reporting; community benefit register; future expansion plan | Yes / No / N/A + Score 0–5 + Rating
37.004 | 37 | WP37 | Sustainable Impact, Performance Monitoring and Future Expansion | Are assumptions for community benefit - governance approval documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | ESG reporting practice; local economic development commitments; utility performance data | Yes / No / N/A + Score 0–5 + Rating
37.005 | 37 | WP37 | Sustainable Impact, Performance Monitoring and Future Expansion | Has the relevant authority, specialist or professional adviser reviewed energy efficiency - governance approval where required? | Authority response, compliance checklist, file note and management approval. | ISO 14001 environmental management principles; water and energy monitoring | Yes / No / N/A + Score 0–5 + Rating
37.006 | 37 | WP37 | Sustainable Impact, Performance Monitoring and Future Expansion | Is the decision record for water performance - governance approval aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | Socio-economic impact reporting; community benefit register; future expansion plan | Yes / No / N/A + Score 0–5 + Rating
37.007 | 37 | WP37 | Sustainable Impact, Performance Monitoring and Future Expansion | Have cost, programme and compliance implications of ESG reporting - legal authority been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | ESG reporting practice; local economic development commitments; utility performance data | Yes / No / N/A + Score 0–5 + Rating
37.008 | 37 | WP37 | Sustainable Impact, Performance Monitoring and Future Expansion | Has the team obtained written confirmation or documented proof for job creation - legal authority? | Current certificate/letter/report, version control and document-control entry. | ISO 14001 environmental management principles; water and energy monitoring | Yes / No / N/A + Score 0–5 + Rating
37.009 | 37 | WP37 | Sustainable Impact, Performance Monitoring and Future Expansion | Does the evidence for local procurement - legal authority support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | Socio-economic impact reporting; community benefit register; future expansion plan | Yes / No / N/A + Score 0–5 + Rating
37.010 | 37 | WP37 | Sustainable Impact, Performance Monitoring and Future Expansion | Have dependencies linked to community benefit - legal authority been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | ESG reporting practice; local economic development commitments; utility performance data | Yes / No / N/A + Score 0–5 + Rating
37.011 | 37 | WP37 | Sustainable Impact, Performance Monitoring and Future Expansion | Has the project team confirmed energy efficiency - legal authority in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | ISO 14001 environmental management principles; water and energy monitoring | Yes / No / N/A + Score 0–5 + Rating
37.012 | 37 | WP37 | Sustainable Impact, Performance Monitoring and Future Expansion | Is there a responsible owner, due date and approval route for water performance - legal authority? | Register entry, supporting drawing/report, approval note and updated risk item. | Socio-economic impact reporting; community benefit register; future expansion plan | Yes / No / N/A + Score 0–5 + Rating
37.013 | 37 | WP37 | Sustainable Impact, Performance Monitoring and Future Expansion | Has the gate file tested whether ESG reporting - technical feasibility creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | ESG reporting practice; local economic development commitments; utility performance data | Yes / No / N/A + Score 0–5 + Rating
37.014 | 37 | WP37 | Sustainable Impact, Performance Monitoring and Future Expansion | Are assumptions for job creation - technical feasibility documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | ISO 14001 environmental management principles; water and energy monitoring | Yes / No / N/A + Score 0–5 + Rating
37.015 | 37 | WP37 | Sustainable Impact, Performance Monitoring and Future Expansion | Has the relevant authority, specialist or professional adviser reviewed local procurement - technical feasibility where required? | Authority response, compliance checklist, file note and management approval. | Socio-economic impact reporting; community benefit register; future expansion plan | Yes / No / N/A + Score 0–5 + Rating
37.016 | 37 | WP37 | Sustainable Impact, Performance Monitoring and Future Expansion | Is the decision record for community benefit - technical feasibility aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | ESG reporting practice; local economic development commitments; utility performance data | Yes / No / N/A + Score 0–5 + Rating
37.017 | 37 | WP37 | Sustainable Impact, Performance Monitoring and Future Expansion | Have cost, programme and compliance implications of energy efficiency - technical feasibility been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | ISO 14001 environmental management principles; water and energy monitoring | Yes / No / N/A + Score 0–5 + Rating
37.018 | 37 | WP37 | Sustainable Impact, Performance Monitoring and Future Expansion | Has the team obtained written confirmation or documented proof for water performance - technical feasibility? | Current certificate/letter/report, version control and document-control entry. | Socio-economic impact reporting; community benefit register; future expansion plan | Yes / No / N/A + Score 0–5 + Rating
37.019 | 37 | WP37 | Sustainable Impact, Performance Monitoring and Future Expansion | Does the evidence for ESG reporting - financial viability support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | ESG reporting practice; local economic development commitments; utility performance data | Yes / No / N/A + Score 0–5 + Rating
37.020 | 37 | WP37 | Sustainable Impact, Performance Monitoring and Future Expansion | Have dependencies linked to job creation - financial viability been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | ISO 14001 environmental management principles; water and energy monitoring | Yes / No / N/A + Score 0–5 + Rating
37.021 | 37 | WP37 | Sustainable Impact, Performance Monitoring and Future Expansion | Has the project team confirmed local procurement - financial viability in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | Socio-economic impact reporting; community benefit register; future expansion plan | Yes / No / N/A + Score 0–5 + Rating
37.022 | 37 | WP37 | Sustainable Impact, Performance Monitoring and Future Expansion | Is there a responsible owner, due date and approval route for community benefit - financial viability? | Register entry, supporting drawing/report, approval note and updated risk item. | ESG reporting practice; local economic development commitments; utility performance data | Yes / No / N/A + Score 0–5 + Rating
37.023 | 37 | WP37 | Sustainable Impact, Performance Monitoring and Future Expansion | Has the gate file tested whether energy efficiency - financial viability creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | ISO 14001 environmental management principles; water and energy monitoring | Yes / No / N/A + Score 0–5 + Rating
37.024 | 37 | WP37 | Sustainable Impact, Performance Monitoring and Future Expansion | Are assumptions for water performance - financial viability documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | Socio-economic impact reporting; community benefit register; future expansion plan | Yes / No / N/A + Score 0–5 + Rating
37.025 | 37 | WP37 | Sustainable Impact, Performance Monitoring and Future Expansion | Has the relevant authority, specialist or professional adviser reviewed ESG reporting - programme impact where required? | Authority response, compliance checklist, file note and management approval. | ESG reporting practice; local economic development commitments; utility performance data | Yes / No / N/A + Score 0–5 + Rating
37.026 | 37 | WP37 | Sustainable Impact, Performance Monitoring and Future Expansion | Is the decision record for job creation - programme impact aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | ISO 14001 environmental management principles; water and energy monitoring | Yes / No / N/A + Score 0–5 + Rating
37.027 | 37 | WP37 | Sustainable Impact, Performance Monitoring and Future Expansion | Have cost, programme and compliance implications of local procurement - programme impact been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | Socio-economic impact reporting; community benefit register; future expansion plan | Yes / No / N/A + Score 0–5 + Rating
37.028 | 37 | WP37 | Sustainable Impact, Performance Monitoring and Future Expansion | Has the team obtained written confirmation or documented proof for community benefit - programme impact? | Current certificate/letter/report, version control and document-control entry. | ESG reporting practice; local economic development commitments; utility performance data | Yes / No / N/A + Score 0–5 + Rating
37.029 | 37 | WP37 | Sustainable Impact, Performance Monitoring and Future Expansion | Does the evidence for energy efficiency - programme impact support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | ISO 14001 environmental management principles; water and energy monitoring | Yes / No / N/A + Score 0–5 + Rating
37.030 | 37 | WP37 | Sustainable Impact, Performance Monitoring and Future Expansion | Have dependencies linked to water performance - programme impact been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | Socio-economic impact reporting; community benefit register; future expansion plan | Yes / No / N/A + Score 0–5 + Rating
37.031 | 37 | WP37 | Sustainable Impact, Performance Monitoring and Future Expansion | Has the project team confirmed ESG reporting - risk mitigation in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | ESG reporting practice; local economic development commitments; utility performance data | Yes / No / N/A + Score 0–5 + Rating
37.032 | 37 | WP37 | Sustainable Impact, Performance Monitoring and Future Expansion | Is there a responsible owner, due date and approval route for job creation - risk mitigation? | Register entry, supporting drawing/report, approval note and updated risk item. | ISO 14001 environmental management principles; water and energy monitoring | Yes / No / N/A + Score 0–5 + Rating
37.033 | 37 | WP37 | Sustainable Impact, Performance Monitoring and Future Expansion | Has the gate file tested whether local procurement - risk mitigation creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | Socio-economic impact reporting; community benefit register; future expansion plan | Yes / No / N/A + Score 0–5 + Rating
37.034 | 37 | WP37 | Sustainable Impact, Performance Monitoring and Future Expansion | Are assumptions for community benefit - risk mitigation documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | ESG reporting practice; local economic development commitments; utility performance data | Yes / No / N/A + Score 0–5 + Rating
37.035 | 37 | WP37 | Sustainable Impact, Performance Monitoring and Future Expansion | Has the relevant authority, specialist or professional adviser reviewed energy efficiency - risk mitigation where required? | Authority response, compliance checklist, file note and management approval. | ISO 14001 environmental management principles; water and energy monitoring | Yes / No / N/A + Score 0–5 + Rating
37.036 | 37 | WP37 | Sustainable Impact, Performance Monitoring and Future Expansion | Is the decision record for water performance - risk mitigation aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | Socio-economic impact reporting; community benefit register; future expansion plan | Yes / No / N/A + Score 0–5 + Rating
37.037 | 37 | WP37 | Sustainable Impact, Performance Monitoring and Future Expansion | Have cost, programme and compliance implications of ESG reporting - stakeholder acceptance been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | ESG reporting practice; local economic development commitments; utility performance data | Yes / No / N/A + Score 0–5 + Rating
37.038 | 37 | WP37 | Sustainable Impact, Performance Monitoring and Future Expansion | Has the team obtained written confirmation or documented proof for job creation - stakeholder acceptance? | Current certificate/letter/report, version control and document-control entry. | ISO 14001 environmental management principles; water and energy monitoring | Yes / No / N/A + Score 0–5 + Rating
37.039 | 37 | WP37 | Sustainable Impact, Performance Monitoring and Future Expansion | Does the evidence for local procurement - stakeholder acceptance support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | Socio-economic impact reporting; community benefit register; future expansion plan | Yes / No / N/A + Score 0–5 + Rating
37.040 | 37 | WP37 | Sustainable Impact, Performance Monitoring and Future Expansion | Have dependencies linked to community benefit - stakeholder acceptance been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | ESG reporting practice; local economic development commitments; utility performance data | Yes / No / N/A + Score 0–5 + Rating
37.041 | 37 | WP37 | Sustainable Impact, Performance Monitoring and Future Expansion | Has the project team confirmed energy efficiency - stakeholder acceptance in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | ISO 14001 environmental management principles; water and energy monitoring | Yes / No / N/A + Score 0–5 + Rating
37.042 | 37 | WP37 | Sustainable Impact, Performance Monitoring and Future Expansion | Is there a responsible owner, due date and approval route for water performance - stakeholder acceptance? | Register entry, supporting drawing/report, approval note and updated risk item. | Socio-economic impact reporting; community benefit register; future expansion plan | Yes / No / N/A + Score 0–5 + Rating
37.043 | 37 | WP37 | Sustainable Impact, Performance Monitoring and Future Expansion | Has the gate file tested whether ESG reporting - document control creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | ESG reporting practice; local economic development commitments; utility performance data | Yes / No / N/A + Score 0–5 + Rating
37.044 | 37 | WP37 | Sustainable Impact, Performance Monitoring and Future Expansion | Are assumptions for job creation - document control documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | ISO 14001 environmental management principles; water and energy monitoring | Yes / No / N/A + Score 0–5 + Rating
37.045 | 37 | WP37 | Sustainable Impact, Performance Monitoring and Future Expansion | Has the relevant authority, specialist or professional adviser reviewed local procurement - document control where required? | Authority response, compliance checklist, file note and management approval. | Socio-economic impact reporting; community benefit register; future expansion plan | Yes / No / N/A + Score 0–5 + Rating
37.046 | 37 | WP37 | Sustainable Impact, Performance Monitoring and Future Expansion | Is the decision record for community benefit - document control aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | ESG reporting practice; local economic development commitments; utility performance data | Yes / No / N/A + Score 0–5 + Rating
37.047 | 37 | WP37 | Sustainable Impact, Performance Monitoring and Future Expansion | Have cost, programme and compliance implications of energy efficiency - document control been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | ISO 14001 environmental management principles; water and energy monitoring | Yes / No / N/A + Score 0–5 + Rating
37.048 | 37 | WP37 | Sustainable Impact, Performance Monitoring and Future Expansion | Has the team obtained written confirmation or documented proof for water performance - document control? | Current certificate/letter/report, version control and document-control entry. | Socio-economic impact reporting; community benefit register; future expansion plan | Yes / No / N/A + Score 0–5 + Rating
37.049 | 37 | WP37 | Sustainable Impact, Performance Monitoring and Future Expansion | Does the evidence for ESG reporting - professional certification support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | ESG reporting practice; local economic development commitments; utility performance data | Yes / No / N/A + Score 0–5 + Rating
37.050 | 37 | WP37 | Sustainable Impact, Performance Monitoring and Future Expansion | Have dependencies linked to job creation - professional certification been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | ISO 14001 environmental management principles; water and energy monitoring | Yes / No / N/A + Score 0–5 + Rating
37.051 | 37 | WP37 | Sustainable Impact, Performance Monitoring and Future Expansion | Has the project team confirmed local procurement - professional certification in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | Socio-economic impact reporting; community benefit register; future expansion plan | Yes / No / N/A + Score 0–5 + Rating
37.052 | 37 | WP37 | Sustainable Impact, Performance Monitoring and Future Expansion | Is there a responsible owner, due date and approval route for community benefit - professional certification? | Register entry, supporting drawing/report, approval note and updated risk item. | ESG reporting practice; local economic development commitments; utility performance data | Yes / No / N/A + Score 0–5 + Rating
37.053 | 37 | WP37 | Sustainable Impact, Performance Monitoring and Future Expansion | Has the gate file tested whether energy efficiency - professional certification creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | ISO 14001 environmental management principles; water and energy monitoring | Yes / No / N/A + Score 0–5 + Rating
37.054 | 37 | WP37 | Sustainable Impact, Performance Monitoring and Future Expansion | Are assumptions for water performance - professional certification documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | Socio-economic impact reporting; community benefit register; future expansion plan | Yes / No / N/A + Score 0–5 + Rating
37.055 | 37 | WP37 | Sustainable Impact, Performance Monitoring and Future Expansion | Has the relevant authority, specialist or professional adviser reviewed ESG reporting - implementation readiness where required? | Authority response, compliance checklist, file note and management approval. | ESG reporting practice; local economic development commitments; utility performance data | Yes / No / N/A + Score 0–5 + Rating
37.056 | 37 | WP37 | Sustainable Impact, Performance Monitoring and Future Expansion | Is the decision record for job creation - implementation readiness aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | ISO 14001 environmental management principles; water and energy monitoring | Yes / No / N/A + Score 0–5 + Rating
37.057 | 37 | WP37 | Sustainable Impact, Performance Monitoring and Future Expansion | Have cost, programme and compliance implications of local procurement - implementation readiness been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | Socio-economic impact reporting; community benefit register; future expansion plan | Yes / No / N/A + Score 0–5 + Rating
37.058 | 37 | WP37 | Sustainable Impact, Performance Monitoring and Future Expansion | Has the team obtained written confirmation or documented proof for community benefit - implementation readiness? | Current certificate/letter/report, version control and document-control entry. | ESG reporting practice; local economic development commitments; utility performance data | Yes / No / N/A + Score 0–5 + Rating
37.059 | 37 | WP37 | Sustainable Impact, Performance Monitoring and Future Expansion | Does the evidence for energy efficiency - implementation readiness support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | ISO 14001 environmental management principles; water and energy monitoring | Yes / No / N/A + Score 0–5 + Rating
37.060 | 37 | WP37 | Sustainable Impact, Performance Monitoring and Future Expansion | Have dependencies linked to water performance - implementation readiness been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | Socio-economic impact reporting; community benefit register; future expansion plan | Yes / No / N/A + Score 0–5 + Rating
37.061 | 37 | WP37 | Sustainable Impact, Performance Monitoring and Future Expansion | Has the project team confirmed ESG reporting - governance approval in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | ESG reporting practice; local economic development commitments; utility performance data | Yes / No / N/A + Score 0–5 + Rating
37.062 | 37 | WP37 | Sustainable Impact, Performance Monitoring and Future Expansion | Is there a responsible owner, due date and approval route for job creation - governance approval? | Register entry, supporting drawing/report, approval note and updated risk item. | ISO 14001 environmental management principles; water and energy monitoring | Yes / No / N/A + Score 0–5 + Rating
37.063 | 37 | WP37 | Sustainable Impact, Performance Monitoring and Future Expansion | Has the gate file tested whether local procurement - governance approval creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | Socio-economic impact reporting; community benefit register; future expansion plan | Yes / No / N/A + Score 0–5 + Rating
37.064 | 37 | WP37 | Sustainable Impact, Performance Monitoring and Future Expansion | Are assumptions for community benefit - governance approval documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | ESG reporting practice; local economic development commitments; utility performance data | Yes / No / N/A + Score 0–5 + Rating
37.065 | 37 | WP37 | Sustainable Impact, Performance Monitoring and Future Expansion | Has the relevant authority, specialist or professional adviser reviewed energy efficiency - governance approval where required? | Authority response, compliance checklist, file note and management approval. | ISO 14001 environmental management principles; water and energy monitoring | Yes / No / N/A + Score 0–5 + Rating
37.066 | 37 | WP37 | Sustainable Impact, Performance Monitoring and Future Expansion | Is the decision record for water performance - governance approval aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | Socio-economic impact reporting; community benefit register; future expansion plan | Yes / No / N/A + Score 0–5 + Rating
37.067 | 37 | WP37 | Sustainable Impact, Performance Monitoring and Future Expansion | Have cost, programme and compliance implications of ESG reporting - legal authority been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | ESG reporting practice; local economic development commitments; utility performance data | Yes / No / N/A + Score 0–5 + Rating
37.068 | 37 | WP37 | Sustainable Impact, Performance Monitoring and Future Expansion | Has the team obtained written confirmation or documented proof for job creation - legal authority? | Current certificate/letter/report, version control and document-control entry. | ISO 14001 environmental management principles; water and energy monitoring | Yes / No / N/A + Score 0–5 + Rating
37.069 | 37 | WP37 | Sustainable Impact, Performance Monitoring and Future Expansion | Does the evidence for local procurement - legal authority support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | Socio-economic impact reporting; community benefit register; future expansion plan | Yes / No / N/A + Score 0–5 + Rating
37.070 | 37 | WP37 | Sustainable Impact, Performance Monitoring and Future Expansion | Have dependencies linked to community benefit - legal authority been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | ESG reporting practice; local economic development commitments; utility performance data | Yes / No / N/A + Score 0–5 + Rating
37.071 | 37 | WP37 | Sustainable Impact, Performance Monitoring and Future Expansion | Has the project team confirmed energy efficiency - legal authority in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | ISO 14001 environmental management principles; water and energy monitoring | Yes / No / N/A + Score 0–5 + Rating
37.072 | 37 | WP37 | Sustainable Impact, Performance Monitoring and Future Expansion | Is there a responsible owner, due date and approval route for water performance - legal authority? | Register entry, supporting drawing/report, approval note and updated risk item. | Socio-economic impact reporting; community benefit register; future expansion plan | Yes / No / N/A + Score 0–5 + Rating
37.073 | 37 | WP37 | Sustainable Impact, Performance Monitoring and Future Expansion | Has the gate file tested whether ESG reporting - technical feasibility creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | ESG reporting practice; local economic development commitments; utility performance data | Yes / No / N/A + Score 0–5 + Rating
37.074 | 37 | WP37 | Sustainable Impact, Performance Monitoring and Future Expansion | Are assumptions for job creation - technical feasibility documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | ISO 14001 environmental management principles; water and energy monitoring | Yes / No / N/A + Score 0–5 + Rating
37.075 | 37 | WP37 | Sustainable Impact, Performance Monitoring and Future Expansion | Has the relevant authority, specialist or professional adviser reviewed local procurement - technical feasibility where required? | Authority response, compliance checklist, file note and management approval. | Socio-economic impact reporting; community benefit register; future expansion plan | Yes / No / N/A + Score 0–5 + Rating
37.076 | 37 | WP37 | Sustainable Impact, Performance Monitoring and Future Expansion | Is the decision record for community benefit - technical feasibility aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | ESG reporting practice; local economic development commitments; utility performance data | Yes / No / N/A + Score 0–5 + Rating
37.077 | 37 | WP37 | Sustainable Impact, Performance Monitoring and Future Expansion | Have cost, programme and compliance implications of energy efficiency - technical feasibility been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | ISO 14001 environmental management principles; water and energy monitoring | Yes / No / N/A + Score 0–5 + Rating
37.078 | 37 | WP37 | Sustainable Impact, Performance Monitoring and Future Expansion | Has the team obtained written confirmation or documented proof for water performance - technical feasibility? | Current certificate/letter/report, version control and document-control entry. | Socio-economic impact reporting; community benefit register; future expansion plan | Yes / No / N/A + Score 0–5 + Rating
37.079 | 37 | WP37 | Sustainable Impact, Performance Monitoring and Future Expansion | Does the evidence for ESG reporting - financial viability support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | ESG reporting practice; local economic development commitments; utility performance data | Yes / No / N/A + Score 0–5 + Rating
37.080 | 37 | WP37 | Sustainable Impact, Performance Monitoring and Future Expansion | Have dependencies linked to job creation - financial viability been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | ISO 14001 environmental management principles; water and energy monitoring | Yes / No / N/A + Score 0–5 + Rating
37.081 | 37 | WP37 | Sustainable Impact, Performance Monitoring and Future Expansion | Has the project team confirmed local procurement - financial viability in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | Socio-economic impact reporting; community benefit register; future expansion plan | Yes / No / N/A + Score 0–5 + Rating
37.082 | 37 | WP37 | Sustainable Impact, Performance Monitoring and Future Expansion | Is there a responsible owner, due date and approval route for community benefit - financial viability? | Register entry, supporting drawing/report, approval note and updated risk item. | ESG reporting practice; local economic development commitments; utility performance data | Yes / No / N/A + Score 0–5 + Rating
37.083 | 37 | WP37 | Sustainable Impact, Performance Monitoring and Future Expansion | Has the gate file tested whether energy efficiency - financial viability creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | ISO 14001 environmental management principles; water and energy monitoring | Yes / No / N/A + Score 0–5 + Rating
37.084 | 37 | WP37 | Sustainable Impact, Performance Monitoring and Future Expansion | Are assumptions for water performance - financial viability documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | Socio-economic impact reporting; community benefit register; future expansion plan | Yes / No / N/A + Score 0–5 + Rating
37.085 | 37 | WP37 | Sustainable Impact, Performance Monitoring and Future Expansion | Has the relevant authority, specialist or professional adviser reviewed ESG reporting - programme impact where required? | Authority response, compliance checklist, file note and management approval. | ESG reporting practice; local economic development commitments; utility performance data | Yes / No / N/A + Score 0–5 + Rating
37.086 | 37 | WP37 | Sustainable Impact, Performance Monitoring and Future Expansion | Is the decision record for job creation - programme impact aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | ISO 14001 environmental management principles; water and energy monitoring | Yes / No / N/A + Score 0–5 + Rating
37.087 | 37 | WP37 | Sustainable Impact, Performance Monitoring and Future Expansion | Have cost, programme and compliance implications of local procurement - programme impact been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | Socio-economic impact reporting; community benefit register; future expansion plan | Yes / No / N/A + Score 0–5 + Rating
37.088 | 37 | WP37 | Sustainable Impact, Performance Monitoring and Future Expansion | Has the team obtained written confirmation or documented proof for community benefit - programme impact? | Current certificate/letter/report, version control and document-control entry. | ESG reporting practice; local economic development commitments; utility performance data | Yes / No / N/A + Score 0–5 + Rating
37.089 | 37 | WP37 | Sustainable Impact, Performance Monitoring and Future Expansion | Does the evidence for energy efficiency - programme impact support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | ISO 14001 environmental management principles; water and energy monitoring | Yes / No / N/A + Score 0–5 + Rating
37.090 | 37 | WP37 | Sustainable Impact, Performance Monitoring and Future Expansion | Have dependencies linked to water performance - programme impact been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | Socio-economic impact reporting; community benefit register; future expansion plan | Yes / No / N/A + Score 0–5 + Rating
37.091 | 37 | WP37 | Sustainable Impact, Performance Monitoring and Future Expansion | Has the project team confirmed ESG reporting - risk mitigation in a current, signed and traceable evidence file? | Signed memo, checklist, source document and responsible-person confirmation. | ESG reporting practice; local economic development commitments; utility performance data | Yes / No / N/A + Score 0–5 + Rating
37.092 | 37 | WP37 | Sustainable Impact, Performance Monitoring and Future Expansion | Is there a responsible owner, due date and approval route for job creation - risk mitigation? | Register entry, supporting drawing/report, approval note and updated risk item. | ISO 14001 environmental management principles; water and energy monitoring | Yes / No / N/A + Score 0–5 + Rating
37.093 | 37 | WP37 | Sustainable Impact, Performance Monitoring and Future Expansion | Has the gate file tested whether local procurement - risk mitigation creates a material risk to Bahlaloga Riverside Complex? | Professional/specialist note, meeting minute, correspondence and decision record. | Socio-economic impact reporting; community benefit register; future expansion plan | Yes / No / N/A + Score 0–5 + Rating
37.094 | 37 | WP37 | Sustainable Impact, Performance Monitoring and Future Expansion | Are assumptions for community benefit - risk mitigation documented, current and supported by source evidence? | Updated schedule, cost note, assumption log and evidence index reference. | ESG reporting practice; local economic development commitments; utility performance data | Yes / No / N/A + Score 0–5 + Rating
37.095 | 37 | WP37 | Sustainable Impact, Performance Monitoring and Future Expansion | Has the relevant authority, specialist or professional adviser reviewed energy efficiency - risk mitigation where required? | Authority response, compliance checklist, file note and management approval. | ISO 14001 environmental management principles; water and energy monitoring | Yes / No / N/A + Score 0–5 + Rating
37.096 | 37 | WP37 | Sustainable Impact, Performance Monitoring and Future Expansion | Is the decision record for water performance - risk mitigation aligned with the approved project mandate and scope? | Due-diligence record, gap analysis, mitigation action and close-out proof. | Socio-economic impact reporting; community benefit register; future expansion plan | Yes / No / N/A + Score 0–5 + Rating
37.097 | 37 | WP37 | Sustainable Impact, Performance Monitoring and Future Expansion | Have cost, programme and compliance implications of ESG reporting - stakeholder acceptance been captured in the risk register? | Reviewed report, annotated plan, gate pack extract and approval signature. | ESG reporting practice; local economic development commitments; utility performance data | Yes / No / N/A + Score 0–5 + Rating
37.098 | 37 | WP37 | Sustainable Impact, Performance Monitoring and Future Expansion | Has the team obtained written confirmation or documented proof for job creation - stakeholder acceptance? | Current certificate/letter/report, version control and document-control entry. | ISO 14001 environmental management principles; water and energy monitoring | Yes / No / N/A + Score 0–5 + Rating
37.099 | 37 | WP37 | Sustainable Impact, Performance Monitoring and Future Expansion | Does the evidence for local procurement - stakeholder acceptance support a clear proceed, hold, revise or stop gate decision? | Inspection/test record, issue log, corrective action and close-out evidence. | Socio-economic impact reporting; community benefit register; future expansion plan | Yes / No / N/A + Score 0–5 + Rating
37.100 | 37 | WP37 | Sustainable Impact, Performance Monitoring and Future Expansion | Have dependencies linked to community benefit - stakeholder acceptance been identified before moving to the next stage? | Tenant/operator/funder/authority confirmation and gate-approval recommendation. | ESG reporting practice; local economic development commitments; utility performance data | Yes / No / N/A + Score 0–5 + Rating

## Evidence & References
Evidence and Reference Coverage by Stage
Most recurrent evidence patterns and reference bases extracted from each stage's 100 source questions
Stage | WP Code | Stage / Work Package | Evidence Pattern 1 | Evidence Pattern 2 | Evidence Pattern 3 | Primary Reference Basis | Coverage
01 | WP01 | Strategic Inception and Project Mandate | Signed memo, checklist, source document and responsible-person confirmation. | Register entry, supporting drawing/report, approval note and updated risk item. | Professional/specialist note, meeting minute, correspondence and decision record. | King IV governance practice; Companies Act 71 of 2008; project mandate file | 100 questions / 6 focus fields
02 | WP02 | Site Identification and Opportunity Discovery | Signed memo, checklist, source document and responsible-person confirmation. | Register entry, supporting drawing/report, approval note and updated risk item. | Professional/specialist note, meeting minute, correspondence and decision record. | SPLUMA Act 16 of 2013; municipal land use scheme; title deed/SG diagram | 100 questions / 6 focus fields
03 | WP03 | Preliminary Site Screening | Signed memo, checklist, source document and responsible-person confirmation. | Register entry, supporting drawing/report, approval note and updated risk item. | Professional/specialist note, meeting minute, correspondence and decision record. | SPLUMA Act 16 of 2013; municipal land use scheme; title deed/SG diagram | 100 questions / 6 focus fields
04 | WP04 | Sponsor and Entity Readiness | Signed memo, checklist, source document and responsible-person confirmation. | Register entry, supporting drawing/report, approval note and updated risk item. | Professional/specialist note, meeting minute, correspondence and decision record. | King IV governance practice; Companies Act 71 of 2008; project mandate file | 100 questions / 6 focus fields
05 | WP05 | Land Security and Site Control | Signed memo, checklist, source document and responsible-person confirmation. | Register entry, supporting drawing/report, approval note and updated risk item. | Professional/specialist note, meeting minute, correspondence and decision record. | SPLUMA Act 16 of 2013; municipal land use scheme; title deed/SG diagram | 100 questions / 6 focus fields
06 | WP06 | Feasibility Studies and Market Demand | Signed memo, checklist, source document and responsible-person confirmation. | Register entry, supporting drawing/report, approval note and updated risk item. | Professional/specialist note, meeting minute, correspondence and decision record. | IFRS/IFRS for SMEs principles; lender due diligence checklist; signed financial model | 100 questions / 6 focus fields
07 | WP07 | Traffic, Access and Mobility Feasibility | Signed memo, checklist, source document and responsible-person confirmation. | Register entry, supporting drawing/report, approval note and updated risk item. | Professional/specialist note, meeting minute, correspondence and decision record. | SANRAL/road authority access requirements; TMH/TRH road design guidance | 100 questions / 6 focus fields
08 | WP08 | Bulk Services and Infrastructure Feasibility | Signed memo, checklist, source document and responsible-person confirmation. | Register entry, supporting drawing/report, approval note and updated risk item. | Professional/specialist note, meeting minute, correspondence and decision record. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | 100 questions / 6 focus fields
09 | WP09 | Environmental Screening and Scoping | Signed memo, checklist, source document and responsible-person confirmation. | Register entry, supporting drawing/report, approval note and updated risk item. | Professional/specialist note, meeting minute, correspondence and decision record. | NEMA Act 107 of 1998; EIA Regulations, 2014; DFFE screening requirements | 100 questions / 6 focus fields
10 | WP10 | Land Use Rights and Zoning | Signed memo, checklist, source document and responsible-person confirmation. | Register entry, supporting drawing/report, approval note and updated risk item. | Professional/specialist note, meeting minute, correspondence and decision record. | SPLUMA Act 16 of 2013; municipal land use scheme; title deed/SG diagram | 100 questions / 6 focus fields
11 | WP11 | Environmental Authorisation - Estimated 10 Months | Signed memo, checklist, source document and responsible-person confirmation. | Register entry, supporting drawing/report, approval note and updated risk item. | Professional/specialist note, meeting minute, correspondence and decision record. | NEMA Act 107 of 1998; EIA Regulations, 2014; DFFE screening requirements | 100 questions / 6 focus fields
12 | WP12 | Stakeholder Mapping and Public Participation | Signed memo, checklist, source document and responsible-person confirmation. | Register entry, supporting drawing/report, approval note and updated risk item. | Professional/specialist note, meeting minute, correspondence and decision record. | King IV governance practice; Companies Act 71 of 2008; project mandate file | 100 questions / 6 focus fields
13 | WP13 | Concept Development | Signed memo, checklist, source document and responsible-person confirmation. | Register entry, supporting drawing/report, approval note and updated risk item. | Professional/specialist note, meeting minute, correspondence and decision record. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | 100 questions / 6 focus fields
14 | WP14 | Retail Masterplanning and GLA Strategy | Signed memo, checklist, source document and responsible-person confirmation. | Register entry, supporting drawing/report, approval note and updated risk item. | Professional/specialist note, meeting minute, correspondence and decision record. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | 100 questions / 6 focus fields
15 | WP15 | Boxer Superstores Anchor Alignment | Signed memo, checklist, source document and responsible-person confirmation. | Register entry, supporting drawing/report, approval note and updated risk item. | Professional/specialist note, meeting minute, correspondence and decision record. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | 100 questions / 6 focus fields
16 | WP16 | Tenant Acquisition Strategy | Signed memo, checklist, source document and responsible-person confirmation. | Register entry, supporting drawing/report, approval note and updated risk item. | Professional/specialist note, meeting minute, correspondence and decision record. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | 100 questions / 6 focus fields
17 | WP17 | Line-Shop Tenant Mix and Leasing | Signed memo, checklist, source document and responsible-person confirmation. | Register entry, supporting drawing/report, approval note and updated risk item. | Professional/specialist note, meeting minute, correspondence and decision record. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | 100 questions / 6 focus fields
18 | WP18 | Fast-Food Chain Restaurant Acquisition | Signed memo, checklist, source document and responsible-person confirmation. | Register entry, supporting drawing/report, approval note and updated risk item. | Professional/specialist note, meeting minute, correspondence and decision record. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | 100 questions / 6 focus fields
19 | WP19 | Fuel Partner and Forecourt Coordination | Signed memo, checklist, source document and responsible-person confirmation. | Register entry, supporting drawing/report, approval note and updated risk item. | Professional/specialist note, meeting minute, correspondence and decision record. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | 100 questions / 6 focus fields
20 | WP20 | Development Design | Signed memo, checklist, source document and responsible-person confirmation. | Register entry, supporting drawing/report, approval note and updated risk item. | Professional/specialist note, meeting minute, correspondence and decision record. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | 100 questions / 6 focus fields
21 | WP21 | Engineering Design and Technical Documentation | Signed memo, checklist, source document and responsible-person confirmation. | Register entry, supporting drawing/report, approval note and updated risk item. | Professional/specialist note, meeting minute, correspondence and decision record. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | 100 questions / 6 focus fields
22 | WP22 | Cost Planning and Financial Modelling | Signed memo, checklist, source document and responsible-person confirmation. | Register entry, supporting drawing/report, approval note and updated risk item. | Professional/specialist note, meeting minute, correspondence and decision record. | IFRS/IFRS for SMEs principles; lender due diligence checklist; signed financial model | 100 questions / 6 focus fields
23 | WP23 | Capital Structuring and Funding Readiness | Signed memo, checklist, source document and responsible-person confirmation. | Register entry, supporting drawing/report, approval note and updated risk item. | Professional/specialist note, meeting minute, correspondence and decision record. | King IV governance practice; Companies Act 71 of 2008; project mandate file | 100 questions / 6 focus fields
24 | WP24 | Procurement Strategy and Tender Documentation | Signed memo, checklist, source document and responsible-person confirmation. | Register entry, supporting drawing/report, approval note and updated risk item. | Professional/specialist note, meeting minute, correspondence and decision record. | IFRS/IFRS for SMEs principles; lender due diligence checklist; signed financial model | 100 questions / 6 focus fields
25 | WP25 | Contractor Due Diligence and Appointment | Signed memo, checklist, source document and responsible-person confirmation. | Register entry, supporting drawing/report, approval note and updated risk item. | Professional/specialist note, meeting minute, correspondence and decision record. | IFRS/IFRS for SMEs principles; lender due diligence checklist; signed financial model | 100 questions / 6 focus fields
26 | WP26 | Regulatory Permitting and Building Plan Approval | Signed memo, checklist, source document and responsible-person confirmation. | Register entry, supporting drawing/report, approval note and updated risk item. | Professional/specialist note, meeting minute, correspondence and decision record. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | 100 questions / 6 focus fields
27 | WP27 | Construction Mobilisation | Signed memo, checklist, source document and responsible-person confirmation. | Register entry, supporting drawing/report, approval note and updated risk item. | Professional/specialist note, meeting minute, correspondence and decision record. | OHS Act 85 of 1993; Construction Regulations, 2014; HSE file | 100 questions / 6 focus fields
28 | WP28 | Civil Works, Earthworks and Access Construction | Signed memo, checklist, source document and responsible-person confirmation. | Register entry, supporting drawing/report, approval note and updated risk item. | Professional/specialist note, meeting minute, correspondence and decision record. | OHS Act 85 of 1993; Construction Regulations, 2014; HSE file | 100 questions / 6 focus fields
29 | WP29 | Building Shells and Services Installation | Signed memo, checklist, source document and responsible-person confirmation. | Register entry, supporting drawing/report, approval note and updated risk item. | Professional/specialist note, meeting minute, correspondence and decision record. | OHS Act 85 of 1993; Construction Regulations, 2014; HSE file | 100 questions / 6 focus fields
30 | WP30 | Tenant Fit-Out Coordination | Signed memo, checklist, source document and responsible-person confirmation. | Register entry, supporting drawing/report, approval note and updated risk item. | Professional/specialist note, meeting minute, correspondence and decision record. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | 100 questions / 6 focus fields
31 | WP31 | Quality Assurance, HSE and Compliance Control | Signed memo, checklist, source document and responsible-person confirmation. | Register entry, supporting drawing/report, approval note and updated risk item. | Professional/specialist note, meeting minute, correspondence and decision record. | OHS Act 85 of 1993; Construction Regulations, 2014; HSE file | 100 questions / 6 focus fields
32 | WP32 | Commissioning and Testing | Signed memo, checklist, source document and responsible-person confirmation. | Register entry, supporting drawing/report, approval note and updated risk item. | Professional/specialist note, meeting minute, correspondence and decision record. | National Building Regulations and Building Standards Act 103 of 1977; SANS 10400 | 100 questions / 6 focus fields
33 | WP33 | Handover to Operators and Tenants | Signed memo, checklist, source document and responsible-person confirmation. | Register entry, supporting drawing/report, approval note and updated risk item. | Professional/specialist note, meeting minute, correspondence and decision record. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | 100 questions / 6 focus fields
34 | WP34 | Operational Ramp-Up | Signed memo, checklist, source document and responsible-person confirmation. | Register entry, supporting drawing/report, approval note and updated risk item. | Professional/specialist note, meeting minute, correspondence and decision record. | Property leasing best practice; FICA due diligence; signed LOI/lease schedule | 100 questions / 6 focus fields
35 | WP35 | Operations Management | Signed memo, checklist, source document and responsible-person confirmation. | Register entry, supporting drawing/report, approval note and updated risk item. | Professional/specialist note, meeting minute, correspondence and decision record. | SANS 10400 occupancy and fire safety; municipal health and fire requirements | 100 questions / 6 focus fields
36 | WP36 | Maintenance Management | Signed memo, checklist, source document and responsible-person confirmation. | Register entry, supporting drawing/report, approval note and updated risk item. | Professional/specialist note, meeting minute, correspondence and decision record. | SANS 10400 occupancy and fire safety; municipal health and fire requirements | 100 questions / 6 focus fields
37 | WP37 | Sustainable Impact, Performance Monitoring and Future Expansion | Signed memo, checklist, source document and responsible-person confirmation. | Register entry, supporting drawing/report, approval note and updated risk item. | Professional/specialist note, meeting minute, correspondence and decision record. | ESG reporting practice; local economic development commitments; utility performance data | 100 questions / 6 focus fields

## Source & Control
Source, Authority and Control
Controlled provenance of the OPBOH 37-stage/work-package architecture
Control Attribute | Controlled Value
Framework | OPBOH™ — Organisational and Project Bill of Health
Module | Full-Cycle Assessment Module
Version | 1.1
Stages / Work Packages | 37
Questions | 3700
Controlled Focus Fields | 222
Stage Source | Bahlaloga_Riverside_Complex_3700_Stage_Gate_Questions_Bank_ FV 2216.docx
Field Source | OPBOH_Full_Cycle_Assessment_Module_Field_Requirements_v1.1.docx
Assessment Inputs | Yes / No / N/A; Score 0–5; rating
Classification | Confidential and Proprietary
Owner | IPAC Governance Systems (Pty) Ltd
Control Principle | Controlled Statement
A date, percentage or tick does not authorise progression. Gate approval depends on accepted, current, complete, signed where applicable and traceable evidence, linked to the responsible owner and reviewed by the correct delegated authority. Critical failures are non-averageable and unresolved conditions must remain visible in the progression decision.
Register Scope | Controlled Statement
This workbook operationalises the 37 sequential project stages/work packages, their 222 controlled focus fields and the 3,700 source stage-gate questions. Lifecycle-cluster labels, purpose statements, role summaries, decision-risk summaries and entry/exit formulations are implementation-oriented register views derived from the controlled stage names, primary focus areas and evidence architecture; they do not replace framework-owner approval or specialist judgement.